## TASK
Activity ID | Activity Status | Activity Name | Actual Start | Actual Finish | (*)BL Project Start | (*)BL Project Finish | Machine | Machine Type | Progress | Department | Machine Label | Machine Label Group | Planned Duration (Hrs) | Planned Duration(hh:mm:ss) | Actual time(hh:mm:sec) | Extra Spending (hh:mm:sec) | Saving(hh:mm:ss) | (BL)Project Start Date | (BL)Project Finish Date | Actual Start Date | Actual Finish Date
CDUVDU1000 | Completed | Feed Cut Out | 26/03/2023 09:30:00 | 26/03/2023 09:30:00 | 26/03/2023 06:00:00 | 26/03/2023 06:00:00 | UNIT SD | PLANT | 100 | OPERATION |  |  | 0 |  |  |  |  | 26-Mar | 26-Mar | 26-Mar | 26-Mar | 03 | Mar
CDUVDU1010 | Completed | Final handover to Maintenance | 26/03/2023 15:16:24 | 06/04/2023 13:46:04 | 26/03/2023 06:00:00 | 04/04/2023 14:00:00 | EQUIPMENT HNDOVR | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 224 | 224:00 | 262:30 | 38:30 |  | 26-Mar | 04-Apr | 26-Mar | 06-Apr | 04 | Apr
CDUVDU1030 | Completed | EQUIPMENT HANDOVER OF 01-FF-001 | 28/03/2023 12:49:06 | 31/03/2023 09:38:04 | 26/03/2023 06:00:00 | 30/03/2023 06:00:00 | 01-FF-001 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 96 | 96:00 | 68:49 |  | 27:11 | 26-Mar | 30-Mar | 28-Mar | 31-Mar | 05 | May
CDUVDU1040 | Completed | EQUIPMENT HANDOVER OF 01-FF-002 | 26/03/2023 12:17:00 | 31/03/2023 12:03:24 | 26/03/2023 06:00:00 | 30/03/2023 06:00:00 | 01-FF-002 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 96 | 96:00 | 119:46 | 23:46 |  | 26-Mar | 30-Mar | 26-Mar | 31-Mar | 06 | Jul
CDUVDU1460 | Completed | EQUIPMENT HANDOVER OF 01-CC-005 | 27/03/2023 11:37:20 | 30/03/2023 09:36:06 | 30/03/2023 08:00:00 | 30/03/2023 08:00:00 | 01-CC-005 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 69:59 | 69:59 |  | 30-Mar | 30-Mar | 27-Mar | 30-Mar | 07 | Aug
CDUVDU1640 | Completed | EQUIPMENT HANDOVER OF 01-CC-001 | 27/03/2023 11:39:19 | 31/03/2023 12:02:48 | 30/03/2023 14:30:00 | 30/03/2023 14:30:00 | 01-CC-001 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 96:23 | 96:23 |  | 30-Mar | 30-Mar | 27-Mar | 31-Mar | 08 | Nov
CDUVDU1650 | Completed | EQUIPMENT HANDOVER OF 01-CC-002 | 31/03/2023 11:50:50 | 31/03/2023 12:02:56 | 30/03/2023 14:30:00 | 30/03/2023 14:30:00 | 01-CC-002 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:12 | 0:12 |  | 30-Mar | 30-Mar | 31-Mar | 31-Mar
CDUVDU1660 | Completed | EQUIPMENT HANDOVER OF 01-CC-003 | 31/03/2023 11:50:30 | 31/03/2023 12:03:06 | 30/03/2023 14:30:00 | 30/03/2023 14:30:00 | 01-CC-003 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:13 | 0:13 |  | 30-Mar | 30-Mar | 31-Mar | 31-Mar
CDUVDU1670 | Completed | EQUIPMENT HANDOVER OF 01-CC-004 | 31/03/2023 11:50:44 | 31/03/2023 12:03:12 | 30/03/2023 14:30:00 | 30/03/2023 14:30:00 | 01-CC-004 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:12 | 0:12 |  | 30-Mar | 30-Mar | 31-Mar | 31-Mar
CDUVDU2050 | Completed | EQUIPMENT HANDOVER OF 01-CC-006 | 27/03/2023 11:40:28 | 01/04/2023 09:49:32 | 31/03/2023 14:30:00 | 31/03/2023 14:30:00 | 01-CC-006 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 118:09 | 118:09 |  | 31-Mar | 31-Mar | 27-Mar | 01-Apr
CDUVDU1860 | Completed | EQUIPMENT HANDOVER OF 01-EE-009B | 27/03/2023 11:41:36 | 01/04/2023 09:49:50 | 31/03/2023 14:30:00 | 31/03/2023 14:30:00 | 01-EE-009B | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 118:08 | 118:08 |  | 31-Mar | 31-Mar | 27-Mar | 01-Apr
CDUVDU1870 | Completed | EQUIPMENT HANDOVER OF 01-EE-091B | 27/03/2023 11:43:47 | 01/04/2023 09:49:58 | 31/03/2023 14:30:00 | 31/03/2023 14:30:00 | 01-EE-091B | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 118:06 | 118:06 |  | 31-Mar | 31-Mar | 27-Mar | 01-Apr
CDUVDU2060 | Completed | EQUIPMENT HANDOVER OF 01-EE-001 | 27/03/2023 11:44:06 | 31/03/2023 11:56:07 | 31/03/2023 14:30:00 | 31/03/2023 14:30:00 | 01-EE-001 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 96:12 | 96:12 |  | 31-Mar | 31-Mar | 27-Mar | 31-Mar
CDUVDU2070 | Completed | EQUIPMENT HANDOVER OF 01-EE-002 | 27/03/2023 11:44:25 | 31/03/2023 11:56:27 | 31/03/2023 14:30:00 | 31/03/2023 14:30:00 | 01-EE-002 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 96:12 | 96:12 |  | 31-Mar | 31-Mar | 27-Mar | 31-Mar
CDUVDU2080 | Completed | EQUIPMENT HANDOVER OF 01-EE-003 | 27/03/2023 11:46:28 | 01/04/2023 09:50:16 | 31/03/2023 14:30:00 | 31/03/2023 14:30:00 | 01-EE-003 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 118:04 | 118:04 |  | 31-Mar | 31-Mar | 27-Mar | 01-Apr
CDUVDU2090 | Completed | EQUIPMENT HANDOVER OF 01-EE-005 | 27/03/2023 11:46:49 | 01/04/2023 09:51:00 | 31/03/2023 14:30:00 | 31/03/2023 14:30:00 | 01-EE-005 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 118:04 | 118:04 |  | 31-Mar | 31-Mar | 27-Mar | 01-Apr
CDUVDU2100 | Completed | EQUIPMENT HANDOVER OF 01-EE-036 | 27/03/2023 11:47:37 | 01/04/2023 10:11:48 | 31/03/2023 14:30:00 | 31/03/2023 14:30:00 | 01-EE-036 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 118:24 | 118:24 |  | 31-Mar | 31-Mar | 27-Mar | 01-Apr
CDUVDU2110 | Completed | EQUIPMENT HANDOVER OF 01-EE-037 | 27/03/2023 11:47:59 | 01/04/2023 10:10:21 | 31/03/2023 14:30:00 | 31/03/2023 14:30:00 | 01-EE-037 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 118:22 | 118:22 |  | 31-Mar | 31-Mar | 27-Mar | 01-Apr
CDUVDU2120 | Completed | EQUIPMENT HANDOVER OF 01-EE-038 | 27/03/2023 11:48:22 | 01/04/2023 10:10:28 | 31/03/2023 14:30:00 | 31/03/2023 14:30:00 | 01-EE-038 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 118:22 | 118:22 |  | 31-Mar | 31-Mar | 27-Mar | 01-Apr
CDUVDU2130 | Completed | EQUIPMENT HANDOVER OF 01-EE-039 | 27/03/2023 11:48:41 | 01/04/2023 10:08:57 | 31/03/2023 14:30:00 | 31/03/2023 14:30:00 | 01-EE-039 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 118:20 | 118:20 |  | 31-Mar | 31-Mar | 27-Mar | 01-Apr
CDUVDU2140 | Completed | EQUIPMENT HANDOVER OF 01-EE-040 | 27/03/2023 11:49:05 | 01/04/2023 10:09:59 | 31/03/2023 14:30:00 | 31/03/2023 14:30:00 | 01-EE-040 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 118:21 | 118:21 |  | 31-Mar | 31-Mar | 27-Mar | 01-Apr
CDUVDU30890 | Completed | EQUIPMENT HANDOVER OF 01-EE-101 | 17/04/2023 16:42:58 | 17/04/2023 16:43:20 | 01/04/2023 15:00:00 | 01/04/2023 15:00:00 | 01-EE-059 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:00 | 0:00 |  | 01-Apr | 01-Apr | 17-Apr | 17-Apr
CDUVDU3100 | Completed | EQUIPMENT HANDOVER OF 01-EE-004 | 27/03/2023 11:49:34 | 31/03/2023 11:56:40 | 01/04/2023 14:30:00 | 01/04/2023 14:30:00 | 01-EE-004 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 96:07 | 96:07 |  | 01-Apr | 01-Apr | 27-Mar | 31-Mar
CDUVDU3110 | Completed | EQUIPMENT HANDOVER OF 01-EE-006 | 27/03/2023 11:49:54 | 31/03/2023 11:56:58 | 01/04/2023 14:30:00 | 01/04/2023 14:30:00 | 01-EE-006 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 96:07 | 96:07 |  | 01-Apr | 01-Apr | 27-Mar | 31-Mar
CDUVDU3120 | Completed | EQUIPMENT HANDOVER OF 01-EE-007 | 27/03/2023 11:50:30 | 31/03/2023 11:57:17 | 01/04/2023 14:30:00 | 01/04/2023 14:30:00 | 01-EE-007 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 96:07 | 96:07 |  | 01-Apr | 01-Apr | 27-Mar | 31-Mar
CDUVDU3130 | Completed | EQUIPMENT HANDOVER OF 01-EE-008 | 27/03/2023 11:51:50 | 01/04/2023 09:50:37 | 01/04/2023 14:30:00 | 01/04/2023 14:30:00 | 01-EE-008 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 117:59 | 117:59 |  | 01-Apr | 01-Apr | 27-Mar | 01-Apr
CDUVDU3140 | Completed | EQUIPMENT HANDOVER OF 01-EE-009A | 27/03/2023 14:34:45 | 01/04/2023 10:17:13 | 01/04/2023 14:30:00 | 01/04/2023 14:30:00 | 01-EE-009A | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 115:42 | 115:42 |  | 01-Apr | 01-Apr | 27-Mar | 01-Apr
CDUVDU3150 | Completed | EQUIPMENT HANDOVER OF 01-EE-010A | 01/04/2023 09:34:26 | 01/04/2023 10:13:11 | 01/04/2023 14:30:00 | 01/04/2023 14:30:00 | 01-EE-010A | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:39 | 0:39 |  | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU3160 | Completed | EQUIPMENT HANDOVER OF 01-EE-010B | 01/04/2023 09:34:52 | 01/04/2023 10:13:18 | 01/04/2023 14:30:00 | 01/04/2023 14:30:00 | 01-EE-010B | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:38 | 0:38 |  | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU3170 | Completed | EQUIPMENT HANDOVER OF 01-EE-011 | 01/04/2023 09:34:44 | 01/04/2023 10:17:05 | 01/04/2023 14:30:00 | 01/04/2023 14:30:00 | 01-EE-011 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:42 | 0:42 |  | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU3180 | Completed | EQUIPMENT HANDOVER OF 01-EE-012 | 01/04/2023 09:35:01 | 01/04/2023 10:17:33 | 01/04/2023 14:30:00 | 01/04/2023 14:30:00 | 01-EE-012 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:43 | 0:43 |  | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU3190 | Completed | EQUIPMENT HANDOVER OF 01-EE-013A | 01/04/2023 09:27:04 | 01/04/2023 10:11:14 | 01/04/2023 14:30:00 | 01/04/2023 14:30:00 | 01-EE-013A | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:44 | 0:44 |  | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU3200 | Completed | EQUIPMENT HANDOVER OF 01-EE-013B | 01/04/2023 09:27:23 | 01/04/2023 10:17:21 | 01/04/2023 14:30:00 | 01/04/2023 14:30:00 | 01-EE-013B | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:50 | 0:50 |  | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU3210 | Completed | EQUIPMENT HANDOVER OF 01-EE-014A | 01/04/2023 09:27:35 | 01/04/2023 10:12:08 | 01/04/2023 14:30:00 | 01/04/2023 14:30:00 | 01-EE-014A | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:45 | 0:45 |  | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU3220 | Completed | EQUIPMENT HANDOVER OF 01-EE-014B | 01/04/2023 09:33:59 | 01/04/2023 10:12:28 | 01/04/2023 14:30:00 | 01/04/2023 14:30:00 | 01-EE-014B | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:38 | 0:38 |  | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU3230 | Completed | EQUIPMENT HANDOVER OF 01-EE-015 | 01/04/2023 09:32:09 | 01/04/2023 10:11:53 | 01/04/2023 14:30:00 | 01/04/2023 14:30:00 | 01-EE-015 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:40 | 0:40 |  | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU3240 | Completed | EQUIPMENT HANDOVER OF 01-EE-016 | 01/04/2023 09:32:21 | 01/04/2023 10:12:14 | 01/04/2023 14:30:00 | 01/04/2023 14:30:00 | 01-EE-016 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:40 | 0:40 |  | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU3250 | Completed | EQUIPMENT HANDOVER OF 01-EE-017 | 01/04/2023 09:33:45 | 01/04/2023 10:13:44 | 01/04/2023 14:30:00 | 01/04/2023 14:30:00 | 01-EE-017 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:40 | 0:40 |  | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU3260 | Completed | EQUIPMENT HANDOVER OF 01-EE-025A | 01/04/2023 09:33:17 | 01/04/2023 10:12:47 | 01/04/2023 14:30:00 | 01/04/2023 14:30:00 | 01-EE-025A | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:40 | 0:40 |  | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU3270 | Completed | EQUIPMENT HANDOVER OF 01-EE-025B | 01/04/2023 09:33:08 | 01/04/2023 10:13:03 | 01/04/2023 14:30:00 | 01/04/2023 14:30:00 | 01-EE-025B | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:40 | 0:40 |  | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU3280 | Completed | EQUIPMENT HANDOVER OF 01-EE-026A | 01/04/2023 09:34:12 | 01/04/2023 10:16:56 | 01/04/2023 14:30:00 | 01/04/2023 14:30:00 | 01-EE-026A | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:43 | 0:43 |  | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU3290 | Completed | EQUIPMENT HANDOVER OF 01-EE-026B | 01/04/2023 09:33:35 | 01/04/2023 10:19:38 | 01/04/2023 14:30:00 | 01/04/2023 14:30:00 | 01-EE-026B | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:46 | 0:46 |  | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU3300 | Completed | EQUIPMENT HANDOVER OF 01-EE-035A | 01/04/2023 10:22:38 | 01/04/2023 10:26:27 | 01/04/2023 14:30:00 | 01/04/2023 14:30:00 | 01-EE-035A | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:04 | 0:04 |  | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU3310 | Completed | EQUIPMENT HANDOVER OF 01-EE-035B | 01/04/2023 10:22:32 | 01/04/2023 10:26:12 | 01/04/2023 14:30:00 | 01/04/2023 14:30:00 | 01-EE-035B | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:04 | 0:04 |  | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU3320 | Completed | EQUIPMENT HANDOVER OF 01-EE-054A | 01/04/2023 09:26:46 | 01/04/2023 10:13:27 | 01/04/2023 14:30:00 | 01/04/2023 14:30:00 | 01-EE-054A | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:47 | 0:47 |  | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU3330 | Completed | EQUIPMENT HANDOVER OF 01-EE-054B | 01/04/2023 09:32:57 | 01/04/2023 10:13:36 | 01/04/2023 14:30:00 | 01/04/2023 14:30:00 | 01-EE-054B | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:41 | 0:41 |  | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU3340 | Completed | EQUIPMENT HANDOVER OF 01-EE-061 | 01/04/2023 09:26:55 | 01/04/2023 10:11:03 | 01/04/2023 14:30:00 | 01/04/2023 14:30:00 | 01-EE-061 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:44 | 0:44 |  | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU3350 | Completed | EQUIPMENT HANDOVER OF 01-EE-062 | 01/04/2023 09:26:32 | 01/04/2023 10:10:43 | 01/04/2023 14:30:00 | 01/04/2023 14:30:00 | 01-EE-062 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:44 | 0:44 |  | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU3360 | Completed | EQUIPMENT HANDOVER OF 01-EE-063A | 01/04/2023 09:25:51 | 01/04/2023 10:10:34 | 01/04/2023 14:30:00 | 01/04/2023 14:30:00 | 01-EE-063A | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:45 | 0:45 |  | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU3370 | Completed | EQUIPMENT HANDOVER OF 01-EE-063B | 01/04/2023 09:26:00 | 01/04/2023 10:10:51 | 01/04/2023 14:30:00 | 01/04/2023 14:30:00 | 01-EE-063B | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:45 | 0:45 |  | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU3380 | Completed | EQUIPMENT HANDOVER OF 01-EE-091A | 01/04/2023 09:27:14 | 01/04/2023 10:11:23 | 01/04/2023 14:30:00 | 01/04/2023 14:30:00 | 01-EE-091A | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:44 | 0:44 |  | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU3390 | Completed | EQUIPMENT HANDOVER OF 01-EE-091C | 01/04/2023 09:32:46 | 01/04/2023 10:12:20 | 01/04/2023 14:30:00 | 01/04/2023 14:30:00 | 01-EE-091C | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:40 | 0:40 |  | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU3400 | Completed | EQUIPMENT HANDOVER OF 01-EE-091D | 01/04/2023 09:33:25 | 01/04/2023 10:12:38 | 01/04/2023 14:30:00 | 01/04/2023 14:30:00 | 01-EE-091D | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:39 | 0:39 |  | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU5400 | Completed | EQUIPMENT HANDOVER OF 01-EE-018 | 01/04/2023 10:23:01 | 01/04/2023 10:27:20 | 02/04/2023 14:30:00 | 02/04/2023 14:30:00 | 01-EE-018 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:04 | 0:04 |  | 02-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU5410 | Completed | EQUIPMENT HANDOVER OF 01-EE-019 | 01/04/2023 09:46:28 | 01/04/2023 10:19:30 | 02/04/2023 14:30:00 | 02/04/2023 14:30:00 | 01-EE-019 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:33 | 0:33 |  | 02-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU5420 | Completed | EQUIPMENT HANDOVER OF 01-EE-020 | 01/04/2023 10:24:10 | 01/04/2023 10:26:58 | 02/04/2023 14:30:00 | 02/04/2023 14:30:00 | 01-EE-020 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:03 | 0:03 |  | 02-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU5430 | Completed | EQUIPMENT HANDOVER OF 01-EE-021 | 01/04/2023 09:42:09 | 01/04/2023 10:19:51 | 02/04/2023 14:30:00 | 02/04/2023 14:30:00 | 01-EE-021 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:38 | 0:38 |  | 02-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU5440 | Completed | EQUIPMENT HANDOVER OF 01-EE-022 | 01/04/2023 09:41:31 | 01/04/2023 10:17:28 | 02/04/2023 14:30:00 | 02/04/2023 14:30:00 | 01-EE-022 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:36 | 0:36 |  | 02-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU5450 | Completed | EQUIPMENT HANDOVER OF 01-EE-023 | 01/04/2023 09:41:41 | 01/04/2023 10:18:03 | 02/04/2023 14:30:00 | 02/04/2023 14:30:00 | 01-EE-023 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:36 | 0:36 |  | 02-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU5460 | Completed | EQUIPMENT HANDOVER OF 01-EE-024 | 01/04/2023 09:48:55 | 01/04/2023 10:18:19 | 02/04/2023 14:30:00 | 02/04/2023 14:30:00 | 01-EE-024 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:29 | 0:29 |  | 02-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU5470 | Completed | EQUIPMENT HANDOVER OF 01-EE-027A | 01/04/2023 10:22:45 | 01/04/2023 10:26:21 | 02/04/2023 14:30:00 | 02/04/2023 14:30:00 | 01-EE-027A | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:04 | 0:04 |  | 02-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU5480 | Completed | EQUIPMENT HANDOVER OF 01-EE-027B | 01/04/2023 10:22:19 | 01/04/2023 10:26:39 | 02/04/2023 14:30:00 | 02/04/2023 14:30:00 | 01-EE-027B | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:04 | 0:04 |  | 02-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU5490 | Completed | EQUIPMENT HANDOVER OF 01-EE-028 | 01/04/2023 10:21:03 | 01/04/2023 10:27:13 | 02/04/2023 14:30:00 | 02/04/2023 14:30:00 | 01-EE-028 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:06 | 0:06 |  | 02-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU5500 | Completed | EQUIPMENT HANDOVER OF 01-EE-029A | 01/04/2023 09:46:09 | 01/04/2023 10:18:40 | 02/04/2023 14:30:00 | 02/04/2023 14:30:00 | 01-EE-029A | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:33 | 0:33 |  | 02-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU5510 | Completed | EQUIPMENT HANDOVER OF 01-EE-029B | 01/04/2023 10:22:54 | 01/04/2023 10:26:48 | 02/04/2023 14:30:00 | 02/04/2023 14:30:00 | 01-EE-029B | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:04 | 0:04 |  | 02-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU5520 | Completed | EQUIPMENT HANDOVER OF 01-EE-046 | 01/04/2023 09:43:45 | 01/04/2023 10:17:42 | 02/04/2023 14:30:00 | 02/04/2023 14:30:00 | 01-EE-046 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:34 | 0:34 |  | 02-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU5530 | Completed | EQUIPMENT HANDOVER OF 01-EE-048 | 01/04/2023 09:46:38 | 01/04/2023 09:51:31 | 02/04/2023 14:30:00 | 02/04/2023 14:30:00 | 01-EE-048 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:05 | 0:05 |  | 02-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU5540 | Completed | EQUIPMENT HANDOVER OF 01-EE-049 | 01/04/2023 09:48:32 | 01/04/2023 10:19:44 | 02/04/2023 14:30:00 | 02/04/2023 14:30:00 | 01-EE-049 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:31 | 0:31 |  | 02-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU5550 | Completed | EQUIPMENT HANDOVER OF 01-EE-050A | 01/04/2023 09:47:04 | 01/04/2023 10:19:24 | 02/04/2023 14:30:00 | 02/04/2023 14:30:00 | 01-EE-050A | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:32 | 0:32 |  | 02-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU5560 | Completed | EQUIPMENT HANDOVER OF 01-EE-050B | 01/04/2023 10:24:21 | 01/04/2023 10:27:26 | 02/04/2023 14:30:00 | 02/04/2023 14:30:00 | 01-EE-050B | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:03 | 0:03 |  | 02-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU5570 | Completed | EQUIPMENT HANDOVER OF 01-EE-051A | 01/04/2023 09:48:44 | 01/04/2023 10:17:57 | 02/04/2023 14:30:00 | 02/04/2023 14:30:00 | 01-EE-051A | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:29 | 0:29 |  | 02-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU5580 | Completed | EQUIPMENT HANDOVER OF 01-EE-051B | 01/04/2023 09:43:33 | 01/04/2023 10:18:10 | 02/04/2023 14:30:00 | 02/04/2023 14:30:00 | 01-EE-051B | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:35 | 0:35 |  | 02-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU5590 | Completed | EQUIPMENT HANDOVER OF 01-EE-052 | 30/03/2023 09:35:00 | 30/03/2023 09:50:00 | 02/04/2023 14:30:00 | 02/04/2023 14:30:00 | 01-EE-052 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:15 | 0:15 |  | 02-Apr | 02-Apr | 30-Mar | 30-Mar
CDUVDU5600 | Completed | EQUIPMENT HANDOVER OF 01-EE-053 | 03/04/2023 09:44:32 | 03/04/2023 09:44:43 | 02/04/2023 14:30:00 | 02/04/2023 14:30:00 | 01-EE-053 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:00 | 0:00 |  | 02-Apr | 02-Apr | 03-Apr | 03-Apr
CDUVDU5610 | Completed | EQUIPMENT HANDOVER OF 01-EE-055 | 01/04/2023 09:41:52 | 01/04/2023 10:18:26 | 02/04/2023 14:30:00 | 02/04/2023 14:30:00 | 01-EE-055 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:37 | 0:37 |  | 02-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU5620 | Completed | EQUIPMENT HANDOVER OF 01-EE-056 | 01/04/2023 09:51:47 | 01/04/2023 10:18:47 | 02/04/2023 14:30:00 | 02/04/2023 14:30:00 | 01-EE-056 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:27 | 0:27 |  | 02-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU5630 | Completed | EQUIPMENT HANDOVER OF 01-EE-059 | 31/03/2023 12:23:10 | 31/03/2023 12:23:17 | 02/04/2023 14:30:00 | 02/04/2023 14:30:00 | 01-EE-059 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:00 | 0:00 |  | 02-Apr | 02-Apr | 31-Mar | 31-Mar
CDUVDU10280 | Completed | EQUIPMENT HANDOVER OF 01-VV-011 | 06/04/2023 17:15:46 | 06/04/2023 17:15:54 | 05/04/2023 14:30:00 | 05/04/2023 14:30:00 | 01-VV-011 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:00 | 0:00 |  | 05-Apr | 05-Apr | 06-Apr | 06-Apr
CDUVDU10290 | Completed | EQUIPMENT HANDOVER OF 01-VV-018 A | 31/03/2023 12:04:57 | 31/03/2023 12:05:01 | 05/04/2023 14:30:00 | 05/04/2023 14:30:00 | 01-VV-018 A | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:00 | 0:00 |  | 05-Apr | 05-Apr | 31-Mar | 31-Mar
CDUVDU10300 | Completed | EQUIPMENT HANDOVER OF 01-VV-018 B | 06/04/2023 11:44:45 | 06/04/2023 11:44:53 | 05/04/2023 14:30:00 | 05/04/2023 14:30:00 | 01-VV-018 B | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:00 | 0:00 |  | 05-Apr | 05-Apr | 06-Apr | 06-Apr
CDUVDU1050 | Completed | EQUIPMENT HANDOVER OF 01-VV-00-47 | 26/03/2023 23:29:47 | 30/03/2023 09:36:26 | 26/03/2023 06:00:00 | 26/03/2023 06:00:00 | 01-VV-00-47 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 82:07 | 82:07 |  | 26-Mar | 26-Mar | 26-Mar | 30-Mar
CDUVDU1470 | Completed | EQUIPMENT HANDOVER OF 01-VV-001 | 30/03/2023 09:17:46 | 31/03/2023 11:54:03 | 30/03/2023 08:00:00 | 30/03/2023 08:00:00 | 01-VV-001 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 26:36 | 26:36 |  | 30-Mar | 30-Mar | 30-Mar | 31-Mar
CDUVDU1480 | Completed | EQUIPMENT HANDOVER OF 01-VV-002 | 30/03/2023 09:37:38 | 31/03/2023 11:54:20 | 30/03/2023 08:00:00 | 30/03/2023 08:00:00 | 01-VV-002 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 26:17 | 26:17 |  | 30-Mar | 30-Mar | 30-Mar | 31-Mar
CDUVDU1490 | Completed | EQUIPMENT HANDOVER OF 01-VV-024 | 31/03/2023 11:49:24 | 31/03/2023 12:03:52 | 30/03/2023 08:00:00 | 30/03/2023 08:00:00 | 01-VV-024 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:14 | 0:14 |  | 30-Mar | 30-Mar | 31-Mar | 31-Mar
CDUVDU1680 | Completed | EQUIPMENT HANDOVER OF 01-VV-009 | 30/03/2023 09:18:45 | 31/03/2023 12:04:13 | 30/03/2023 14:30:00 | 30/03/2023 14:30:00 | 01-VV-009 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 26:45 | 26:45 |  | 30-Mar | 30-Mar | 30-Mar | 31-Mar
CDUVDU1900 | Completed | EQUIPMENT HANDOVER OF 01-VV-007 | 30/03/2023 09:36:48 | 30/03/2023 09:36:53 | 31/03/2023 09:30:00 | 31/03/2023 09:30:00 | 01-VV-007 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:00 | 0:00 |  | 31-Mar | 31-Mar | 30-Mar | 30-Mar
CDUVDU2150 | Completed | EQUIPMENT HANDOVER OF 01-VV-006 | 31/03/2023 11:51:11 | 31/03/2023 11:55:30 | 31/03/2023 14:30:00 | 31/03/2023 14:30:00 | 01-VV-006 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:04 | 0:04 |  | 31-Mar | 31-Mar | 31-Mar | 31-Mar
CDUVDU2160 | Completed | EQUIPMENT HANDOVER OF 01-VV-008 | 01/04/2023 09:25:23 | 01/04/2023 09:52:12 | 31/03/2023 14:30:00 | 31/03/2023 14:30:00 | 01-VV-008 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:27 | 0:27 |  | 31-Mar | 31-Mar | 01-Apr | 01-Apr
CDUVDU2170 | Completed | EQUIPMENT HANDOVER OF 01-VV-026 | 01/04/2023 09:52:23 | 01/04/2023 09:52:31 | 31/03/2023 14:30:00 | 31/03/2023 14:30:00 | 01-VV-026 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:00 | 0:00 |  | 31-Mar | 31-Mar | 01-Apr | 01-Apr
CDUVDU2180 | Completed | EQUIPMENT HANDOVER OF 01-VV-004 | 31/03/2023 11:51:01 | 31/03/2023 11:54:35 | 31/03/2023 14:30:00 | 31/03/2023 14:30:00 | 01-VV-004 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:04 | 0:04 |  | 31-Mar | 31-Mar | 31-Mar | 31-Mar
CDUVDU2350 | Completed | EQUIPMENT HANDOVER OF 01-VV-005 | 31/03/2023 11:51:26 | 31/03/2023 11:55:11 | 31/03/2023 16:30:00 | 31/03/2023 16:30:00 | 01-VV-005 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:04 | 0:04 |  | 31-Mar | 31-Mar | 31-Mar | 31-Mar
CDUVDU2890 | Completed | EQUIPMENT HANDOVER OF 01-VV-021 | 01/04/2023 16:50:03 | 01/04/2023 16:50:16 | 01/04/2023 09:30:00 | 01/04/2023 09:30:00 | 01-VV-021 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:00 | 0:00 |  | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU2900 | Completed | EQUIPMENT HANDOVER OF 01-VV-027 | 01/04/2023 09:25:36 | 01/04/2023 09:52:45 | 01/04/2023 09:30:00 | 01/04/2023 09:30:00 | 01-VV-027 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:27 | 0:27 |  | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU3410 | Completed | EQUIPMENT HANDOVER OF 01-VV-010 | 31/03/2023 12:25:25 | 31/03/2023 12:25:32 | 01/04/2023 14:30:00 | 01/04/2023 14:30:00 | 01-VV-010 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:00 | 0:00 |  | 01-Apr | 01-Apr | 31-Mar | 31-Mar
CDUVDU3420 | Completed | EQUIPMENT HANDOVER OF 01-VV-012 | 01/04/2023 09:35:20 | 01/04/2023 09:52:54 | 01/04/2023 14:30:00 | 01/04/2023 14:30:00 | 01-VV-012 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:18 | 0:18 |  | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU3430 | Completed | EQUIPMENT HANDOVER OF 01-VV-015 | 01/04/2023 09:41:17 | 01/04/2023 09:53:07 | 01/04/2023 14:30:00 | 01/04/2023 14:30:00 | 01-VV-015 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:12 | 0:12 |  | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU4970 | Completed | EQUIPMENT HANDOVER OF 01-VV-019 | 02/04/2023 11:37:34 | 02/04/2023 11:37:40 | 02/04/2023 09:30:00 | 02/04/2023 09:30:00 | 01-VV-019 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:00 | 0:00 |  | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU4980 | Completed | EQUIPMENT HANDOVER OF 01-VV-023 | 01/04/2023 09:53:41 | 01/04/2023 09:53:55 | 02/04/2023 09:30:00 | 02/04/2023 09:30:00 | 01-VV-023 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:00 | 0:00 |  | 02-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU5640 | Completed | EQUIPMENT HANDOVER OF 01-VV-022 | 01/04/2023 09:43:06 | 01/04/2023 09:53:28 | 02/04/2023 14:30:00 | 02/04/2023 14:30:00 | 01-VV-022 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:10 | 0:10 |  | 02-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU5650 | Completed | EQUIPMENT HANDOVER OF 01-VV-020 | 02/04/2023 11:38:12 | 02/04/2023 11:38:18 | 02/04/2023 14:30:00 | 02/04/2023 14:30:00 | 01-VV-020 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:00 | 0:00 |  | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU5660 | Completed | EQUIPMENT HANDOVER OF 01-VV-025 | 01/04/2023 12:37:49 | 01/04/2023 12:37:54 | 02/04/2023 14:30:00 | 02/04/2023 14:30:00 | 01-VV-025 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:00 | 0:00 |  | 02-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU7190 | Completed | EQUIPMENT HANDOVER OF 01-WG-00-001A | 01/04/2023 09:56:19 | 01/04/2023 09:56:41 | 03/04/2023 09:30:00 | 03/04/2023 09:30:00 | 01-WG-00-001A | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:00 | 0:00 |  | 03-Apr | 03-Apr | 01-Apr | 01-Apr
CDUVDU7200 | Completed | EQUIPMENT HANDOVER OF 01-WG-00-001B | 01/04/2023 10:24:34 | 01/04/2023 10:27:50 | 03/04/2023 09:30:00 | 03/04/2023 09:30:00 | 01-WG-00-001B | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:03 | 0:03 |  | 03-Apr | 03-Apr | 01-Apr | 01-Apr
CDUVDU7210 | Completed | EQUIPMENT HANDOVER OF 01-WG-00-002A | 01/04/2023 09:56:57 | 01/04/2023 09:57:03 | 03/04/2023 09:30:00 | 03/04/2023 09:30:00 | 01-WG-00-002A | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:00 | 0:00 |  | 03-Apr | 03-Apr | 01-Apr | 01-Apr
CDUVDU7220 | Completed | EQUIPMENT HANDOVER OF 01-WG-00-002B | 01/04/2023 09:57:19 | 01/04/2023 10:00:37 | 03/04/2023 09:30:00 | 03/04/2023 09:30:00 | 01-WG-00-002B | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:03 | 0:03 |  | 03-Apr | 03-Apr | 01-Apr | 01-Apr
CDUVDU7230 | Completed | EQUIPMENT HANDOVER OF 01-WG-00-003A | 01/04/2023 09:57:45 | 01/04/2023 09:57:49 | 03/04/2023 09:30:00 | 03/04/2023 09:30:00 | 01-WG-00-003A | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:00 | 0:00 |  | 03-Apr | 03-Apr | 01-Apr | 01-Apr
CDUVDU7240 | Completed | EQUIPMENT HANDOVER OF 01-WG-00-003B | 01/04/2023 09:59:45 | 01/04/2023 10:00:57 | 03/04/2023 09:30:00 | 03/04/2023 09:30:00 | 01-WG-00-003B | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:01 | 0:01 |  | 03-Apr | 03-Apr | 01-Apr | 01-Apr
CDUVDU7250 | Completed | EQUIPMENT HANDOVER OF 01-WG-00-004A | 01/04/2023 10:01:20 | 01/04/2023 10:02:54 | 03/04/2023 09:30:00 | 03/04/2023 09:30:00 | 01-WG-00-004A | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:02 | 0:02 |  | 03-Apr | 03-Apr | 01-Apr | 01-Apr
CDUVDU7260 | Completed | EQUIPMENT HANDOVER OF 01-WG-00-004B | 01/04/2023 10:01:30 | 01/04/2023 10:01:52 | 03/04/2023 09:30:00 | 03/04/2023 09:30:00 | 01-WG-00-004B | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:00 | 0:00 |  | 03-Apr | 03-Apr | 01-Apr | 01-Apr
CDUVDU7270 | Completed | EQUIPMENT HANDOVER OF 01-WG-00-005A | 01/04/2023 10:25:46 | 01/04/2023 10:27:36 | 03/04/2023 09:30:00 | 03/04/2023 09:30:00 | 01-WG-00-005A | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:02 | 0:02 |  | 03-Apr | 03-Apr | 01-Apr | 01-Apr
CDUVDU7280 | Completed | EQUIPMENT HANDOVER OF 01-WG-00-005B | 01/04/2023 10:03:16 | 01/04/2023 10:03:20 | 03/04/2023 09:30:00 | 03/04/2023 09:30:00 | 01-WG-00-005B | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:00 | 0:00 |  | 03-Apr | 03-Apr | 01-Apr | 01-Apr
CDUVDU7290 | Completed | EQUIPMENT HANDOVER OF 01-WG-00-006A | 01/04/2023 10:20:41 | 01/04/2023 10:28:18 | 03/04/2023 09:30:00 | 03/04/2023 09:30:00 | 01-WG-00-006A | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:08 | 0:08 |  | 03-Apr | 03-Apr | 01-Apr | 01-Apr
CDUVDU7300 | Completed | EQUIPMENT HANDOVER OF 01-WG-00-006B | 01/04/2023 10:03:45 | 01/04/2023 10:04:06 | 03/04/2023 09:30:00 | 03/04/2023 09:30:00 | 01-WG-00-006B | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:00 | 0:00 |  | 03-Apr | 03-Apr | 01-Apr | 01-Apr
CDUVDU7310 | Completed | EQUIPMENT HANDOVER OF 01-WG-00-007A | 01/04/2023 10:24:48 | 01/04/2023 16:50:44 | 03/04/2023 09:30:00 | 03/04/2023 09:30:00 | 01-WG-00-007A | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 6:26 | 6:26 |  | 03-Apr | 03-Apr | 01-Apr | 01-Apr
CDUVDU7320 | Completed | EQUIPMENT HANDOVER OF 01-WG-00-007B | 01/04/2023 10:04:20 | 01/04/2023 10:04:23 | 03/04/2023 09:30:00 | 03/04/2023 09:30:00 | 01-WG-00-007B | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:00 | 0:00 |  | 03-Apr | 03-Apr | 01-Apr | 01-Apr
CDUVDU7330 | Completed | EQUIPMENT HANDOVER OF 01-WG-00-008A | 01/04/2023 10:00:13 | 01/04/2023 10:00:17 | 03/04/2023 09:30:00 | 03/04/2023 09:30:00 | 01-WG-00-008A | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:00 | 0:00 |  | 03-Apr | 03-Apr | 01-Apr | 01-Apr
CDUVDU7340 | Completed | EQUIPMENT HANDOVER OF 01-WG-00-008B | 01/04/2023 10:25:02 | 01/04/2023 10:27:43 | 03/04/2023 09:30:00 | 03/04/2023 09:30:00 | 01-WG-00-008B | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:03 | 0:03 |  | 03-Apr | 03-Apr | 01-Apr | 01-Apr
CDUVDU7350 | Completed | EQUIPMRNT HANDOVER OF SEAL POT/VOLUME BOTTLE | 03/04/2023 09:45:49 | 03/04/2023 09:45:49 | 03/04/2023 09:30:00 | 03/04/2023 09:30:00 | SEAL POT/VOLUME BOTTLE | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:00 |  |  | 03-Apr | 03-Apr | 03-Apr | 03-Apr
CDUVDU7360 | Completed | EQUIPMRNT HANDOVER OF CI/DE | 03/04/2023 09:45:49 | 03/04/2023 09:45:49 | 03/04/2023 09:30:00 | 03/04/2023 09:30:00 | CI/DE | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:00 |  |  | 03-Apr | 03-Apr | 03-Apr | 03-Apr
CDUVDU7660 | Completed | EQUIPMENT HANDOVER OF 01-VV-014 | 02/04/2023 11:39:09 | 02/04/2023 11:39:17 | 03/04/2023 14:30:00 | 03/04/2023 14:30:00 | 01-VV-014 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:00 | 0:00 |  | 03-Apr | 03-Apr | 02-Apr | 02-Apr
CDUVDU7670 | Completed | EQUIPMENT HANDOVER OF 01-VV-013 | 02/04/2023 11:39:50 | 02/04/2023 11:39:57 | 03/04/2023 14:30:00 | 03/04/2023 14:30:00 | 01-VV-013 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:00 | 0:00 |  | 03-Apr | 03-Apr | 02-Apr | 02-Apr
CDUVDU1500 | Completed | EQUIPMENT HANDOVER OF 01-EA-002 | 01/04/2023 09:25:06 | 01/04/2023 10:12:02 | 30/03/2023 08:00:00 | 30/03/2023 08:00:00 | 01-EA-0020 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:47 | 0:47 |  | 30-Mar | 30-Mar | 01-Apr | 01-Apr
CDUVDU1510 | Completed | EQUIPMENT HANDOVER OF 01-EA-004 | 01/04/2023 09:25:10 | 01/04/2023 10:10:14 | 30/03/2023 08:00:00 | 30/03/2023 08:00:00 | 01-EA-004 | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:45 | 0:45 |  | 30-Mar | 30-Mar | 01-Apr | 01-Apr
CDUVDU1520 | Completed | EQUIPMENT HANDOVER OF 01-EA-005A | 30/03/2023 14:49:03 | 31/03/2023 12:00:46 | 30/03/2023 08:00:00 | 30/03/2023 08:00:00 | 01-EA-005A | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 21:12 | 21:12 |  | 30-Mar | 30-Mar | 30-Mar | 31-Mar
CDUVDU1530 | Completed | EQUIPMENT HANDOVER OF 01-EA-005B | 30/03/2023 14:49:20 | 31/03/2023 12:01:10 | 30/03/2023 08:00:00 | 30/03/2023 08:00:00 | 01-EA-005B | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 21:12 | 21:12 |  | 30-Mar | 30-Mar | 30-Mar | 31-Mar
CDUVDU1540 | Completed | EQUIPMENT HANDOVER OF 01-EA-005C | 30/03/2023 14:49:37 | 31/03/2023 12:01:27 | 30/03/2023 08:00:00 | 30/03/2023 08:00:00 | 01-EA-005C | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 21:12 | 21:12 |  | 30-Mar | 30-Mar | 30-Mar | 31-Mar
CDUVDU1550 | Completed | EQUIPMENT HANDOVER OF 01-EA-005D | 30/03/2023 14:50:06 | 01/04/2023 10:09:28 | 30/03/2023 08:00:00 | 30/03/2023 08:00:00 | 01-EA-005D | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 43:19 | 43:19 |  | 30-Mar | 30-Mar | 30-Mar | 01-Apr
CDUVDU1690 | Completed | EQUIPMENT HANDOVER OF 01-EA-001A | 31/03/2023 11:49:06 | 31/03/2023 11:57:34 | 30/03/2023 14:30:00 | 30/03/2023 14:30:00 | 01-EA-001A | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:08 | 0:08 |  | 30-Mar | 30-Mar | 31-Mar | 31-Mar
CDUVDU1700 | Completed | EQUIPMENT HANDOVER OF 01-EA-001B | 31/03/2023 11:49:41 | 31/03/2023 11:58:16 | 30/03/2023 14:30:00 | 30/03/2023 14:30:00 | 01-EA-001B | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:09 | 0:09 |  | 30-Mar | 30-Mar | 31-Mar | 31-Mar
CDUVDU1710 | Completed | EQUIPMENT HANDOVER OF 01-EA-001C | 31/03/2023 11:49:56 | 31/03/2023 11:58:58 | 30/03/2023 14:30:00 | 30/03/2023 14:30:00 | 01-EA-001C | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:09 | 0:09 |  | 30-Mar | 30-Mar | 31-Mar | 31-Mar
CDUVDU1720 | Completed | EQUIPMENT HANDOVER OF 01-EA-001D | 31/03/2023 11:44:40 | 31/03/2023 11:59:14 | 30/03/2023 14:30:00 | 30/03/2023 14:30:00 | 01-EA-001D | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:15 | 0:15 |  | 30-Mar | 30-Mar | 31-Mar | 31-Mar
CDUVDU1730 | Completed | EQUIPMENT HANDOVER OF 01-EA-001E | 31/03/2023 11:50:05 | 01/04/2023 10:10:08 | 30/03/2023 14:30:00 | 30/03/2023 14:30:00 | 01-EA-001E | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 22:20 | 22:20 |  | 30-Mar | 30-Mar | 31-Mar | 01-Apr
CDUVDU1740 | Completed | EQUIPMENT HANDOVER OF 01-EA-001F | 31/03/2023 11:50:21 | 31/03/2023 12:00:10 | 30/03/2023 14:30:00 | 30/03/2023 14:30:00 | 01-EA-001F | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:10 | 0:10 |  | 30-Mar | 30-Mar | 31-Mar | 31-Mar
CDUVDU1750 | Completed | EQUIPMENT HANDOVER OF 01-EA-006A | 01/04/2023 10:20:15 | 01/04/2023 10:26:05 | 30/03/2023 14:30:00 | 30/03/2023 14:30:00 | 01-EA-006A | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:06 | 0:06 |  | 30-Mar | 30-Mar | 01-Apr | 01-Apr
CDUVDU1760 | Completed | EQUIPMENT HANDOVER OF 01-EA-006B | 01/04/2023 10:20:11 | 01/04/2023 10:26:32 | 30/03/2023 14:30:00 | 30/03/2023 14:30:00 | 01-EA-006B | EQUIPMENT HNDOVR | 100 | OPERATION |  |  | 0 | 0:00 | 0:06 | 0:06 |  | 30-Mar | 30-Mar | 01-Apr | 01-Apr
CDUVDU10530 | Completed | Back Dome Boxup | 05/04/2023 23:53:00 | 06/04/2023 06:53:00 | 05/04/2023 18:30:00 | 06/04/2023 02:30:00 | 01-EE-001 | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 7:00 |  | 1:00 | 05-Apr | 06-Apr | 05-Apr | 06-Apr
CDUVDU10810 | Completed | Final Test | 06/04/2023 09:57:48 | 06/04/2023 12:28:33 | 06/04/2023 02:30:00 | 06/04/2023 17:30:00 | 01-EE-001 | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 2:31 |  | 12:29 | 06-Apr | 06-Apr | 06-Apr | 06-Apr
CDUVDU11770 | Completed | Deblinding | 18/04/2023 00:16:31 | 18/04/2023 00:16:35 | 06/04/2023 17:30:00 | 07/04/2023 01:30:00 | 01-EE-001 | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 06-Apr | 07-Apr | 18-Apr | 18-Apr
CDUVDU2190 | Completed | Blinding As Per Blind List | 31/03/2023 12:27:39 | 01/04/2023 01:08:41 | 31/03/2023 14:30:00 | 01/04/2023 00:30:00 | 01-EE-001 | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 10 | 10:00 | 12:41 | 2:41 |  | 31-Mar | 01-Apr | 31-Mar | 01-Apr
CDUVDU2590 | Completed | Carryout Component Dropping | 31/03/2023 12:37:51 | 31/03/2023 17:21:21 | 01/04/2023 00:30:00 | 01/04/2023 08:30:00 | 01-EE-001 | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 4:43 |  | 3:17 | 01-Apr | 01-Apr | 31-Mar | 31-Mar
CDUVDU2790 | Completed | Carryout Bundle Pullout | 31/03/2023 17:16:36 | 31/03/2023 17:16:45 | 01/04/2023 08:30:00 | 01/04/2023 14:30:00 | 01-EE-001 | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 0:00 |  | 6:00 | 01-Apr | 01-Apr | 31-Mar | 31-Mar
CDUVDU3450 | Completed | Pre Cleaning Inspection | 31/03/2023 17:24:27 | 31/03/2023 17:25:33 | 01/04/2023 14:30:00 | 01/04/2023 16:30:00 | 01-EE-001 | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:01 |  | 1:59 | 01-Apr | 01-Apr | 31-Mar | 31-Mar
CDUVDU3900 | Completed | Bundle Shifting to Bay | 01/04/2023 01:08:02 | 01/04/2023 01:08:41 | 01/04/2023 16:30:00 | 01/04/2023 19:30:00 | 01-EE-001 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:01 |  | 2:59 | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU3920 | Completed | Hydrojetting of Tube Bundle | 01/04/2023 01:08:02 | 02/04/2023 05:41:54 | 01/04/2023 19:30:00 | 02/04/2023 09:30:00 | 01-EE-001 | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 14 | 14:00 | 28:34 | 14:34 |  | 01-Apr | 02-Apr | 01-Apr | 02-Apr
CDUVDU4990 | Completed | Air Drying | 02/04/2023 05:44:47 | 02/04/2023 05:58:35 | 02/04/2023 09:30:00 | 02/04/2023 17:30:00 | 01-EE-001 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:14 |  | 7:46 | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU6230 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 02/04/2023 05:58:48 | 03/04/2023 17:13:20 | 02/04/2023 17:30:00 | 02/04/2023 23:30:00 | 01-EE-001 | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 35:15 | 29:15 |  | 02-Apr | 02-Apr | 02-Apr | 03-Apr
CDUVDU6610 | Completed | Shifting of bundle from bay | 03/04/2023 17:12:23 | 03/04/2023 17:12:29 | 02/04/2023 23:30:00 | 03/04/2023 02:30:00 | 01-EE-001 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 02-Apr | 03-Apr | 03-Apr | 03-Apr
CDUVDU6760 | Completed | Carryout Bundle Insertion | 03/04/2023 18:51:14 | 03/04/2023 19:14:44 | 03/04/2023 02:30:00 | 03/04/2023 10:30:00 | 01-EE-001 | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 0:24 |  | 7:37 | 03-Apr | 03-Apr | 03-Apr | 03-Apr
CDUVDU7430 | Completed | Channelhead Boxup | 04/04/2023 09:50:33 | 04/04/2023 19:16:44 | 03/04/2023 10:30:00 | 03/04/2023 16:30:00 | 01-EE-001 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 9:26 | 3:26 |  | 03-Apr | 03-Apr | 04-Apr | 04-Apr
CDUVDU7940 | Completed | Test Ring Boxup | 04/04/2023 09:53:41 | 04/04/2023 19:16:52 | 03/04/2023 16:30:00 | 04/04/2023 00:30:00 | 01-EE-001 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 9:23 | 1:23 |  | 03-Apr | 04-Apr | 04-Apr | 04-Apr
CDUVDU8270 | Completed | Carryout Shell Test | 05/04/2023 07:35:50 | 05/04/2023 07:35:54 | 04/04/2023 00:30:00 | 04/04/2023 15:30:00 | 01-EE-001 | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 0:00 |  | 15:00 | 04-Apr | 04-Apr | 05-Apr | 05-Apr
CDUVDU9060 | Completed | Test Ring Drop Down | 05/04/2023 15:41:14 | 05/04/2023 15:41:22 | 04/04/2023 15:30:00 | 04/04/2023 21:30:00 | 01-EE-001 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 04-Apr | 04-Apr | 05-Apr | 05-Apr
CDUVDU9300 | Completed | Floating Head Box-up | 05/04/2023 15:41:55 | 05/04/2023 15:42:03 | 04/04/2023 21:30:00 | 05/04/2023 03:30:00 | 01-EE-001 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 04-Apr | 05-Apr | 05-Apr | 05-Apr
CDUVDU9620 | Completed | Tube Test | 05/04/2023 19:28:51 | 05/04/2023 19:28:57 | 05/04/2023 03:30:00 | 05/04/2023 18:30:00 | 01-EE-001 | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 15 | 15:00 | 0:00 |  | 15:00 | 05-Apr | 05-Apr | 05-Apr | 05-Apr
CDUVDU10830 | Completed | Air Drying | 04/04/2023 21:31:41 | 04/04/2023 21:31:41 | 06/04/2023 02:30:00 | 06/04/2023 10:30:00 | 01-EE-009B | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  |  | 06-Apr | 06-Apr | 04-Apr | 04-Apr
CDUVDU11280 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 04/04/2023 21:31:41 | 04/04/2023 21:31:41 | 06/04/2023 10:30:00 | 06/04/2023 16:30:00 | 01-EE-009B | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  |  | 06-Apr | 06-Apr | 04-Apr | 04-Apr
CDUVDU11710 | Completed | Shifting of bundle from bay | 05/04/2023 15:37:19 | 05/04/2023 15:37:28 | 06/04/2023 16:30:00 | 06/04/2023 19:30:00 | 01-EE-009B | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 06-Apr | 06-Apr | 05-Apr | 05-Apr
CDUVDU11910 | Completed | Carryout Bundle Insertion | 05/04/2023 15:37:38 | 05/04/2023 15:38:28 | 06/04/2023 19:30:00 | 07/04/2023 03:30:00 | 01-EE-009B | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 0:01 |  | 7:59 | 06-Apr | 07-Apr | 05-Apr | 05-Apr
CDUVDU12500 | Completed | Channelhead Boxup | 06/04/2023 07:43:55 | 06/04/2023 07:44:00 | 07/04/2023 03:30:00 | 07/04/2023 09:30:00 | 01-EE-009B | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 07-Apr | 07-Apr | 06-Apr | 06-Apr
CDUVDU12840 | Completed | Test Ring Boxup | 07/04/2023 07:15:06 | 07/04/2023 07:15:09 | 07/04/2023 09:30:00 | 07/04/2023 17:30:00 | 01-EE-009B | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  | 8:00 | 07-Apr | 07-Apr | 07-Apr | 07-Apr
CDUVDU13320 | Completed | Carryout Shell Test | 07/04/2023 07:15:25 | 07/04/2023 18:52:03 | 07/04/2023 17:30:00 | 08/04/2023 08:30:00 | 01-EE-009B | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 11:37 |  | 3:23 | 07-Apr | 08-Apr | 07-Apr | 07-Apr
CDUVDU14250 | Completed | Test Ring Drop Down | 07/04/2023 18:52:21 | 08/04/2023 07:24:45 | 08/04/2023 08:30:00 | 08/04/2023 14:30:00 | 01-EE-009B | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 12:32 | 6:32 |  | 08-Apr | 08-Apr | 07-Apr | 08-Apr
CDUVDU14770 | Completed | Floating Head Box-up | 08/04/2023 07:37:22 | 08/04/2023 07:37:22 | 08/04/2023 14:30:00 | 08/04/2023 20:30:00 | 01-EE-009B | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 08-Apr | 08-Apr | 08-Apr | 08-Apr
CDUVDU15130 | Completed | Tube Test | 09/04/2023 07:21:01 | 09/04/2023 17:05:09 | 08/04/2023 20:30:00 | 09/04/2023 11:30:00 | 01-EE-009B | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 15 | 15:00 | 9:44 |  | 5:16 | 08-Apr | 09-Apr | 09-Apr | 09-Apr
CDUVDU16410 | Completed | Back Dome Boxup | 10/04/2023 07:05:05 | 10/04/2023 10:20:39 | 09/04/2023 11:30:00 | 09/04/2023 19:30:00 | 01-EE-009B | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 3:16 |  | 4:44 | 09-Apr | 09-Apr | 10-Apr | 10-Apr
CDUVDU17140 | Completed | Final Test | 10/04/2023 10:51:44 | 10/04/2023 19:32:27 | 09/04/2023 19:30:00 | 10/04/2023 10:30:00 | 01-EE-009B | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 8:41 |  | 6:19 | 09-Apr | 10-Apr | 10-Apr | 10-Apr
CDUVDU18600 | Completed | Deblinding | 18/04/2023 09:44:00 | 20/04/2023 02:58:00 | 10/04/2023 10:30:00 | 10/04/2023 18:30:00 | 01-EE-009B | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 41:14 | 33:14 |  | 10-Apr | 10-Apr | 18-Apr | 20-Apr
CDUVDU1880 | Completed | Blinding As Per Blind List | 02/04/2023 05:48:38 | 02/04/2023 05:48:38 | 31/03/2023 14:30:00 | 31/03/2023 22:30:00 | 01-EE-009B | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  |  | 31-Mar | 31-Mar | 02-Apr | 02-Apr
CDUVDU2360 | Completed | Carryout Component Dropping | 01/04/2023 03:28:20 | 01/04/2023 10:09:45 | 31/03/2023 22:30:00 | 01/04/2023 06:30:00 | 01-EE-009B | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 6:41 |  | 1:19 | 31-Mar | 01-Apr | 01-Apr | 01-Apr
CDUVDU2640 | Completed | Carryout Bundle Pullout | 01/04/2023 16:07:13 | 01/04/2023 16:07:19 | 01/04/2023 06:30:00 | 01/04/2023 12:30:00 | 01-EE-009B | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 0:00 |  | 6:00 | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU2740 | Completed | Pre Cleaning Inspection | 01/04/2023 16:47:21 | 02/04/2023 05:48:38 | 01/04/2023 12:30:00 | 01/04/2023 14:30:00 | 01-EE-009B | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 13:01 | 11:01 |  | 01-Apr | 01-Apr | 01-Apr | 02-Apr
CDUVDU2840 | Completed | Bundle Shifting to Bay | 02/04/2023 06:23:09 | 02/04/2023 06:23:13 | 01/04/2023 14:30:00 | 01/04/2023 17:30:00 | 01-EE-009B | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 01-Apr | 01-Apr | 02-Apr | 02-Apr
CDUVDU9450 | Completed | Hydrojetting of Tube Bundle | 02/04/2023 16:00:19 | 04/04/2023 07:30:46 | 05/04/2023 00:30:00 | 06/04/2023 02:30:00 | 01-EE-009B | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 26 | 26:00 | 39:30 | 13:30 |  | 05-Apr | 06-Apr | 02-Apr | 04-Apr
CDUVDU10840 | Completed | Hydrojetting of Tube Bundle | 03/04/2023 06:10:49 | 04/04/2023 21:32:06 | 06/04/2023 02:30:00 | 07/04/2023 17:30:00 | 01-EE-010A | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 39 | 39:00 | 39:21 | 0:21 |  | 06-Apr | 07-Apr | 03-Apr | 04-Apr
CDUVDU13330 | Completed | Air Drying | 04/04/2023 21:32:06 | 04/04/2023 21:32:06 | 07/04/2023 17:30:00 | 08/04/2023 05:30:00 | 01-EE-010A | EXCHANGER | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:00 |  |  | 07-Apr | 08-Apr | 04-Apr | 04-Apr
CDUVDU14010 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 04/04/2023 21:32:06 | 04/04/2023 21:32:06 | 08/04/2023 05:30:00 | 08/04/2023 11:30:00 | 01-EE-010A | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  |  | 08-Apr | 08-Apr | 04-Apr | 04-Apr
CDUVDU14500 | Completed | Shifting of bundle from bay | 05/04/2023 07:22:58 | 05/04/2023 07:22:58 | 08/04/2023 11:30:00 | 08/04/2023 14:30:00 | 01-EE-010A | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  |  | 08-Apr | 08-Apr | 05-Apr | 05-Apr
CDUVDU14780 | Completed | Carryout Bundle Insertion | 05/04/2023 07:22:58 | 05/04/2023 07:22:58 | 08/04/2023 14:30:00 | 08/04/2023 22:30:00 | 01-EE-010A | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 0:00 |  |  | 08-Apr | 08-Apr | 05-Apr | 05-Apr
CDUVDU15280 | Completed | Channelhead Boxup | 05/04/2023 07:22:58 | 05/04/2023 07:22:58 | 08/04/2023 22:30:00 | 09/04/2023 04:30:00 | 01-EE-010A | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 08-Apr | 09-Apr | 05-Apr | 05-Apr
CDUVDU15880 | Completed | Test Ring Boxup | 05/04/2023 10:14:22 | 05/04/2023 19:30:37 | 09/04/2023 04:30:00 | 09/04/2023 12:30:00 | 01-EE-010A | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 9:16 | 1:16 |  | 09-Apr | 09-Apr | 05-Apr | 05-Apr
CDUVDU16480 | Completed | Carryout Shell Test | 05/04/2023 19:25:00 | 06/04/2023 07:25:50 | 09/04/2023 12:30:00 | 10/04/2023 03:30:00 | 01-EE-010A | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 12:01 |  | 2:59 | 09-Apr | 10-Apr | 05-Apr | 06-Apr
CDUVDU17960 | Completed | Test Ring Drop Down | 08/04/2023 07:25:09 | 08/04/2023 07:25:18 | 10/04/2023 03:30:00 | 10/04/2023 09:30:00 | 01-EE-010A | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 10-Apr | 10-Apr | 08-Apr | 08-Apr
CDUVDU18490 | Completed | Floating Head Box-up | 08/04/2023 07:37:52 | 08/04/2023 07:37:52 | 10/04/2023 09:30:00 | 10/04/2023 15:30:00 | 01-EE-010A | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 10-Apr | 10-Apr | 08-Apr | 08-Apr
CDUVDU19100 | Completed | Tube Test | 09/04/2023 07:21:44 | 09/04/2023 17:05:22 | 10/04/2023 15:30:00 | 11/04/2023 06:30:00 | 01-EE-010A | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 15 | 15:00 | 9:44 |  | 5:16 | 10-Apr | 11-Apr | 09-Apr | 09-Apr
CDUVDU20630 | Completed | Back Dome Boxup | 10/04/2023 07:06:22 | 10/04/2023 10:22:51 | 11/04/2023 06:30:00 | 11/04/2023 14:30:00 | 01-EE-010A | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 3:16 |  | 4:44 | 11-Apr | 11-Apr | 10-Apr | 10-Apr
CDUVDU21530 | Completed | Final Test | 10/04/2023 19:32:45 | 10/04/2023 19:32:50 | 11/04/2023 14:30:00 | 12/04/2023 05:30:00 | 01-EE-010A | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 0:00 |  | 15:00 | 11-Apr | 12-Apr | 10-Apr | 10-Apr
CDUVDU22970 | Completed | Deblinding | 18/04/2023 09:45:00 | 20/04/2023 02:58:00 | 12/04/2023 05:30:00 | 12/04/2023 14:30:00 | 01-EE-010A | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 9 | 9:00 | 41:13 | 32:13 |  | 12-Apr | 12-Apr | 18-Apr | 20-Apr
CDUVDU3520 | Completed | Blinding As Per Blind List | 02/04/2023 05:47:10 | 02/04/2023 05:47:10 | 01/04/2023 14:30:00 | 01/04/2023 22:30:00 | 01-EE-010A | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  |  | 01-Apr | 01-Apr | 02-Apr | 02-Apr
CDUVDU4160 | Completed | Carryout Component Dropping | 01/04/2023 03:23:34 | 01/04/2023 16:09:48 | 01/04/2023 22:30:00 | 02/04/2023 06:30:00 | 01-EE-010A | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 12:46 | 4:46 |  | 01-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU4670 | Completed | Carryout Bundle Pullout | 01/04/2023 18:47:24 | 01/04/2023 18:47:29 | 02/04/2023 06:30:00 | 02/04/2023 12:30:00 | 01-EE-010A | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 0:00 |  | 6:00 | 02-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU5150 | Completed | Pre Cleaning Inspection | 02/04/2023 05:47:10 | 02/04/2023 05:47:10 | 02/04/2023 12:30:00 | 02/04/2023 14:30:00 | 01-EE-010A | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  |  | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU5730 | Completed | Bundle Shifting to Bay | 02/04/2023 06:23:55 | 02/04/2023 06:23:55 | 02/04/2023 14:30:00 | 02/04/2023 17:30:00 | 01-EE-010A | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  |  | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU13340 | Completed | Hydrojetting of Tube Bundle | 03/04/2023 06:11:11 | 04/04/2023 16:23:37 | 07/04/2023 17:30:00 | 09/04/2023 09:30:00 | 01-EE-010B | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 40 | 40:00 | 34:12 |  | 5:48 | 07-Apr | 09-Apr | 03-Apr | 04-Apr
CDUVDU16210 | Completed | Air Drying | 04/04/2023 21:39:31 | 04/04/2023 21:39:31 | 09/04/2023 09:30:00 | 09/04/2023 21:30:00 | 01-EE-010B | EXCHANGER | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:00 |  |  | 09-Apr | 09-Apr | 04-Apr | 04-Apr
CDUVDU17260 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 04/04/2023 16:24:26 | 04/04/2023 21:39:31 | 09/04/2023 21:30:00 | 10/04/2023 03:30:00 | 01-EE-010B | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 5:15 |  | 0:45 | 09-Apr | 10-Apr | 04-Apr | 04-Apr
CDUVDU17970 | Completed | Shifting of bundle from bay | 04/04/2023 16:25:11 | 04/04/2023 16:25:16 | 10/04/2023 03:30:00 | 10/04/2023 07:30:00 | 01-EE-010B | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 10-Apr | 10-Apr | 04-Apr | 04-Apr
CDUVDU18380 | Completed | Carryout Bundle Insertion | 04/04/2023 16:25:24 | 05/04/2023 07:23:18 | 10/04/2023 07:30:00 | 10/04/2023 15:30:00 | 01-EE-010B | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 14:58 | 6:58 |  | 10-Apr | 10-Apr | 04-Apr | 05-Apr
CDUVDU19110 | Completed | Channelhead Boxup | 05/04/2023 07:23:18 | 05/04/2023 07:23:18 | 10/04/2023 15:30:00 | 10/04/2023 21:30:00 | 01-EE-010B | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 10-Apr | 10-Apr | 05-Apr | 05-Apr
CDUVDU19660 | Completed | Test Ring Boxup | 05/04/2023 10:16:34 | 05/04/2023 19:30:57 | 10/04/2023 21:30:00 | 11/04/2023 05:30:00 | 01-EE-010B | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 9:14 | 1:14 |  | 10-Apr | 11-Apr | 05-Apr | 05-Apr
CDUVDU20520 | Completed | Carryout Shell Test | 05/04/2023 17:26:00 | 06/04/2023 07:26:57 | 11/04/2023 05:30:00 | 11/04/2023 20:30:00 | 01-EE-010B | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 14:01 |  | 0:59 | 11-Apr | 11-Apr | 05-Apr | 06-Apr
CDUVDU22090 | Completed | Test Ring Drop Down | 08/04/2023 07:38:09 | 08/04/2023 07:38:09 | 11/04/2023 20:30:00 | 12/04/2023 02:30:00 | 01-EE-010B | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 11-Apr | 12-Apr | 08-Apr | 08-Apr
CDUVDU22630 | Completed | Floating Head Box-up | 08/04/2023 07:38:09 | 08/04/2023 07:38:09 | 12/04/2023 02:30:00 | 12/04/2023 08:30:00 | 01-EE-010B | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 12-Apr | 12-Apr | 08-Apr | 08-Apr
CDUVDU23210 | Completed | Tube Test | 09/04/2023 07:22:14 | 09/04/2023 17:05:33 | 12/04/2023 08:30:00 | 12/04/2023 23:30:00 | 01-EE-010B | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 15 | 15:00 | 9:43 |  | 5:17 | 12-Apr | 12-Apr | 09-Apr | 09-Apr
CDUVDU24490 | Completed | Back Dome Boxup | 10/04/2023 07:07:03 | 10/04/2023 10:23:18 | 12/04/2023 23:30:00 | 13/04/2023 07:30:00 | 01-EE-010B | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 3:16 |  | 4:44 | 12-Apr | 13-Apr | 10-Apr | 10-Apr
CDUVDU25040 | Completed | Final Test | 10/04/2023 19:33:05 | 10/04/2023 19:33:09 | 13/04/2023 07:30:00 | 13/04/2023 22:30:00 | 01-EE-010B | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 0:00 |  | 15:00 | 13-Apr | 13-Apr | 10-Apr | 10-Apr
CDUVDU25880 | Completed | Deblinding | 18/04/2023 09:45:23 | 22/04/2023 18:23:00 | 13/04/2023 22:30:00 | 14/04/2023 06:30:00 | 01-EE-010B | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 104:38 | 96:38 |  | 13-Apr | 14-Apr | 18-Apr | 22-Apr
CDUVDU3530 | Completed | Blinding As Per Blind List | 02/04/2023 05:47:38 | 02/04/2023 05:47:38 | 01/04/2023 14:30:00 | 01/04/2023 22:30:00 | 01-EE-010B | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  |  | 01-Apr | 01-Apr | 02-Apr | 02-Apr
CDUVDU4170 | Completed | Carryout Component Dropping | 01/04/2023 03:26:16 | 01/04/2023 10:12:27 | 01/04/2023 22:30:00 | 02/04/2023 06:30:00 | 01-EE-010B | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 6:46 |  | 1:14 | 01-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU4680 | Completed | Carryout Bundle Pullout | 01/04/2023 18:47:44 | 01/04/2023 18:47:50 | 02/04/2023 06:30:00 | 02/04/2023 12:30:00 | 01-EE-010B | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 0:00 |  | 6:00 | 02-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU5160 | Completed | Pre Cleaning Inspection | 02/04/2023 05:47:38 | 02/04/2023 05:47:38 | 02/04/2023 12:30:00 | 02/04/2023 14:30:00 | 01-EE-010B | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  |  | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU5740 | Completed | Bundle Shifting to Bay | 02/04/2023 06:24:42 | 02/04/2023 06:24:42 | 02/04/2023 14:30:00 | 02/04/2023 17:30:00 | 01-EE-010B | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  |  | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU16220 | Completed | Hydrojetting of Tube Bundle | 07/04/2023 07:18:23 | 07/04/2023 07:18:23 | 09/04/2023 09:30:00 | 09/04/2023 22:30:00 | 01-EE-011 | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 13 | 13:00 | 0:00 |  |  | 09-Apr | 09-Apr | 07-Apr | 07-Apr
CDUVDU17380 | Completed | Air Drying | 07/04/2023 07:18:23 | 07/04/2023 07:18:23 | 09/04/2023 22:30:00 | 10/04/2023 04:30:00 | 01-EE-011 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 09-Apr | 10-Apr | 07-Apr | 07-Apr
CDUVDU18090 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 07/04/2023 07:18:23 | 07/04/2023 07:18:23 | 10/04/2023 04:30:00 | 10/04/2023 10:30:00 | 01-EE-011 | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  |  | 10-Apr | 10-Apr | 07-Apr | 07-Apr
CDUVDU18610 | Completed | Shifting of bundle from bay | 08/04/2023 13:03:35 | 08/04/2023 13:03:35 | 10/04/2023 10:30:00 | 10/04/2023 13:30:00 | 01-EE-011 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  |  | 10-Apr | 10-Apr | 08-Apr | 08-Apr
CDUVDU18880 | Completed | Carryout Bundle Insertion | 08/04/2023 13:03:35 | 08/04/2023 13:03:35 | 10/04/2023 13:30:00 | 10/04/2023 21:30:00 | 01-EE-011 | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 0:00 |  |  | 10-Apr | 10-Apr | 08-Apr | 08-Apr
CDUVDU19670 | Completed | Channelhead Boxup | 10/04/2023 10:25:16 | 10/04/2023 10:25:23 | 10/04/2023 21:30:00 | 11/04/2023 03:30:00 | 01-EE-011 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 10-Apr | 11-Apr | 10-Apr | 10-Apr
CDUVDU20390 | Completed | Test Ring Boxup | 10/04/2023 19:33:19 | 11/04/2023 06:49:24 | 11/04/2023 03:30:00 | 11/04/2023 11:30:00 | 01-EE-011 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 11:16 | 3:16 |  | 11-Apr | 11-Apr | 10-Apr | 11-Apr
CDUVDU21150 | Completed | Carryout Shell Test | 11/04/2023 06:49:33 | 12/04/2023 15:55:51 | 11/04/2023 11:30:00 | 12/04/2023 02:30:00 | 01-EE-011 | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 33:06 | 18:06 |  | 11-Apr | 12-Apr | 11-Apr | 12-Apr
CDUVDU22640 | Completed | Test Ring Drop Down | 12/04/2023 15:56:01 | 12/04/2023 15:56:06 | 12/04/2023 02:30:00 | 12/04/2023 08:30:00 | 01-EE-011 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 12-Apr | 12-Apr | 12-Apr | 12-Apr
CDUVDU23220 | Completed | Floating Head Box-up | 12/04/2023 15:56:16 | 13/04/2023 07:29:55 | 12/04/2023 08:30:00 | 12/04/2023 14:30:00 | 01-EE-011 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 15:34 | 9:34 |  | 12-Apr | 12-Apr | 12-Apr | 13-Apr
CDUVDU23790 | Completed | Tube Test | 13/04/2023 07:30:11 | 13/04/2023 16:57:36 | 12/04/2023 14:30:00 | 13/04/2023 05:30:00 | 01-EE-011 | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 15 | 15:00 | 9:27 |  | 5:33 | 12-Apr | 13-Apr | 13-Apr | 13-Apr
CDUVDU24900 | Completed | Back Dome Boxup | 13/04/2023 16:58:03 | 14/04/2023 07:41:16 | 13/04/2023 05:30:00 | 13/04/2023 13:30:00 | 01-EE-011 | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 14:43 | 6:43 |  | 13-Apr | 13-Apr | 13-Apr | 14-Apr
CDUVDU25340 | Completed | Final Test | 14/04/2023 00:44:37 | 15/04/2023 05:43:49 | 13/04/2023 13:30:00 | 14/04/2023 04:30:00 | 01-EE-011 | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 28:59 | 13:59 |  | 13-Apr | 14-Apr | 14-Apr | 15-Apr
CDUVDU26190 | Completed | Deblinding | 17/04/2023 09:53:00 | 20/04/2023 02:58:00 | 14/04/2023 04:30:00 | 14/04/2023 12:30:00 | 01-EE-011 | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 65:05 | 57:05 |  | 14-Apr | 14-Apr | 17-Apr | 20-Apr
CDUVDU3540 | Completed | Blinding As Per Blind List | 02/04/2023 07:32:04 | 02/04/2023 07:32:04 | 01/04/2023 14:30:00 | 01/04/2023 22:30:00 | 01-EE-011 | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  |  | 01-Apr | 01-Apr | 02-Apr | 02-Apr
CDUVDU4180 | Completed | Carryout Component Dropping | 31/03/2023 18:57:19 | 02/04/2023 06:25:15 | 01/04/2023 22:30:00 | 02/04/2023 06:30:00 | 01-EE-011 | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 35:28 | 27:28 |  | 01-Apr | 02-Apr | 31-Mar | 02-Apr
CDUVDU4690 | Completed | Carryout Bundle Pullout | 02/04/2023 19:09:45 | 02/04/2023 19:09:51 | 02/04/2023 06:30:00 | 02/04/2023 12:30:00 | 01-EE-011 | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 0:00 |  | 6:00 | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU5170 | Completed | Pre Cleaning Inspection | 03/04/2023 06:11:36 | 03/04/2023 06:11:36 | 02/04/2023 12:30:00 | 02/04/2023 14:30:00 | 01-EE-011 | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  |  | 02-Apr | 02-Apr | 03-Apr | 03-Apr
CDUVDU5750 | Completed | Bundle Shifting to Bay | 04/04/2023 07:31:51 | 04/04/2023 07:31:54 | 02/04/2023 14:30:00 | 02/04/2023 17:30:00 | 01-EE-011 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 02-Apr | 02-Apr | 04-Apr | 04-Apr
CDUVDU17390 | Completed | Hydrojetting of Tube Bundle | 04/04/2023 21:39:51 | 04/04/2023 21:39:51 | 09/04/2023 22:30:00 | 10/04/2023 11:30:00 | 01-EE-012 | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 13 | 13:00 | 0:00 |  |  | 09-Apr | 10-Apr | 04-Apr | 04-Apr
CDUVDU18660 | Completed | Air Drying | 04/04/2023 21:39:51 | 04/04/2023 21:39:51 | 10/04/2023 11:30:00 | 10/04/2023 17:30:00 | 01-EE-012 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 10-Apr | 10-Apr | 04-Apr | 04-Apr
CDUVDU19260 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 04/04/2023 21:39:51 | 04/04/2023 21:39:51 | 10/04/2023 17:30:00 | 10/04/2023 23:30:00 | 01-EE-012 | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  |  | 10-Apr | 10-Apr | 04-Apr | 04-Apr
CDUVDU19910 | Completed | Shifting of bundle from bay | 06/04/2023 07:45:10 | 06/04/2023 07:45:10 | 10/04/2023 23:30:00 | 11/04/2023 02:30:00 | 01-EE-012 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  |  | 10-Apr | 11-Apr | 06-Apr | 06-Apr
CDUVDU20310 | Completed | Carryout Bundle Insertion | 06/04/2023 07:45:10 | 06/04/2023 07:45:10 | 11/04/2023 02:30:00 | 11/04/2023 10:30:00 | 01-EE-012 | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 0:00 |  |  | 11-Apr | 11-Apr | 06-Apr | 06-Apr
CDUVDU20980 | Completed | Channelhead Boxup | 07/04/2023 07:18:52 | 07/04/2023 07:18:52 | 11/04/2023 10:30:00 | 11/04/2023 16:30:00 | 01-EE-012 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 11-Apr | 11-Apr | 07-Apr | 07-Apr
CDUVDU21650 | Completed | Test Ring Boxup | 07/04/2023 11:57:25 | 07/04/2023 11:59:26 | 11/04/2023 16:30:00 | 12/04/2023 00:30:00 | 01-EE-012 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:02 |  | 7:58 | 11-Apr | 12-Apr | 07-Apr | 07-Apr
CDUVDU22380 | Completed | Carryout Shell Test | 07/04/2023 11:57:25 | 07/04/2023 18:54:03 | 12/04/2023 00:30:00 | 12/04/2023 15:30:00 | 01-EE-012 | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 6:57 |  | 8:03 | 12-Apr | 12-Apr | 07-Apr | 07-Apr
CDUVDU23840 | Completed | Test Ring Drop Down | 07/04/2023 18:53:43 | 07/04/2023 18:53:50 | 12/04/2023 15:30:00 | 12/04/2023 21:30:00 | 01-EE-012 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 12-Apr | 12-Apr | 07-Apr | 07-Apr
CDUVDU24300 | Completed | Floating Head Box-up | 07/04/2023 18:54:30 | 08/04/2023 07:38:39 | 12/04/2023 21:30:00 | 13/04/2023 03:30:00 | 01-EE-012 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 12:44 | 6:44 |  | 12-Apr | 13-Apr | 07-Apr | 08-Apr
CDUVDU24770 | Completed | Tube Test | 08/04/2023 09:46:14 | 08/04/2023 16:04:20 | 13/04/2023 03:30:00 | 13/04/2023 18:30:00 | 01-EE-012 | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 15 | 15:00 | 6:18 |  | 8:42 | 13-Apr | 13-Apr | 08-Apr | 08-Apr
CDUVDU25720 | Completed | Back Dome Boxup | 08/04/2023 16:04:28 | 09/04/2023 10:30:38 | 13/04/2023 18:30:00 | 14/04/2023 02:30:00 | 01-EE-012 | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 18:26 | 10:26 |  | 13-Apr | 14-Apr | 08-Apr | 09-Apr
CDUVDU26100 | Completed | Final Test | 09/04/2023 18:30:07 | 10/04/2023 09:23:16 | 14/04/2023 02:30:00 | 14/04/2023 17:30:00 | 01-EE-012 | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 14:53 |  | 0:07 | 14-Apr | 14-Apr | 09-Apr | 10-Apr
CDUVDU26800 | Completed | Deblinding | 18/04/2023 09:45:00 | 18/04/2023 17:45:00 | 14/04/2023 17:30:00 | 15/04/2023 01:30:00 | 01-EE-012 | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 8:00 |  |  | 14-Apr | 15-Apr | 18-Apr | 18-Apr
CDUVDU3550 | Completed | Blinding As Per Blind List | 01/04/2023 03:12:19 | 01/04/2023 03:12:39 | 01/04/2023 14:30:00 | 01/04/2023 22:30:00 | 01-EE-012 | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU4190 | Completed | Carryout Component Dropping | 01/04/2023 03:12:30 | 01/04/2023 10:14:28 | 01/04/2023 22:30:00 | 02/04/2023 06:30:00 | 01-EE-012 | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 7:02 |  | 0:58 | 01-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU4700 | Completed | Carryout Bundle Pullout | 02/04/2023 19:10:45 | 02/04/2023 19:10:51 | 02/04/2023 06:30:00 | 02/04/2023 12:30:00 | 01-EE-012 | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 0:00 |  | 6:00 | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU5180 | Completed | Pre Cleaning Inspection | 03/04/2023 06:12:06 | 03/04/2023 06:12:06 | 02/04/2023 12:30:00 | 02/04/2023 14:30:00 | 01-EE-012 | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  |  | 02-Apr | 02-Apr | 03-Apr | 03-Apr
CDUVDU5760 | Completed | Bundle Shifting to Bay | 03/04/2023 06:12:34 | 03/04/2023 06:12:34 | 02/04/2023 14:30:00 | 02/04/2023 17:30:00 | 01-EE-012 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  |  | 02-Apr | 02-Apr | 03-Apr | 03-Apr
CDUVDU18670 | Completed | Hydrojetting of Tube Bundle | 04/04/2023 21:40:31 | 04/04/2023 21:40:31 | 10/04/2023 11:30:00 | 11/04/2023 00:30:00 | 01-EE-013A | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 13 | 13:00 | 0:00 |  |  | 10-Apr | 11-Apr | 04-Apr | 04-Apr
CDUVDU20040 | Completed | Air Drying | 04/04/2023 21:40:31 | 04/04/2023 21:40:31 | 11/04/2023 00:30:00 | 11/04/2023 06:30:00 | 01-EE-013A | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 11-Apr | 11-Apr | 04-Apr | 04-Apr
CDUVDU20640 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 04/04/2023 21:40:31 | 04/04/2023 21:40:31 | 11/04/2023 06:30:00 | 11/04/2023 12:30:00 | 01-EE-013A | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  |  | 11-Apr | 11-Apr | 04-Apr | 04-Apr
CDUVDU21200 | Completed | Shifting of bundle from bay | 05/04/2023 07:24:16 | 05/04/2023 07:24:16 | 11/04/2023 12:30:00 | 11/04/2023 15:30:00 | 01-EE-013A | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  |  | 11-Apr | 11-Apr | 05-Apr | 05-Apr
CDUVDU21610 | Completed | Carryout Bundle Insertion | 05/04/2023 07:24:16 | 05/04/2023 07:24:16 | 11/04/2023 15:30:00 | 11/04/2023 23:30:00 | 01-EE-013A | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 0:00 |  |  | 11-Apr | 11-Apr | 05-Apr | 05-Apr
CDUVDU22320 | Completed | Channelhead Boxup | 06/04/2023 15:43:06 | 07/04/2023 07:20:08 | 11/04/2023 23:30:00 | 12/04/2023 05:30:00 | 01-EE-013A | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 15:37 | 9:37 |  | 11-Apr | 12-Apr | 06-Apr | 07-Apr
CDUVDU22980 | Completed | Test Ring Boxup | 06/04/2023 15:43:42 | 07/04/2023 07:20:08 | 12/04/2023 05:30:00 | 12/04/2023 13:30:00 | 01-EE-013A | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 15:36 | 7:36 |  | 12-Apr | 12-Apr | 06-Apr | 07-Apr
CDUVDU23620 | Completed | Carryout Shell Test | 07/04/2023 08:00:58 | 07/04/2023 08:00:58 | 12/04/2023 13:30:00 | 13/04/2023 04:30:00 | 01-EE-013A | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 0:00 |  |  | 12-Apr | 13-Apr | 07-Apr | 07-Apr
CDUVDU24840 | Completed | Test Ring Drop Down | 07/04/2023 12:01:17 | 07/04/2023 12:01:24 | 13/04/2023 04:30:00 | 13/04/2023 10:30:00 | 01-EE-013A | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 13-Apr | 13-Apr | 07-Apr | 07-Apr
CDUVDU25270 | Completed | Floating Head Box-up | 07/04/2023 19:00:07 | 08/04/2023 07:39:18 | 13/04/2023 10:30:00 | 13/04/2023 16:30:00 | 01-EE-013A | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 12:39 | 6:39 |  | 13-Apr | 13-Apr | 07-Apr | 08-Apr
CDUVDU25580 | Completed | Tube Test | 08/04/2023 07:39:28 | 08/04/2023 16:03:55 | 13/04/2023 16:30:00 | 14/04/2023 07:30:00 | 01-EE-013A | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 15 | 15:00 | 8:24 |  | 6:36 | 13-Apr | 14-Apr | 08-Apr | 08-Apr
CDUVDU26310 | Completed | Back Dome Boxup | 09/04/2023 07:23:39 | 09/04/2023 07:23:39 | 14/04/2023 07:30:00 | 14/04/2023 15:30:00 | 01-EE-013A | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 0:00 |  |  | 14-Apr | 14-Apr | 09-Apr | 09-Apr
CDUVDU26690 | Completed | Final Test | 10/04/2023 07:08:20 | 10/04/2023 09:23:45 | 14/04/2023 15:30:00 | 15/04/2023 06:30:00 | 01-EE-013A | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 2:15 |  | 12:45 | 14-Apr | 15-Apr | 10-Apr | 10-Apr
CDUVDU27270 | Completed | Deblinding | 18/04/2023 09:45:56 | 18/04/2023 17:52:50 | 15/04/2023 06:30:00 | 15/04/2023 14:30:00 | 01-EE-013A | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 8:07 | 0:07 |  | 15-Apr | 15-Apr | 18-Apr | 18-Apr
CDUVDU3560 | Completed | Blinding As Per Blind List | 02/04/2023 07:32:50 | 02/04/2023 07:32:50 | 01/04/2023 14:30:00 | 01/04/2023 22:30:00 | 01-EE-013A | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  |  | 01-Apr | 01-Apr | 02-Apr | 02-Apr
CDUVDU4200 | Completed | Carryout Component Dropping | 01/04/2023 16:13:44 | 01/04/2023 19:08:04 | 01/04/2023 22:30:00 | 02/04/2023 06:30:00 | 01-EE-013A | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 2:54 |  | 5:06 | 01-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU4710 | Completed | Carryout Bundle Pullout | 03/04/2023 01:57:53 | 03/04/2023 01:57:59 | 02/04/2023 06:30:00 | 02/04/2023 12:30:00 | 01-EE-013A | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 0:00 |  | 6:00 | 02-Apr | 02-Apr | 03-Apr | 03-Apr
CDUVDU5190 | Completed | Pre Cleaning Inspection | 03/04/2023 06:13:13 | 03/04/2023 06:13:13 | 02/04/2023 12:30:00 | 02/04/2023 14:30:00 | 01-EE-013A | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  |  | 02-Apr | 02-Apr | 03-Apr | 03-Apr
CDUVDU5770 | Completed | Bundle Shifting to Bay | 03/04/2023 06:13:13 | 03/04/2023 06:13:13 | 02/04/2023 14:30:00 | 02/04/2023 17:30:00 | 01-EE-013A | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  |  | 02-Apr | 02-Apr | 03-Apr | 03-Apr
CDUVDU20050 | Completed | Hydrojetting of Tube Bundle | 04/04/2023 21:40:47 | 04/04/2023 21:40:47 | 11/04/2023 00:30:00 | 11/04/2023 13:30:00 | 01-EE-013B | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 13 | 13:00 | 0:00 |  |  | 11-Apr | 11-Apr | 04-Apr | 04-Apr
CDUVDU21240 | Completed | Air Drying | 04/04/2023 21:40:47 | 04/04/2023 21:40:47 | 11/04/2023 13:30:00 | 11/04/2023 19:30:00 | 01-EE-013B | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 11-Apr | 11-Apr | 04-Apr | 04-Apr
CDUVDU22010 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 04/04/2023 21:40:47 | 04/04/2023 21:40:47 | 11/04/2023 19:30:00 | 12/04/2023 01:30:00 | 01-EE-013B | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  |  | 11-Apr | 12-Apr | 04-Apr | 04-Apr
CDUVDU22440 | Completed | Shifting of bundle from bay | 05/04/2023 07:24:32 | 05/04/2023 07:24:32 | 12/04/2023 01:30:00 | 12/04/2023 04:30:00 | 01-EE-013B | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  |  | 12-Apr | 12-Apr | 05-Apr | 05-Apr
CDUVDU22860 | Completed | Carryout Bundle Insertion | 05/04/2023 07:24:32 | 05/04/2023 07:24:32 | 12/04/2023 04:30:00 | 12/04/2023 12:30:00 | 01-EE-013B | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 0:00 |  |  | 12-Apr | 12-Apr | 05-Apr | 05-Apr
CDUVDU23600 | Completed | Channelhead Boxup | 06/04/2023 15:47:07 | 07/04/2023 07:20:40 | 12/04/2023 12:30:00 | 12/04/2023 18:30:00 | 01-EE-013B | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 15:34 | 9:34 |  | 12-Apr | 12-Apr | 06-Apr | 07-Apr
CDUVDU24130 | Completed | Test Ring Boxup | 06/04/2023 15:47:26 | 07/04/2023 07:20:40 | 12/04/2023 18:30:00 | 13/04/2023 02:30:00 | 01-EE-013B | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 15:33 | 7:33 |  | 12-Apr | 13-Apr | 06-Apr | 07-Apr
CDUVDU24720 | Completed | Carryout Shell Test | 07/04/2023 08:01:17 | 07/04/2023 08:01:17 | 13/04/2023 02:30:00 | 13/04/2023 17:30:00 | 01-EE-013B | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 0:00 |  |  | 13-Apr | 13-Apr | 07-Apr | 07-Apr
CDUVDU25610 | Completed | Test Ring Drop Down | 07/04/2023 12:01:40 | 07/04/2023 12:01:46 | 13/04/2023 17:30:00 | 13/04/2023 23:30:00 | 01-EE-013B | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 13-Apr | 13-Apr | 07-Apr | 07-Apr
CDUVDU25900 | Completed | Floating Head Box-up | 07/04/2023 18:58:28 | 07/04/2023 18:58:34 | 13/04/2023 23:30:00 | 14/04/2023 05:30:00 | 01-EE-013B | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 13-Apr | 14-Apr | 07-Apr | 07-Apr
CDUVDU26230 | Completed | Tube Test | 08/04/2023 07:39:59 | 08/04/2023 16:04:09 | 14/04/2023 05:30:00 | 14/04/2023 20:30:00 | 01-EE-013B | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 15 | 15:00 | 8:24 |  | 6:36 | 14-Apr | 14-Apr | 08-Apr | 08-Apr
CDUVDU26890 | Completed | Back Dome Boxup | 09/04/2023 07:23:22 | 09/04/2023 07:23:22 | 14/04/2023 20:30:00 | 15/04/2023 04:30:00 | 01-EE-013B | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 0:00 |  |  | 14-Apr | 15-Apr | 09-Apr | 09-Apr
CDUVDU27200 | Completed | Final Test | 10/04/2023 07:09:04 | 10/04/2023 09:24:18 | 15/04/2023 04:30:00 | 15/04/2023 19:30:00 | 01-EE-013B | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 2:15 |  | 12:45 | 15-Apr | 15-Apr | 10-Apr | 10-Apr
CDUVDU27720 | Completed | Deblinding | 18/04/2023 09:46:11 | 18/04/2023 17:53:04 | 15/04/2023 19:30:00 | 16/04/2023 03:30:00 | 01-EE-013B | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 8:07 | 0:07 |  | 15-Apr | 16-Apr | 18-Apr | 18-Apr
CDUVDU3570 | Completed | Blinding As Per Blind List | 02/04/2023 07:33:14 | 02/04/2023 07:33:14 | 01/04/2023 14:30:00 | 01/04/2023 22:30:00 | 01-EE-013B | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  |  | 01-Apr | 01-Apr | 02-Apr | 02-Apr
CDUVDU4210 | Completed | Carryout Component Dropping | 01/04/2023 16:14:18 | 01/04/2023 19:08:24 | 01/04/2023 22:30:00 | 02/04/2023 06:30:00 | 01-EE-013B | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 2:54 |  | 5:06 | 01-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU4720 | Completed | Carryout Bundle Pullout | 02/04/2023 19:12:04 | 02/04/2023 19:12:09 | 02/04/2023 06:30:00 | 02/04/2023 12:30:00 | 01-EE-013B | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 0:00 |  | 6:00 | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU5200 | Completed | Pre Cleaning Inspection | 03/04/2023 06:13:37 | 03/04/2023 06:13:37 | 02/04/2023 12:30:00 | 02/04/2023 14:30:00 | 01-EE-013B | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  |  | 02-Apr | 02-Apr | 03-Apr | 03-Apr
CDUVDU5780 | Completed | Bundle Shifting to Bay | 03/04/2023 06:13:37 | 03/04/2023 06:13:37 | 02/04/2023 14:30:00 | 02/04/2023 17:30:00 | 01-EE-013B | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  |  | 02-Apr | 02-Apr | 03-Apr | 03-Apr
CDUVDU21250 | Completed | Hydrojetting of Tube Bundle | 07/04/2023 07:21:03 | 07/04/2023 08:02:10 | 11/04/2023 13:30:00 | 12/04/2023 15:30:00 | 01-EE-014A | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 26 | 26:00 | 0:41 |  | 25:19 | 11-Apr | 12-Apr | 07-Apr | 07-Apr
CDUVDU23850 | Completed | Air Drying | 07/04/2023 08:02:10 | 07/04/2023 08:02:10 | 12/04/2023 15:30:00 | 12/04/2023 23:30:00 | 01-EE-014A | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  |  | 12-Apr | 12-Apr | 07-Apr | 07-Apr
CDUVDU24500 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 07/04/2023 08:02:10 | 07/04/2023 08:02:10 | 12/04/2023 23:30:00 | 13/04/2023 05:30:00 | 01-EE-014A | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  |  | 12-Apr | 13-Apr | 07-Apr | 07-Apr
CDUVDU24910 | Completed | Shifting of bundle from bay | 08/04/2023 07:28:15 | 08/04/2023 07:28:15 | 13/04/2023 05:30:00 | 13/04/2023 09:30:00 | 01-EE-014A | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  |  | 13-Apr | 13-Apr | 08-Apr | 08-Apr
CDUVDU25160 | Completed | Carryout Bundle Insertion | 08/04/2023 07:28:15 | 08/04/2023 07:28:15 | 13/04/2023 09:30:00 | 13/04/2023 17:30:00 | 01-EE-014A | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 0:00 |  |  | 13-Apr | 13-Apr | 08-Apr | 08-Apr
CDUVDU25620 | Completed | Channelhead Boxup | 07/04/2023 22:02:52 | 07/04/2023 22:02:52 | 13/04/2023 17:30:00 | 13/04/2023 23:30:00 | 01-EE-014A | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 13-Apr | 13-Apr | 07-Apr | 07-Apr
CDUVDU25910 | Completed | Test Ring Boxup | 08/04/2023 07:28:15 | 08/04/2023 07:28:15 | 13/04/2023 23:30:00 | 14/04/2023 07:30:00 | 01-EE-014A | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  |  | 13-Apr | 14-Apr | 08-Apr | 08-Apr
CDUVDU26320 | Completed | Carryout Shell Test | 07/04/2023 22:00:55 | 07/04/2023 22:00:55 | 14/04/2023 07:30:00 | 14/04/2023 22:30:00 | 01-EE-014A | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 0:00 |  |  | 14-Apr | 14-Apr | 07-Apr | 07-Apr
CDUVDU27010 | Completed | Test Ring Drop Down | 13/04/2023 19:00:32 | 13/04/2023 19:00:37 | 14/04/2023 22:30:00 | 15/04/2023 04:30:00 | 01-EE-014A | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 14-Apr | 15-Apr | 13-Apr | 13-Apr
CDUVDU27210 | Completed | Floating Head Box-up | 14/04/2023 05:02:08 | 15/04/2023 05:45:14 | 15/04/2023 04:30:00 | 15/04/2023 10:30:00 | 01-EE-014A | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 24:43 | 18:43 |  | 15-Apr | 15-Apr | 14-Apr | 15-Apr
CDUVDU27430 | Completed | Tube Test | 15/04/2023 00:20:53 | 16/04/2023 17:39:03 | 15/04/2023 10:30:00 | 16/04/2023 01:30:00 | 01-EE-014A | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 15 | 15:00 | 41:18 | 26:18 |  | 15-Apr | 16-Apr | 15-Apr | 16-Apr
CDUVDU27890 | Completed | Back Dome Boxup | 17/04/2023 01:42:33 | 17/04/2023 01:42:41 | 16/04/2023 01:30:00 | 16/04/2023 09:30:00 | 01-EE-014A | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 0:00 |  | 8:00 | 16-Apr | 16-Apr | 17-Apr | 17-Apr
CDUVDU28170 | Completed | Final Test | 17/04/2023 01:43:00 | 17/04/2023 01:43:03 | 16/04/2023 09:30:00 | 17/04/2023 00:30:00 | 01-EE-014A | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 0:00 |  | 15:00 | 16-Apr | 17-Apr | 17-Apr | 17-Apr
CDUVDU28630 | Completed | Deblinding | 18/04/2023 09:46:25 | 18/04/2023 17:53:21 | 17/04/2023 00:30:00 | 17/04/2023 08:30:00 | 01-EE-014A | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 8:07 | 0:07 |  | 17-Apr | 17-Apr | 18-Apr | 18-Apr
CDUVDU3580 | Completed | Blinding As Per Blind List | 02/04/2023 06:26:24 | 02/04/2023 06:26:29 | 01/04/2023 14:30:00 | 01/04/2023 22:30:00 | 01-EE-014A | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 01-Apr | 01-Apr | 02-Apr | 02-Apr
CDUVDU4220 | Completed | Carryout Component Dropping | 01/04/2023 16:15:21 | 01/04/2023 19:00:14 | 01/04/2023 22:30:00 | 02/04/2023 06:30:00 | 01-EE-014A | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 2:45 |  | 5:15 | 01-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU4730 | Completed | Carryout Bundle Pullout | 01/04/2023 18:48:14 | 03/04/2023 04:37:59 | 02/04/2023 06:30:00 | 02/04/2023 12:30:00 | 01-EE-014A | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 33:50 | 27:50 |  | 02-Apr | 02-Apr | 01-Apr | 03-Apr
CDUVDU5210 | Completed | Pre Cleaning Inspection | 03/04/2023 06:14:01 | 03/04/2023 17:43:37 | 02/04/2023 12:30:00 | 02/04/2023 14:30:00 | 01-EE-014A | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 11:30 | 9:30 |  | 02-Apr | 02-Apr | 03-Apr | 03-Apr
CDUVDU5790 | Completed | Bundle Shifting to Bay | 03/04/2023 06:14:01 | 06/04/2023 15:51:59 | 02/04/2023 14:30:00 | 02/04/2023 17:30:00 | 01-EE-014A | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 81:38 | 78:38 |  | 02-Apr | 02-Apr | 03-Apr | 06-Apr
CDUVDU23860 | Completed | Hydrojetting of Tube Bundle | 07/04/2023 07:23:01 | 07/04/2023 07:23:01 | 12/04/2023 15:30:00 | 13/04/2023 17:30:00 | 01-EE-014B | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 26 | 26:00 | 0:00 |  |  | 12-Apr | 13-Apr | 07-Apr | 07-Apr
CDUVDU25630 | Completed | Air Drying | 07/04/2023 07:23:01 | 07/04/2023 07:23:01 | 13/04/2023 17:30:00 | 14/04/2023 01:30:00 | 01-EE-014B | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  |  | 13-Apr | 14-Apr | 07-Apr | 07-Apr
CDUVDU25980 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 07/04/2023 07:23:01 | 07/04/2023 07:23:01 | 14/04/2023 01:30:00 | 14/04/2023 07:30:00 | 01-EE-014B | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  |  | 14-Apr | 14-Apr | 07-Apr | 07-Apr
CDUVDU26330 | Completed | Shifting of bundle from bay | 09/04/2023 07:23:06 | 09/04/2023 07:23:06 | 14/04/2023 07:30:00 | 14/04/2023 11:30:00 | 01-EE-014B | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  |  | 14-Apr | 14-Apr | 09-Apr | 09-Apr
CDUVDU26500 | Completed | Carryout Bundle Insertion | 09/04/2023 07:23:06 | 09/04/2023 07:23:06 | 14/04/2023 11:30:00 | 14/04/2023 19:30:00 | 01-EE-014B | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 0:00 |  |  | 14-Apr | 14-Apr | 09-Apr | 09-Apr
CDUVDU26860 | Completed | Channelhead Boxup | 07/04/2023 22:03:41 | 07/04/2023 22:03:41 | 14/04/2023 19:30:00 | 15/04/2023 01:30:00 | 01-EE-014B | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 14-Apr | 15-Apr | 07-Apr | 07-Apr
CDUVDU27060 | Completed | Test Ring Boxup | 09/04/2023 07:23:06 | 09/04/2023 07:23:06 | 15/04/2023 01:30:00 | 15/04/2023 09:30:00 | 01-EE-014B | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  |  | 15-Apr | 15-Apr | 09-Apr | 09-Apr
CDUVDU27380 | Completed | Carryout Shell Test | 07/04/2023 22:03:41 | 07/04/2023 22:03:41 | 15/04/2023 09:30:00 | 16/04/2023 00:30:00 | 01-EE-014B | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 0:00 |  |  | 15-Apr | 16-Apr | 07-Apr | 07-Apr
CDUVDU27870 | Completed | Test Ring Drop Down | 13/04/2023 19:00:49 | 13/04/2023 19:03:58 | 16/04/2023 00:30:00 | 16/04/2023 06:30:00 | 01-EE-014B | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:03 |  | 5:57 | 16-Apr | 16-Apr | 13-Apr | 13-Apr
CDUVDU28090 | Completed | Floating Head Box-up | 14/04/2023 05:02:43 | 15/04/2023 05:45:41 | 16/04/2023 06:30:00 | 16/04/2023 12:30:00 | 01-EE-014B | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 24:43 | 18:43 |  | 16-Apr | 16-Apr | 14-Apr | 15-Apr
CDUVDU28320 | Completed | Tube Test | 15/04/2023 00:21:19 | 16/04/2023 17:39:47 | 16/04/2023 12:30:00 | 17/04/2023 03:30:00 | 01-EE-014B | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 15 | 15:00 | 41:18 | 26:18 |  | 16-Apr | 17-Apr | 15-Apr | 16-Apr
CDUVDU28730 | Completed | Back Dome Boxup | 17/04/2023 01:43:48 | 17/04/2023 01:44:01 | 17/04/2023 03:30:00 | 17/04/2023 11:30:00 | 01-EE-014B | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 0:00 |  | 8:00 | 17-Apr | 17-Apr | 17-Apr | 17-Apr
CDUVDU28910 | Completed | Final Test | 17/04/2023 01:49:56 | 17/04/2023 01:50:13 | 17/04/2023 11:30:00 | 18/04/2023 02:30:00 | 01-EE-014B | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 0:00 |  | 15:00 | 17-Apr | 18-Apr | 17-Apr | 17-Apr
CDUVDU29260 | Completed | Deblinding | 18/04/2023 09:46:35 | 18/04/2023 17:53:53 | 18/04/2023 02:30:00 | 18/04/2023 10:30:00 | 01-EE-014B | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 8:07 | 0:07 |  | 18-Apr | 18-Apr | 18-Apr | 18-Apr
CDUVDU3590 | Completed | Blinding As Per Blind List | 02/04/2023 06:26:54 | 02/04/2023 06:26:59 | 01/04/2023 14:30:00 | 01/04/2023 22:30:00 | 01-EE-014B | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 01-Apr | 01-Apr | 02-Apr | 02-Apr
CDUVDU4230 | Completed | Carryout Component Dropping | 01/04/2023 16:15:47 | 01/04/2023 18:59:48 | 01/04/2023 22:30:00 | 02/04/2023 06:30:00 | 01-EE-014B | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 2:44 |  | 5:16 | 01-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU4740 | Completed | Carryout Bundle Pullout | 01/04/2023 18:49:00 | 02/04/2023 19:19:43 | 02/04/2023 06:30:00 | 02/04/2023 12:30:00 | 01-EE-014B | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 24:31 | 18:31 |  | 02-Apr | 02-Apr | 01-Apr | 02-Apr
CDUVDU5220 | Completed | Pre Cleaning Inspection | 03/04/2023 06:15:11 | 03/04/2023 06:15:11 | 02/04/2023 12:30:00 | 02/04/2023 14:30:00 | 01-EE-014B | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  |  | 02-Apr | 02-Apr | 03-Apr | 03-Apr
CDUVDU5800 | Completed | Bundle Shifting to Bay | 03/04/2023 06:15:11 | 03/04/2023 06:15:11 | 02/04/2023 14:30:00 | 02/04/2023 17:30:00 | 01-EE-014B | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  |  | 02-Apr | 02-Apr | 03-Apr | 03-Apr
CDUVDU10110 | Completed | Air Drying | 04/04/2023 21:40:12 | 04/04/2023 21:40:12 | 05/04/2023 13:30:00 | 05/04/2023 21:30:00 | 01-EE-017 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  |  | 05-Apr | 05-Apr | 04-Apr | 04-Apr
CDUVDU10600 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 04/04/2023 21:40:12 | 04/04/2023 21:40:12 | 05/04/2023 21:30:00 | 06/04/2023 03:30:00 | 01-EE-017 | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  |  | 05-Apr | 06-Apr | 04-Apr | 04-Apr
CDUVDU10920 | Completed | Shifting of bundle from bay | 08/04/2023 07:33:04 | 08/04/2023 07:33:04 | 06/04/2023 03:30:00 | 06/04/2023 07:30:00 | 01-EE-017 | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  |  | 06-Apr | 06-Apr | 08-Apr | 08-Apr
CDUVDU11150 | Completed | Carryout Bundle Insertion | 06/04/2023 07:47:42 | 06/04/2023 07:47:42 | 06/04/2023 07:30:00 | 06/04/2023 15:30:00 | 01-EE-017 | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 0:00 |  |  | 06-Apr | 06-Apr | 06-Apr | 06-Apr
CDUVDU11620 | Completed | Channelhead Boxup | 06/04/2023 07:47:42 | 06/04/2023 07:47:42 | 06/04/2023 15:30:00 | 06/04/2023 21:30:00 | 01-EE-017 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 06-Apr | 06-Apr | 06-Apr | 06-Apr
CDUVDU12040 | Completed | Test Ring Boxup | 10/04/2023 07:11:17 | 10/04/2023 07:11:17 | 06/04/2023 21:30:00 | 07/04/2023 05:30:00 | 01-EE-017 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  |  | 06-Apr | 07-Apr | 10-Apr | 10-Apr
CDUVDU12620 | Completed | Carryout Shell Test | 10/04/2023 07:11:32 | 11/04/2023 07:44:32 | 07/04/2023 05:30:00 | 07/04/2023 20:30:00 | 01-EE-017 | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 24:33 | 9:33 |  | 07-Apr | 07-Apr | 10-Apr | 11-Apr
CDUVDU13540 | Completed | Test Ring Drop Down | 11/04/2023 17:50:46 | 11/04/2023 17:51:48 | 07/04/2023 20:30:00 | 08/04/2023 02:30:00 | 01-EE-017 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:01 |  | 5:59 | 07-Apr | 08-Apr | 11-Apr | 11-Apr
CDUVDU13910 | Completed | Floating Head Box-up | 11/04/2023 17:51:58 | 12/04/2023 00:13:28 | 08/04/2023 02:30:00 | 08/04/2023 08:30:00 | 01-EE-017 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 6:22 | 0:22 |  | 08-Apr | 08-Apr | 11-Apr | 12-Apr
CDUVDU14260 | Completed | Tube Test | 12/04/2023 00:13:40 | 14/04/2023 05:10:06 | 08/04/2023 08:30:00 | 08/04/2023 23:30:00 | 01-EE-017 | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 15 | 15:00 | 52:56 | 37:56 |  | 08-Apr | 08-Apr | 12-Apr | 14-Apr
CDUVDU15380 | Completed | Back Dome Boxup | 14/04/2023 05:10:17 | 14/04/2023 17:11:06 | 08/04/2023 23:30:00 | 09/04/2023 07:30:00 | 01-EE-017 | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 12:01 | 4:01 |  | 08-Apr | 09-Apr | 14-Apr | 14-Apr
CDUVDU16010 | Completed | Final Test | 14/04/2023 17:11:21 | 14/04/2023 17:11:25 | 09/04/2023 07:30:00 | 09/04/2023 22:30:00 | 01-EE-017 | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 0:00 |  | 15:00 | 09-Apr | 09-Apr | 14-Apr | 14-Apr
CDUVDU17420 | Completed | Deblinding | 18/04/2023 09:47:00 | 20/04/2023 02:58:00 | 09/04/2023 22:30:00 | 10/04/2023 06:30:00 | 01-EE-017 | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 41:11 | 33:11 |  | 09-Apr | 10-Apr | 18-Apr | 20-Apr
CDUVDU3640 | Completed | Blinding As Per Blind List | 02/04/2023 07:37:14 | 02/04/2023 07:37:14 | 01/04/2023 14:30:00 | 01/04/2023 22:30:00 | 01-EE-017 | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  |  | 01-Apr | 01-Apr | 02-Apr | 02-Apr
CDUVDU4270 | Completed | Carryout Component Dropping | 02/04/2023 07:35:08 | 02/04/2023 07:35:08 | 01/04/2023 22:30:00 | 02/04/2023 06:30:00 | 01-EE-017 | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  |  | 01-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU4770 | Completed | Carryout Bundle Pullout | 02/04/2023 12:39:42 | 02/04/2023 12:39:48 | 02/04/2023 06:30:00 | 02/04/2023 12:30:00 | 01-EE-017 | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 0:00 |  | 6:00 | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU5240 | Completed | Pre Cleaning Inspection | 02/04/2023 12:41:45 | 02/04/2023 12:42:23 | 02/04/2023 12:30:00 | 02/04/2023 14:30:00 | 01-EE-017 | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:01 |  | 1:59 | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU5870 | Completed | Bundle Shifting to Bay | 02/04/2023 12:42:56 | 03/04/2023 06:17:15 | 02/04/2023 14:30:00 | 02/04/2023 17:30:00 | 01-EE-017 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 17:34 | 14:34 |  | 02-Apr | 02-Apr | 02-Apr | 03-Apr
CDUVDU9470 | Completed | Hydrojetting of Tube Bundle | 04/04/2023 07:34:26 | 04/04/2023 07:34:29 | 05/04/2023 00:30:00 | 05/04/2023 13:30:00 | 01-EE-017 | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 13 | 13:00 | 0:00 |  | 13:00 | 05-Apr | 05-Apr | 04-Apr | 04-Apr
CDUVDU10470 | Completed | Tube Test | 05/04/2023 19:29:00 | 06/04/2023 06:54:21 | 05/04/2023 16:30:00 | 06/04/2023 07:30:00 | 01-EE-002 | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 15 | 15:00 | 11:25 |  | 3:35 | 05-Apr | 06-Apr | 05-Apr | 06-Apr
CDUVDU11120 | Completed | Back Dome Boxup | 06/04/2023 12:23:47 | 07/04/2023 06:49:55 | 06/04/2023 07:30:00 | 06/04/2023 15:30:00 | 01-EE-002 | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 18:26 | 10:26 |  | 06-Apr | 06-Apr | 06-Apr | 07-Apr
CDUVDU11580 | Completed | Final Test | 07/04/2023 07:43:56 | 07/04/2023 07:56:31 | 06/04/2023 15:30:00 | 07/04/2023 06:30:00 | 01-EE-002 | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 0:13 |  | 14:47 | 06-Apr | 07-Apr | 07-Apr | 07-Apr
CDUVDU12670 | Completed | Deblinding | 14/04/2023 04:13:59 | 14/04/2023 04:14:03 | 07/04/2023 06:30:00 | 07/04/2023 14:30:00 | 01-EE-002 | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 07-Apr | 07-Apr | 14-Apr | 14-Apr
CDUVDU2200 | Completed | Blinding As Per Blind List | 31/03/2023 12:27:52 | 01/04/2023 09:07:31 | 31/03/2023 14:30:00 | 31/03/2023 22:30:00 | 01-EE-002 | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 20:40 | 12:40 |  | 31-Mar | 31-Mar | 31-Mar | 01-Apr
CDUVDU2530 | Completed | Carryout Component Dropping | 31/03/2023 12:36:46 | 31/03/2023 17:20:55 | 31/03/2023 22:30:00 | 01/04/2023 06:30:00 | 01-EE-002 | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 4:44 |  | 3:16 | 31-Mar | 01-Apr | 31-Mar | 31-Mar
CDUVDU3460 | Completed | Carryout Bundle Pullout | 31/03/2023 17:19:08 | 31/03/2023 17:19:13 | 01/04/2023 14:30:00 | 01/04/2023 20:30:00 | 01-EE-002 | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 0:00 |  | 6:00 | 01-Apr | 01-Apr | 31-Mar | 31-Mar
CDUVDU3930 | Completed | Pre Cleaning Inspection | 31/03/2023 17:26:09 | 31/03/2023 17:27:22 | 01/04/2023 20:30:00 | 01/04/2023 22:30:00 | 01-EE-002 | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:01 |  | 1:59 | 01-Apr | 01-Apr | 31-Mar | 31-Mar
CDUVDU4100 | Completed | Bundle Shifting to Bay | 01/04/2023 01:12:37 | 01/04/2023 01:12:44 | 01/04/2023 22:30:00 | 02/04/2023 01:30:00 | 01-EE-002 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 01-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU5000 | Completed | Hydrojetting of Tube Bundle | 01/04/2023 10:04:06 | 02/04/2023 05:45:32 | 02/04/2023 09:30:00 | 02/04/2023 22:30:00 | 01-EE-002 | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 13 | 13:00 | 19:41 | 6:41 |  | 02-Apr | 02-Apr | 01-Apr | 02-Apr
CDUVDU6410 | Completed | Air Drying | 02/04/2023 05:45:43 | 02/04/2023 05:59:18 | 02/04/2023 22:30:00 | 03/04/2023 06:30:00 | 01-EE-002 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:14 |  | 7:46 | 02-Apr | 03-Apr | 02-Apr | 02-Apr
CDUVDU6890 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 02/04/2023 05:59:31 | 03/04/2023 17:13:35 | 03/04/2023 06:30:00 | 03/04/2023 12:30:00 | 01-EE-002 | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 35:14 | 29:14 |  | 03-Apr | 03-Apr | 02-Apr | 03-Apr
CDUVDU7480 | Completed | Shifting of bundle from bay | 03/04/2023 17:13:09 | 03/04/2023 17:13:14 | 03/04/2023 12:30:00 | 03/04/2023 15:30:00 | 01-EE-002 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 03-Apr | 03-Apr | 03-Apr | 03-Apr
CDUVDU7780 | Completed | Carryout Bundle Insertion | 03/04/2023 17:13:23 | 03/04/2023 18:49:41 | 03/04/2023 15:30:00 | 03/04/2023 23:30:00 | 01-EE-002 | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 1:36 |  | 6:24 | 03-Apr | 03-Apr | 03-Apr | 03-Apr
CDUVDU8160 | Completed | Channelhead Boxup | 04/04/2023 08:03:11 | 04/04/2023 08:03:16 | 03/04/2023 23:30:00 | 04/04/2023 05:30:00 | 01-EE-002 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 03-Apr | 04-Apr | 04-Apr | 04-Apr
CDUVDU8440 | Completed | Test Ring Boxup | 04/04/2023 08:03:38 | 04/04/2023 08:03:42 | 04/04/2023 05:30:00 | 04/04/2023 13:30:00 | 01-EE-002 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  | 8:00 | 04-Apr | 04-Apr | 04-Apr | 04-Apr
CDUVDU8720 | Completed | Carryout Shell Test | 05/04/2023 09:43:06 | 05/04/2023 09:44:29 | 04/04/2023 13:30:00 | 05/04/2023 04:30:00 | 01-EE-002 | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 0:01 |  | 14:59 | 04-Apr | 05-Apr | 05-Apr | 05-Apr
CDUVDU9700 | Completed | Test Ring Drop Down | 05/04/2023 09:43:32 | 05/04/2023 09:45:09 | 05/04/2023 04:30:00 | 05/04/2023 10:30:00 | 01-EE-002 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:02 |  | 5:58 | 05-Apr | 05-Apr | 05-Apr | 05-Apr
CDUVDU9970 | Completed | Floating Head Box-up | 05/04/2023 09:46:45 | 05/04/2023 19:15:49 | 05/04/2023 10:30:00 | 05/04/2023 16:30:00 | 01-EE-002 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 9:29 | 3:29 |  | 05-Apr | 05-Apr | 05-Apr | 05-Apr
CDUVDU10320 | Completed | Shifting of bundle from bay | 10/04/2023 15:48:58 | 10/04/2023 15:49:06 | 05/04/2023 14:30:00 | 05/04/2023 17:30:00 | 01-EE-016 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 05-Apr | 05-Apr | 10-Apr | 10-Apr
CDUVDU10510 | Completed | Carryout Bundle Insertion | 10/04/2023 15:49:14 | 10/04/2023 19:34:29 | 05/04/2023 17:30:00 | 06/04/2023 01:30:00 | 01-EE-016 | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 3:45 |  | 4:15 | 05-Apr | 06-Apr | 10-Apr | 10-Apr
CDUVDU10720 | Completed | Channelhead Boxup | 12/04/2023 06:38:36 | 12/04/2023 06:38:36 | 06/04/2023 01:30:00 | 06/04/2023 07:30:00 | 01-EE-016 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 06-Apr | 06-Apr | 12-Apr | 12-Apr
CDUVDU11140 | Completed | Test Ring Boxup | 13/04/2023 03:39:31 | 13/04/2023 03:39:36 | 06/04/2023 07:30:00 | 06/04/2023 15:30:00 | 01-EE-016 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  | 8:00 | 06-Apr | 06-Apr | 13-Apr | 13-Apr
CDUVDU11600 | Completed | Carryout Shell Test | 13/04/2023 03:39:31 | 14/04/2023 07:45:13 | 06/04/2023 15:30:00 | 07/04/2023 06:30:00 | 01-EE-016 | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 28:06 | 13:06 |  | 06-Apr | 07-Apr | 13-Apr | 14-Apr
CDUVDU12700 | Completed | Test Ring Drop Down | 15/04/2023 05:46:27 | 15/04/2023 05:46:41 | 07/04/2023 06:30:00 | 07/04/2023 12:30:00 | 01-EE-016 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 07-Apr | 07-Apr | 15-Apr | 15-Apr
CDUVDU13010 | Completed | Floating Head Box-up | 15/04/2023 05:46:36 | 16/04/2023 00:51:04 | 07/04/2023 12:30:00 | 07/04/2023 18:30:00 | 01-EE-016 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 19:04 | 13:04 |  | 07-Apr | 07-Apr | 15-Apr | 16-Apr
CDUVDU13440 | Completed | Tube Test | 16/04/2023 00:51:13 | 16/04/2023 16:38:29 | 07/04/2023 18:30:00 | 08/04/2023 09:30:00 | 01-EE-016 | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 15 | 15:00 | 15:47 | 0:47 |  | 07-Apr | 08-Apr | 16-Apr | 16-Apr
CDUVDU14330 | Completed | Back Dome Boxup | 16/04/2023 16:38:38 | 17/04/2023 02:23:54 | 08/04/2023 09:30:00 | 08/04/2023 17:30:00 | 01-EE-016 | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 9:45 | 1:45 |  | 08-Apr | 08-Apr | 16-Apr | 17-Apr
CDUVDU14990 | Completed | Final Test | 17/04/2023 02:24:11 | 17/04/2023 07:17:14 | 08/04/2023 17:30:00 | 09/04/2023 08:30:00 | 01-EE-016 | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 4:53 |  | 10:07 | 08-Apr | 09-Apr | 17-Apr | 17-Apr
CDUVDU16120 | Completed | Deblinding | 18/04/2023 09:46:00 | 20/04/2023 02:58:00 | 09/04/2023 08:30:00 | 09/04/2023 16:30:00 | 01-EE-016 | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 41:12 | 33:12 |  | 09-Apr | 09-Apr | 18-Apr | 20-Apr
CDUVDU3610 | Completed | Blinding As Per Blind List | 02/04/2023 06:28:41 | 02/04/2023 06:28:45 | 01/04/2023 14:30:00 | 01/04/2023 22:30:00 | 01-EE-016 | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 01-Apr | 01-Apr | 02-Apr | 02-Apr
CDUVDU4250 | Completed | Carryout Component Dropping | 02/04/2023 06:28:41 | 02/04/2023 07:34:48 | 01/04/2023 22:30:00 | 02/04/2023 06:30:00 | 01-EE-016 | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 1:06 |  | 6:54 | 01-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU4760 | Completed | Carryout Bundle Pullout | 02/04/2023 19:13:46 | 02/04/2023 19:13:51 | 02/04/2023 06:30:00 | 02/04/2023 12:30:00 | 01-EE-016 | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 0:00 |  | 6:00 | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU5230 | Completed | Pre Cleaning Inspection | 03/04/2023 06:16:23 | 03/04/2023 06:16:36 | 02/04/2023 12:30:00 | 02/04/2023 14:30:00 | 01-EE-016 | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  | 2:00 | 02-Apr | 02-Apr | 03-Apr | 03-Apr
CDUVDU5820 | Completed | Bundle Shifting to Bay | 03/04/2023 06:16:23 | 03/04/2023 06:16:36 | 02/04/2023 14:30:00 | 02/04/2023 17:30:00 | 01-EE-016 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 02-Apr | 02-Apr | 03-Apr | 03-Apr
CDUVDU8150 | Completed | Hydrojetting of Tube Bundle | 07/04/2023 22:13:35 | 07/04/2023 22:13:35 | 03/04/2023 22:30:00 | 05/04/2023 00:30:00 | 01-EE-016 | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 26 | 26:00 | 0:00 |  |  | 03-Apr | 05-Apr | 07-Apr | 07-Apr
CDUVDU9460 | Completed | Air Drying | 07/04/2023 22:13:35 | 07/04/2023 22:13:35 | 05/04/2023 00:30:00 | 05/04/2023 08:30:00 | 01-EE-016 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  |  | 05-Apr | 05-Apr | 07-Apr | 07-Apr
CDUVDU9910 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 07/04/2023 22:13:35 | 07/04/2023 22:13:35 | 05/04/2023 08:30:00 | 05/04/2023 14:30:00 | 01-EE-016 | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  |  | 05-Apr | 05-Apr | 07-Apr | 07-Apr
CDUVDU10100 | Completed | Carryout Shell Test | 07/04/2023 22:04:09 | 07/04/2023 22:04:09 | 05/04/2023 13:30:00 | 06/04/2023 04:30:00 | 01-EE-015 | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 0:00 |  |  | 05-Apr | 06-Apr | 07-Apr | 07-Apr
CDUVDU11020 | Completed | Test Ring Drop Down | 11/04/2023 05:47:54 | 11/04/2023 05:48:03 | 06/04/2023 04:30:00 | 06/04/2023 10:30:00 | 01-EE-015 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 06-Apr | 06-Apr | 11-Apr | 11-Apr
CDUVDU11290 | Completed | Floating Head Box-up | 11/04/2023 05:47:54 | 11/04/2023 05:48:03 | 06/04/2023 10:30:00 | 06/04/2023 16:30:00 | 01-EE-015 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 06-Apr | 06-Apr | 11-Apr | 11-Apr
CDUVDU11720 | Completed | Tube Test | 11/04/2023 05:47:54 | 11/04/2023 05:48:03 | 06/04/2023 16:30:00 | 07/04/2023 07:30:00 | 01-EE-015 | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 15 | 15:00 | 0:00 |  | 15:00 | 06-Apr | 07-Apr | 11-Apr | 11-Apr
CDUVDU12770 | Completed | Back Dome Boxup | 13/04/2023 03:38:38 | 13/04/2023 03:38:41 | 07/04/2023 07:30:00 | 07/04/2023 15:30:00 | 01-EE-015 | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 0:00 |  | 8:00 | 07-Apr | 07-Apr | 13-Apr | 13-Apr
CDUVDU13240 | Completed | Final Test | 13/04/2023 17:03:13 | 14/04/2023 00:43:37 | 07/04/2023 15:30:00 | 08/04/2023 06:30:00 | 01-EE-015 | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 7:40 |  | 7:20 | 07-Apr | 08-Apr | 13-Apr | 14-Apr
CDUVDU14080 | Completed | Deblinding | 18/04/2023 09:46:00 | 20/04/2023 02:58:00 | 08/04/2023 06:30:00 | 08/04/2023 14:30:00 | 01-EE-015 | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 41:12 | 33:12 |  | 08-Apr | 08-Apr | 18-Apr | 20-Apr
CDUVDU3600 | Completed | Blinding As Per Blind List | 02/04/2023 06:27:53 | 02/04/2023 06:27:53 | 01/04/2023 14:30:00 | 01/04/2023 22:30:00 | 01-EE-015 | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  |  | 01-Apr | 01-Apr | 02-Apr | 02-Apr
CDUVDU4240 | Completed | Carryout Component Dropping | 02/04/2023 06:27:44 | 02/04/2023 06:27:44 | 01/04/2023 22:30:00 | 02/04/2023 06:30:00 | 01-EE-015 | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  |  | 01-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU4750 | Completed | Carryout Bundle Pullout | 03/04/2023 02:00:07 | 03/04/2023 05:02:42 | 02/04/2023 06:30:00 | 02/04/2023 14:30:00 | 01-EE-015 | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 8 | 8:00 | 3:03 |  | 4:57 | 02-Apr | 02-Apr | 03-Apr | 03-Apr
CDUVDU5810 | Completed | Pre Cleaning Inspection | 03/04/2023 17:43:16 | 03/04/2023 17:43:21 | 02/04/2023 14:30:00 | 02/04/2023 16:30:00 | 01-EE-015 | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  | 2:00 | 02-Apr | 02-Apr | 03-Apr | 03-Apr
CDUVDU6200 | Completed | Bundle Shifting to Bay | 06/04/2023 01:31:00 | 06/04/2023 07:31:00 | 02/04/2023 16:30:00 | 02/04/2023 20:30:00 | 01-EE-015 | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 6:00 | 2:00 |  | 02-Apr | 02-Apr | 06-Apr | 06-Apr
CDUVDU6300 | Completed | Hydrojetting of Tube Bundle | 05/04/2023 07:31:00 | 06/04/2023 07:31:00 | 02/04/2023 20:30:00 | 03/04/2023 22:30:00 | 01-EE-015 | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 26 | 26:00 | 24:00 |  | 2:00 | 02-Apr | 03-Apr | 05-Apr | 06-Apr
CDUVDU8140 | Completed | Air Drying | 05/04/2023 22:31:00 | 06/04/2023 07:31:00 | 03/04/2023 22:30:00 | 04/04/2023 06:30:00 | 01-EE-015 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 9:00 | 1:00 |  | 03-Apr | 04-Apr | 05-Apr | 06-Apr
CDUVDU8470 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 07/04/2023 04:35:23 | 07/04/2023 04:35:27 | 04/04/2023 06:30:00 | 04/04/2023 12:30:00 | 01-EE-015 | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  | 6:00 | 04-Apr | 04-Apr | 07-Apr | 07-Apr
CDUVDU8700 | Completed | Shifting of bundle from bay | 08/04/2023 07:40:40 | 08/04/2023 07:40:40 | 04/04/2023 12:30:00 | 04/04/2023 15:30:00 | 01-EE-015 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  |  | 04-Apr | 04-Apr | 08-Apr | 08-Apr
CDUVDU9090 | Completed | Carryout Bundle Insertion | 08/04/2023 07:40:40 | 08/04/2023 07:40:40 | 04/04/2023 15:30:00 | 04/04/2023 23:30:00 | 01-EE-015 | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 0:00 |  |  | 04-Apr | 04-Apr | 08-Apr | 08-Apr
CDUVDU9360 | Completed | Channelhead Boxup | 08/04/2023 16:06:19 | 09/04/2023 07:23:53 | 04/04/2023 23:30:00 | 05/04/2023 05:30:00 | 01-EE-015 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 15:18 | 9:18 |  | 04-Apr | 05-Apr | 08-Apr | 09-Apr
CDUVDU9790 | Completed | Test Ring Boxup | 09/04/2023 15:16:38 | 10/04/2023 10:29:31 | 05/04/2023 05:30:00 | 05/04/2023 13:30:00 | 01-EE-015 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 19:13 | 11:13 |  | 05-Apr | 05-Apr | 09-Apr | 10-Apr
CDUVDU10120 | Completed | Hydrojetting of Tube Bundle | 29/03/2023 23:13:31 | 29/03/2023 23:13:31 | 05/04/2023 13:30:00 | 06/04/2023 02:30:00 | 01-EE-018 | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 13 | 13:00 | 0:00 |  |  | 05-Apr | 06-Apr | 29-Mar | 29-Mar
CDUVDU10850 | Completed | Air Drying | 29/03/2023 23:13:31 | 29/03/2023 23:13:31 | 06/04/2023 02:30:00 | 06/04/2023 10:30:00 | 01-EE-018 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  |  | 06-Apr | 06-Apr | 29-Mar | 29-Mar
CDUVDU11300 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 29/03/2023 23:13:31 | 29/03/2023 23:13:31 | 06/04/2023 10:30:00 | 06/04/2023 16:30:00 | 01-EE-018 | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  |  | 06-Apr | 06-Apr | 29-Mar | 29-Mar
CDUVDU11730 | Completed | Shifting of bundle from bay | 31/03/2023 15:05:49 | 31/03/2023 15:05:56 | 06/04/2023 16:30:00 | 06/04/2023 19:30:00 | 01-EE-018 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 06-Apr | 06-Apr | 31-Mar | 31-Mar
CDUVDU11920 | Completed | Carryout Bundle Insertion | 31/03/2023 15:06:39 | 31/03/2023 15:06:51 | 06/04/2023 19:30:00 | 07/04/2023 03:30:00 | 01-EE-018 | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 0:00 |  | 8:00 | 06-Apr | 07-Apr | 31-Mar | 31-Mar
CDUVDU12510 | Completed | Channelhead Boxup | 31/03/2023 15:07:06 | 31/03/2023 18:48:18 | 07/04/2023 03:30:00 | 07/04/2023 09:30:00 | 01-EE-018 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 3:41 |  | 2:19 | 07-Apr | 07-Apr | 31-Mar | 31-Mar
CDUVDU12850 | Completed | Test Ring Boxup | 31/03/2023 15:08:41 | 06/04/2023 07:32:53 | 07/04/2023 09:30:00 | 07/04/2023 17:30:00 | 01-EE-018 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 136:24 | 128:24 |  | 07-Apr | 07-Apr | 31-Mar | 06-Apr
CDUVDU13360 | Completed | Carryout Shell Test | 31/03/2023 21:05:00 | 16/04/2023 00:52:40 | 07/04/2023 17:30:00 | 08/04/2023 08:30:00 | 01-EE-018 | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 363:48 | 348:48 |  | 07-Apr | 08-Apr | 31-Mar | 16-Apr
CDUVDU14270 | Completed | Test Ring Drop Down | 17/04/2023 02:27:29 | 17/04/2023 02:27:35 | 08/04/2023 08:30:00 | 08/04/2023 14:30:00 | 01-EE-018 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 08-Apr | 08-Apr | 17-Apr | 17-Apr
CDUVDU14790 | Completed | Floating Head Box-up | 17/04/2023 02:27:53 | 17/04/2023 02:27:57 | 08/04/2023 14:30:00 | 08/04/2023 20:30:00 | 01-EE-018 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 08-Apr | 08-Apr | 17-Apr | 17-Apr
CDUVDU15150 | Completed | Tube Test | 17/04/2023 02:28:18 | 17/04/2023 17:16:12 | 08/04/2023 20:30:00 | 09/04/2023 11:30:00 | 01-EE-018 | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 15 | 15:00 | 14:48 |  | 0:12 | 08-Apr | 09-Apr | 17-Apr | 17-Apr
CDUVDU16420 | Completed | Back Dome Boxup | 17/04/2023 17:20:23 | 17/04/2023 23:31:06 | 09/04/2023 11:30:00 | 09/04/2023 19:30:00 | 01-EE-018 | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 6:11 |  | 1:49 | 09-Apr | 09-Apr | 17-Apr | 17-Apr
CDUVDU17150 | Completed | Final Test | 18/04/2023 07:08:40 | 18/04/2023 07:08:48 | 09/04/2023 19:30:00 | 10/04/2023 10:30:00 | 01-EE-018 | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 0:00 |  | 15:00 | 09-Apr | 10-Apr | 18-Apr | 18-Apr
CDUVDU18620 | Completed | Deblinding | 20/04/2023 12:11:59 | 22/04/2023 18:23:37 | 10/04/2023 10:30:00 | 10/04/2023 18:30:00 | 01-EE-018 | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 54:12 | 46:12 |  | 10-Apr | 10-Apr | 20-Apr | 22-Apr
CDUVDU5880 | Completed | Blinding As Per Blind List | 27/03/2023 08:26:00 | 27/03/2023 15:27:00 | 02/04/2023 14:30:00 | 02/04/2023 22:30:00 | 01-EE-018 | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 7:01 |  | 0:59 | 02-Apr | 02-Apr | 27-Mar | 27-Mar
CDUVDU6470 | Completed | Carryout Component Dropping | 27/03/2023 11:28:00 | 27/03/2023 18:28:00 | 02/04/2023 22:30:00 | 03/04/2023 06:30:00 | 01-EE-018 | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 7:00 |  | 1:00 | 02-Apr | 03-Apr | 27-Mar | 27-Mar
CDUVDU6930 | Completed | Carryout Bundle Pullout | 28/03/2023 11:45:21 | 28/03/2023 11:45:21 | 03/04/2023 06:30:00 | 03/04/2023 12:30:00 | 01-EE-018 | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 0:00 |  |  | 03-Apr | 03-Apr | 28-Mar | 28-Mar
CDUVDU7530 | Completed | Pre Cleaning Inspection | 30/03/2023 05:17:12 | 30/03/2023 05:17:12 | 03/04/2023 12:30:00 | 03/04/2023 14:30:00 | 01-EE-018 | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  |  | 03-Apr | 03-Apr | 30-Mar | 30-Mar
CDUVDU7710 | Completed | Bundle Shifting to Bay | 29/03/2023 23:13:31 | 29/03/2023 23:13:31 | 03/04/2023 14:30:00 | 03/04/2023 17:30:00 | 01-EE-018 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  |  | 03-Apr | 03-Apr | 29-Mar | 29-Mar
CDUVDU10860 | Completed | Hydrojetting of Tube Bundle | 06/04/2023 07:37:22 | 08/04/2023 07:34:08 | 06/04/2023 02:30:00 | 06/04/2023 15:30:00 | 01-EE-019 | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 13 | 13:00 | 47:57 | 34:57 |  | 06-Apr | 06-Apr | 06-Apr | 08-Apr
CDUVDU11630 | Completed | Air Drying | 08/04/2023 07:34:19 | 08/04/2023 07:34:19 | 06/04/2023 15:30:00 | 06/04/2023 23:30:00 | 01-EE-019 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  |  | 06-Apr | 06-Apr | 08-Apr | 08-Apr
CDUVDU12230 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 08/04/2023 13:06:02 | 08/04/2023 13:06:02 | 06/04/2023 23:30:00 | 07/04/2023 05:30:00 | 01-EE-019 | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  |  | 06-Apr | 07-Apr | 08-Apr | 08-Apr
CDUVDU12630 | Completed | Shifting of bundle from bay | 08/04/2023 13:06:02 | 08/04/2023 13:06:02 | 07/04/2023 05:30:00 | 07/04/2023 09:30:00 | 01-EE-019 | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  |  | 07-Apr | 07-Apr | 08-Apr | 08-Apr
CDUVDU12860 | Completed | Carryout Bundle Insertion | 08/04/2023 13:06:02 | 08/04/2023 13:06:02 | 07/04/2023 09:30:00 | 07/04/2023 17:30:00 | 01-EE-019 | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 0:00 |  |  | 07-Apr | 07-Apr | 08-Apr | 08-Apr
CDUVDU13370 | Completed | Channelhead Boxup | 11/04/2023 06:53:54 | 11/04/2023 07:44:54 | 07/04/2023 17:30:00 | 07/04/2023 23:30:00 | 01-EE-019 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:51 |  | 5:09 | 07-Apr | 07-Apr | 11-Apr | 11-Apr
CDUVDU13690 | Completed | Test Ring Boxup | 12/04/2023 15:56:41 | 12/04/2023 15:56:47 | 07/04/2023 23:30:00 | 08/04/2023 07:30:00 | 01-EE-019 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  | 8:00 | 07-Apr | 08-Apr | 12-Apr | 12-Apr
CDUVDU14170 | Completed | Carryout Shell Test | 12/04/2023 15:57:03 | 12/04/2023 15:57:08 | 08/04/2023 07:30:00 | 08/04/2023 22:30:00 | 01-EE-019 | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 0:00 |  | 15:00 | 08-Apr | 08-Apr | 12-Apr | 12-Apr
CDUVDU15290 | Completed | Test Ring Drop Down | 12/04/2023 15:57:32 | 12/04/2023 15:57:41 | 08/04/2023 22:30:00 | 09/04/2023 04:30:00 | 01-EE-019 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 08-Apr | 09-Apr | 12-Apr | 12-Apr
CDUVDU15890 | Completed | Floating Head Box-up | 12/04/2023 15:57:52 | 14/04/2023 00:52:08 | 09/04/2023 04:30:00 | 09/04/2023 10:30:00 | 01-EE-019 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 32:54 | 26:54 |  | 09-Apr | 09-Apr | 12-Apr | 14-Apr
CDUVDU16350 | Completed | Tube Test | 14/04/2023 00:50:11 | 14/04/2023 17:10:46 | 09/04/2023 10:30:00 | 10/04/2023 01:30:00 | 01-EE-019 | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 15 | 15:00 | 16:21 | 1:21 |  | 09-Apr | 10-Apr | 14-Apr | 14-Apr
CDUVDU17700 | Completed | Back Dome Boxup | 15/04/2023 00:16:26 | 15/04/2023 00:16:34 | 10/04/2023 01:30:00 | 10/04/2023 09:30:00 | 01-EE-019 | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 0:00 |  | 8:00 | 10-Apr | 10-Apr | 15-Apr | 15-Apr
CDUVDU18510 | Completed | Final Test | 15/04/2023 00:16:51 | 16/04/2023 11:53:35 | 10/04/2023 09:30:00 | 11/04/2023 00:30:00 | 01-EE-019 | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 35:37 | 20:37 |  | 10-Apr | 11-Apr | 15-Apr | 16-Apr
CDUVDU20070 | Completed | Deblinding | 20/04/2023 12:12:14 | 22/04/2023 18:23:57 | 11/04/2023 00:30:00 | 11/04/2023 08:30:00 | 01-EE-019 | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 54:12 | 46:12 |  | 11-Apr | 11-Apr | 20-Apr | 22-Apr
CDUVDU5890 | Completed | Blinding As Per Blind List | 02/04/2023 06:30:33 | 02/04/2023 06:30:33 | 02/04/2023 14:30:00 | 02/04/2023 22:30:00 | 01-EE-019 | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  |  | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU6480 | Completed | Carryout Component Dropping | 02/04/2023 12:44:53 | 02/04/2023 19:16:11 | 02/04/2023 22:30:00 | 03/04/2023 06:30:00 | 01-EE-019 | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 6:31 |  | 1:29 | 02-Apr | 03-Apr | 02-Apr | 02-Apr
CDUVDU6940 | Completed | Carryout Bundle Pullout | 03/04/2023 02:02:26 | 03/04/2023 02:02:32 | 03/04/2023 06:30:00 | 03/04/2023 12:30:00 | 01-EE-019 | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 0:00 |  | 6:00 | 03-Apr | 03-Apr | 03-Apr | 03-Apr
CDUVDU7540 | Completed | Pre Cleaning Inspection | 03/04/2023 17:44:29 | 03/04/2023 17:44:40 | 03/04/2023 12:30:00 | 03/04/2023 14:30:00 | 01-EE-019 | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  | 2:00 | 03-Apr | 03-Apr | 03-Apr | 03-Apr
CDUVDU7720 | Completed | Bundle Shifting to Bay | 04/04/2023 10:04:03 | 04/04/2023 10:04:09 | 03/04/2023 14:30:00 | 03/04/2023 17:30:00 | 01-EE-019 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 03-Apr | 03-Apr | 04-Apr | 04-Apr
CDUVDU11610 | Completed | Hydrojetting of Tube Bundle | 06/04/2023 11:35:40 | 06/04/2023 11:36:10 | 06/04/2023 15:30:00 | 07/04/2023 17:30:00 | 01-EE-020 | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 26 | 26:00 | 0:01 |  | 25:59 | 06-Apr | 07-Apr | 06-Apr | 06-Apr
CDUVDU13350 | Completed | Air Drying | 06/04/2023 11:35:54 | 06/04/2023 11:36:16 | 07/04/2023 17:30:00 | 08/04/2023 01:30:00 | 01-EE-020 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  | 8:00 | 07-Apr | 08-Apr | 06-Apr | 06-Apr
CDUVDU13770 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 05/04/2023 22:19:25 | 05/04/2023 22:19:25 | 08/04/2023 01:30:00 | 08/04/2023 07:30:00 | 01-EE-020 | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  |  | 08-Apr | 08-Apr | 05-Apr | 05-Apr
CDUVDU14160 | Completed | Shifting of bundle from bay | 07/04/2023 12:04:10 | 07/04/2023 12:04:16 | 08/04/2023 07:30:00 | 08/04/2023 11:30:00 | 01-EE-020 | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 08-Apr | 08-Apr | 07-Apr | 07-Apr
CDUVDU14510 | Completed | Carryout Bundle Insertion | 07/04/2023 12:04:36 | 07/04/2023 12:04:40 | 08/04/2023 11:30:00 | 08/04/2023 19:30:00 | 01-EE-020 | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 0:00 |  | 8:00 | 08-Apr | 08-Apr | 07-Apr | 07-Apr
CDUVDU15090 | Completed | Channelhead Boxup | 09/04/2023 07:25:20 | 09/04/2023 07:25:20 | 08/04/2023 19:30:00 | 09/04/2023 01:30:00 | 01-EE-020 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 08-Apr | 09-Apr | 09-Apr | 09-Apr
CDUVDU15610 | Completed | Test Ring Boxup | 07/04/2023 12:04:49 | 11/04/2023 06:54:42 | 09/04/2023 01:30:00 | 09/04/2023 09:30:00 | 01-EE-020 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 90:50 | 82:50 |  | 09-Apr | 09-Apr | 07-Apr | 11-Apr
CDUVDU16230 | Completed | Carryout Shell Test | 11/04/2023 06:54:51 | 12/04/2023 06:39:44 | 09/04/2023 09:30:00 | 10/04/2023 00:30:00 | 01-EE-020 | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 23:45 | 8:45 |  | 09-Apr | 10-Apr | 11-Apr | 12-Apr
CDUVDU17610 | Completed | Test Ring Drop Down | 12/04/2023 10:27:07 | 13/04/2023 03:42:51 | 10/04/2023 00:30:00 | 10/04/2023 06:30:00 | 01-EE-020 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 17:16 | 11:16 |  | 10-Apr | 10-Apr | 12-Apr | 13-Apr
CDUVDU18330 | Completed | Floating Head Box-up | 13/04/2023 03:43:14 | 14/04/2023 00:55:27 | 10/04/2023 06:30:00 | 10/04/2023 12:30:00 | 01-EE-020 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 21:12 | 15:12 |  | 10-Apr | 10-Apr | 13-Apr | 14-Apr
CDUVDU18750 | Completed | Tube Test | 14/04/2023 00:53:38 | 14/04/2023 07:48:02 | 10/04/2023 12:30:00 | 11/04/2023 03:30:00 | 01-EE-020 | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 15 | 15:00 | 6:54 |  | 8:06 | 10-Apr | 11-Apr | 14-Apr | 14-Apr
CDUVDU20400 | Completed | Back Dome Boxup | 15/04/2023 00:17:18 | 15/04/2023 00:18:01 | 11/04/2023 03:30:00 | 11/04/2023 11:30:00 | 01-EE-020 | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 0:01 |  | 7:59 | 11-Apr | 11-Apr | 15-Apr | 15-Apr
CDUVDU21160 | Completed | Final Test | 15/04/2023 07:08:51 | 16/04/2023 06:39:16 | 11/04/2023 11:30:00 | 12/04/2023 02:30:00 | 01-EE-020 | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 23:30 | 8:30 |  | 11-Apr | 12-Apr | 15-Apr | 16-Apr
CDUVDU22650 | Completed | Deblinding | 20/04/2023 12:12:26 | 22/04/2023 18:24:14 | 12/04/2023 02:30:00 | 12/04/2023 10:30:00 | 01-EE-020 | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 54:12 | 46:12 |  | 12-Apr | 12-Apr | 20-Apr | 22-Apr
CDUVDU5830 | Completed | Blinding As Per Blind List | 02/04/2023 06:31:09 | 02/04/2023 06:31:09 | 02/04/2023 14:30:00 | 02/04/2023 22:30:00 | 01-EE-020 | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  |  | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU6430 | Completed | Carryout Component Dropping | 02/04/2023 12:46:48 | 02/04/2023 19:16:38 | 02/04/2023 22:30:00 | 03/04/2023 06:30:00 | 01-EE-020 | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 6:30 |  | 1:30 | 02-Apr | 03-Apr | 02-Apr | 02-Apr
CDUVDU6900 | Completed | Carryout Bundle Pullout | 03/04/2023 02:03:44 | 03/04/2023 02:04:18 | 03/04/2023 06:30:00 | 03/04/2023 12:30:00 | 01-EE-020 | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 0:01 |  | 5:59 | 03-Apr | 03-Apr | 03-Apr | 03-Apr
CDUVDU7490 | Completed | Pre Cleaning Inspection | 03/04/2023 17:46:06 | 03/04/2023 17:46:09 | 03/04/2023 12:30:00 | 03/04/2023 14:30:00 | 01-EE-020 | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  | 2:00 | 03-Apr | 03-Apr | 03-Apr | 03-Apr
CDUVDU7680 | Completed | Bundle Shifting to Bay | 04/04/2023 07:36:41 | 04/04/2023 07:36:41 | 03/04/2023 14:30:00 | 03/04/2023 17:30:00 | 01-EE-020 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  |  | 03-Apr | 03-Apr | 04-Apr | 04-Apr
CDUVDU13380 | Completed | Hydrojetting of Tube Bundle | 29/03/2023 23:09:43 | 29/03/2023 23:09:43 | 07/04/2023 17:30:00 | 08/04/2023 07:30:00 | 01-EE-021 | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 14 | 14:00 | 0:00 |  |  | 07-Apr | 08-Apr | 29-Mar | 29-Mar
CDUVDU14180 | Completed | Air Drying | 29/03/2023 23:09:43 | 29/03/2023 23:09:43 | 08/04/2023 07:30:00 | 08/04/2023 15:30:00 | 01-EE-021 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  |  | 08-Apr | 08-Apr | 29-Mar | 29-Mar
CDUVDU14860 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 29/03/2023 23:09:43 | 29/03/2023 23:09:43 | 08/04/2023 15:30:00 | 08/04/2023 21:30:00 | 01-EE-021 | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  |  | 08-Apr | 08-Apr | 29-Mar | 29-Mar
CDUVDU15200 | Completed | Shifting of bundle from bay | 30/03/2023 17:25:30 | 30/03/2023 17:25:37 | 08/04/2023 21:30:00 | 09/04/2023 00:30:00 | 01-EE-021 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 08-Apr | 09-Apr | 30-Mar | 30-Mar
CDUVDU15440 | Completed | Carryout Bundle Insertion | 30/03/2023 17:25:49 | 30/03/2023 17:26:20 | 09/04/2023 00:30:00 | 09/04/2023 08:30:00 | 01-EE-021 | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 0:01 |  | 7:59 | 09-Apr | 09-Apr | 30-Mar | 30-Mar
CDUVDU16130 | Completed | Channelhead Boxup | 30/03/2023 17:26:34 | 30/03/2023 17:26:47 | 09/04/2023 08:30:00 | 09/04/2023 14:30:00 | 01-EE-021 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 09-Apr | 09-Apr | 30-Mar | 30-Mar
CDUVDU16720 | Completed | Test Ring Boxup | 30/03/2023 17:29:53 | 30/03/2023 17:30:10 | 09/04/2023 14:30:00 | 09/04/2023 22:30:00 | 01-EE-021 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  | 8:00 | 09-Apr | 09-Apr | 30-Mar | 30-Mar
CDUVDU17430 | Completed | Carryout Shell Test | 30/03/2023 17:33:52 | 30/03/2023 17:35:08 | 09/04/2023 22:30:00 | 10/04/2023 13:30:00 | 01-EE-021 | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 0:01 |  | 14:59 | 09-Apr | 10-Apr | 30-Mar | 30-Mar
CDUVDU18890 | Completed | Test Ring Drop Down | 31/03/2023 15:02:24 | 31/03/2023 15:02:32 | 10/04/2023 13:30:00 | 10/04/2023 19:30:00 | 01-EE-021 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 10-Apr | 10-Apr | 31-Mar | 31-Mar
CDUVDU19430 | Completed | Floating Head Box-up | 31/03/2023 15:03:26 | 31/03/2023 15:03:36 | 10/04/2023 19:30:00 | 11/04/2023 01:30:00 | 01-EE-021 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 10-Apr | 11-Apr | 31-Mar | 31-Mar
CDUVDU20110 | Completed | Tube Test | 31/03/2023 15:03:54 | 31/03/2023 15:03:59 | 11/04/2023 01:30:00 | 11/04/2023 16:30:00 | 01-EE-021 | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 15 | 15:00 | 0:00 |  | 15:00 | 11-Apr | 11-Apr | 31-Mar | 31-Mar
CDUVDU21670 | Completed | Back Dome Boxup | 31/03/2023 18:45:40 | 31/03/2023 18:46:26 | 11/04/2023 16:30:00 | 12/04/2023 00:30:00 | 01-EE-021 | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 0:01 |  | 7:59 | 11-Apr | 12-Apr | 31-Mar | 31-Mar
CDUVDU22390 | Completed | Final Test | 31/03/2023 18:46:55 | 31/03/2023 18:47:01 | 12/04/2023 00:30:00 | 12/04/2023 15:30:00 | 01-EE-021 | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 0:00 |  | 15:00 | 12-Apr | 12-Apr | 31-Mar | 31-Mar
CDUVDU23880 | Completed | Deblinding | 20/04/2023 12:12:35 | 20/04/2023 12:12:43 | 12/04/2023 15:30:00 | 12/04/2023 23:30:00 | 01-EE-021 | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 12-Apr | 12-Apr | 20-Apr | 20-Apr
CDUVDU5900 | Completed | Blinding As Per Blind List | 28/03/2023 11:35:00 | 29/03/2023 11:35:38 | 02/04/2023 14:30:00 | 02/04/2023 22:30:00 | 01-EE-021 | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 24:01 | 16:01 |  | 02-Apr | 02-Apr | 28-Mar | 29-Mar
CDUVDU6490 | Completed | Carryout Component Dropping | 29/03/2023 11:36:15 | 29/03/2023 11:36:33 | 02/04/2023 22:30:00 | 03/04/2023 06:30:00 | 01-EE-021 | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  | 8:00 | 02-Apr | 03-Apr | 29-Mar | 29-Mar
CDUVDU6950 | Completed | Carryout Bundle Pullout | 29/03/2023 11:36:49 | 29/03/2023 11:36:58 | 03/04/2023 06:30:00 | 03/04/2023 12:30:00 | 01-EE-021 | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 0:00 |  | 6:00 | 03-Apr | 03-Apr | 29-Mar | 29-Mar
CDUVDU7550 | Completed | Pre Cleaning Inspection | 29/03/2023 13:50:55 | 29/03/2023 13:51:01 | 03/04/2023 12:30:00 | 03/04/2023 14:30:00 | 01-EE-021 | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  | 2:00 | 03-Apr | 03-Apr | 29-Mar | 29-Mar
CDUVDU7730 | Completed | Bundle Shifting to Bay | 29/03/2023 23:09:43 | 29/03/2023 23:09:43 | 03/04/2023 14:30:00 | 03/04/2023 17:30:00 | 01-EE-021 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  |  | 03-Apr | 03-Apr | 29-Mar | 29-Mar
CDUVDU14190 | Completed | Hydrojetting of Tube Bundle | 06/04/2023 07:39:31 | 06/04/2023 07:39:31 | 08/04/2023 07:30:00 | 08/04/2023 20:30:00 | 01-EE-022 | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 13 | 13:00 | 0:00 |  |  | 08-Apr | 08-Apr | 06-Apr | 06-Apr
CDUVDU15160 | Completed | Air Drying | 06/04/2023 07:48:02 | 06/04/2023 07:48:02 | 08/04/2023 20:30:00 | 09/04/2023 04:30:00 | 01-EE-022 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  |  | 08-Apr | 09-Apr | 06-Apr | 06-Apr
CDUVDU15900 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 06/04/2023 07:48:02 | 06/04/2023 07:48:02 | 09/04/2023 04:30:00 | 09/04/2023 10:30:00 | 01-EE-022 | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  |  | 09-Apr | 09-Apr | 06-Apr | 06-Apr
CDUVDU16360 | Completed | Shifting of bundle from bay | 06/04/2023 11:47:11 | 06/04/2023 11:47:38 | 09/04/2023 10:30:00 | 09/04/2023 13:30:00 | 01-EE-022 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 09-Apr | 09-Apr | 06-Apr | 06-Apr
CDUVDU16550 | Completed | Carryout Bundle Insertion | 06/04/2023 11:47:28 | 06/04/2023 13:42:20 | 09/04/2023 13:30:00 | 09/04/2023 21:30:00 | 01-EE-022 | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 1:55 |  | 6:05 | 09-Apr | 09-Apr | 06-Apr | 06-Apr
CDUVDU17280 | Completed | Channelhead Boxup | 13/04/2023 03:44:02 | 16/04/2023 17:41:37 | 09/04/2023 21:30:00 | 10/04/2023 03:30:00 | 01-EE-022 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 85:58 | 79:58 |  | 09-Apr | 10-Apr | 13-Apr | 16-Apr
CDUVDU17980 | Completed | Test Ring Boxup | 15/04/2023 00:19:30 | 17/04/2023 02:31:54 | 10/04/2023 03:30:00 | 10/04/2023 11:30:00 | 01-EE-022 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 50:12 | 42:12 |  | 10-Apr | 10-Apr | 15-Apr | 17-Apr
CDUVDU18680 | Completed | Carryout Shell Test | 17/04/2023 02:32:14 | 18/04/2023 17:42:45 | 10/04/2023 11:30:00 | 11/04/2023 02:30:00 | 01-EE-022 | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 39:11 | 24:11 |  | 10-Apr | 11-Apr | 17-Apr | 18-Apr
CDUVDU20340 | Completed | Test Ring Drop Down | 18/04/2023 18:03:43 | 19/04/2023 02:27:41 | 11/04/2023 02:30:00 | 11/04/2023 08:30:00 | 01-EE-022 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 8:24 | 2:24 |  | 11-Apr | 11-Apr | 18-Apr | 19-Apr
CDUVDU20800 | Completed | Floating Head Box-up | 19/04/2023 02:27:53 | 19/04/2023 02:27:56 | 11/04/2023 08:30:00 | 11/04/2023 14:30:00 | 01-EE-022 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 11-Apr | 11-Apr | 19-Apr | 19-Apr
CDUVDU21550 | Completed | Tube Test | 19/04/2023 02:28:07 | 20/04/2023 12:13:57 | 11/04/2023 14:30:00 | 12/04/2023 05:30:00 | 01-EE-022 | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 15 | 15:00 | 33:46 | 18:46 |  | 11-Apr | 12-Apr | 19-Apr | 20-Apr
CDUVDU22990 | Completed | Back Dome Boxup | 20/04/2023 18:05:16 | 20/04/2023 18:05:20 | 12/04/2023 05:30:00 | 12/04/2023 13:30:00 | 01-EE-022 | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 0:00 |  | 8:00 | 12-Apr | 12-Apr | 20-Apr | 20-Apr
CDUVDU23630 | Completed | Final Test | 20/04/2023 18:05:37 | 20/04/2023 23:22:41 | 12/04/2023 13:30:00 | 13/04/2023 04:30:00 | 01-EE-022 | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 5:17 |  | 9:43 | 12-Apr | 13-Apr | 20-Apr | 20-Apr
CDUVDU24850 | Completed | Deblinding | 22/04/2023 18:24:33 | 23/04/2023 09:46:18 | 13/04/2023 04:30:00 | 13/04/2023 12:30:00 | 01-EE-022 | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 15:22 | 7:22 |  | 13-Apr | 13-Apr | 22-Apr | 23-Apr
CDUVDU5910 | Completed | Blinding As Per Blind List | 02/04/2023 06:31:57 | 02/04/2023 06:31:57 | 02/04/2023 14:30:00 | 02/04/2023 22:30:00 | 01-EE-022 | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  |  | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU6500 | Completed | Carryout Component Dropping | 02/04/2023 17:26:53 | 03/04/2023 04:33:48 | 02/04/2023 22:30:00 | 03/04/2023 06:30:00 | 01-EE-022 | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 11:07 | 3:07 |  | 02-Apr | 03-Apr | 02-Apr | 03-Apr
CDUVDU6960 | Completed | Carryout Bundle Pullout | 04/04/2023 10:02:32 | 04/04/2023 10:02:37 | 03/04/2023 06:30:00 | 03/04/2023 12:30:00 | 01-EE-022 | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 0:00 |  | 6:00 | 03-Apr | 03-Apr | 04-Apr | 04-Apr
CDUVDU7560 | Completed | Pre Cleaning Inspection | 04/04/2023 20:52:24 | 04/04/2023 22:16:32 | 03/04/2023 12:30:00 | 03/04/2023 14:30:00 | 01-EE-022 | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 1:24 |  | 0:36 | 03-Apr | 03-Apr | 04-Apr | 04-Apr
CDUVDU7740 | Completed | Bundle Shifting to Bay | 06/04/2023 07:39:31 | 06/04/2023 07:39:31 | 03/04/2023 14:30:00 | 03/04/2023 17:30:00 | 01-EE-022 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  |  | 03-Apr | 03-Apr | 06-Apr | 06-Apr
CDUVDU15140 | Completed | Hydrojetting of Tube Bundle | 11/04/2023 06:56:12 | 19/04/2023 11:43:16 | 08/04/2023 20:30:00 | 09/04/2023 22:30:00 | 01-EE-023 | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 26 | 26:00 | 196:47 | 170:47 |  | 08-Apr | 09-Apr | 11-Apr | 19-Apr
CDUVDU17400 | Completed | Air Drying | 21/04/2023 19:01:49 | 21/04/2023 19:01:55 | 09/04/2023 22:30:00 | 10/04/2023 06:30:00 | 01-EE-023 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  | 8:00 | 09-Apr | 10-Apr | 21-Apr | 21-Apr
CDUVDU18340 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 21/04/2023 19:02:08 | 21/04/2023 19:02:13 | 10/04/2023 06:30:00 | 10/04/2023 12:30:00 | 01-EE-023 | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  | 6:00 | 10-Apr | 10-Apr | 21-Apr | 21-Apr
CDUVDU18760 | Completed | Shifting of bundle from bay | 21/04/2023 19:02:20 | 21/04/2023 19:02:26 | 10/04/2023 12:30:00 | 10/04/2023 15:30:00 | 01-EE-023 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 10-Apr | 10-Apr | 21-Apr | 21-Apr
CDUVDU19120 | Completed | Carryout Bundle Insertion | 21/04/2023 19:02:34 | 21/04/2023 19:04:15 | 10/04/2023 15:30:00 | 10/04/2023 23:30:00 | 01-EE-023 | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 0:02 |  | 7:58 | 10-Apr | 10-Apr | 21-Apr | 21-Apr
CDUVDU19920 | Completed | Channelhead Boxup | 22/04/2023 07:17:42 | 22/04/2023 23:11:56 | 10/04/2023 23:30:00 | 11/04/2023 05:30:00 | 01-EE-023 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 15:54 | 9:54 |  | 10-Apr | 11-Apr | 22-Apr | 22-Apr
CDUVDU20530 | Completed | Test Ring Boxup | 22/04/2023 10:48:41 | 23/04/2023 06:46:36 | 11/04/2023 05:30:00 | 11/04/2023 13:30:00 | 01-EE-023 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 19:58 | 11:58 |  | 11-Apr | 11-Apr | 22-Apr | 23-Apr
CDUVDU21260 | Completed | Carryout Shell Test | 22/04/2023 23:11:45 | 23/04/2023 15:05:48 | 11/04/2023 13:30:00 | 12/04/2023 04:30:00 | 01-EE-023 | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 15:54 | 0:54 |  | 11-Apr | 12-Apr | 22-Apr | 23-Apr
CDUVDU22870 | Completed | Test Ring Drop Down | 24/04/2023 06:44:54 | 24/04/2023 06:45:00 | 12/04/2023 04:30:00 | 12/04/2023 10:30:00 | 01-EE-023 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 12-Apr | 12-Apr | 24-Apr | 24-Apr
CDUVDU23370 | Completed | Floating Head Box-up | 24/04/2023 06:45:14 | 24/04/2023 18:29:07 | 12/04/2023 10:30:00 | 12/04/2023 16:30:00 | 01-EE-023 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 11:44 | 5:44 |  | 12-Apr | 12-Apr | 24-Apr | 24-Apr
CDUVDU23960 | Completed | Tube Test | 24/04/2023 18:29:32 | 25/04/2023 07:09:32 | 12/04/2023 16:30:00 | 13/04/2023 07:30:00 | 01-EE-023 | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 15 | 15:00 | 12:40 |  | 2:20 | 12-Apr | 13-Apr | 24-Apr | 25-Apr
CDUVDU25050 | Completed | Back Dome Boxup | 25/04/2023 11:25:45 | 25/04/2023 17:21:05 | 13/04/2023 07:30:00 | 13/04/2023 15:30:00 | 01-EE-023 | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 5:55 |  | 2:05 | 13-Apr | 13-Apr | 25-Apr | 25-Apr
CDUVDU25510 | Completed | Final Test | 25/04/2023 17:21:22 | 25/04/2023 17:21:38 | 13/04/2023 15:30:00 | 14/04/2023 06:30:00 | 01-EE-023 | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 0:00 |  | 15:00 | 13-Apr | 14-Apr | 25-Apr | 25-Apr
CDUVDU26300 | Completed | Deblinding | 25/04/2023 22:41:47 | 26/04/2023 05:07:00 | 14/04/2023 06:30:00 | 14/04/2023 14:30:00 | 01-EE-023 | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 6:25 |  | 1:35 | 14-Apr | 14-Apr | 25-Apr | 26-Apr
CDUVDU5840 | Completed | Blinding As Per Blind List | 02/04/2023 06:32:22 | 02/04/2023 06:32:22 | 02/04/2023 14:30:00 | 02/04/2023 22:30:00 | 01-EE-023 | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  |  | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU6440 | Completed | Carryout Component Dropping | 03/04/2023 04:33:05 | 03/04/2023 04:33:15 | 02/04/2023 22:30:00 | 03/04/2023 06:30:00 | 01-EE-023 | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  | 8:00 | 02-Apr | 03-Apr | 03-Apr | 03-Apr
CDUVDU6910 | Completed | Carryout Bundle Pullout | 07/04/2023 07:35:36 | 07/04/2023 07:35:36 | 03/04/2023 06:30:00 | 03/04/2023 12:30:00 | 01-EE-023 | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 0:00 |  |  | 03-Apr | 03-Apr | 07-Apr | 07-Apr
CDUVDU7500 | Completed | Pre Cleaning Inspection | 07/04/2023 07:35:36 | 07/04/2023 07:35:36 | 03/04/2023 12:30:00 | 03/04/2023 14:30:00 | 01-EE-023 | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  |  | 03-Apr | 03-Apr | 07-Apr | 07-Apr
CDUVDU7690 | Completed | Bundle Shifting to Bay | 08/04/2023 09:53:32 | 08/04/2023 09:53:38 | 03/04/2023 14:30:00 | 03/04/2023 17:30:00 | 01-EE-023 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 03-Apr | 03-Apr | 08-Apr | 08-Apr
CDUVDU18190 | Completed | Hydrojetting of Tube Bundle | 03/04/2023 05:51:44 | 03/04/2023 05:51:48 | 10/04/2023 05:30:00 | 10/04/2023 11:30:00 | 01-EE-025A | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 6 | 6:00 | 0:00 |  | 6:00 | 10-Apr | 10-Apr | 03-Apr | 03-Apr
CDUVDU18690 | Completed | Air Drying | 05/04/2023 09:51:49 | 05/04/2023 09:57:20 | 10/04/2023 11:30:00 | 10/04/2023 14:30:00 | 01-EE-025A | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:06 |  | 2:54 | 10-Apr | 10-Apr | 05-Apr | 05-Apr
CDUVDU19040 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 05/04/2023 09:52:53 | 05/04/2023 09:57:27 | 10/04/2023 14:30:00 | 10/04/2023 20:30:00 | 01-EE-025A | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:05 |  | 5:55 | 10-Apr | 10-Apr | 05-Apr | 05-Apr
CDUVDU19530 | Completed | Shifting of bundle from bay | 05/04/2023 09:57:00 | 05/04/2023 09:57:06 | 10/04/2023 20:30:00 | 10/04/2023 23:30:00 | 01-EE-025A | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 10-Apr | 10-Apr | 05-Apr | 05-Apr
CDUVDU19940 | Completed | Carryout Bundle Insertion | 05/04/2023 09:54:17 | 05/04/2023 09:57:34 | 10/04/2023 23:30:00 | 11/04/2023 05:30:00 | 01-EE-025A | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 6 | 6:00 | 0:03 |  | 5:57 | 10-Apr | 11-Apr | 05-Apr | 05-Apr
CDUVDU20540 | Completed | Channelhead Boxup | 05/04/2023 16:29:32 | 05/04/2023 16:29:32 | 11/04/2023 05:30:00 | 11/04/2023 11:30:00 | 01-EE-025A | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 11-Apr | 11-Apr | 05-Apr | 05-Apr
CDUVDU21170 | Completed | Test Ring Boxup | 05/04/2023 16:29:32 | 05/04/2023 16:29:32 | 11/04/2023 11:30:00 | 11/04/2023 19:30:00 | 01-EE-025A | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  |  | 11-Apr | 11-Apr | 05-Apr | 05-Apr
CDUVDU22030 | Completed | Carryout Shell Test | 05/04/2023 16:29:48 | 07/04/2023 07:46:49 | 11/04/2023 19:30:00 | 12/04/2023 03:30:00 | 01-EE-025A | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 8 | 8:00 | 39:17 | 31:17 |  | 11-Apr | 12-Apr | 05-Apr | 07-Apr
CDUVDU22810 | Completed | Test Ring Drop Down | 08/04/2023 06:55:54 | 08/04/2023 06:56:03 | 12/04/2023 03:30:00 | 12/04/2023 07:30:00 | 01-EE-025A | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 12-Apr | 12-Apr | 08-Apr | 08-Apr
CDUVDU23150 | Completed | Floating Head Box-up | 08/04/2023 07:14:52 | 08/04/2023 07:15:04 | 12/04/2023 07:30:00 | 12/04/2023 11:30:00 | 01-EE-025A | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 12-Apr | 12-Apr | 08-Apr | 08-Apr
CDUVDU23550 | Completed | Tube Test | 08/04/2023 07:15:24 | 08/04/2023 07:15:36 | 12/04/2023 11:30:00 | 12/04/2023 19:30:00 | 01-EE-025A | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 8 | 8:00 | 0:00 |  | 8:00 | 12-Apr | 12-Apr | 08-Apr | 08-Apr
CDUVDU24160 | Completed | Back Dome Boxup | 08/04/2023 07:41:09 | 08/04/2023 07:41:09 | 12/04/2023 19:30:00 | 12/04/2023 23:30:00 | 01-EE-025A | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  |  | 12-Apr | 12-Apr | 08-Apr | 08-Apr
CDUVDU24510 | Completed | Final Test | 08/04/2023 07:41:09 | 08/04/2023 07:41:09 | 12/04/2023 23:30:00 | 13/04/2023 07:30:00 | 01-EE-025A | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 8 | 8:00 | 0:00 |  |  | 12-Apr | 13-Apr | 08-Apr | 08-Apr
CDUVDU25060 | Completed | Deblinding | 16/04/2023 06:44:25 | 16/04/2023 10:16:36 | 13/04/2023 07:30:00 | 13/04/2023 13:30:00 | 01-EE-025A | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 6 | 6:00 | 3:32 |  | 2:28 | 13-Apr | 13-Apr | 16-Apr | 16-Apr
CDUVDU3650 | Completed | Blinding As Per Blind List | 01/04/2023 01:08:00 | 01/04/2023 10:08:51 | 01/04/2023 14:30:00 | 01/04/2023 20:30:00 | 01-EE-025A | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 6 | 6:00 | 9:01 | 3:01 |  | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU3950 | Completed | Carryout Component Dropping | 01/04/2023 10:09:08 | 02/04/2023 06:04:10 | 01/04/2023 20:30:00 | 02/04/2023 00:30:00 | 01-EE-025A | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 4 | 4:00 | 19:55 | 15:55 |  | 01-Apr | 02-Apr | 01-Apr | 02-Apr
CDUVDU4420 | Completed | Carryout Bundle Pullout | 02/04/2023 06:04:23 | 02/04/2023 06:04:35 | 02/04/2023 00:30:00 | 02/04/2023 08:30:00 | 01-EE-025A | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 8 | 8:00 | 0:00 |  | 8:00 | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU4910 | Completed | Pre Cleaning Inspection | 02/04/2023 06:04:23 | 02/04/2023 06:04:35 | 02/04/2023 08:30:00 | 02/04/2023 10:30:00 | 01-EE-025A | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  | 2:00 | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU5080 | Completed | Bundle Shifting to Bay | 03/04/2023 05:50:57 | 03/04/2023 05:51:10 | 02/04/2023 10:30:00 | 02/04/2023 13:30:00 | 01-EE-025A | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 02-Apr | 02-Apr | 03-Apr | 03-Apr
CDUVDU18700 | Completed | Hydrojetting of Tube Bundle | 03/04/2023 05:52:27 | 03/04/2023 05:52:41 | 10/04/2023 11:30:00 | 10/04/2023 17:30:00 | 01-EE-025B | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 6 | 6:00 | 0:00 |  | 6:00 | 10-Apr | 10-Apr | 03-Apr | 03-Apr
CDUVDU19280 | Completed | Air Drying | 05/04/2023 09:58:38 | 05/04/2023 09:58:43 | 10/04/2023 17:30:00 | 10/04/2023 20:30:00 | 01-EE-025B | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 10-Apr | 10-Apr | 05-Apr | 05-Apr
CDUVDU19540 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 05/04/2023 09:59:08 | 05/04/2023 09:59:13 | 10/04/2023 20:30:00 | 11/04/2023 02:30:00 | 01-EE-025B | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  | 6:00 | 10-Apr | 11-Apr | 05-Apr | 05-Apr
CDUVDU20350 | Completed | Shifting of bundle from bay | 05/04/2023 09:59:21 | 05/04/2023 09:59:26 | 11/04/2023 02:30:00 | 11/04/2023 06:30:00 | 01-EE-025B | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 11-Apr | 11-Apr | 05-Apr | 05-Apr
CDUVDU20650 | Completed | Carryout Bundle Insertion | 05/04/2023 09:59:42 | 05/04/2023 09:59:50 | 11/04/2023 06:30:00 | 11/04/2023 12:30:00 | 01-EE-025B | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 6 | 6:00 | 0:00 |  | 6:00 | 11-Apr | 11-Apr | 05-Apr | 05-Apr
CDUVDU21210 | Completed | Channelhead Boxup | 05/04/2023 16:31:02 | 05/04/2023 16:31:02 | 11/04/2023 12:30:00 | 11/04/2023 18:30:00 | 01-EE-025B | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 11-Apr | 11-Apr | 05-Apr | 05-Apr
CDUVDU21960 | Completed | Test Ring Boxup | 05/04/2023 16:31:02 | 05/04/2023 16:31:02 | 11/04/2023 18:30:00 | 12/04/2023 02:30:00 | 01-EE-025B | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  |  | 11-Apr | 12-Apr | 05-Apr | 05-Apr
CDUVDU22660 | Completed | Carryout Shell Test | 05/04/2023 16:31:20 | 07/04/2023 07:47:04 | 12/04/2023 02:30:00 | 12/04/2023 10:30:00 | 01-EE-025B | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 8 | 8:00 | 39:16 | 31:16 |  | 12-Apr | 12-Apr | 05-Apr | 07-Apr
CDUVDU23390 | Completed | Test Ring Drop Down | 08/04/2023 06:56:24 | 08/04/2023 06:56:28 | 12/04/2023 10:30:00 | 12/04/2023 14:30:00 | 01-EE-025B | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 12-Apr | 12-Apr | 08-Apr | 08-Apr
CDUVDU23800 | Completed | Floating Head Box-up | 08/04/2023 07:16:07 | 08/04/2023 07:16:14 | 12/04/2023 14:30:00 | 12/04/2023 18:30:00 | 01-EE-025B | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 12-Apr | 12-Apr | 08-Apr | 08-Apr
CDUVDU24140 | Completed | Tube Test | 08/04/2023 07:16:31 | 08/04/2023 07:16:36 | 12/04/2023 18:30:00 | 13/04/2023 02:30:00 | 01-EE-025B | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 8 | 8:00 | 0:00 |  | 8:00 | 12-Apr | 13-Apr | 08-Apr | 08-Apr
CDUVDU24730 | Completed | Back Dome Boxup | 08/04/2023 07:41:28 | 08/04/2023 07:41:28 | 13/04/2023 02:30:00 | 13/04/2023 06:30:00 | 01-EE-025B | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  |  | 13-Apr | 13-Apr | 08-Apr | 08-Apr
CDUVDU25020 | Completed | Final Test | 08/04/2023 07:41:28 | 08/04/2023 07:41:28 | 13/04/2023 06:30:00 | 13/04/2023 14:30:00 | 01-EE-025B | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 8 | 8:00 | 0:00 |  |  | 13-Apr | 13-Apr | 08-Apr | 08-Apr
CDUVDU25470 | Completed | Deblinding | 16/04/2023 06:44:56 | 16/04/2023 10:17:02 | 13/04/2023 14:30:00 | 13/04/2023 20:30:00 | 01-EE-025B | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 6 | 6:00 | 3:32 |  | 2:28 | 13-Apr | 13-Apr | 16-Apr | 16-Apr
CDUVDU3660 | Completed | Blinding As Per Blind List | 01/04/2023 01:09:00 | 01/04/2023 10:09:48 | 01/04/2023 14:30:00 | 01/04/2023 20:30:00 | 01-EE-025B | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 6 | 6:00 | 9:01 | 3:01 |  | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU3960 | Completed | Carryout Component Dropping | 01/04/2023 10:09:55 | 02/04/2023 06:05:24 | 01/04/2023 20:30:00 | 02/04/2023 00:30:00 | 01-EE-025B | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 4 | 4:00 | 19:55 | 15:55 |  | 01-Apr | 02-Apr | 01-Apr | 02-Apr
CDUVDU4430 | Completed | Carryout Bundle Pullout | 02/04/2023 06:05:11 | 02/04/2023 06:05:24 | 02/04/2023 00:30:00 | 02/04/2023 06:30:00 | 01-EE-025B | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 0:00 |  | 6:00 | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU4780 | Completed | Pre Cleaning Inspection | 02/04/2023 07:51:38 | 02/04/2023 07:51:38 | 02/04/2023 06:30:00 | 02/04/2023 08:30:00 | 01-EE-025B | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  |  | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU4920 | Completed | Bundle Shifting to Bay | 03/04/2023 05:52:27 | 03/04/2023 05:52:33 | 02/04/2023 08:30:00 | 02/04/2023 11:30:00 | 01-EE-025B | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 02-Apr | 02-Apr | 03-Apr | 03-Apr
CDUVDU10360 | Completed | Carryout Shell Test | 07/04/2023 06:51:24 | 07/04/2023 07:44:47 | 05/04/2023 15:30:00 | 06/04/2023 06:30:00 | 01-EE-003 | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 0:53 |  | 14:07 | 05-Apr | 06-Apr | 07-Apr | 07-Apr
CDUVDU11100 | Completed | Test Ring Drop Down | 07/04/2023 07:44:47 | 07/04/2023 07:44:47 | 06/04/2023 06:30:00 | 06/04/2023 12:30:00 | 01-EE-003 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 06-Apr | 06-Apr | 07-Apr | 07-Apr
CDUVDU11390 | Completed | Floating Head Box-up | 07/04/2023 11:32:39 | 08/04/2023 07:13:55 | 06/04/2023 12:30:00 | 06/04/2023 18:30:00 | 01-EE-003 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 19:41 | 13:41 |  | 06-Apr | 06-Apr | 07-Apr | 08-Apr
CDUVDU11880 | Completed | Tube Test | 08/04/2023 07:14:17 | 08/04/2023 07:14:25 | 06/04/2023 18:30:00 | 07/04/2023 09:30:00 | 01-EE-003 | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 15 | 15:00 | 0:00 |  | 15:00 | 06-Apr | 07-Apr | 08-Apr | 08-Apr
CDUVDU12830 | Completed | Back Dome Boxup | 08/04/2023 07:44:48 | 08/04/2023 07:44:48 | 07/04/2023 09:30:00 | 07/04/2023 17:30:00 | 01-EE-003 | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 0:00 |  |  | 07-Apr | 07-Apr | 08-Apr | 08-Apr
CDUVDU13310 | Completed | Final Test | 08/04/2023 09:32:25 | 08/04/2023 18:40:57 | 07/04/2023 17:30:00 | 08/04/2023 08:30:00 | 01-EE-003 | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 9:09 |  | 5:51 | 07-Apr | 08-Apr | 08-Apr | 08-Apr
CDUVDU14230 | Completed | Deblinding | 14/04/2023 04:15:29 | 14/04/2023 04:15:35 | 08/04/2023 08:30:00 | 08/04/2023 16:30:00 | 01-EE-003 | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 08-Apr | 08-Apr | 14-Apr | 14-Apr
CDUVDU2210 | Completed | Blinding As Per Blind List | 31/03/2023 12:28:09 | 01/04/2023 03:03:15 | 31/03/2023 14:30:00 | 31/03/2023 22:30:00 | 01-EE-003 | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 14:35 | 6:35 |  | 31-Mar | 31-Mar | 31-Mar | 01-Apr
CDUVDU2540 | Completed | Carryout Component Dropping | 31/03/2023 17:28:21 | 01/04/2023 09:43:19 | 31/03/2023 22:30:00 | 01/04/2023 06:30:00 | 01-EE-003 | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 16:15 | 8:15 |  | 31-Mar | 01-Apr | 31-Mar | 01-Apr
CDUVDU3940 | Completed | Carryout Bundle Pullout | 02/04/2023 05:42:52 | 02/04/2023 05:42:52 | 01/04/2023 20:30:00 | 02/04/2023 02:30:00 | 01-EE-003 | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 0:00 |  |  | 01-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU4520 | Completed | Pre Cleaning Inspection | 03/04/2023 05:47:46 | 03/04/2023 05:47:51 | 02/04/2023 02:30:00 | 02/04/2023 04:30:00 | 01-EE-003 | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  | 2:00 | 02-Apr | 02-Apr | 03-Apr | 03-Apr
CDUVDU4610 | Completed | Bundle Shifting to Bay | 02/04/2023 23:01:00 | 03/04/2023 04:02:00 | 02/04/2023 04:30:00 | 02/04/2023 07:30:00 | 01-EE-003 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 5:01 | 2:01 |  | 02-Apr | 02-Apr | 02-Apr | 03-Apr
CDUVDU6420 | Completed | Hydrojetting of Tube Bundle | 03/04/2023 11:01:41 | 05/04/2023 18:45:44 | 02/04/2023 22:30:00 | 04/04/2023 00:30:00 | 01-EE-003 | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 26 | 26:00 | 55:44 | 29:44 |  | 02-Apr | 04-Apr | 03-Apr | 05-Apr
CDUVDU8280 | Completed | Air Drying | 05/04/2023 18:47:34 | 05/04/2023 18:47:43 | 04/04/2023 00:30:00 | 04/04/2023 08:30:00 | 01-EE-003 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  | 8:00 | 04-Apr | 04-Apr | 05-Apr | 05-Apr
CDUVDU8570 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 05/04/2023 18:48:15 | 05/04/2023 18:48:22 | 04/04/2023 08:30:00 | 04/04/2023 14:30:00 | 01-EE-003 | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  | 6:00 | 04-Apr | 04-Apr | 05-Apr | 05-Apr
CDUVDU9040 | Completed | Shifting of bundle from bay | 05/04/2023 18:48:52 | 05/04/2023 18:48:57 | 04/04/2023 14:30:00 | 04/04/2023 17:30:00 | 01-EE-003 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 04-Apr | 04-Apr | 05-Apr | 05-Apr
CDUVDU9210 | Completed | Carryout Bundle Insertion | 06/04/2023 09:52:42 | 06/04/2023 09:52:59 | 04/04/2023 17:30:00 | 05/04/2023 01:30:00 | 01-EE-003 | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 0:00 |  | 8:00 | 04-Apr | 05-Apr | 06-Apr | 06-Apr
CDUVDU9490 | Completed | Channelhead Boxup | 06/04/2023 15:30:17 | 06/04/2023 15:30:25 | 05/04/2023 01:30:00 | 05/04/2023 07:30:00 | 01-EE-003 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 05-Apr | 05-Apr | 06-Apr | 06-Apr
CDUVDU9830 | Completed | Test Ring Boxup | 06/04/2023 12:21:55 | 06/04/2023 18:19:18 | 05/04/2023 07:30:00 | 05/04/2023 15:30:00 | 01-EE-003 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 5:57 |  | 2:03 | 05-Apr | 05-Apr | 06-Apr | 06-Apr
CDUVDU20360 | Completed | Hydrojetting of Tube Bundle | 03/04/2023 05:53:12 | 03/04/2023 05:53:12 | 11/04/2023 02:30:00 | 11/04/2023 09:30:00 | 01-EE-026A | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 7 | 7:00 | 0:00 |  |  | 11-Apr | 11-Apr | 03-Apr | 03-Apr
CDUVDU20870 | Completed | Air Drying | 04/04/2023 08:01:50 | 04/04/2023 08:01:50 | 11/04/2023 09:30:00 | 11/04/2023 12:30:00 | 01-EE-026A | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  |  | 11-Apr | 11-Apr | 04-Apr | 04-Apr
CDUVDU21220 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 04/04/2023 08:01:50 | 04/04/2023 08:01:50 | 11/04/2023 12:30:00 | 11/04/2023 18:30:00 | 01-EE-026A | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  |  | 11-Apr | 11-Apr | 04-Apr | 04-Apr
CDUVDU21970 | Completed | Shifting of bundle from bay | 04/04/2023 08:01:50 | 04/04/2023 08:01:50 | 11/04/2023 18:30:00 | 11/04/2023 21:30:00 | 01-EE-026A | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  |  | 11-Apr | 11-Apr | 04-Apr | 04-Apr
CDUVDU22130 | Completed | Carryout Bundle Insertion | 04/04/2023 08:01:50 | 04/04/2023 08:01:50 | 11/04/2023 21:30:00 | 12/04/2023 03:30:00 | 01-EE-026A | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 6 | 6:00 | 0:00 |  |  | 11-Apr | 12-Apr | 04-Apr | 04-Apr
CDUVDU22820 | Completed | Channelhead Boxup | 08/04/2023 07:46:35 | 08/04/2023 07:46:35 | 12/04/2023 03:30:00 | 12/04/2023 09:30:00 | 01-EE-026A | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 12-Apr | 12-Apr | 08-Apr | 08-Apr
CDUVDU23270 | Completed | Test Ring Boxup | 04/04/2023 16:42:47 | 08/04/2023 15:53:01 | 12/04/2023 09:30:00 | 12/04/2023 17:30:00 | 01-EE-026A | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 95:10 | 87:10 |  | 12-Apr | 12-Apr | 04-Apr | 08-Apr
CDUVDU24020 | Completed | Carryout Shell Test | 08/04/2023 15:53:58 | 09/04/2023 07:08:54 | 12/04/2023 17:30:00 | 13/04/2023 01:30:00 | 01-EE-026A | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 8 | 8:00 | 15:15 | 7:15 |  | 12-Apr | 13-Apr | 08-Apr | 09-Apr
CDUVDU24600 | Completed | Test Ring Drop Down | 09/04/2023 10:16:38 | 09/04/2023 10:16:46 | 13/04/2023 01:30:00 | 13/04/2023 05:30:00 | 01-EE-026A | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 13-Apr | 13-Apr | 09-Apr | 09-Apr
CDUVDU24920 | Completed | Floating Head Box-up | 10/04/2023 10:09:09 | 10/04/2023 10:09:15 | 13/04/2023 05:30:00 | 13/04/2023 09:30:00 | 01-EE-026A | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 13-Apr | 13-Apr | 10-Apr | 10-Apr
CDUVDU25180 | Completed | Tube Test | 10/04/2023 15:38:45 | 10/04/2023 19:34:06 | 13/04/2023 09:30:00 | 13/04/2023 17:30:00 | 01-EE-026A | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 8 | 8:00 | 3:55 |  | 4:05 | 13-Apr | 13-Apr | 10-Apr | 10-Apr
CDUVDU25640 | Completed | Back Dome Boxup | 11/04/2023 10:36:04 | 11/04/2023 10:36:11 | 13/04/2023 17:30:00 | 13/04/2023 21:30:00 | 01-EE-026A | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  | 4:00 | 13-Apr | 13-Apr | 11-Apr | 11-Apr
CDUVDU25820 | Completed | Final Test | 11/04/2023 10:36:25 | 11/04/2023 17:41:10 | 13/04/2023 21:30:00 | 14/04/2023 05:30:00 | 01-EE-026A | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 8 | 8:00 | 7:05 |  | 0:55 | 13-Apr | 14-Apr | 11-Apr | 11-Apr
CDUVDU26240 | Completed | Deblinding | 17/04/2023 09:37:54 | 18/04/2023 00:22:27 | 14/04/2023 05:30:00 | 14/04/2023 11:30:00 | 01-EE-026A | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 6 | 6:00 | 14:45 | 8:45 |  | 14-Apr | 14-Apr | 17-Apr | 18-Apr
CDUVDU3670 | Completed | Blinding As Per Blind List | 31/03/2023 18:48:00 | 31/03/2023 21:48:00 | 01/04/2023 14:30:00 | 01/04/2023 20:30:00 | 01-EE-026A | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 6 | 6:00 | 3:00 |  | 3:00 | 01-Apr | 01-Apr | 31-Mar | 31-Mar
CDUVDU3970 | Completed | Carryout Component Dropping | 31/03/2023 21:48:00 | 01/04/2023 00:48:00 | 01/04/2023 20:30:00 | 02/04/2023 00:30:00 | 01-EE-026A | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 4 | 4:00 | 3:00 |  | 1:00 | 01-Apr | 02-Apr | 31-Mar | 01-Apr
CDUVDU4440 | Completed | Carryout Bundle Pullout | 01/04/2023 00:48:00 | 01/04/2023 09:48:11 | 02/04/2023 00:30:00 | 02/04/2023 06:30:00 | 01-EE-026A | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 9:00 | 3:00 |  | 02-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU4790 | Completed | Pre Cleaning Inspection | 03/04/2023 05:53:12 | 03/04/2023 05:53:12 | 02/04/2023 06:30:00 | 02/04/2023 08:30:00 | 01-EE-026A | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  |  | 02-Apr | 02-Apr | 03-Apr | 03-Apr
CDUVDU4930 | Completed | Bundle Shifting to Bay | 03/04/2023 05:53:12 | 03/04/2023 05:53:12 | 02/04/2023 08:30:00 | 02/04/2023 11:30:00 | 01-EE-026A | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  |  | 02-Apr | 02-Apr | 03-Apr | 03-Apr
CDUVDU20880 | Completed | Hydrojetting of Tube Bundle | 08/04/2023 15:55:54 | 11/04/2023 06:42:36 | 11/04/2023 09:30:00 | 11/04/2023 15:30:00 | 01-EE-026B | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 6 | 6:00 | 62:47 | 56:47 |  | 11-Apr | 11-Apr | 08-Apr | 11-Apr
CDUVDU21620 | Completed | Air Drying | 12/04/2023 15:38:14 | 12/04/2023 15:38:19 | 11/04/2023 15:30:00 | 11/04/2023 18:30:00 | 01-EE-026B | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 11-Apr | 11-Apr | 12-Apr | 12-Apr
CDUVDU21980 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 12/04/2023 15:38:34 | 12/04/2023 15:38:39 | 11/04/2023 18:30:00 | 12/04/2023 00:30:00 | 01-EE-026B | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  | 6:00 | 11-Apr | 12-Apr | 12-Apr | 12-Apr
CDUVDU22400 | Completed | Shifting of bundle from bay | 12/04/2023 15:38:49 | 12/04/2023 15:38:55 | 12/04/2023 00:30:00 | 12/04/2023 03:30:00 | 01-EE-026B | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 12-Apr | 12-Apr | 12-Apr | 12-Apr
CDUVDU22830 | Completed | Carryout Bundle Insertion | 12/04/2023 15:39:03 | 12/04/2023 15:39:09 | 12/04/2023 03:30:00 | 12/04/2023 09:30:00 | 01-EE-026B | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 6 | 6:00 | 0:00 |  | 6:00 | 12-Apr | 12-Apr | 12-Apr | 12-Apr
CDUVDU23280 | Completed | Channelhead Boxup | 13/04/2023 03:23:50 | 14/04/2023 04:34:00 | 12/04/2023 09:30:00 | 12/04/2023 15:30:00 | 01-EE-026B | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 25:10 | 19:10 |  | 12-Apr | 12-Apr | 13-Apr | 14-Apr
CDUVDU23890 | Completed | Test Ring Boxup | 15/04/2023 03:36:05 | 15/04/2023 03:36:15 | 12/04/2023 15:30:00 | 12/04/2023 23:30:00 | 01-EE-026B | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  | 8:00 | 12-Apr | 12-Apr | 15-Apr | 15-Apr
CDUVDU24520 | Completed | Carryout Shell Test | 15/04/2023 03:36:25 | 15/04/2023 07:16:04 | 12/04/2023 23:30:00 | 13/04/2023 07:30:00 | 01-EE-026B | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 8 | 8:00 | 3:40 |  | 4:20 | 12-Apr | 13-Apr | 15-Apr | 15-Apr
CDUVDU25070 | Completed | Test Ring Drop Down | 15/04/2023 07:16:14 | 15/04/2023 07:16:45 | 13/04/2023 07:30:00 | 13/04/2023 11:30:00 | 01-EE-026B | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:01 |  | 3:59 | 13-Apr | 13-Apr | 15-Apr | 15-Apr
CDUVDU25300 | Completed | Floating Head Box-up | 15/04/2023 17:27:26 | 15/04/2023 17:27:30 | 13/04/2023 11:30:00 | 13/04/2023 15:30:00 | 01-EE-026B | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 13-Apr | 13-Apr | 15-Apr | 15-Apr
CDUVDU25520 | Completed | Tube Test | 15/04/2023 17:27:51 | 16/04/2023 00:56:16 | 13/04/2023 15:30:00 | 13/04/2023 23:30:00 | 01-EE-026B | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 8 | 8:00 | 7:28 |  | 0:32 | 13-Apr | 13-Apr | 15-Apr | 16-Apr
CDUVDU25920 | Completed | Back Dome Boxup | 16/04/2023 00:56:28 | 16/04/2023 00:56:38 | 13/04/2023 23:30:00 | 14/04/2023 03:30:00 | 01-EE-026B | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  | 4:00 | 13-Apr | 14-Apr | 16-Apr | 16-Apr
CDUVDU26140 | Completed | Final Test | 16/04/2023 00:56:47 | 16/04/2023 16:42:04 | 14/04/2023 03:30:00 | 14/04/2023 11:30:00 | 01-EE-026B | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 8 | 8:00 | 15:45 | 7:45 |  | 14-Apr | 14-Apr | 16-Apr | 16-Apr
CDUVDU26520 | Completed | Deblinding | 17/04/2023 09:36:43 | 18/04/2023 00:26:59 | 14/04/2023 11:30:00 | 14/04/2023 17:30:00 | 01-EE-026B | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 6 | 6:00 | 14:50 | 8:50 |  | 14-Apr | 14-Apr | 17-Apr | 18-Apr
CDUVDU3680 | Completed | Blinding As Per Blind List | 06/04/2023 09:37:23 | 06/04/2023 11:16:32 | 01/04/2023 14:30:00 | 01/04/2023 20:30:00 | 01-EE-026B | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 6 | 6:00 | 1:39 |  | 4:21 | 01-Apr | 01-Apr | 06-Apr | 06-Apr
CDUVDU3980 | Completed | Carryout Component Dropping | 01/04/2023 09:58:57 | 01/04/2023 09:59:03 | 01/04/2023 20:30:00 | 02/04/2023 00:30:00 | 01-EE-026B | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 4 | 4:00 | 0:00 |  | 4:00 | 01-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU4450 | Completed | Carryout Bundle Pullout | 02/04/2023 05:50:33 | 05/04/2023 19:21:57 | 02/04/2023 00:30:00 | 02/04/2023 06:30:00 | 01-EE-026B | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 85:31 | 79:31 |  | 02-Apr | 02-Apr | 02-Apr | 05-Apr
CDUVDU4800 | Completed | Pre Cleaning Inspection | 02/04/2023 05:50:50 | 02/04/2023 05:50:53 | 02/04/2023 06:30:00 | 02/04/2023 08:30:00 | 01-EE-026B | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  | 2:00 | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU4940 | Completed | Bundle Shifting to Bay | 02/04/2023 06:06:17 | 02/04/2023 06:06:23 | 02/04/2023 08:30:00 | 02/04/2023 11:30:00 | 01-EE-026B | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU12940 | Completed | Hydrojetting of Tube Bundle | 06/04/2023 07:04:20 | 06/04/2023 11:51:58 | 07/04/2023 11:30:00 | 08/04/2023 13:30:00 | 01-EE-029A | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 26 | 26:00 | 4:48 |  | 21:12 | 07-Apr | 08-Apr | 06-Apr | 06-Apr
CDUVDU14590 | Completed | Air Drying | 06/04/2023 11:51:32 | 06/04/2023 11:52:10 | 08/04/2023 13:30:00 | 08/04/2023 21:30:00 | 01-EE-029A | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:01 |  | 7:59 | 08-Apr | 08-Apr | 06-Apr | 06-Apr
CDUVDU15190 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 06/04/2023 11:55:29 | 06/04/2023 11:56:18 | 08/04/2023 21:30:00 | 09/04/2023 03:30:00 | 01-EE-029A | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:01 |  | 5:59 | 08-Apr | 09-Apr | 06-Apr | 06-Apr
CDUVDU15800 | Completed | Shifting of bundle from bay | 06/04/2023 11:55:57 | 06/04/2023 11:56:04 | 09/04/2023 03:30:00 | 09/04/2023 07:30:00 | 01-EE-029A | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 09-Apr | 09-Apr | 06-Apr | 06-Apr
CDUVDU16000 | Completed | Carryout Bundle Insertion | 08/04/2023 07:48:07 | 08/04/2023 12:15:42 | 09/04/2023 07:30:00 | 09/04/2023 15:30:00 | 01-EE-029A | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 4:28 |  | 3:32 | 09-Apr | 09-Apr | 08-Apr | 08-Apr
CDUVDU16750 | Completed | Channelhead Boxup | 11/04/2023 20:09:11 | 11/04/2023 20:09:16 | 09/04/2023 15:30:00 | 09/04/2023 21:30:00 | 01-EE-029A | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 09-Apr | 09-Apr | 11-Apr | 11-Apr
CDUVDU17270 | Completed | Test Ring Boxup | 13/04/2023 19:13:08 | 13/04/2023 19:13:13 | 09/04/2023 21:30:00 | 10/04/2023 05:30:00 | 01-EE-029A | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  | 8:00 | 09-Apr | 10-Apr | 13-Apr | 13-Apr
CDUVDU18170 | Completed | Carryout Shell Test | 13/04/2023 19:18:53 | 13/04/2023 19:22:40 | 10/04/2023 05:30:00 | 10/04/2023 20:30:00 | 01-EE-029A | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 0:04 |  | 14:56 | 10-Apr | 10-Apr | 13-Apr | 13-Apr
CDUVDU19520 | Completed | Test Ring Drop Down | 15/04/2023 03:31:08 | 15/04/2023 03:31:27 | 10/04/2023 20:30:00 | 11/04/2023 02:30:00 | 01-EE-029A | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 10-Apr | 11-Apr | 15-Apr | 15-Apr
CDUVDU20320 | Completed | Floating Head Box-up | 15/04/2023 03:31:17 | 15/04/2023 03:31:41 | 11/04/2023 02:30:00 | 11/04/2023 08:30:00 | 01-EE-029A | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 11-Apr | 11-Apr | 15-Apr | 15-Apr
CDUVDU20780 | Completed | Tube Test | 15/04/2023 03:31:52 | 16/04/2023 00:58:18 | 11/04/2023 08:30:00 | 11/04/2023 23:30:00 | 01-EE-029A | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 15 | 15:00 | 21:26 | 6:26 |  | 11-Apr | 11-Apr | 15-Apr | 16-Apr
CDUVDU22330 | Completed | Back Dome Boxup | 16/04/2023 00:58:26 | 16/04/2023 06:41:56 | 11/04/2023 23:30:00 | 12/04/2023 07:30:00 | 01-EE-029A | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 5:43 |  | 2:17 | 11-Apr | 12-Apr | 16-Apr | 16-Apr
CDUVDU23130 | Completed | Final Test | 16/04/2023 11:46:11 | 16/04/2023 18:53:56 | 12/04/2023 07:30:00 | 12/04/2023 22:30:00 | 01-EE-029A | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 7:08 |  | 7:52 | 12-Apr | 12-Apr | 16-Apr | 16-Apr
CDUVDU24410 | Completed | Deblinding | 18/04/2023 00:27:57 | 18/04/2023 00:28:01 | 12/04/2023 22:30:00 | 13/04/2023 06:30:00 | 01-EE-029A | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 12-Apr | 13-Apr | 18-Apr | 18-Apr
CDUVDU5850 | Completed | Blinding As Per Blind List | 02/04/2023 06:07:37 | 02/04/2023 06:07:46 | 02/04/2023 14:30:00 | 02/04/2023 22:30:00 | 01-EE-029A | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU6450 | Completed | Carryout Component Dropping | 02/04/2023 06:07:37 | 02/04/2023 06:07:46 | 02/04/2023 22:30:00 | 03/04/2023 06:30:00 | 01-EE-029A | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  | 8:00 | 02-Apr | 03-Apr | 02-Apr | 02-Apr
CDUVDU6920 | Completed | Carryout Bundle Pullout | 03/04/2023 04:39:10 | 04/04/2023 12:00:15 | 03/04/2023 06:30:00 | 03/04/2023 12:30:00 | 01-EE-029A | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 31:21 | 25:21 |  | 03-Apr | 03-Apr | 03-Apr | 04-Apr
CDUVDU7510 | Completed | Pre Cleaning Inspection | 04/04/2023 21:41:15 | 04/04/2023 21:41:15 | 03/04/2023 12:30:00 | 03/04/2023 14:30:00 | 01-EE-029A | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  |  | 03-Apr | 03-Apr | 04-Apr | 04-Apr
CDUVDU7700 | Completed | Bundle Shifting to Bay | 06/04/2023 03:04:00 | 06/04/2023 07:04:27 | 03/04/2023 14:30:00 | 03/04/2023 17:30:00 | 01-EE-029A | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 4:00 | 1:00 |  | 03-Apr | 03-Apr | 06-Apr | 06-Apr
CDUVDU14600 | Completed | Hydrojetting of Tube Bundle | 05/04/2023 19:00:06 | 05/04/2023 19:00:11 | 08/04/2023 13:30:00 | 09/04/2023 15:30:00 | 01-EE-029B | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 26 | 26:00 | 0:00 |  | 26:00 | 08-Apr | 09-Apr | 05-Apr | 05-Apr
CDUVDU16760 | Completed | Air Drying | 05/04/2023 19:00:35 | 05/04/2023 19:00:40 | 09/04/2023 15:30:00 | 09/04/2023 23:30:00 | 01-EE-029B | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  | 8:00 | 09-Apr | 09-Apr | 05-Apr | 05-Apr
CDUVDU17510 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 05/04/2023 21:59:45 | 05/04/2023 21:59:49 | 09/04/2023 23:30:00 | 10/04/2023 05:30:00 | 01-EE-029B | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  | 6:00 | 09-Apr | 10-Apr | 05-Apr | 05-Apr
CDUVDU18180 | Completed | Shifting of bundle from bay | 08/04/2023 07:47:30 | 08/04/2023 07:47:30 | 10/04/2023 05:30:00 | 10/04/2023 09:30:00 | 01-EE-029B | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  |  | 10-Apr | 10-Apr | 08-Apr | 08-Apr
CDUVDU18500 | Completed | Carryout Bundle Insertion | 08/04/2023 07:47:30 | 08/04/2023 07:47:30 | 10/04/2023 09:30:00 | 10/04/2023 17:30:00 | 01-EE-029B | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 0:00 |  |  | 10-Apr | 10-Apr | 08-Apr | 08-Apr
CDUVDU19270 | Completed | Channelhead Boxup | 11/04/2023 20:09:27 | 11/04/2023 20:09:33 | 10/04/2023 17:30:00 | 10/04/2023 23:30:00 | 01-EE-029B | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 10-Apr | 10-Apr | 11-Apr | 11-Apr
CDUVDU19930 | Completed | Test Ring Boxup | 14/04/2023 04:34:50 | 14/04/2023 04:35:03 | 10/04/2023 23:30:00 | 11/04/2023 07:30:00 | 01-EE-029B | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  | 8:00 | 10-Apr | 11-Apr | 14-Apr | 14-Apr
CDUVDU20710 | Completed | Carryout Shell Test | 14/04/2023 04:34:50 | 14/04/2023 07:52:36 | 11/04/2023 07:30:00 | 11/04/2023 22:30:00 | 01-EE-029B | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 3:18 |  | 11:42 | 11-Apr | 11-Apr | 14-Apr | 14-Apr
CDUVDU22270 | Completed | Test Ring Drop Down | 15/04/2023 03:32:37 | 15/04/2023 03:32:57 | 11/04/2023 22:30:00 | 12/04/2023 04:30:00 | 01-EE-029B | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 11-Apr | 12-Apr | 15-Apr | 15-Apr
CDUVDU22880 | Completed | Floating Head Box-up | 15/04/2023 03:32:47 | 15/04/2023 03:33:08 | 12/04/2023 04:30:00 | 12/04/2023 10:30:00 | 01-EE-029B | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 12-Apr | 12-Apr | 15-Apr | 15-Apr
CDUVDU23380 | Completed | Tube Test | 15/04/2023 03:33:19 | 15/04/2023 17:23:22 | 12/04/2023 10:30:00 | 13/04/2023 01:30:00 | 01-EE-029B | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 15 | 15:00 | 13:50 |  | 1:10 | 12-Apr | 13-Apr | 15-Apr | 15-Apr
CDUVDU24590 | Completed | Back Dome Boxup | 16/04/2023 00:59:00 | 16/04/2023 06:42:16 | 13/04/2023 01:30:00 | 13/04/2023 09:30:00 | 01-EE-029B | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 5:43 |  | 2:17 | 13-Apr | 13-Apr | 16-Apr | 16-Apr
CDUVDU25170 | Completed | Final Test | 16/04/2023 11:46:25 | 17/04/2023 01:35:44 | 13/04/2023 09:30:00 | 14/04/2023 00:30:00 | 01-EE-029B | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 13:49 |  | 1:11 | 13-Apr | 14-Apr | 16-Apr | 17-Apr
CDUVDU25970 | Completed | Deblinding | 18/04/2023 00:34:37 | 18/04/2023 00:34:52 | 14/04/2023 00:30:00 | 14/04/2023 08:30:00 | 01-EE-029B | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 14-Apr | 14-Apr | 18-Apr | 18-Apr
CDUVDU5860 | Completed | Blinding As Per Blind List | 02/04/2023 06:08:09 | 02/04/2023 06:08:17 | 02/04/2023 14:30:00 | 02/04/2023 22:30:00 | 01-EE-029B | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU6460 | Completed | Carryout Component Dropping | 02/04/2023 06:08:09 | 02/04/2023 06:08:17 | 02/04/2023 22:30:00 | 03/04/2023 06:30:00 | 01-EE-029B | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  | 8:00 | 02-Apr | 03-Apr | 02-Apr | 02-Apr
CDUVDU7520 | Completed | Carryout Bundle Pullout | 04/04/2023 12:03:36 | 04/04/2023 16:14:29 | 03/04/2023 12:30:00 | 03/04/2023 18:30:00 | 01-EE-029B | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 4:11 |  | 1:49 | 03-Apr | 03-Apr | 04-Apr | 04-Apr
CDUVDU8000 | Completed | Pre Cleaning Inspection | 04/04/2023 21:41:30 | 04/04/2023 21:41:30 | 03/04/2023 18:30:00 | 03/04/2023 20:30:00 | 01-EE-029B | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  |  | 03-Apr | 03-Apr | 04-Apr | 04-Apr
CDUVDU8040 | Completed | Bundle Shifting to Bay | 05/04/2023 18:59:42 | 05/04/2023 18:59:48 | 03/04/2023 20:30:00 | 03/04/2023 23:30:00 | 01-EE-029B | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 03-Apr | 03-Apr | 05-Apr | 05-Apr
CDUVDU14340 | Completed | Hydrojetting of Tube Bundle | 03/04/2023 05:54:57 | 03/04/2023 05:55:06 | 08/04/2023 09:30:00 | 08/04/2023 15:30:00 | 01-EE-035A | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 6 | 6:00 | 0:00 |  | 6:00 | 08-Apr | 08-Apr | 03-Apr | 03-Apr
CDUVDU14870 | Completed | Air Drying | 03/04/2023 05:55:17 | 06/04/2023 07:07:47 | 08/04/2023 15:30:00 | 08/04/2023 18:30:00 | 01-EE-035A | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 73:13 | 70:13 |  | 08-Apr | 08-Apr | 03-Apr | 06-Apr
CDUVDU15040 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 03/04/2023 18:20:23 | 03/04/2023 18:20:31 | 08/04/2023 18:30:00 | 09/04/2023 00:30:00 | 01-EE-035A | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  | 6:00 | 08-Apr | 09-Apr | 03-Apr | 03-Apr
CDUVDU15450 | Completed | Shifting of bundle from bay | 07/04/2023 06:59:42 | 07/04/2023 06:59:47 | 09/04/2023 00:30:00 | 09/04/2023 03:30:00 | 01-EE-035A | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 09-Apr | 09-Apr | 07-Apr | 07-Apr
CDUVDU15810 | Completed | Carryout Bundle Insertion | 08/04/2023 07:10:05 | 08/04/2023 07:10:15 | 09/04/2023 03:30:00 | 09/04/2023 09:30:00 | 01-EE-035A | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 6 | 6:00 | 0:00 |  | 6:00 | 09-Apr | 09-Apr | 08-Apr | 08-Apr
CDUVDU16240 | Completed | Channelhead Boxup | 08/04/2023 07:42:21 | 08/04/2023 07:42:21 | 09/04/2023 09:30:00 | 09/04/2023 15:30:00 | 01-EE-035A | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 09-Apr | 09-Apr | 08-Apr | 08-Apr
CDUVDU16780 | Completed | Test Ring Boxup | 08/04/2023 07:42:51 | 08/04/2023 15:44:10 | 09/04/2023 15:30:00 | 09/04/2023 23:30:00 | 01-EE-035A | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 8:01 | 0:01 |  | 09-Apr | 09-Apr | 08-Apr | 08-Apr
CDUVDU17520 | Completed | Carryout Shell Test | 08/04/2023 15:47:06 | 08/04/2023 21:47:16 | 09/04/2023 23:30:00 | 10/04/2023 05:30:00 | 01-EE-035A | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 6 | 6:00 | 6:00 | 0:00 |  | 09-Apr | 10-Apr | 08-Apr | 08-Apr
CDUVDU18210 | Completed | Test Ring Drop Down | 09/04/2023 06:50:02 | 09/04/2023 06:52:08 | 10/04/2023 05:30:00 | 10/04/2023 09:30:00 | 01-EE-035A | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:02 |  | 3:58 | 10-Apr | 10-Apr | 09-Apr | 09-Apr
CDUVDU18520 | Completed | Floating Head Box-up | 09/04/2023 09:53:26 | 09/04/2023 09:53:31 | 10/04/2023 09:30:00 | 10/04/2023 13:30:00 | 01-EE-035A | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 10-Apr | 10-Apr | 09-Apr | 09-Apr
CDUVDU18900 | Completed | Tube Test | 09/04/2023 10:08:48 | 09/04/2023 14:52:29 | 10/04/2023 13:30:00 | 10/04/2023 19:30:00 | 01-EE-035A | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 6 | 6:00 | 4:44 |  | 1:16 | 10-Apr | 10-Apr | 09-Apr | 09-Apr
CDUVDU19440 | Completed | Back Dome Boxup | 09/04/2023 16:50:47 | 09/04/2023 16:52:18 | 10/04/2023 19:30:00 | 10/04/2023 23:30:00 | 01-EE-035A | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:02 |  | 3:58 | 10-Apr | 10-Apr | 09-Apr | 09-Apr
CDUVDU19960 | Completed | Final Test | 10/04/2023 06:57:20 | 10/04/2023 09:27:08 | 10/04/2023 23:30:00 | 11/04/2023 05:30:00 | 01-EE-035A | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 6 | 6:00 | 2:30 |  | 3:30 | 10-Apr | 11-Apr | 10-Apr | 10-Apr
CDUVDU20560 | Completed | Deblinding | 13/04/2023 20:15:00 | 14/04/2023 05:15:00 | 11/04/2023 05:30:00 | 11/04/2023 11:30:00 | 01-EE-035A | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 6 | 6:00 | 9:00 | 3:00 |  | 11-Apr | 11-Apr | 13-Apr | 14-Apr
CDUVDU3690 | Completed | Blinding As Per Blind List | 01/04/2023 06:32:23 | 01/04/2023 06:32:23 | 01/04/2023 14:30:00 | 01/04/2023 20:30:00 | 01-EE-035A | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 6 | 6:00 | 0:00 |  |  | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU3990 | Completed | Carryout Component Dropping | 01/04/2023 06:32:23 | 01/04/2023 06:32:23 | 01/04/2023 20:30:00 | 02/04/2023 00:30:00 | 01-EE-035A | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 4 | 4:00 | 0:00 |  |  | 01-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU4460 | Completed | Carryout Bundle Pullout | 01/04/2023 06:32:23 | 01/04/2023 06:32:23 | 02/04/2023 00:30:00 | 02/04/2023 06:30:00 | 01-EE-035A | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 0:00 |  |  | 02-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU4810 | Completed | Pre Cleaning Inspection | 01/04/2023 06:32:23 | 01/04/2023 06:32:23 | 02/04/2023 06:30:00 | 02/04/2023 08:30:00 | 01-EE-035A | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  |  | 02-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU4950 | Completed | Bundle Shifting to Bay | 01/04/2023 09:48:43 | 01/04/2023 09:48:57 | 02/04/2023 08:30:00 | 02/04/2023 11:30:00 | 01-EE-035A | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 02-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU14880 | Completed | Hydrojetting of Tube Bundle | 03/04/2023 18:20:52 | 03/04/2023 18:20:59 | 08/04/2023 15:30:00 | 08/04/2023 22:30:00 | 01-EE-035B | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 7 | 7:00 | 0:00 |  | 7:00 | 08-Apr | 08-Apr | 03-Apr | 03-Apr
CDUVDU15300 | Completed | Air Drying | 03/04/2023 18:22:02 | 03/04/2023 18:22:07 | 08/04/2023 22:30:00 | 09/04/2023 01:30:00 | 01-EE-035B | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 08-Apr | 09-Apr | 03-Apr | 03-Apr
CDUVDU15620 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 03/04/2023 18:21:41 | 03/04/2023 18:21:50 | 09/04/2023 01:30:00 | 09/04/2023 07:30:00 | 01-EE-035B | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  | 6:00 | 09-Apr | 09-Apr | 03-Apr | 03-Apr
CDUVDU16020 | Completed | Shifting of bundle from bay | 08/04/2023 07:10:53 | 08/04/2023 07:11:02 | 09/04/2023 07:30:00 | 09/04/2023 10:30:00 | 01-EE-035B | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 09-Apr | 09-Apr | 08-Apr | 08-Apr
CDUVDU16370 | Completed | Carryout Bundle Insertion | 08/04/2023 07:10:53 | 08/04/2023 07:11:02 | 09/04/2023 10:30:00 | 09/04/2023 16:30:00 | 01-EE-035B | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 6 | 6:00 | 0:00 |  | 6:00 | 09-Apr | 09-Apr | 08-Apr | 08-Apr
CDUVDU16830 | Completed | Channelhead Boxup | 08/04/2023 07:43:13 | 08/04/2023 07:43:13 | 09/04/2023 16:30:00 | 09/04/2023 22:30:00 | 01-EE-035B | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 09-Apr | 09-Apr | 08-Apr | 08-Apr
CDUVDU17460 | Completed | Test Ring Boxup | 08/04/2023 07:43:33 | 08/04/2023 15:45:09 | 09/04/2023 22:30:00 | 10/04/2023 06:30:00 | 01-EE-035B | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 8:02 | 0:02 |  | 09-Apr | 10-Apr | 08-Apr | 08-Apr
CDUVDU18350 | Completed | Carryout Shell Test | 08/04/2023 15:46:10 | 08/04/2023 21:47:48 | 10/04/2023 06:30:00 | 10/04/2023 14:30:00 | 01-EE-035B | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 8 | 8:00 | 6:02 |  | 1:58 | 10-Apr | 10-Apr | 08-Apr | 08-Apr
CDUVDU19060 | Completed | Test Ring Drop Down | 09/04/2023 06:51:40 | 09/04/2023 06:51:51 | 10/04/2023 14:30:00 | 10/04/2023 18:30:00 | 01-EE-035B | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 10-Apr | 10-Apr | 09-Apr | 09-Apr
CDUVDU19400 | Completed | Floating Head Box-up | 09/04/2023 09:57:33 | 09/04/2023 09:57:39 | 10/04/2023 18:30:00 | 10/04/2023 22:30:00 | 01-EE-035B | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 10-Apr | 10-Apr | 09-Apr | 09-Apr
CDUVDU19750 | Completed | Tube Test | 09/04/2023 10:09:11 | 09/04/2023 14:53:32 | 10/04/2023 22:30:00 | 11/04/2023 06:30:00 | 01-EE-035B | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 8 | 8:00 | 4:44 |  | 3:16 | 10-Apr | 11-Apr | 09-Apr | 09-Apr
CDUVDU20670 | Completed | Back Dome Boxup | 09/04/2023 16:52:31 | 09/04/2023 16:52:39 | 11/04/2023 06:30:00 | 11/04/2023 10:30:00 | 01-EE-035B | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  | 4:00 | 11-Apr | 11-Apr | 09-Apr | 09-Apr
CDUVDU21000 | Completed | Final Test | 10/04/2023 06:57:54 | 10/04/2023 09:27:42 | 11/04/2023 10:30:00 | 11/04/2023 18:30:00 | 01-EE-035B | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 8 | 8:00 | 2:30 |  | 5:30 | 11-Apr | 11-Apr | 10-Apr | 10-Apr
CDUVDU22000 | Completed | Deblinding | 14/04/2023 20:33:00 | 15/04/2023 05:33:10 | 11/04/2023 18:30:00 | 12/04/2023 00:30:00 | 01-EE-035B | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 6 | 6:00 | 9:00 | 3:00 |  | 11-Apr | 12-Apr | 14-Apr | 15-Apr
CDUVDU3700 | Completed | Blinding As Per Blind List | 31/03/2023 09:43:00 | 31/03/2023 15:43:00 | 01/04/2023 14:30:00 | 01/04/2023 20:30:00 | 01-EE-035B | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 6 | 6:00 | 6:00 |  |  | 01-Apr | 01-Apr | 31-Mar | 31-Mar
CDUVDU4000 | Completed | Carryout Component Dropping | 31/03/2023 15:43:00 | 31/03/2023 21:43:00 | 01/04/2023 20:30:00 | 02/04/2023 00:30:00 | 01-EE-035B | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 4 | 4:00 | 6:00 | 2:00 |  | 01-Apr | 02-Apr | 31-Mar | 31-Mar
CDUVDU4470 | Completed | Carryout Bundle Pullout | 01/04/2023 09:43:00 | 01/04/2023 21:43:00 | 02/04/2023 00:30:00 | 02/04/2023 06:30:00 | 01-EE-035B | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 12:00 | 6:00 |  | 02-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU4820 | Completed | Pre Cleaning Inspection | 01/04/2023 09:49:46 | 01/04/2023 09:49:51 | 02/04/2023 06:30:00 | 02/04/2023 08:30:00 | 01-EE-035B | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  | 2:00 | 02-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU4960 | Completed | Bundle Shifting to Bay | 01/04/2023 09:49:59 | 01/04/2023 09:50:05 | 02/04/2023 08:30:00 | 02/04/2023 11:30:00 | 01-EE-035B | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 02-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU15310 | Completed | Hydrojetting of Tube Bundle | 03/04/2023 05:57:27 | 03/04/2023 05:57:32 | 08/04/2023 22:30:00 | 09/04/2023 05:30:00 | 01-EE-036 | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 7 | 7:00 | 0:00 |  | 7:00 | 08-Apr | 09-Apr | 03-Apr | 03-Apr
CDUVDU15920 | Completed | Air Drying | 03/04/2023 05:57:27 | 06/04/2023 07:08:29 | 09/04/2023 05:30:00 | 09/04/2023 08:30:00 | 01-EE-036 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 73:11 | 70:11 |  | 09-Apr | 09-Apr | 03-Apr | 06-Apr
CDUVDU16140 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 10/04/2023 06:58:25 | 10/04/2023 06:58:37 | 09/04/2023 08:30:00 | 09/04/2023 14:30:00 | 01-EE-036 | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  | 6:00 | 09-Apr | 09-Apr | 10-Apr | 10-Apr
CDUVDU16730 | Completed | Shifting of bundle from bay | 12/04/2023 18:37:01 | 12/04/2023 18:37:06 | 09/04/2023 14:30:00 | 09/04/2023 17:30:00 | 01-EE-036 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 09-Apr | 09-Apr | 12-Apr | 12-Apr
CDUVDU16870 | Completed | Carryout Bundle Insertion | 12/04/2023 18:37:13 | 12/04/2023 18:37:29 | 09/04/2023 17:30:00 | 09/04/2023 23:30:00 | 01-EE-036 | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 6 | 6:00 | 0:00 |  | 6:00 | 09-Apr | 09-Apr | 12-Apr | 12-Apr
CDUVDU17530 | Completed | Channelhead Boxup | 13/04/2023 03:30:23 | 13/04/2023 16:51:15 | 09/04/2023 23:30:00 | 10/04/2023 05:30:00 | 01-EE-036 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 13:21 | 7:21 |  | 09-Apr | 10-Apr | 13-Apr | 13-Apr
CDUVDU18220 | Completed | Test Ring Boxup | 13/04/2023 16:51:27 | 13/04/2023 16:51:35 | 10/04/2023 05:30:00 | 10/04/2023 13:30:00 | 01-EE-036 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  | 8:00 | 10-Apr | 10-Apr | 13-Apr | 13-Apr
CDUVDU18910 | Completed | Carryout Shell Test | 13/04/2023 16:52:37 | 13/04/2023 19:11:13 | 10/04/2023 13:30:00 | 10/04/2023 21:30:00 | 01-EE-036 | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 8 | 8:00 | 2:19 |  | 5:41 | 10-Apr | 10-Apr | 13-Apr | 13-Apr
CDUVDU19680 | Completed | Test Ring Drop Down | 14/04/2023 04:36:46 | 14/04/2023 04:36:50 | 10/04/2023 21:30:00 | 11/04/2023 01:30:00 | 01-EE-036 | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 10-Apr | 11-Apr | 14-Apr | 14-Apr
CDUVDU20120 | Completed | Floating Head Box-up | 14/04/2023 04:36:46 | 14/04/2023 07:53:10 | 11/04/2023 01:30:00 | 11/04/2023 05:30:00 | 01-EE-036 | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 3:16 |  | 0:44 | 11-Apr | 11-Apr | 14-Apr | 14-Apr
CDUVDU20570 | Completed | Tube Test | 14/04/2023 07:53:20 | 14/04/2023 07:53:29 | 11/04/2023 05:30:00 | 11/04/2023 13:30:00 | 01-EE-036 | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 8 | 8:00 | 0:00 |  | 8:00 | 11-Apr | 11-Apr | 14-Apr | 14-Apr
CDUVDU21280 | Completed | Back Dome Boxup | 14/04/2023 11:00:51 | 14/04/2023 11:01:04 | 11/04/2023 13:30:00 | 11/04/2023 17:30:00 | 01-EE-036 | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  | 4:00 | 11-Apr | 11-Apr | 14-Apr | 14-Apr
CDUVDU21900 | Completed | Final Test | 14/04/2023 11:02:50 | 14/04/2023 18:26:23 | 11/04/2023 17:30:00 | 12/04/2023 01:30:00 | 01-EE-036 | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 8 | 8:00 | 7:24 |  | 0:36 | 11-Apr | 12-Apr | 14-Apr | 14-Apr
CDUVDU2240 | Completed | Blinding As Per Blind List | 01/04/2023 06:35:15 | 01/04/2023 06:35:15 | 31/03/2023 14:30:00 | 31/03/2023 20:30:00 | 01-EE-036 | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 6 | 6:00 | 0:00 |  |  | 31-Mar | 31-Mar | 01-Apr | 01-Apr
CDUVDU22470 | Completed | Deblinding | 16/04/2023 06:42:44 | 16/04/2023 06:42:52 | 12/04/2023 01:30:00 | 12/04/2023 07:30:00 | 01-EE-036 | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 6 | 6:00 | 0:00 |  | 6:00 | 12-Apr | 12-Apr | 16-Apr | 16-Apr
CDUVDU2400 | Completed | Carryout Component Dropping | 31/03/2023 19:10:34 | 31/03/2023 19:10:43 | 31/03/2023 20:30:00 | 01/04/2023 00:30:00 | 01-EE-036 | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 4 | 4:00 | 0:00 |  | 4:00 | 31-Mar | 01-Apr | 31-Mar | 31-Mar
CDUVDU2600 | Completed | Carryout Bundle Pullout | 01/04/2023 06:35:15 | 01/04/2023 06:35:15 | 01/04/2023 00:30:00 | 01/04/2023 06:30:00 | 01-EE-036 | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 0:00 |  |  | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU2700 | Completed | Pre Cleaning Inspection | 01/04/2023 06:35:15 | 01/04/2023 06:35:15 | 01/04/2023 06:30:00 | 01/04/2023 08:30:00 | 01-EE-036 | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  |  | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU2800 | Completed | Bundle Shifting to Bay | 01/04/2023 09:51:51 | 01/04/2023 09:51:56 | 01/04/2023 08:30:00 | 01/04/2023 11:30:00 | 01-EE-036 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU15930 | Completed | Hydrojetting of Tube Bundle | 03/04/2023 05:59:16 | 03/04/2023 05:59:20 | 09/04/2023 05:30:00 | 09/04/2023 11:30:00 | 01-EE-037 | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 6 | 6:00 | 0:00 |  | 6:00 | 09-Apr | 09-Apr | 03-Apr | 03-Apr
CDUVDU16430 | Completed | Air Drying | 04/04/2023 22:12:56 | 04/04/2023 22:12:56 | 09/04/2023 11:30:00 | 09/04/2023 14:30:00 | 01-EE-037 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  |  | 09-Apr | 09-Apr | 04-Apr | 04-Apr
CDUVDU16740 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 04/04/2023 08:44:11 | 04/04/2023 22:12:56 | 09/04/2023 14:30:00 | 09/04/2023 20:30:00 | 01-EE-037 | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 13:29 | 7:29 |  | 09-Apr | 09-Apr | 04-Apr | 04-Apr
CDUVDU17240 | Completed | Shifting of bundle from bay | 05/04/2023 07:42:06 | 05/04/2023 07:42:18 | 09/04/2023 20:30:00 | 09/04/2023 23:30:00 | 01-EE-037 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 09-Apr | 09-Apr | 05-Apr | 05-Apr
CDUVDU17540 | Completed | Carryout Bundle Insertion | 05/04/2023 07:35:01 | 05/04/2023 07:35:01 | 09/04/2023 23:30:00 | 10/04/2023 05:30:00 | 01-EE-037 | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 6 | 6:00 | 0:00 |  |  | 09-Apr | 10-Apr | 05-Apr | 05-Apr
CDUVDU18230 | Completed | Channelhead Boxup | 05/04/2023 07:41:38 | 05/04/2023 07:41:45 | 10/04/2023 05:30:00 | 10/04/2023 11:30:00 | 01-EE-037 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 10-Apr | 10-Apr | 05-Apr | 05-Apr
CDUVDU18710 | Completed | Test Ring Boxup | 05/04/2023 07:43:38 | 05/04/2023 16:32:08 | 10/04/2023 11:30:00 | 10/04/2023 19:30:00 | 01-EE-037 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 8:48 | 0:48 |  | 10-Apr | 10-Apr | 05-Apr | 05-Apr
CDUVDU19450 | Completed | Carryout Shell Test | 05/04/2023 16:32:21 | 09/04/2023 06:49:08 | 10/04/2023 19:30:00 | 11/04/2023 03:30:00 | 01-EE-037 | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 8 | 8:00 | 86:17 | 78:17 |  | 10-Apr | 11-Apr | 05-Apr | 09-Apr
CDUVDU20410 | Completed | Test Ring Drop Down | 09/04/2023 10:18:10 | 10/04/2023 10:03:36 | 11/04/2023 03:30:00 | 11/04/2023 07:30:00 | 01-EE-037 | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 23:45 | 19:45 |  | 11-Apr | 11-Apr | 09-Apr | 10-Apr
CDUVDU20720 | Completed | Floating Head Box-up | 10/04/2023 10:03:46 | 10/04/2023 10:03:52 | 11/04/2023 07:30:00 | 11/04/2023 11:30:00 | 01-EE-037 | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 11-Apr | 11-Apr | 10-Apr | 10-Apr
CDUVDU21180 | Completed | Tube Test | 10/04/2023 10:05:06 | 10/04/2023 19:35:43 | 11/04/2023 11:30:00 | 11/04/2023 19:30:00 | 01-EE-037 | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 8 | 8:00 | 9:31 | 1:31 |  | 11-Apr | 11-Apr | 10-Apr | 10-Apr
CDUVDU22040 | Completed | Back Dome Boxup | 11/04/2023 07:35:39 | 11/04/2023 07:35:39 | 11/04/2023 19:30:00 | 11/04/2023 23:30:00 | 01-EE-037 | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  |  | 11-Apr | 11-Apr | 11-Apr | 11-Apr
CDUVDU22340 | Completed | Final Test | 11/04/2023 07:36:24 | 11/04/2023 10:47:42 | 11/04/2023 23:30:00 | 12/04/2023 07:30:00 | 01-EE-037 | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 8 | 8:00 | 3:11 |  | 4:49 | 11-Apr | 12-Apr | 11-Apr | 11-Apr
CDUVDU2250 | Completed | Blinding As Per Blind List | 01/04/2023 04:01:49 | 01/04/2023 04:02:19 | 31/03/2023 14:30:00 | 31/03/2023 20:30:00 | 01-EE-037 | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 6 | 6:00 | 0:01 |  | 5:59 | 31-Mar | 31-Mar | 01-Apr | 01-Apr
CDUVDU23160 | Completed | Deblinding | 14/04/2023 04:37:36 | 14/04/2023 04:38:02 | 12/04/2023 07:30:00 | 12/04/2023 13:30:00 | 01-EE-037 | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 6 | 6:00 | 0:00 |  | 6:00 | 12-Apr | 12-Apr | 14-Apr | 14-Apr
CDUVDU2410 | Completed | Carryout Component Dropping | 01/04/2023 04:01:49 | 01/04/2023 04:02:19 | 31/03/2023 20:30:00 | 01/04/2023 00:30:00 | 01-EE-037 | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 4 | 4:00 | 0:01 |  | 4:00 | 31-Mar | 01-Apr | 01-Apr | 01-Apr
CDUVDU2610 | Completed | Carryout Bundle Pullout | 01/04/2023 04:01:49 | 01/04/2023 04:02:19 | 01/04/2023 00:30:00 | 01/04/2023 06:30:00 | 01-EE-037 | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 0:01 |  | 5:59 | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU2710 | Completed | Pre Cleaning Inspection | 01/04/2023 06:35:57 | 01/04/2023 06:35:57 | 01/04/2023 06:30:00 | 01/04/2023 08:30:00 | 01-EE-037 | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  |  | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU2810 | Completed | Bundle Shifting to Bay | 01/04/2023 09:51:08 | 01/04/2023 09:51:20 | 01/04/2023 08:30:00 | 01/04/2023 11:30:00 | 01-EE-037 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU16440 | Completed | Hydrojetting of Tube Bundle | 03/04/2023 10:29:14 | 03/04/2023 10:29:14 | 09/04/2023 11:30:00 | 09/04/2023 17:30:00 | 01-EE-038 | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 6 | 6:00 | 0:00 |  |  | 09-Apr | 09-Apr | 03-Apr | 03-Apr
CDUVDU16880 | Completed | Air Drying | 04/04/2023 08:01:02 | 04/04/2023 08:01:02 | 09/04/2023 17:30:00 | 09/04/2023 20:30:00 | 01-EE-038 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  |  | 09-Apr | 09-Apr | 04-Apr | 04-Apr
CDUVDU17250 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 04/04/2023 08:01:02 | 04/04/2023 08:01:02 | 09/04/2023 20:30:00 | 10/04/2023 02:30:00 | 01-EE-038 | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  |  | 09-Apr | 10-Apr | 04-Apr | 04-Apr
CDUVDU17840 | Completed | Shifting of bundle from bay | 04/04/2023 08:01:02 | 04/04/2023 08:01:02 | 10/04/2023 02:30:00 | 10/04/2023 05:30:00 | 01-EE-038 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  |  | 10-Apr | 10-Apr | 04-Apr | 04-Apr
CDUVDU18240 | Completed | Carryout Bundle Insertion | 04/04/2023 08:01:02 | 04/04/2023 08:01:02 | 10/04/2023 05:30:00 | 10/04/2023 11:30:00 | 01-EE-038 | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 6 | 6:00 | 0:00 |  |  | 10-Apr | 10-Apr | 04-Apr | 04-Apr
CDUVDU18720 | Completed | Channelhead Boxup | 04/04/2023 16:37:31 | 07/04/2023 07:01:12 | 10/04/2023 11:30:00 | 10/04/2023 17:30:00 | 01-EE-038 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 62:24 | 56:24 |  | 10-Apr | 10-Apr | 04-Apr | 07-Apr
CDUVDU19300 | Completed | Test Ring Boxup | 04/04/2023 16:38:56 | 04/04/2023 16:40:10 | 10/04/2023 17:30:00 | 11/04/2023 01:30:00 | 01-EE-038 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:01 |  | 7:59 | 10-Apr | 11-Apr | 04-Apr | 04-Apr
CDUVDU20130 | Completed | Carryout Shell Test | 08/04/2023 15:51:55 | 09/04/2023 07:12:39 | 11/04/2023 01:30:00 | 11/04/2023 09:30:00 | 01-EE-038 | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 8 | 8:00 | 15:21 | 7:21 |  | 11-Apr | 11-Apr | 08-Apr | 09-Apr
CDUVDU20890 | Completed | Test Ring Drop Down | 09/04/2023 10:18:26 | 09/04/2023 10:18:32 | 11/04/2023 09:30:00 | 11/04/2023 13:30:00 | 01-EE-038 | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 11-Apr | 11-Apr | 09-Apr | 09-Apr
CDUVDU21290 | Completed | Floating Head Box-up | 11/04/2023 06:41:43 | 11/04/2023 06:42:00 | 11/04/2023 13:30:00 | 11/04/2023 17:30:00 | 01-EE-038 | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 11-Apr | 11-Apr | 11-Apr | 11-Apr
CDUVDU21910 | Completed | Tube Test | 11/04/2023 06:41:43 | 11/04/2023 06:42:00 | 11/04/2023 17:30:00 | 12/04/2023 01:30:00 | 01-EE-038 | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 8 | 8:00 | 0:00 |  | 8:00 | 11-Apr | 12-Apr | 11-Apr | 11-Apr
CDUVDU22480 | Completed | Back Dome Boxup | 11/04/2023 06:41:43 | 11/04/2023 06:42:00 | 12/04/2023 01:30:00 | 12/04/2023 05:30:00 | 01-EE-038 | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  | 4:00 | 12-Apr | 12-Apr | 11-Apr | 11-Apr
CDUVDU2260 | Completed | Blinding As Per Blind List | 01/04/2023 03:58:35 | 01/04/2023 03:58:53 | 31/03/2023 14:30:00 | 31/03/2023 20:30:00 | 01-EE-038 | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 6 | 6:00 | 0:00 |  | 6:00 | 31-Mar | 31-Mar | 01-Apr | 01-Apr
CDUVDU23010 | Completed | Final Test | 11/04/2023 06:41:43 | 11/04/2023 06:42:00 | 12/04/2023 05:30:00 | 12/04/2023 13:30:00 | 01-EE-038 | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 8 | 8:00 | 0:00 |  | 8:00 | 12-Apr | 12-Apr | 11-Apr | 11-Apr
CDUVDU23650 | Completed | Deblinding | 14/04/2023 04:54:53 | 14/04/2023 04:55:01 | 12/04/2023 13:30:00 | 12/04/2023 19:30:00 | 01-EE-038 | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 6 | 6:00 | 0:00 |  | 6:00 | 12-Apr | 12-Apr | 14-Apr | 14-Apr
CDUVDU2420 | Completed | Carryout Component Dropping | 01/04/2023 03:58:35 | 01/04/2023 03:58:53 | 31/03/2023 20:30:00 | 01/04/2023 00:30:00 | 01-EE-038 | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 4 | 4:00 | 0:00 |  | 4:00 | 31-Mar | 01-Apr | 01-Apr | 01-Apr
CDUVDU2620 | Completed | Carryout Bundle Pullout | 01/04/2023 03:58:35 | 01/04/2023 03:58:53 | 01/04/2023 00:30:00 | 01/04/2023 06:30:00 | 01-EE-038 | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 0:00 |  | 6:00 | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU2720 | Completed | Pre Cleaning Inspection | 01/04/2023 09:55:08 | 01/04/2023 09:55:13 | 01/04/2023 06:30:00 | 01/04/2023 08:30:00 | 01-EE-038 | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  | 2:00 | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU2820 | Completed | Bundle Shifting to Bay | 01/04/2023 09:55:39 | 01/04/2023 17:30:58 | 01/04/2023 08:30:00 | 01/04/2023 11:30:00 | 01-EE-038 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 7:35 | 4:35 |  | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU16890 | Completed | Hydrojetting of Tube Bundle | 02/04/2023 06:13:58 | 03/04/2023 10:29:45 | 09/04/2023 17:30:00 | 10/04/2023 00:30:00 | 01-EE-039 | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 7 | 7:00 | 28:16 | 21:16 |  | 09-Apr | 10-Apr | 02-Apr | 03-Apr
CDUVDU17630 | Completed | Air Drying | 04/04/2023 08:01:28 | 04/04/2023 08:01:28 | 10/04/2023 00:30:00 | 10/04/2023 03:30:00 | 01-EE-039 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  |  | 10-Apr | 10-Apr | 04-Apr | 04-Apr
CDUVDU17990 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 04/04/2023 08:01:28 | 04/04/2023 08:01:28 | 10/04/2023 03:30:00 | 10/04/2023 09:30:00 | 01-EE-039 | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  |  | 10-Apr | 10-Apr | 04-Apr | 04-Apr
CDUVDU18530 | Completed | Shifting of bundle from bay | 04/04/2023 08:01:28 | 04/04/2023 08:01:28 | 10/04/2023 09:30:00 | 10/04/2023 12:30:00 | 01-EE-039 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  |  | 10-Apr | 10-Apr | 04-Apr | 04-Apr
CDUVDU18770 | Completed | Carryout Bundle Insertion | 04/04/2023 08:01:28 | 04/04/2023 08:01:28 | 10/04/2023 12:30:00 | 10/04/2023 18:30:00 | 01-EE-039 | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 6 | 6:00 | 0:00 |  |  | 10-Apr | 10-Apr | 04-Apr | 04-Apr
CDUVDU19410 | Completed | Channelhead Boxup | 06/04/2023 07:13:08 | 08/04/2023 07:46:17 | 10/04/2023 18:30:00 | 11/04/2023 00:30:00 | 01-EE-039 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 48:33 | 42:33 |  | 10-Apr | 11-Apr | 06-Apr | 08-Apr
CDUVDU20080 | Completed | Test Ring Boxup | 08/04/2023 09:37:00 | 09/04/2023 07:13:42 | 11/04/2023 00:30:00 | 11/04/2023 08:30:00 | 01-EE-039 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 21:37 | 13:37 |  | 11-Apr | 11-Apr | 08-Apr | 09-Apr
CDUVDU20810 | Completed | Carryout Shell Test | 09/04/2023 16:56:22 | 10/04/2023 19:36:00 | 11/04/2023 08:30:00 | 11/04/2023 16:30:00 | 01-EE-039 | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 8 | 8:00 | 26:40 | 18:40 |  | 11-Apr | 11-Apr | 09-Apr | 10-Apr
CDUVDU21680 | Completed | Test Ring Drop Down | 10/04/2023 10:06:56 | 10/04/2023 10:07:02 | 11/04/2023 16:30:00 | 11/04/2023 20:30:00 | 01-EE-039 | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 11-Apr | 11-Apr | 10-Apr | 10-Apr
CDUVDU22100 | Completed | Floating Head Box-up | 10/04/2023 10:07:12 | 10/04/2023 10:07:18 | 11/04/2023 20:30:00 | 12/04/2023 00:30:00 | 01-EE-039 | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 11-Apr | 12-Apr | 10-Apr | 10-Apr
CDUVDU22410 | Completed | Tube Test | 10/04/2023 10:07:37 | 10/04/2023 19:36:07 | 12/04/2023 00:30:00 | 12/04/2023 08:30:00 | 01-EE-039 | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 8 | 8:00 | 9:29 | 1:29 |  | 12-Apr | 12-Apr | 10-Apr | 10-Apr
CDUVDU2270 | Completed | Blinding As Per Blind List | 01/04/2023 03:55:36 | 01/04/2023 03:55:56 | 31/03/2023 14:30:00 | 31/03/2023 20:30:00 | 01-EE-039 | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 6 | 6:00 | 0:00 |  | 6:00 | 31-Mar | 31-Mar | 01-Apr | 01-Apr
CDUVDU23230 | Completed | Back Dome Boxup | 11/04/2023 06:42:32 | 11/04/2023 06:42:44 | 12/04/2023 08:30:00 | 12/04/2023 12:30:00 | 01-EE-039 | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  | 4:00 | 12-Apr | 12-Apr | 11-Apr | 11-Apr
CDUVDU23610 | Completed | Final Test | 11/04/2023 06:42:32 | 11/04/2023 06:42:44 | 12/04/2023 12:30:00 | 12/04/2023 20:30:00 | 01-EE-039 | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 8 | 8:00 | 0:00 |  | 8:00 | 12-Apr | 12-Apr | 11-Apr | 11-Apr
CDUVDU24220 | Completed | Deblinding | 14/04/2023 20:34:00 | 15/04/2023 05:34:37 | 12/04/2023 20:30:00 | 13/04/2023 02:30:00 | 01-EE-039 | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 6 | 6:00 | 9:01 | 3:01 |  | 12-Apr | 13-Apr | 14-Apr | 15-Apr
CDUVDU2430 | Completed | Carryout Component Dropping | 01/04/2023 03:55:36 | 01/04/2023 03:55:56 | 31/03/2023 20:30:00 | 01/04/2023 00:30:00 | 01-EE-039 | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 4 | 4:00 | 0:00 |  | 4:00 | 31-Mar | 01-Apr | 01-Apr | 01-Apr
CDUVDU2630 | Completed | Carryout Bundle Pullout | 01/04/2023 03:55:36 | 01/04/2023 03:55:56 | 01/04/2023 00:30:00 | 01/04/2023 06:30:00 | 01-EE-039 | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 0:00 |  | 6:00 | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU2730 | Completed | Pre Cleaning Inspection | 01/04/2023 06:37:06 | 01/04/2023 06:37:06 | 01/04/2023 06:30:00 | 01/04/2023 08:30:00 | 01-EE-039 | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  |  | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU2830 | Completed | Bundle Shifting to Bay | 01/04/2023 09:55:56 | 01/04/2023 17:27:57 | 01/04/2023 08:30:00 | 01/04/2023 11:30:00 | 01-EE-039 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 7:32 | 4:32 |  | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU10480 | Completed | Shifting of bundle from bay | 11/04/2023 06:39:24 | 11/04/2023 06:39:33 | 05/04/2023 16:30:00 | 05/04/2023 19:30:00 | 01-EE-004 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 05-Apr | 05-Apr | 11-Apr | 11-Apr
CDUVDU10560 | Completed | Carryout Bundle Insertion | 11/04/2023 06:39:24 | 11/04/2023 06:39:33 | 05/04/2023 19:30:00 | 06/04/2023 03:30:00 | 01-EE-004 | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 0:00 |  | 8:00 | 05-Apr | 06-Apr | 11-Apr | 11-Apr
CDUVDU10910 | Completed | Channelhead Boxup | 11/04/2023 07:33:59 | 11/04/2023 07:33:59 | 06/04/2023 03:30:00 | 06/04/2023 09:30:00 | 01-EE-004 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 06-Apr | 06-Apr | 11-Apr | 11-Apr
CDUVDU11230 | Completed | Test Ring Boxup | 11/04/2023 07:34:39 | 12/04/2023 00:16:20 | 06/04/2023 09:30:00 | 06/04/2023 17:30:00 | 01-EE-004 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 16:42 | 8:42 |  | 06-Apr | 06-Apr | 11-Apr | 12-Apr
CDUVDU11780 | Completed | Carryout Shell Test | 12/04/2023 00:16:32 | 13/04/2023 19:12:43 | 06/04/2023 17:30:00 | 07/04/2023 08:30:00 | 01-EE-004 | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 42:56 | 27:56 |  | 06-Apr | 07-Apr | 12-Apr | 13-Apr
CDUVDU12810 | Completed | Test Ring Drop Down | 14/04/2023 04:18:37 | 14/04/2023 04:18:44 | 07/04/2023 08:30:00 | 07/04/2023 14:30:00 | 01-EE-004 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 07-Apr | 07-Apr | 14-Apr | 14-Apr
CDUVDU13170 | Completed | Floating Head Box-up | 14/04/2023 04:18:37 | 14/04/2023 10:56:10 | 07/04/2023 14:30:00 | 07/04/2023 20:30:00 | 01-EE-004 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 6:38 | 0:38 |  | 07-Apr | 07-Apr | 14-Apr | 14-Apr
CDUVDU13520 | Completed | Tube Test | 15/04/2023 05:06:38 | 15/04/2023 17:26:44 | 07/04/2023 20:30:00 | 08/04/2023 11:30:00 | 01-EE-004 | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 15 | 15:00 | 12:20 |  | 2:40 | 07-Apr | 08-Apr | 15-Apr | 15-Apr
CDUVDU14480 | Completed | Back Dome Boxup | 16/04/2023 01:02:34 | 16/04/2023 01:02:42 | 08/04/2023 11:30:00 | 08/04/2023 19:30:00 | 01-EE-004 | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 0:00 |  | 8:00 | 08-Apr | 08-Apr | 16-Apr | 16-Apr
CDUVDU15080 | Completed | Final Test | 15/04/2023 08:10:00 | 16/04/2023 10:14:02 | 08/04/2023 19:30:00 | 09/04/2023 10:30:00 | 01-EE-004 | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 26:04 | 11:04 |  | 08-Apr | 09-Apr | 15-Apr | 16-Apr
CDUVDU16340 | Completed | Deblinding | 16/04/2023 11:44:57 | 18/04/2023 00:18:09 | 09/04/2023 10:30:00 | 09/04/2023 18:30:00 | 01-EE-004 | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 36:33 | 28:33 |  | 09-Apr | 09-Apr | 16-Apr | 18-Apr
CDUVDU3480 | Completed | Blinding As Per Blind List | 31/03/2023 12:28:22 | 01/04/2023 03:46:42 | 01/04/2023 14:30:00 | 01/04/2023 22:30:00 | 01-EE-004 | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 15:18 | 7:18 |  | 01-Apr | 01-Apr | 31-Mar | 01-Apr
CDUVDU4120 | Completed | Carryout Component Dropping | 31/03/2023 12:41:32 | 01/04/2023 09:41:03 | 01/04/2023 22:30:00 | 02/04/2023 06:30:00 | 01-EE-004 | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 21:00 | 13:00 |  | 01-Apr | 02-Apr | 31-Mar | 01-Apr
CDUVDU4640 | Completed | Carryout Bundle Pullout | 01/04/2023 15:45:50 | 01/04/2023 15:46:56 | 02/04/2023 06:30:00 | 02/04/2023 12:30:00 | 01-EE-004 | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 0:01 |  | 5:59 | 02-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU5120 | Completed | Pre Cleaning Inspection | 01/04/2023 16:38:57 | 01/04/2023 16:39:03 | 02/04/2023 12:30:00 | 02/04/2023 14:30:00 | 01-EE-004 | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  | 2:00 | 02-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU5700 | Completed | Bundle Shifting to Bay | 02/04/2023 06:00:31 | 02/04/2023 06:00:38 | 02/04/2023 14:30:00 | 02/04/2023 17:30:00 | 01-EE-004 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU8290 | Completed | Hydrojetting of Tube Bundle | 02/04/2023 06:00:31 | 10/04/2023 10:01:44 | 04/04/2023 00:30:00 | 05/04/2023 02:30:00 | 01-EE-004 | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 26 | 26:00 | 196:01 | 170:01 |  | 04-Apr | 05-Apr | 02-Apr | 10-Apr
CDUVDU9580 | Completed | Air Drying | 11/04/2023 06:39:24 | 11/04/2023 06:39:33 | 05/04/2023 02:30:00 | 05/04/2023 10:30:00 | 01-EE-004 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  | 8:00 | 05-Apr | 05-Apr | 11-Apr | 11-Apr
CDUVDU9980 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 11/04/2023 06:39:24 | 11/04/2023 06:39:33 | 05/04/2023 10:30:00 | 05/04/2023 16:30:00 | 01-EE-004 | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  | 6:00 | 05-Apr | 05-Apr | 11-Apr | 11-Apr
CDUVDU10140 | Completed | Hydrojetting of Tube Bundle | 07/04/2023 22:07:28 | 07/04/2023 22:07:28 | 05/04/2023 13:30:00 | 06/04/2023 02:30:00 | 01-EE-046 | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 13 | 13:00 | 0:00 |  |  | 05-Apr | 06-Apr | 07-Apr | 07-Apr
CDUVDU10870 | Completed | Air Drying | 07/04/2023 22:07:28 | 07/04/2023 22:07:28 | 06/04/2023 02:30:00 | 06/04/2023 10:30:00 | 01-EE-046 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  |  | 06-Apr | 06-Apr | 07-Apr | 07-Apr
CDUVDU11310 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 07/04/2023 22:07:28 | 07/04/2023 22:07:28 | 06/04/2023 10:30:00 | 06/04/2023 16:30:00 | 01-EE-046 | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  |  | 06-Apr | 06-Apr | 07-Apr | 07-Apr
CDUVDU11740 | Completed | Shifting of bundle from bay | 08/04/2023 07:15:51 | 08/04/2023 07:15:59 | 06/04/2023 16:30:00 | 06/04/2023 19:30:00 | 01-EE-046 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 06-Apr | 06-Apr | 08-Apr | 08-Apr
CDUVDU11930 | Completed | Carryout Bundle Insertion | 08/04/2023 07:44:01 | 08/04/2023 07:44:01 | 06/04/2023 19:30:00 | 07/04/2023 03:30:00 | 01-EE-046 | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 0:00 |  |  | 06-Apr | 07-Apr | 08-Apr | 08-Apr
CDUVDU12530 | Completed | Channelhead Boxup | 09/04/2023 10:19:52 | 09/04/2023 10:19:57 | 07/04/2023 03:30:00 | 07/04/2023 09:30:00 | 01-EE-046 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 07-Apr | 07-Apr | 09-Apr | 09-Apr
CDUVDU12870 | Completed | Test Ring Boxup | 09/04/2023 10:20:53 | 09/04/2023 10:20:59 | 07/04/2023 09:30:00 | 07/04/2023 17:30:00 | 01-EE-046 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  | 8:00 | 07-Apr | 07-Apr | 09-Apr | 09-Apr
CDUVDU13390 | Completed | Carryout Shell Test | 10/04/2023 15:42:05 | 11/04/2023 03:19:55 | 07/04/2023 17:30:00 | 08/04/2023 08:30:00 | 01-EE-046 | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 11:38 |  | 3:22 | 07-Apr | 08-Apr | 10-Apr | 11-Apr
CDUVDU14280 | Completed | Test Ring Drop Down | 11/04/2023 07:38:50 | 11/04/2023 07:38:50 | 08/04/2023 08:30:00 | 08/04/2023 14:30:00 | 01-EE-046 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 08-Apr | 08-Apr | 11-Apr | 11-Apr
CDUVDU14810 | Completed | Floating Head Box-up | 11/04/2023 07:38:50 | 11/04/2023 07:38:50 | 08/04/2023 14:30:00 | 08/04/2023 20:30:00 | 01-EE-046 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 08-Apr | 08-Apr | 11-Apr | 11-Apr
CDUVDU15170 | Completed | Tube Test | 11/04/2023 07:39:12 | 12/04/2023 07:45:13 | 08/04/2023 20:30:00 | 09/04/2023 11:30:00 | 01-EE-046 | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 15 | 15:00 | 24:06 | 9:06 |  | 08-Apr | 09-Apr | 11-Apr | 12-Apr
CDUVDU16450 | Completed | Back Dome Boxup | 12/04/2023 07:53:29 | 12/04/2023 07:53:39 | 09/04/2023 11:30:00 | 09/04/2023 19:30:00 | 01-EE-046 | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 0:00 |  | 8:00 | 09-Apr | 09-Apr | 12-Apr | 12-Apr
CDUVDU17160 | Completed | Final Test | 12/04/2023 18:35:34 | 12/04/2023 18:35:39 | 09/04/2023 19:30:00 | 10/04/2023 10:30:00 | 01-EE-046 | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 0:00 |  | 15:00 | 09-Apr | 10-Apr | 12-Apr | 12-Apr
CDUVDU18640 | Completed | Deblinding | 17/04/2023 17:09:50 | 17/04/2023 17:10:03 | 10/04/2023 10:30:00 | 10/04/2023 18:30:00 | 01-EE-046 | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 10-Apr | 10-Apr | 17-Apr | 17-Apr
CDUVDU5960 | Completed | Blinding As Per Blind List | 02/04/2023 06:11:00 | 02/04/2023 06:11:03 | 02/04/2023 14:30:00 | 02/04/2023 22:30:00 | 01-EE-046 | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU6510 | Completed | Carryout Component Dropping | 02/04/2023 05:41:43 | 02/04/2023 05:41:43 | 02/04/2023 22:30:00 | 03/04/2023 06:30:00 | 01-EE-046 | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  |  | 02-Apr | 03-Apr | 02-Apr | 02-Apr
CDUVDU7010 | Completed | Carryout Bundle Pullout | 02/04/2023 05:41:43 | 02/04/2023 05:41:43 | 03/04/2023 06:30:00 | 03/04/2023 12:30:00 | 01-EE-046 | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 0:00 |  |  | 03-Apr | 03-Apr | 02-Apr | 02-Apr
CDUVDU7570 | Completed | Pre Cleaning Inspection | 02/04/2023 07:49:05 | 02/04/2023 07:49:05 | 03/04/2023 12:30:00 | 03/04/2023 14:30:00 | 01-EE-046 | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  |  | 03-Apr | 03-Apr | 02-Apr | 02-Apr
CDUVDU7750 | Completed | Bundle Shifting to Bay | 07/04/2023 07:03:14 | 07/04/2023 07:03:18 | 03/04/2023 14:30:00 | 03/04/2023 17:30:00 | 01-EE-046 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 03-Apr | 03-Apr | 07-Apr | 07-Apr
CDUVDU11640 | Completed | Hydrojetting of Tube Bundle | 08/04/2023 07:18:06 | 08/04/2023 07:18:14 | 06/04/2023 15:30:00 | 06/04/2023 22:30:00 | 01-EE-048 | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 7 | 7:00 | 0:00 |  | 7:00 | 06-Apr | 06-Apr | 08-Apr | 08-Apr
CDUVDU12180 | Completed | Air Drying | 08/04/2023 07:18:06 | 08/04/2023 07:18:14 | 06/04/2023 22:30:00 | 07/04/2023 01:30:00 | 01-EE-048 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 06-Apr | 07-Apr | 08-Apr | 08-Apr
CDUVDU12320 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 08/04/2023 07:18:06 | 08/04/2023 07:18:14 | 07/04/2023 01:30:00 | 07/04/2023 07:30:00 | 01-EE-048 | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  | 6:00 | 07-Apr | 07-Apr | 08-Apr | 08-Apr
CDUVDU12780 | Completed | Shifting of bundle from bay | 08/04/2023 07:48:33 | 08/04/2023 07:48:33 | 07/04/2023 07:30:00 | 07/04/2023 10:30:00 | 01-EE-048 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  |  | 07-Apr | 07-Apr | 08-Apr | 08-Apr
CDUVDU12920 | Completed | Carryout Bundle Insertion | 08/04/2023 07:48:33 | 08/04/2023 07:48:33 | 07/04/2023 10:30:00 | 07/04/2023 16:30:00 | 01-EE-048 | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 6 | 6:00 | 0:00 |  |  | 07-Apr | 07-Apr | 08-Apr | 08-Apr
CDUVDU13290 | Completed | Channelhead Boxup | 10/04/2023 07:01:35 | 10/04/2023 07:01:44 | 07/04/2023 16:30:00 | 07/04/2023 22:30:00 | 01-EE-048 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 07-Apr | 07-Apr | 10-Apr | 10-Apr
CDUVDU13680 | Completed | Test Ring Boxup | 10/04/2023 18:12:16 | 10/04/2023 18:12:27 | 07/04/2023 22:30:00 | 08/04/2023 06:30:00 | 01-EE-048 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  | 8:00 | 07-Apr | 08-Apr | 10-Apr | 10-Apr
CDUVDU14090 | Completed | Carryout Shell Test | 10/04/2023 18:12:45 | 11/04/2023 07:29:32 | 08/04/2023 06:30:00 | 08/04/2023 14:30:00 | 01-EE-048 | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 8 | 8:00 | 13:17 | 5:17 |  | 08-Apr | 08-Apr | 10-Apr | 11-Apr
CDUVDU14800 | Completed | Test Ring Drop Down | 12/04/2023 07:42:36 | 12/04/2023 07:42:47 | 08/04/2023 14:30:00 | 08/04/2023 18:30:00 | 01-EE-048 | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 08-Apr | 08-Apr | 12-Apr | 12-Apr
CDUVDU15050 | Completed | Floating Head Box-up | 12/04/2023 07:42:56 | 12/04/2023 07:43:06 | 08/04/2023 18:30:00 | 08/04/2023 22:30:00 | 01-EE-048 | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 08-Apr | 08-Apr | 12-Apr | 12-Apr
CDUVDU15320 | Completed | Tube Test | 12/04/2023 07:43:19 | 12/04/2023 07:43:31 | 08/04/2023 22:30:00 | 09/04/2023 06:30:00 | 01-EE-048 | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 8 | 8:00 | 0:00 |  | 8:00 | 08-Apr | 09-Apr | 12-Apr | 12-Apr
CDUVDU15970 | Completed | Back Dome Boxup | 12/04/2023 07:54:21 | 12/04/2023 07:54:33 | 09/04/2023 06:30:00 | 09/04/2023 10:30:00 | 01-EE-048 | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  | 4:00 | 09-Apr | 09-Apr | 12-Apr | 12-Apr
CDUVDU16380 | Completed | Final Test | 13/04/2023 03:32:36 | 13/04/2023 12:23:13 | 09/04/2023 10:30:00 | 09/04/2023 18:30:00 | 01-EE-048 | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 8 | 8:00 | 8:51 | 0:51 |  | 09-Apr | 09-Apr | 13-Apr | 13-Apr
CDUVDU16930 | Completed | Deblinding | 18/04/2023 07:15:49 | 18/04/2023 07:15:57 | 09/04/2023 18:30:00 | 10/04/2023 00:30:00 | 01-EE-048 | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 6 | 6:00 | 0:00 |  | 6:00 | 09-Apr | 10-Apr | 18-Apr | 18-Apr
CDUVDU5940 | Completed | Blinding As Per Blind List | 02/04/2023 05:40:56 | 02/04/2023 05:40:56 | 02/04/2023 14:30:00 | 02/04/2023 20:30:00 | 01-EE-048 | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 6 | 6:00 | 0:00 |  |  | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU6330 | Completed | Carryout Component Dropping | 01/04/2023 19:12:36 | 01/04/2023 19:12:46 | 02/04/2023 20:30:00 | 03/04/2023 00:30:00 | 01-EE-048 | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 4 | 4:00 | 0:00 |  | 4:00 | 02-Apr | 03-Apr | 01-Apr | 01-Apr
CDUVDU6730 | Completed | Carryout Bundle Pullout | 02/04/2023 05:40:56 | 02/04/2023 05:40:56 | 03/04/2023 00:30:00 | 03/04/2023 06:30:00 | 01-EE-048 | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 0:00 |  |  | 03-Apr | 03-Apr | 02-Apr | 02-Apr
CDUVDU6990 | Completed | Pre Cleaning Inspection | 02/04/2023 07:50:43 | 02/04/2023 07:50:43 | 03/04/2023 06:30:00 | 03/04/2023 08:30:00 | 01-EE-048 | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  |  | 03-Apr | 03-Apr | 02-Apr | 02-Apr
CDUVDU7160 | Completed | Bundle Shifting to Bay | 03/04/2023 06:01:25 | 03/04/2023 06:01:25 | 03/04/2023 08:30:00 | 03/04/2023 11:30:00 | 01-EE-048 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  |  | 03-Apr | 03-Apr | 03-Apr | 03-Apr
CDUVDU10130 | Completed | Air Drying | 04/04/2023 22:13:26 | 04/04/2023 22:13:26 | 05/04/2023 13:30:00 | 05/04/2023 16:30:00 | 01-EE-049 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  |  | 05-Apr | 05-Apr | 04-Apr | 04-Apr
CDUVDU10490 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 04/04/2023 22:13:26 | 04/04/2023 22:13:26 | 05/04/2023 16:30:00 | 05/04/2023 22:30:00 | 01-EE-049 | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  |  | 05-Apr | 05-Apr | 04-Apr | 04-Apr
CDUVDU10620 | Completed | Shifting of bundle from bay | 05/04/2023 07:35:26 | 05/04/2023 07:35:26 | 05/04/2023 22:30:00 | 06/04/2023 01:30:00 | 01-EE-049 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  |  | 05-Apr | 06-Apr | 05-Apr | 05-Apr
CDUVDU10730 | Completed | Carryout Bundle Insertion | 05/04/2023 07:35:26 | 05/04/2023 07:35:26 | 06/04/2023 01:30:00 | 06/04/2023 07:30:00 | 01-EE-049 | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 6 | 6:00 | 0:00 |  |  | 06-Apr | 06-Apr | 05-Apr | 05-Apr
CDUVDU11160 | Completed | Channelhead Boxup | 05/04/2023 10:00:54 | 05/04/2023 12:14:13 | 06/04/2023 07:30:00 | 06/04/2023 13:30:00 | 01-EE-049 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 2:13 |  | 3:47 | 06-Apr | 06-Apr | 05-Apr | 05-Apr
CDUVDU11430 | Completed | Test Ring Boxup | 05/04/2023 10:03:46 | 05/04/2023 19:36:06 | 06/04/2023 13:30:00 | 06/04/2023 21:30:00 | 01-EE-049 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 9:32 | 1:32 |  | 06-Apr | 06-Apr | 05-Apr | 05-Apr
CDUVDU12050 | Completed | Carryout Shell Test | 06/04/2023 07:18:51 | 06/04/2023 10:06:18 | 06/04/2023 21:30:00 | 07/04/2023 03:30:00 | 01-EE-049 | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 6 | 6:00 | 2:47 |  | 3:13 | 06-Apr | 07-Apr | 06-Apr | 06-Apr
CDUVDU12520 | Completed | Test Ring Drop Down | 07/04/2023 07:45:51 | 07/04/2023 07:45:51 | 07/04/2023 03:30:00 | 07/04/2023 07:30:00 | 01-EE-049 | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  |  | 07-Apr | 07-Apr | 07-Apr | 07-Apr
CDUVDU12790 | Completed | Floating Head Box-up | 07/04/2023 07:45:51 | 07/04/2023 07:45:51 | 07/04/2023 07:30:00 | 07/04/2023 11:30:00 | 01-EE-049 | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  |  | 07-Apr | 07-Apr | 07-Apr | 07-Apr
CDUVDU12950 | Completed | Tube Test | 07/04/2023 07:45:51 | 07/04/2023 07:45:51 | 07/04/2023 11:30:00 | 07/04/2023 20:30:00 | 01-EE-049 | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 9 | 9:00 | 0:00 |  |  | 07-Apr | 07-Apr | 07-Apr | 07-Apr
CDUVDU13550 | Completed | Back Dome Boxup | 07/04/2023 11:50:12 | 07/04/2023 11:50:17 | 07/04/2023 20:30:00 | 08/04/2023 00:30:00 | 01-EE-049 | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  | 4:00 | 07-Apr | 08-Apr | 07-Apr | 07-Apr
CDUVDU13720 | Completed | Final Test | 07/04/2023 11:50:52 | 07/04/2023 22:27:35 | 08/04/2023 00:30:00 | 08/04/2023 09:30:00 | 01-EE-049 | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 9 | 9:00 | 10:37 | 1:37 |  | 08-Apr | 08-Apr | 07-Apr | 07-Apr
CDUVDU14350 | Completed | Deblinding | 17/04/2023 09:45:16 | 17/04/2023 17:07:43 | 08/04/2023 09:30:00 | 08/04/2023 15:30:00 | 01-EE-049 | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 6 | 6:00 | 7:22 | 1:22 |  | 08-Apr | 08-Apr | 17-Apr | 17-Apr
CDUVDU5950 | Completed | Blinding As Per Blind List | 31/03/2023 17:54:00 | 31/03/2023 21:54:00 | 02/04/2023 14:30:00 | 02/04/2023 20:30:00 | 01-EE-049 | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 6 | 6:00 | 4:00 |  | 2:00 | 02-Apr | 02-Apr | 31-Mar | 31-Mar
CDUVDU6340 | Completed | Carryout Component Dropping | 31/03/2023 21:54:00 | 01/04/2023 00:54:00 | 02/04/2023 20:30:00 | 03/04/2023 00:30:00 | 01-EE-049 | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 4 | 4:00 | 3:00 |  | 1:00 | 02-Apr | 03-Apr | 31-Mar | 01-Apr
CDUVDU6740 | Completed | Carryout Bundle Pullout | 01/04/2023 00:54:00 | 01/04/2023 09:54:59 | 03/04/2023 00:30:00 | 03/04/2023 06:30:00 | 01-EE-049 | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 9:01 | 3:01 |  | 03-Apr | 03-Apr | 01-Apr | 01-Apr
CDUVDU7000 | Completed | Pre Cleaning Inspection | 01/04/2023 10:03:41 | 01/04/2023 16:41:26 | 03/04/2023 06:30:00 | 03/04/2023 08:30:00 | 01-EE-049 | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 6:38 | 4:38 |  | 03-Apr | 03-Apr | 01-Apr | 01-Apr
CDUVDU7170 | Completed | Bundle Shifting to Bay | 03/04/2023 06:01:52 | 03/04/2023 06:02:02 | 03/04/2023 08:30:00 | 03/04/2023 11:30:00 | 01-EE-049 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 03-Apr | 03-Apr | 03-Apr | 03-Apr
CDUVDU9840 | Completed | Hydrojetting of Tube Bundle | 04/04/2023 22:13:26 | 04/04/2023 22:13:26 | 05/04/2023 07:30:00 | 05/04/2023 13:30:00 | 01-EE-049 | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 6 | 6:00 | 0:00 |  |  | 05-Apr | 05-Apr | 04-Apr | 04-Apr
CDUVDU19310 | Completed | Hydrojetting of Tube Bundle | 05/04/2023 18:56:13 | 05/04/2023 18:56:17 | 10/04/2023 17:30:00 | 11/04/2023 07:30:00 | 01-EE-050A | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 14 | 14:00 | 0:00 |  | 14:00 | 10-Apr | 11-Apr | 05-Apr | 05-Apr
CDUVDU20730 | Completed | Air Drying | 05/04/2023 18:56:47 | 05/04/2023 18:56:53 | 11/04/2023 07:30:00 | 11/04/2023 15:30:00 | 01-EE-050A | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  | 8:00 | 11-Apr | 11-Apr | 05-Apr | 05-Apr
CDUVDU21630 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 05/04/2023 18:57:18 | 05/04/2023 22:01:08 | 11/04/2023 15:30:00 | 11/04/2023 21:30:00 | 01-EE-050A | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 3:04 |  | 2:56 | 11-Apr | 11-Apr | 05-Apr | 05-Apr
CDUVDU22150 | Completed | Shifting of bundle from bay | 07/04/2023 07:46:13 | 07/04/2023 07:46:13 | 11/04/2023 21:30:00 | 12/04/2023 00:30:00 | 01-EE-050A | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  |  | 11-Apr | 12-Apr | 07-Apr | 07-Apr
CDUVDU22420 | Completed | Carryout Bundle Insertion | 07/04/2023 07:46:13 | 07/04/2023 07:46:13 | 12/04/2023 00:30:00 | 12/04/2023 08:30:00 | 01-EE-050A | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 0:00 |  |  | 12-Apr | 12-Apr | 07-Apr | 07-Apr
CDUVDU23240 | Completed | Channelhead Boxup | 07/04/2023 11:46:49 | 09/04/2023 17:00:55 | 12/04/2023 08:30:00 | 12/04/2023 14:30:00 | 01-EE-050A | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 53:14 | 47:14 |  | 12-Apr | 12-Apr | 07-Apr | 09-Apr
CDUVDU23810 | Completed | Test Ring Boxup | 09/04/2023 17:01:31 | 10/04/2023 15:41:12 | 12/04/2023 14:30:00 | 12/04/2023 22:30:00 | 01-EE-050A | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 22:40 | 14:40 |  | 12-Apr | 12-Apr | 09-Apr | 10-Apr
CDUVDU24420 | Completed | Carryout Shell Test | 11/04/2023 10:46:50 | 12/04/2023 07:41:11 | 12/04/2023 22:30:00 | 13/04/2023 13:30:00 | 01-EE-050A | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 20:54 | 5:54 |  | 12-Apr | 13-Apr | 11-Apr | 12-Apr
CDUVDU25350 | Completed | Test Ring Drop Down | 12/04/2023 15:47:41 | 12/04/2023 15:47:47 | 13/04/2023 13:30:00 | 13/04/2023 19:30:00 | 01-EE-050A | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 13-Apr | 13-Apr | 12-Apr | 12-Apr
CDUVDU25740 | Completed | Floating Head Box-up | 13/04/2023 03:33:24 | 13/04/2023 03:34:10 | 13/04/2023 19:30:00 | 14/04/2023 01:30:00 | 01-EE-050A | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:01 |  | 5:59 | 13-Apr | 14-Apr | 13-Apr | 13-Apr
CDUVDU25990 | Completed | Tube Test | 13/04/2023 10:23:28 | 13/04/2023 19:10:32 | 14/04/2023 01:30:00 | 14/04/2023 16:30:00 | 01-EE-050A | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 15 | 15:00 | 8:47 |  | 6:13 | 14-Apr | 14-Apr | 13-Apr | 13-Apr
CDUVDU26770 | Completed | Back Dome Boxup | 14/04/2023 07:55:35 | 15/04/2023 03:25:58 | 14/04/2023 16:30:00 | 15/04/2023 00:30:00 | 01-EE-050A | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 19:30 | 11:30 |  | 14-Apr | 15-Apr | 14-Apr | 15-Apr
CDUVDU27040 | Completed | Final Test | 15/04/2023 03:26:15 | 16/04/2023 16:53:21 | 15/04/2023 00:30:00 | 15/04/2023 15:30:00 | 01-EE-050A | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 37:27 | 22:27 |  | 15-Apr | 15-Apr | 15-Apr | 16-Apr
CDUVDU27610 | Completed | Deblinding | 17/04/2023 17:04:22 | 18/04/2023 00:39:16 | 15/04/2023 15:30:00 | 15/04/2023 23:30:00 | 01-EE-050A | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 7:35 |  | 0:25 | 15-Apr | 15-Apr | 17-Apr | 18-Apr
CDUVDU5970 | Completed | Blinding As Per Blind List | 31/03/2023 17:04:00 | 01/04/2023 01:04:00 | 02/04/2023 14:30:00 | 02/04/2023 22:30:00 | 01-EE-050A | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 8:00 |  |  | 02-Apr | 02-Apr | 31-Mar | 01-Apr
CDUVDU6520 | Completed | Carryout Component Dropping | 01/04/2023 01:04:00 | 02/04/2023 05:38:27 | 02/04/2023 22:30:00 | 03/04/2023 06:30:00 | 01-EE-050A | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 28:34 | 20:34 |  | 02-Apr | 03-Apr | 01-Apr | 02-Apr
CDUVDU7020 | Completed | Carryout Bundle Pullout | 02/04/2023 17:15:28 | 04/04/2023 07:25:45 | 03/04/2023 06:30:00 | 03/04/2023 12:30:00 | 01-EE-050A | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 38:10 | 32:10 |  | 03-Apr | 03-Apr | 02-Apr | 04-Apr
CDUVDU7580 | Completed | Pre Cleaning Inspection | 03/04/2023 06:03:26 | 05/04/2023 15:53:18 | 03/04/2023 12:30:00 | 03/04/2023 14:30:00 | 01-EE-050A | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 57:50 | 55:50 |  | 03-Apr | 03-Apr | 03-Apr | 05-Apr
CDUVDU7760 | Completed | Bundle Shifting to Bay | 05/04/2023 18:55:54 | 05/04/2023 18:55:59 | 03/04/2023 14:30:00 | 03/04/2023 17:30:00 | 01-EE-050A | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 03-Apr | 03-Apr | 05-Apr | 05-Apr
CDUVDU20740 | Completed | Hydrojetting of Tube Bundle | 05/04/2023 20:20:00 | 06/04/2023 07:21:09 | 11/04/2023 07:30:00 | 11/04/2023 20:30:00 | 01-EE-050B | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 13 | 13:00 | 11:01 |  | 1:59 | 11-Apr | 11-Apr | 05-Apr | 06-Apr
CDUVDU22110 | Completed | Air Drying | 05/04/2023 22:21:00 | 06/04/2023 07:21:27 | 11/04/2023 20:30:00 | 12/04/2023 04:30:00 | 01-EE-050B | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 9:00 | 1:00 |  | 11-Apr | 12-Apr | 05-Apr | 06-Apr
CDUVDU22890 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 05/04/2023 22:03:21 | 05/04/2023 22:03:26 | 12/04/2023 04:30:00 | 12/04/2023 10:30:00 | 01-EE-050B | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  | 6:00 | 12-Apr | 12-Apr | 05-Apr | 05-Apr
CDUVDU23410 | Completed | Shifting of bundle from bay | 07/04/2023 07:04:19 | 07/04/2023 07:46:32 | 12/04/2023 10:30:00 | 12/04/2023 13:30:00 | 01-EE-050B | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:42 |  | 2:18 | 12-Apr | 12-Apr | 07-Apr | 07-Apr
CDUVDU23660 | Completed | Carryout Bundle Insertion | 07/04/2023 07:46:32 | 07/04/2023 07:46:32 | 12/04/2023 13:30:00 | 12/04/2023 21:30:00 | 01-EE-050B | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 0:00 |  |  | 12-Apr | 12-Apr | 07-Apr | 07-Apr
CDUVDU24310 | Completed | Channelhead Boxup | 07/04/2023 11:48:28 | 09/04/2023 15:07:39 | 12/04/2023 21:30:00 | 13/04/2023 03:30:00 | 01-EE-050B | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 51:19 | 45:19 |  | 12-Apr | 13-Apr | 07-Apr | 09-Apr
CDUVDU24780 | Completed | Test Ring Boxup | 09/04/2023 17:01:09 | 10/04/2023 10:13:01 | 13/04/2023 03:30:00 | 13/04/2023 11:30:00 | 01-EE-050B | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 17:12 | 9:12 |  | 13-Apr | 13-Apr | 09-Apr | 10-Apr
CDUVDU25310 | Completed | Carryout Shell Test | 11/04/2023 10:47:06 | 12/04/2023 07:41:31 | 13/04/2023 11:30:00 | 14/04/2023 02:30:00 | 01-EE-050B | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 20:54 | 5:54 |  | 13-Apr | 14-Apr | 11-Apr | 12-Apr
CDUVDU26110 | Completed | Test Ring Drop Down | 12/04/2023 15:47:57 | 12/04/2023 15:48:09 | 14/04/2023 02:30:00 | 14/04/2023 08:30:00 | 01-EE-050B | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 14-Apr | 14-Apr | 12-Apr | 12-Apr
CDUVDU26350 | Completed | Floating Head Box-up | 13/04/2023 03:34:22 | 13/04/2023 03:34:30 | 14/04/2023 08:30:00 | 14/04/2023 14:30:00 | 01-EE-050B | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 14-Apr | 14-Apr | 13-Apr | 13-Apr
CDUVDU26650 | Completed | Tube Test | 13/04/2023 10:24:19 | 13/04/2023 19:10:41 | 14/04/2023 14:30:00 | 15/04/2023 05:30:00 | 01-EE-050B | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 15 | 15:00 | 8:46 |  | 6:14 | 14-Apr | 15-Apr | 13-Apr | 13-Apr
CDUVDU27230 | Completed | Back Dome Boxup | 14/04/2023 07:56:57 | 15/04/2023 03:27:12 | 15/04/2023 05:30:00 | 15/04/2023 13:30:00 | 01-EE-050B | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 19:30 | 11:30 |  | 15-Apr | 15-Apr | 14-Apr | 15-Apr
CDUVDU27530 | Completed | Final Test | 15/04/2023 03:27:23 | 16/04/2023 16:53:51 | 15/04/2023 13:30:00 | 16/04/2023 04:30:00 | 01-EE-050B | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 37:26 | 22:26 |  | 15-Apr | 16-Apr | 15-Apr | 16-Apr
CDUVDU28030 | Completed | Deblinding | 17/04/2023 17:05:09 | 18/04/2023 11:34:24 | 16/04/2023 04:30:00 | 16/04/2023 12:30:00 | 01-EE-050B | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 18:29 | 10:29 |  | 16-Apr | 16-Apr | 17-Apr | 18-Apr
CDUVDU5980 | Completed | Blinding As Per Blind List | 31/03/2023 17:06:00 | 01/04/2023 01:06:00 | 02/04/2023 14:30:00 | 02/04/2023 22:30:00 | 01-EE-050B | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 8:00 |  | 0:00 | 02-Apr | 02-Apr | 31-Mar | 01-Apr
CDUVDU6530 | Completed | Carryout Component Dropping | 01/04/2023 01:06:00 | 02/04/2023 05:38:42 | 02/04/2023 22:30:00 | 03/04/2023 06:30:00 | 01-EE-050B | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 28:33 | 20:33 |  | 02-Apr | 03-Apr | 01-Apr | 02-Apr
CDUVDU7030 | Completed | Carryout Bundle Pullout | 02/04/2023 17:16:31 | 02/04/2023 17:16:38 | 03/04/2023 06:30:00 | 03/04/2023 12:30:00 | 01-EE-050B | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 0:00 |  | 6:00 | 03-Apr | 03-Apr | 02-Apr | 02-Apr
CDUVDU7590 | Completed | Pre Cleaning Inspection | 03/04/2023 06:04:31 | 03/04/2023 06:04:31 | 03/04/2023 12:30:00 | 03/04/2023 14:30:00 | 01-EE-050B | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  |  | 03-Apr | 03-Apr | 03-Apr | 03-Apr
CDUVDU7770 | Completed | Bundle Shifting to Bay | 03/04/2023 06:04:31 | 03/04/2023 06:04:31 | 03/04/2023 14:30:00 | 03/04/2023 17:30:00 | 01-EE-050B | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  |  | 03-Apr | 03-Apr | 03-Apr | 03-Apr
CDUVDU12190 | Completed | Hydrojetting of Tube Bundle | 04/04/2023 08:05:07 | 04/04/2023 08:05:07 | 06/04/2023 22:30:00 | 07/04/2023 11:30:00 | 01-EE-061 | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 13 | 13:00 | 0:00 |  |  | 06-Apr | 07-Apr | 04-Apr | 04-Apr
CDUVDU12960 | Completed | Air Drying | 04/04/2023 08:05:07 | 04/04/2023 08:05:07 | 07/04/2023 11:30:00 | 07/04/2023 19:30:00 | 01-EE-061 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  |  | 07-Apr | 07-Apr | 04-Apr | 04-Apr
CDUVDU13470 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 04/04/2023 08:05:07 | 04/04/2023 08:05:07 | 07/04/2023 19:30:00 | 08/04/2023 01:30:00 | 01-EE-061 | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  |  | 07-Apr | 08-Apr | 04-Apr | 04-Apr
CDUVDU13780 | Completed | Shifting of bundle from bay | 04/04/2023 16:52:24 | 04/04/2023 16:52:29 | 08/04/2023 01:30:00 | 08/04/2023 04:30:00 | 01-EE-061 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 08-Apr | 08-Apr | 04-Apr | 04-Apr
CDUVDU13990 | Completed | Carryout Bundle Insertion | 04/04/2023 16:52:37 | 04/04/2023 16:52:43 | 08/04/2023 04:30:00 | 08/04/2023 12:30:00 | 01-EE-061 | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 0:00 |  | 8:00 | 08-Apr | 08-Apr | 04-Apr | 04-Apr
CDUVDU14550 | Completed | Channelhead Boxup | 05/04/2023 07:45:14 | 05/04/2023 07:45:14 | 08/04/2023 12:30:00 | 08/04/2023 18:30:00 | 01-EE-061 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 08-Apr | 08-Apr | 05-Apr | 05-Apr
CDUVDU15060 | Completed | Test Ring Boxup | 05/04/2023 07:46:31 | 07/04/2023 12:32:46 | 08/04/2023 18:30:00 | 09/04/2023 02:30:00 | 01-EE-061 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 52:46 | 44:46 |  | 08-Apr | 09-Apr | 05-Apr | 07-Apr
CDUVDU15770 | Completed | Carryout Shell Test | 07/04/2023 12:30:45 | 07/04/2023 12:32:55 | 09/04/2023 02:30:00 | 09/04/2023 17:30:00 | 01-EE-061 | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 0:02 |  | 14:58 | 09-Apr | 09-Apr | 07-Apr | 07-Apr
CDUVDU16900 | Completed | Test Ring Drop Down | 07/04/2023 12:31:02 | 07/04/2023 12:33:01 | 09/04/2023 17:30:00 | 09/04/2023 23:30:00 | 01-EE-061 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:02 |  | 5:58 | 09-Apr | 09-Apr | 07-Apr | 07-Apr
CDUVDU17550 | Completed | Floating Head Box-up | 07/04/2023 12:31:24 | 07/04/2023 12:33:06 | 09/04/2023 23:30:00 | 10/04/2023 05:30:00 | 01-EE-061 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:02 |  | 5:58 | 09-Apr | 10-Apr | 07-Apr | 07-Apr
CDUVDU18250 | Completed | Tube Test | 07/04/2023 12:32:17 | 07/04/2023 12:33:18 | 10/04/2023 05:30:00 | 10/04/2023 20:30:00 | 01-EE-061 | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 15 | 15:00 | 0:01 |  | 14:59 | 10-Apr | 10-Apr | 07-Apr | 07-Apr
CDUVDU19550 | Completed | Back Dome Boxup | 08/04/2023 07:21:54 | 08/04/2023 09:30:53 | 10/04/2023 20:30:00 | 11/04/2023 04:30:00 | 01-EE-061 | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 2:09 |  | 5:51 | 10-Apr | 11-Apr | 08-Apr | 08-Apr
CDUVDU20480 | Completed | Final Test | 08/04/2023 09:30:42 | 08/04/2023 09:30:46 | 11/04/2023 04:30:00 | 11/04/2023 19:30:00 | 01-EE-061 | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 0:00 |  | 15:00 | 11-Apr | 11-Apr | 08-Apr | 08-Apr
CDUVDU22050 | Completed | Deblinding | 14/04/2023 04:57:37 | 14/04/2023 04:58:05 | 11/04/2023 19:30:00 | 12/04/2023 03:30:00 | 01-EE-061 | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 11-Apr | 12-Apr | 14-Apr | 14-Apr
CDUVDU3710 | Completed | Blinding As Per Blind List | 02/04/2023 05:04:46 | 02/04/2023 05:08:07 | 01/04/2023 14:30:00 | 01/04/2023 22:30:00 | 01-EE-061 | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:03 |  | 7:57 | 01-Apr | 01-Apr | 02-Apr | 02-Apr
CDUVDU4280 | Completed | Carryout Component Dropping | 02/04/2023 05:04:46 | 02/04/2023 05:08:25 | 01/04/2023 22:30:00 | 02/04/2023 06:30:00 | 01-EE-061 | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:04 |  | 7:56 | 01-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU4830 | Completed | Carryout Bundle Pullout | 02/04/2023 05:04:46 | 02/04/2023 05:09:34 | 02/04/2023 06:30:00 | 02/04/2023 12:30:00 | 01-EE-061 | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 0:05 |  | 5:55 | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU5250 | Completed | Pre Cleaning Inspection | 02/04/2023 05:04:46 | 02/04/2023 06:12:34 | 02/04/2023 12:30:00 | 02/04/2023 14:30:00 | 01-EE-061 | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 1:08 |  | 0:52 | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU5990 | Completed | Bundle Shifting to Bay | 02/04/2023 05:04:46 | 02/04/2023 05:09:57 | 02/04/2023 14:30:00 | 02/04/2023 17:30:00 | 01-EE-061 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:05 |  | 2:55 | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU17410 | Completed | Hydrojetting of Tube Bundle | 05/04/2023 16:33:04 | 05/04/2023 16:33:04 | 09/04/2023 22:30:00 | 11/04/2023 00:30:00 | 01-EE-062 | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 26 | 26:00 | 0:00 |  |  | 09-Apr | 11-Apr | 05-Apr | 05-Apr
CDUVDU20060 | Completed | Air Drying | 05/04/2023 16:33:04 | 05/04/2023 16:33:04 | 11/04/2023 00:30:00 | 11/04/2023 08:30:00 | 01-EE-062 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  |  | 11-Apr | 11-Apr | 05-Apr | 05-Apr
CDUVDU20790 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 05/04/2023 16:33:04 | 05/04/2023 16:33:04 | 11/04/2023 08:30:00 | 11/04/2023 14:30:00 | 01-EE-062 | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  |  | 11-Apr | 11-Apr | 05-Apr | 05-Apr
CDUVDU21540 | Completed | Shifting of bundle from bay | 05/04/2023 16:33:04 | 05/04/2023 16:33:04 | 11/04/2023 14:30:00 | 11/04/2023 17:30:00 | 01-EE-062 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  |  | 11-Apr | 11-Apr | 05-Apr | 05-Apr
CDUVDU21890 | Completed | Carryout Bundle Insertion | 05/04/2023 16:33:04 | 05/04/2023 19:52:05 | 11/04/2023 17:30:00 | 12/04/2023 01:30:00 | 01-EE-062 | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 3:19 |  | 4:41 | 11-Apr | 12-Apr | 05-Apr | 05-Apr
CDUVDU22450 | Completed | Channelhead Boxup | 05/04/2023 16:33:04 | 05/04/2023 16:33:04 | 12/04/2023 01:30:00 | 12/04/2023 07:30:00 | 01-EE-062 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 12-Apr | 12-Apr | 05-Apr | 05-Apr
CDUVDU23140 | Completed | Test Ring Boxup | 05/04/2023 16:33:04 | 05/04/2023 16:33:04 | 12/04/2023 07:30:00 | 12/04/2023 15:30:00 | 01-EE-062 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  |  | 12-Apr | 12-Apr | 05-Apr | 05-Apr
CDUVDU23870 | Completed | Carryout Shell Test | 05/04/2023 16:33:14 | 07/04/2023 21:59:00 | 12/04/2023 15:30:00 | 13/04/2023 06:30:00 | 01-EE-062 | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 53:26 | 38:26 |  | 12-Apr | 13-Apr | 05-Apr | 07-Apr
CDUVDU25010 | Completed | Test Ring Drop Down | 10/04/2023 10:15:55 | 11/04/2023 17:47:28 | 13/04/2023 06:30:00 | 13/04/2023 12:30:00 | 01-EE-062 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 31:32 | 25:32 |  | 13-Apr | 13-Apr | 10-Apr | 11-Apr
CDUVDU25330 | Completed | Floating Head Box-up | 11/04/2023 17:47:49 | 11/04/2023 17:47:55 | 13/04/2023 12:30:00 | 13/04/2023 18:30:00 | 01-EE-062 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 13-Apr | 13-Apr | 11-Apr | 11-Apr
CDUVDU25730 | Completed | Tube Test | 12/04/2023 06:36:45 | 12/04/2023 15:54:42 | 13/04/2023 18:30:00 | 14/04/2023 09:30:00 | 01-EE-062 | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 15 | 15:00 | 9:18 |  | 5:42 | 13-Apr | 14-Apr | 12-Apr | 12-Apr
CDUVDU26390 | Completed | Back Dome Boxup | 13/04/2023 03:45:31 | 13/04/2023 07:26:14 | 14/04/2023 09:30:00 | 14/04/2023 17:30:00 | 01-EE-062 | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 3:41 |  | 4:19 | 14-Apr | 14-Apr | 13-Apr | 13-Apr
CDUVDU26810 | Completed | Final Test | 13/04/2023 07:27:28 | 13/04/2023 19:11:42 | 14/04/2023 17:30:00 | 15/04/2023 08:30:00 | 01-EE-062 | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 11:44 |  | 3:16 | 14-Apr | 15-Apr | 13-Apr | 13-Apr
CDUVDU27360 | Completed | Deblinding | 18/04/2023 00:57:44 | 18/04/2023 00:57:49 | 15/04/2023 08:30:00 | 15/04/2023 16:30:00 | 01-EE-062 | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 15-Apr | 15-Apr | 18-Apr | 18-Apr
CDUVDU3630 | Completed | Blinding As Per Blind List | 02/04/2023 06:32:47 | 02/04/2023 06:32:54 | 01/04/2023 14:30:00 | 01/04/2023 22:30:00 | 01-EE-062 | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 01-Apr | 01-Apr | 02-Apr | 02-Apr
CDUVDU4260 | Completed | Carryout Component Dropping | 02/04/2023 07:30:30 | 02/04/2023 07:30:30 | 01/04/2023 22:30:00 | 02/04/2023 06:30:00 | 01-EE-062 | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  |  | 01-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU8480 | Completed | Carryout Bundle Pullout | 02/04/2023 15:15:39 | 02/04/2023 15:15:46 | 04/04/2023 06:30:00 | 04/04/2023 12:30:00 | 01-EE-062 | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 0:00 |  | 6:00 | 04-Apr | 04-Apr | 02-Apr | 02-Apr
CDUVDU8710 | Completed | Pre Cleaning Inspection | 02/04/2023 17:47:34 | 02/04/2023 17:47:38 | 04/04/2023 12:30:00 | 04/04/2023 14:30:00 | 01-EE-062 | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  | 2:00 | 04-Apr | 04-Apr | 02-Apr | 02-Apr
CDUVDU9050 | Completed | Bundle Shifting to Bay | 03/04/2023 06:19:06 | 03/04/2023 06:19:06 | 04/04/2023 14:30:00 | 04/04/2023 17:30:00 | 01-EE-062 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  |  | 04-Apr | 04-Apr | 03-Apr | 03-Apr
CDUVDU20090 | Completed | Hydrojetting of Tube Bundle | 03/04/2023 11:02:52 | 04/04/2023 07:39:45 | 11/04/2023 00:30:00 | 11/04/2023 13:30:00 | 01-EE-063A | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 13 | 13:00 | 20:37 | 7:37 |  | 11-Apr | 11-Apr | 03-Apr | 04-Apr
CDUVDU21300 | Completed | Air Drying | 04/04/2023 19:29:14 | 04/04/2023 19:29:19 | 11/04/2023 13:30:00 | 11/04/2023 21:30:00 | 01-EE-063A | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  | 8:00 | 11-Apr | 11-Apr | 04-Apr | 04-Apr
CDUVDU22160 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 04/04/2023 19:29:38 | 04/04/2023 19:29:45 | 11/04/2023 21:30:00 | 12/04/2023 03:30:00 | 01-EE-063A | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  | 6:00 | 11-Apr | 12-Apr | 04-Apr | 04-Apr
CDUVDU22840 | Completed | Shifting of bundle from bay | 04/04/2023 19:30:01 | 04/04/2023 19:30:06 | 12/04/2023 03:30:00 | 12/04/2023 07:30:00 | 01-EE-063A | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 12-Apr | 12-Apr | 04-Apr | 04-Apr
CDUVDU23170 | Completed | Carryout Bundle Insertion | 04/04/2023 19:30:16 | 05/04/2023 07:22:00 | 12/04/2023 07:30:00 | 12/04/2023 15:30:00 | 01-EE-063A | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 11:52 | 3:52 |  | 12-Apr | 12-Apr | 04-Apr | 05-Apr
CDUVDU23900 | Completed | Channelhead Boxup | 05/04/2023 07:23:39 | 05/04/2023 07:23:39 | 12/04/2023 15:30:00 | 12/04/2023 21:30:00 | 01-EE-063A | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 12-Apr | 12-Apr | 05-Apr | 05-Apr
CDUVDU24320 | Completed | Test Ring Boxup | 05/04/2023 15:48:27 | 05/04/2023 16:34:00 | 12/04/2023 21:30:00 | 13/04/2023 05:30:00 | 01-EE-063A | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:46 |  | 7:14 | 12-Apr | 13-Apr | 05-Apr | 05-Apr
CDUVDU24930 | Completed | Carryout Shell Test | 05/04/2023 16:34:15 | 06/04/2023 16:29:16 | 13/04/2023 05:30:00 | 13/04/2023 20:30:00 | 01-EE-063A | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 23:55 | 8:55 |  | 13-Apr | 13-Apr | 05-Apr | 06-Apr
CDUVDU25770 | Completed | Test Ring Drop Down | 06/04/2023 18:27:48 | 06/04/2023 18:27:55 | 13/04/2023 20:30:00 | 14/04/2023 02:30:00 | 01-EE-063A | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 13-Apr | 14-Apr | 06-Apr | 06-Apr
CDUVDU26120 | Completed | Floating Head Box-up | 07/04/2023 07:37:33 | 08/04/2023 07:36:42 | 14/04/2023 02:30:00 | 14/04/2023 08:30:00 | 01-EE-063A | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 23:59 | 17:59 |  | 14-Apr | 14-Apr | 07-Apr | 08-Apr
CDUVDU26360 | Completed | Tube Test | 09/04/2023 07:26:47 | 09/04/2023 07:26:47 | 14/04/2023 08:30:00 | 14/04/2023 23:30:00 | 01-EE-063A | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 15 | 15:00 | 0:00 |  |  | 14-Apr | 14-Apr | 09-Apr | 09-Apr
CDUVDU27030 | Completed | Back Dome Boxup | 09/04/2023 07:26:47 | 09/04/2023 07:26:47 | 14/04/2023 23:30:00 | 15/04/2023 07:30:00 | 01-EE-063A | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 0:00 |  |  | 14-Apr | 15-Apr | 09-Apr | 09-Apr
CDUVDU27290 | Completed | Final Test | 09/04/2023 07:27:09 | 09/04/2023 10:26:36 | 15/04/2023 07:30:00 | 15/04/2023 22:30:00 | 01-EE-063A | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 2:59 |  | 12:01 | 15-Apr | 15-Apr | 09-Apr | 09-Apr
CDUVDU27840 | Completed | Deblinding | 18/04/2023 00:58:35 | 18/04/2023 00:58:39 | 15/04/2023 22:30:00 | 16/04/2023 06:30:00 | 01-EE-063A | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 15-Apr | 16-Apr | 18-Apr | 18-Apr
CDUVDU3720 | Completed | Blinding As Per Blind List | 02/04/2023 06:33:11 | 02/04/2023 06:33:11 | 01/04/2023 14:30:00 | 01/04/2023 22:30:00 | 01-EE-063A | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  |  | 01-Apr | 01-Apr | 02-Apr | 02-Apr
CDUVDU4290 | Completed | Carryout Component Dropping | 02/04/2023 07:31:16 | 02/04/2023 07:31:16 | 01/04/2023 22:30:00 | 02/04/2023 06:30:00 | 01-EE-063A | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  |  | 01-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU8010 | Completed | Carryout Bundle Pullout | 02/04/2023 10:43:57 | 02/04/2023 10:44:03 | 03/04/2023 18:30:00 | 04/04/2023 00:30:00 | 01-EE-063A | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 0:00 |  | 6:00 | 03-Apr | 04-Apr | 02-Apr | 02-Apr
CDUVDU8300 | Completed | Pre Cleaning Inspection | 02/04/2023 17:47:59 | 02/04/2023 17:48:03 | 04/04/2023 00:30:00 | 04/04/2023 02:30:00 | 01-EE-063A | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  | 2:00 | 04-Apr | 04-Apr | 02-Apr | 02-Apr
CDUVDU8350 | Completed | Bundle Shifting to Bay | 03/04/2023 06:19:26 | 03/04/2023 06:19:26 | 04/04/2023 02:30:00 | 04/04/2023 05:30:00 | 01-EE-063A | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  |  | 04-Apr | 04-Apr | 03-Apr | 03-Apr
CDUVDU21310 | Completed | Hydrojetting of Tube Bundle | 03/04/2023 11:03:24 | 04/04/2023 07:41:06 | 11/04/2023 13:30:00 | 12/04/2023 02:30:00 | 01-EE-063B | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 13 | 13:00 | 20:38 | 7:38 |  | 11-Apr | 12-Apr | 03-Apr | 04-Apr
CDUVDU22670 | Completed | Air Drying | 04/04/2023 19:27:31 | 04/04/2023 19:27:36 | 12/04/2023 02:30:00 | 12/04/2023 10:30:00 | 01-EE-063B | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  | 8:00 | 12-Apr | 12-Apr | 04-Apr | 04-Apr
CDUVDU23420 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 04/04/2023 19:27:51 | 04/04/2023 19:27:55 | 12/04/2023 10:30:00 | 12/04/2023 16:30:00 | 01-EE-063B | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  | 6:00 | 12-Apr | 12-Apr | 04-Apr | 04-Apr
CDUVDU23970 | Completed | Shifting of bundle from bay | 04/04/2023 19:28:07 | 04/04/2023 19:28:11 | 12/04/2023 16:30:00 | 12/04/2023 19:30:00 | 01-EE-063B | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 12-Apr | 12-Apr | 04-Apr | 04-Apr
CDUVDU24170 | Completed | Carryout Bundle Insertion | 04/04/2023 19:28:18 | 04/04/2023 19:28:25 | 12/04/2023 19:30:00 | 13/04/2023 03:30:00 | 01-EE-063B | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 0:00 |  | 8:00 | 12-Apr | 13-Apr | 04-Apr | 04-Apr
CDUVDU24790 | Completed | Channelhead Boxup | 05/04/2023 15:50:04 | 05/04/2023 15:50:09 | 13/04/2023 03:30:00 | 13/04/2023 09:30:00 | 01-EE-063B | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 13-Apr | 13-Apr | 05-Apr | 05-Apr
CDUVDU25190 | Completed | Test Ring Boxup | 05/04/2023 15:50:17 | 06/04/2023 07:42:07 | 13/04/2023 09:30:00 | 13/04/2023 17:30:00 | 01-EE-063B | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 15:52 | 7:52 |  | 13-Apr | 13-Apr | 05-Apr | 06-Apr
CDUVDU25650 | Completed | Carryout Shell Test | 06/04/2023 07:42:30 | 06/04/2023 16:29:35 | 13/04/2023 17:30:00 | 14/04/2023 08:30:00 | 01-EE-063B | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 8:47 |  | 6:13 | 13-Apr | 14-Apr | 06-Apr | 06-Apr
CDUVDU26370 | Completed | Test Ring Drop Down | 06/04/2023 18:28:12 | 06/04/2023 18:28:17 | 14/04/2023 08:30:00 | 14/04/2023 14:30:00 | 01-EE-063B | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 14-Apr | 14-Apr | 06-Apr | 06-Apr
CDUVDU26660 | Completed | Floating Head Box-up | 07/04/2023 11:54:37 | 07/04/2023 11:54:53 | 14/04/2023 14:30:00 | 14/04/2023 20:30:00 | 01-EE-063B | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 14-Apr | 14-Apr | 07-Apr | 07-Apr
CDUVDU26900 | Completed | Tube Test | 09/04/2023 07:27:46 | 09/04/2023 07:27:56 | 14/04/2023 20:30:00 | 15/04/2023 11:30:00 | 01-EE-063B | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 15 | 15:00 | 0:00 |  | 15:00 | 14-Apr | 15-Apr | 09-Apr | 09-Apr
CDUVDU27460 | Completed | Back Dome Boxup | 09/04/2023 07:27:46 | 09/04/2023 07:27:56 | 15/04/2023 11:30:00 | 15/04/2023 19:30:00 | 01-EE-063B | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 0:00 |  | 8:00 | 15-Apr | 15-Apr | 09-Apr | 09-Apr
CDUVDU27730 | Completed | Final Test | 09/04/2023 07:27:46 | 09/04/2023 10:27:40 | 15/04/2023 19:30:00 | 16/04/2023 10:30:00 | 01-EE-063B | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 3:00 |  | 12:00 | 15-Apr | 16-Apr | 09-Apr | 09-Apr
CDUVDU28260 | Completed | Deblinding | 18/04/2023 00:59:23 | 18/04/2023 00:59:27 | 16/04/2023 10:30:00 | 16/04/2023 18:30:00 | 01-EE-063B | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 16-Apr | 16-Apr | 18-Apr | 18-Apr
CDUVDU3730 | Completed | Blinding As Per Blind List | 02/04/2023 06:33:26 | 02/04/2023 06:33:26 | 01/04/2023 14:30:00 | 01/04/2023 22:30:00 | 01-EE-063B | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  |  | 01-Apr | 01-Apr | 02-Apr | 02-Apr
CDUVDU4300 | Completed | Carryout Component Dropping | 02/04/2023 07:31:38 | 02/04/2023 07:31:38 | 01/04/2023 22:30:00 | 02/04/2023 06:30:00 | 01-EE-063B | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  |  | 01-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU8310 | Completed | Carryout Bundle Pullout | 02/04/2023 10:42:49 | 03/04/2023 04:40:24 | 04/04/2023 00:30:00 | 04/04/2023 06:30:00 | 01-EE-063B | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 17:58 | 11:58 |  | 04-Apr | 04-Apr | 02-Apr | 03-Apr
CDUVDU8490 | Completed | Pre Cleaning Inspection | 02/04/2023 17:48:23 | 02/04/2023 17:48:28 | 04/04/2023 06:30:00 | 04/04/2023 08:30:00 | 01-EE-063B | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  | 2:00 | 04-Apr | 04-Apr | 02-Apr | 02-Apr
CDUVDU8580 | Completed | Bundle Shifting to Bay | 03/04/2023 06:20:10 | 03/04/2023 06:20:19 | 04/04/2023 08:30:00 | 04/04/2023 11:30:00 | 01-EE-063B | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 04-Apr | 04-Apr | 03-Apr | 03-Apr
CDUVDU22680 | Completed | Hydrojetting of Tube Bundle | 09/04/2023 11:15:57 | 14/04/2023 07:49:14 | 12/04/2023 02:30:00 | 13/04/2023 02:30:00 | 01-EE-091A | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 24 | 24:00 | 116:33 | 92:33 |  | 12-Apr | 13-Apr | 09-Apr | 14-Apr
CDUVDU24740 | Completed | Air Drying | 14/04/2023 07:49:54 | 14/04/2023 07:50:08 | 13/04/2023 02:30:00 | 13/04/2023 10:30:00 | 01-EE-091A | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  | 8:00 | 13-Apr | 13-Apr | 14-Apr | 14-Apr
CDUVDU25280 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 14/04/2023 07:49:54 | 14/04/2023 07:50:17 | 13/04/2023 10:30:00 | 13/04/2023 16:30:00 | 01-EE-091A | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  | 6:00 | 13-Apr | 13-Apr | 14-Apr | 14-Apr
CDUVDU25590 | Completed | Shifting of bundle from bay | 14/04/2023 17:11:53 | 14/04/2023 17:11:58 | 13/04/2023 16:30:00 | 13/04/2023 19:30:00 | 01-EE-091A | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 13-Apr | 13-Apr | 14-Apr | 14-Apr
CDUVDU25750 | Completed | Carryout Bundle Insertion | 14/04/2023 17:12:05 | 14/04/2023 17:12:10 | 13/04/2023 19:30:00 | 14/04/2023 03:30:00 | 01-EE-091A | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 0:00 |  | 8:00 | 13-Apr | 14-Apr | 14-Apr | 14-Apr
CDUVDU26150 | Completed | Channelhead Boxup | 15/04/2023 07:09:48 | 15/04/2023 07:10:00 | 14/04/2023 03:30:00 | 14/04/2023 09:30:00 | 01-EE-091A | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 14-Apr | 14-Apr | 15-Apr | 15-Apr
CDUVDU26400 | Completed | Test Ring Boxup | 16/04/2023 16:35:33 | 18/04/2023 11:11:34 | 14/04/2023 09:30:00 | 14/04/2023 17:30:00 | 01-EE-091A | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 42:36 | 34:36 |  | 14-Apr | 14-Apr | 16-Apr | 18-Apr
CDUVDU26820 | Completed | Carryout Shell Test | 17/04/2023 23:38:32 | 18/04/2023 17:41:54 | 14/04/2023 17:30:00 | 15/04/2023 08:30:00 | 01-EE-091A | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 18:03 | 3:03 |  | 14-Apr | 15-Apr | 17-Apr | 18-Apr
CDUVDU27370 | Completed | Test Ring Drop Down | 19/04/2023 10:21:46 | 19/04/2023 10:21:54 | 15/04/2023 08:30:00 | 15/04/2023 14:30:00 | 01-EE-091A | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 15-Apr | 15-Apr | 19-Apr | 19-Apr
CDUVDU27600 | Completed | Floating Head Box-up | 19/04/2023 00:05:00 | 20/04/2023 02:58:00 | 15/04/2023 14:30:00 | 15/04/2023 20:30:00 | 01-EE-091A | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 26:53 | 20:53 |  | 15-Apr | 15-Apr | 19-Apr | 20-Apr
CDUVDU27740 | Completed | Tube Test | 20/04/2023 02:58:00 | 20/04/2023 02:58:00 | 15/04/2023 20:30:00 | 16/04/2023 11:30:00 | 01-EE-091A | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 15 | 15:00 | 0:00 |  |  | 15-Apr | 16-Apr | 20-Apr | 20-Apr
CDUVDU28270 | Completed | Back Dome Boxup | 20/04/2023 02:58:00 | 20/04/2023 02:58:00 | 16/04/2023 11:30:00 | 16/04/2023 19:30:00 | 01-EE-091A | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 0:00 |  |  | 16-Apr | 16-Apr | 20-Apr | 20-Apr
CDUVDU28490 | Completed | Final Test | 20/04/2023 18:57:02 | 21/04/2023 06:43:27 | 16/04/2023 19:30:00 | 17/04/2023 10:30:00 | 01-EE-091A | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 11:46 |  | 3:14 | 16-Apr | 17-Apr | 20-Apr | 21-Apr
CDUVDU28870 | Completed | Deblinding | 22/04/2023 18:25:53 | 22/04/2023 18:26:15 | 17/04/2023 10:30:00 | 17/04/2023 18:30:00 | 01-EE-091A | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 17-Apr | 17-Apr | 22-Apr | 22-Apr
CDUVDU3740 | Completed | Blinding As Per Blind List | 02/04/2023 06:33:45 | 02/04/2023 06:33:45 | 01/04/2023 14:30:00 | 01/04/2023 22:30:00 | 01-EE-091A | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  |  | 01-Apr | 01-Apr | 02-Apr | 02-Apr
CDUVDU4310 | Completed | Carryout Component Dropping | 03/04/2023 07:37:34 | 05/04/2023 07:22:18 | 01/04/2023 22:30:00 | 02/04/2023 06:30:00 | 01-EE-091A | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 47:45 | 39:45 |  | 01-Apr | 02-Apr | 03-Apr | 05-Apr
CDUVDU4840 | Completed | Carryout Bundle Pullout | 06/04/2023 18:33:29 | 06/04/2023 18:37:15 | 02/04/2023 06:30:00 | 02/04/2023 12:30:00 | 01-EE-091A | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 0:04 |  | 5:56 | 02-Apr | 02-Apr | 06-Apr | 06-Apr
CDUVDU5260 | Completed | Pre Cleaning Inspection | 07/04/2023 07:36:03 | 07/04/2023 07:36:03 | 02/04/2023 12:30:00 | 02/04/2023 14:30:00 | 01-EE-091A | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  |  | 02-Apr | 02-Apr | 07-Apr | 07-Apr
CDUVDU6000 | Completed | Bundle Shifting to Bay | 09/04/2023 07:28:27 | 09/04/2023 07:28:27 | 02/04/2023 14:30:00 | 02/04/2023 17:30:00 | 01-EE-091A | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  |  | 02-Apr | 02-Apr | 09-Apr | 09-Apr
CDUVDU11060 | Completed | Air Drying | 09/04/2023 09:52:30 | 09/04/2023 09:52:35 | 06/04/2023 05:30:00 | 06/04/2023 13:30:00 | 01-EE-005 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  | 8:00 | 06-Apr | 06-Apr | 09-Apr | 09-Apr
CDUVDU11420 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 08/04/2023 21:11:46 | 08/04/2023 21:11:46 | 06/04/2023 13:30:00 | 06/04/2023 19:30:00 | 01-EE-005 | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  |  | 06-Apr | 06-Apr | 08-Apr | 08-Apr
CDUVDU11900 | Completed | Shifting of bundle from bay | 09/04/2023 06:53:42 | 09/04/2023 06:53:42 | 06/04/2023 19:30:00 | 06/04/2023 22:30:00 | 01-EE-005 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  |  | 06-Apr | 06-Apr | 09-Apr | 09-Apr
CDUVDU12170 | Completed | Carryout Bundle Insertion | 09/04/2023 06:53:42 | 09/04/2023 06:53:42 | 06/04/2023 22:30:00 | 07/04/2023 06:30:00 | 01-EE-005 | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 0:00 |  |  | 06-Apr | 07-Apr | 09-Apr | 09-Apr
CDUVDU12680 | Completed | Channelhead Boxup | 09/04/2023 06:53:42 | 09/04/2023 06:53:42 | 07/04/2023 06:30:00 | 07/04/2023 12:30:00 | 01-EE-005 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 07-Apr | 07-Apr | 09-Apr | 09-Apr
CDUVDU12990 | Completed | Test Ring Boxup | 09/04/2023 06:53:42 | 09/04/2023 06:53:42 | 07/04/2023 12:30:00 | 07/04/2023 20:30:00 | 01-EE-005 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  |  | 07-Apr | 07-Apr | 09-Apr | 09-Apr
CDUVDU13530 | Completed | Carryout Shell Test | 10/04/2023 06:48:50 | 10/04/2023 09:20:48 | 07/04/2023 20:30:00 | 08/04/2023 11:30:00 | 01-EE-005 | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 2:32 |  | 12:28 | 07-Apr | 08-Apr | 10-Apr | 10-Apr
CDUVDU14490 | Completed | Test Ring Drop Down | 11/04/2023 07:27:42 | 11/04/2023 07:27:42 | 08/04/2023 11:30:00 | 08/04/2023 17:30:00 | 01-EE-005 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 08-Apr | 08-Apr | 11-Apr | 11-Apr
CDUVDU14970 | Completed | Floating Head Box-up | 11/04/2023 07:26:37 | 11/04/2023 07:26:37 | 08/04/2023 17:30:00 | 08/04/2023 23:30:00 | 01-EE-005 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 08-Apr | 08-Apr | 11-Apr | 11-Apr
CDUVDU15370 | Completed | Tube Test | 11/04/2023 07:26:37 | 11/04/2023 07:26:37 | 08/04/2023 23:30:00 | 09/04/2023 14:30:00 | 01-EE-005 | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 15 | 15:00 | 0:00 |  |  | 08-Apr | 09-Apr | 11-Apr | 11-Apr
CDUVDU16710 | Completed | Back Dome Boxup | 11/04/2023 07:33:13 | 11/04/2023 07:33:13 | 09/04/2023 14:30:00 | 09/04/2023 22:30:00 | 01-EE-005 | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 0:00 |  |  | 09-Apr | 09-Apr | 11-Apr | 11-Apr
CDUVDU17370 | Completed | Final Test | 11/04/2023 10:37:52 | 14/04/2023 04:20:06 | 09/04/2023 22:30:00 | 10/04/2023 13:30:00 | 01-EE-005 | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 65:42 | 50:42 |  | 09-Apr | 10-Apr | 11-Apr | 14-Apr
CDUVDU18870 | Completed | Deblinding | 14/04/2023 04:20:19 | 14/04/2023 04:20:29 | 10/04/2023 13:30:00 | 10/04/2023 21:30:00 | 01-EE-005 | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 10-Apr | 10-Apr | 14-Apr | 14-Apr
CDUVDU2220 | Completed | Blinding As Per Blind List | 01/04/2023 04:09:58 | 01/04/2023 04:10:18 | 31/03/2023 14:30:00 | 31/03/2023 22:30:00 | 01-EE-005 | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 31-Mar | 31-Mar | 01-Apr | 01-Apr
CDUVDU2550 | Completed | Carryout Component Dropping | 01/04/2023 04:09:58 | 02/04/2023 05:54:42 | 31/03/2023 22:30:00 | 01/04/2023 06:30:00 | 01-EE-005 | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 25:45 | 17:45 |  | 31-Mar | 01-Apr | 01-Apr | 02-Apr
CDUVDU5130 | Completed | Carryout Bundle Pullout | 01/04/2023 15:49:04 | 01/04/2023 15:49:10 | 02/04/2023 12:30:00 | 02/04/2023 18:30:00 | 01-EE-005 | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 0:00 |  | 6:00 | 02-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU6240 | Completed | Pre Cleaning Inspection | 01/04/2023 16:39:34 | 01/04/2023 16:39:40 | 02/04/2023 18:30:00 | 02/04/2023 20:30:00 | 01-EE-005 | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  | 2:00 | 02-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU6280 | Completed | Bundle Shifting to Bay | 02/04/2023 06:01:55 | 02/04/2023 06:02:00 | 02/04/2023 20:30:00 | 02/04/2023 23:30:00 | 01-EE-005 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU9590 | Completed | Hydrojetting of Tube Bundle | 02/04/2023 06:01:55 | 08/04/2023 06:54:01 | 05/04/2023 02:30:00 | 06/04/2023 05:30:00 | 01-EE-005 | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 27 | 27:00 | 144:52 | 117:52 |  | 05-Apr | 06-Apr | 02-Apr | 08-Apr
CDUVDU25790 | Completed | Hydrojetting of Tube Bundle | 09/04/2023 07:29:23 | 10/04/2023 07:15:12 | 13/04/2023 20:30:00 | 14/04/2023 13:30:00 | 01-EE-091C | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 17 | 17:00 | 23:46 | 6:46 |  | 13-Apr | 14-Apr | 09-Apr | 10-Apr
CDUVDU26560 | Completed | Air Drying | 10/04/2023 07:15:12 | 10/04/2023 07:15:12 | 14/04/2023 13:30:00 | 14/04/2023 21:30:00 | 01-EE-091C | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  |  | 14-Apr | 14-Apr | 10-Apr | 10-Apr
CDUVDU26920 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 10/04/2023 03:04:26 | 10/04/2023 03:04:26 | 14/04/2023 21:30:00 | 15/04/2023 03:30:00 | 01-EE-091C | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  |  | 14-Apr | 15-Apr | 10-Apr | 10-Apr
CDUVDU27140 | Completed | Shifting of bundle from bay | 13/04/2023 05:28:56 | 13/04/2023 05:29:00 | 15/04/2023 03:30:00 | 15/04/2023 07:30:00 | 01-EE-091C | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 15-Apr | 15-Apr | 13-Apr | 13-Apr
CDUVDU27300 | Completed | Carryout Bundle Insertion | 18/04/2023 19:30:27 | 19/04/2023 02:32:44 | 15/04/2023 07:30:00 | 15/04/2023 15:30:00 | 01-EE-091C | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 7:02 |  | 0:58 | 15-Apr | 15-Apr | 18-Apr | 19-Apr
CDUVDU27620 | Completed | Channelhead Boxup | 19/04/2023 06:51:36 | 19/04/2023 06:52:31 | 15/04/2023 15:30:00 | 15/04/2023 21:30:00 | 01-EE-091C | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:01 |  | 5:59 | 15-Apr | 15-Apr | 19-Apr | 19-Apr
CDUVDU27770 | Completed | Test Ring Boxup | 19/04/2023 07:13:50 | 19/04/2023 18:17:43 | 15/04/2023 21:30:00 | 16/04/2023 05:30:00 | 01-EE-091C | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 11:04 | 3:04 |  | 15-Apr | 16-Apr | 19-Apr | 19-Apr
CDUVDU28040 | Completed | Carryout Shell Test | 20/04/2023 02:52:00 | 20/04/2023 02:58:00 | 16/04/2023 05:30:00 | 16/04/2023 20:30:00 | 01-EE-091C | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 0:06 |  | 14:54 | 16-Apr | 16-Apr | 20-Apr | 20-Apr
CDUVDU28510 | Completed | Test Ring Drop Down | 21/04/2023 12:23:39 | 21/04/2023 19:00:16 | 16/04/2023 20:30:00 | 17/04/2023 02:30:00 | 01-EE-091C | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 6:37 | 0:37 |  | 16-Apr | 17-Apr | 21-Apr | 21-Apr
CDUVDU28700 | Completed | Floating Head Box-up | 21/04/2023 19:01:11 | 22/04/2023 18:26:55 | 17/04/2023 02:30:00 | 17/04/2023 08:30:00 | 01-EE-091C | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 23:26 | 17:26 |  | 17-Apr | 17-Apr | 21-Apr | 22-Apr
CDUVDU28830 | Completed | Tube Test | 22/04/2023 23:10:52 | 23/04/2023 06:45:35 | 17/04/2023 08:30:00 | 17/04/2023 23:30:00 | 01-EE-091C | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 15 | 15:00 | 7:35 |  | 7:25 | 17-Apr | 17-Apr | 22-Apr | 23-Apr
CDUVDU29170 | Completed | Back Dome Boxup | 23/04/2023 09:46:11 | 24/04/2023 00:41:32 | 17/04/2023 23:30:00 | 18/04/2023 07:30:00 | 01-EE-091C | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 14:55 | 6:55 |  | 17-Apr | 18-Apr | 23-Apr | 24-Apr
CDUVDU29350 | Completed | Final Test | 24/04/2023 00:41:23 | 24/04/2023 11:32:42 | 18/04/2023 07:30:00 | 18/04/2023 22:30:00 | 01-EE-091C | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 10:51 |  | 4:09 | 18-Apr | 18-Apr | 24-Apr | 24-Apr
CDUVDU29610 | Completed | Deblinding | 24/04/2023 18:28:18 | 25/04/2023 04:50:26 | 18/04/2023 22:30:00 | 19/04/2023 06:30:00 | 01-EE-091C | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 10:22 | 2:22 |  | 18-Apr | 19-Apr | 24-Apr | 25-Apr
CDUVDU3750 | Completed | Blinding As Per Blind List | 02/04/2023 06:34:18 | 02/04/2023 06:34:18 | 01/04/2023 14:30:00 | 01/04/2023 22:30:00 | 01-EE-091C | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  |  | 01-Apr | 01-Apr | 02-Apr | 02-Apr
CDUVDU4320 | Completed | Carryout Component Dropping | 05/04/2023 10:20:03 | 07/04/2023 07:36:45 | 01/04/2023 22:30:00 | 02/04/2023 06:30:00 | 01-EE-091C | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 45:17 | 37:17 |  | 01-Apr | 02-Apr | 05-Apr | 07-Apr
CDUVDU4850 | Completed | Carryout Bundle Pullout | 08/04/2023 07:41:48 | 08/04/2023 07:41:48 | 02/04/2023 06:30:00 | 02/04/2023 12:30:00 | 01-EE-091C | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 0:00 |  |  | 02-Apr | 02-Apr | 08-Apr | 08-Apr
CDUVDU5270 | Completed | Pre Cleaning Inspection | 08/04/2023 07:41:48 | 08/04/2023 07:41:48 | 02/04/2023 12:30:00 | 02/04/2023 14:30:00 | 01-EE-091C | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  |  | 02-Apr | 02-Apr | 08-Apr | 08-Apr
CDUVDU6010 | Completed | Bundle Shifting to Bay | 09/04/2023 07:29:23 | 09/04/2023 07:29:41 | 02/04/2023 14:30:00 | 02/04/2023 17:30:00 | 01-EE-091C | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 02-Apr | 02-Apr | 09-Apr | 09-Apr
CDUVDU1890 | Completed | Blinding As Per Blind List | 02/04/2023 06:34:01 | 02/04/2023 06:34:01 | 31/03/2023 14:30:00 | 31/03/2023 22:30:00 | 01-EE-091B | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  |  | 31-Mar | 31-Mar | 02-Apr | 02-Apr
CDUVDU2370 | Completed | Carryout Component Dropping | 03/04/2023 07:39:58 | 05/04/2023 07:22:33 | 31/03/2023 22:30:00 | 01/04/2023 06:30:00 | 01-EE-091B | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 47:43 | 39:43 |  | 31-Mar | 01-Apr | 03-Apr | 05-Apr
CDUVDU24750 | Completed | Hydrojetting of Tube Bundle | 09/04/2023 11:15:39 | 14/04/2023 05:15:51 | 13/04/2023 02:30:00 | 13/04/2023 20:30:00 | 01-EE-091B | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 18 | 18:00 | 114:00 | 96:00 |  | 13-Apr | 13-Apr | 09-Apr | 14-Apr
CDUVDU25780 | Completed | Air Drying | 13/04/2023 23:46:00 | 14/04/2023 07:46:14 | 13/04/2023 20:30:00 | 14/04/2023 04:30:00 | 01-EE-091B | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 8:00 | 0:00 |  | 13-Apr | 14-Apr | 13-Apr | 14-Apr
CDUVDU26200 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 14/04/2023 07:47:11 | 14/04/2023 07:48:56 | 14/04/2023 04:30:00 | 14/04/2023 10:30:00 | 01-EE-091B | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:02 |  | 5:58 | 14-Apr | 14-Apr | 14-Apr | 14-Apr
CDUVDU26480 | Completed | Shifting of bundle from bay | 14/04/2023 07:50:51 | 14/04/2023 07:51:29 | 14/04/2023 10:30:00 | 14/04/2023 13:30:00 | 01-EE-091B | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:01 |  | 2:59 | 14-Apr | 14-Apr | 14-Apr | 14-Apr
CDUVDU2650 | Completed | Carryout Bundle Pullout | 06/04/2023 18:33:55 | 06/04/2023 18:34:00 | 01/04/2023 06:30:00 | 01/04/2023 12:30:00 | 01-EE-091B | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 0:00 |  | 6:00 | 01-Apr | 01-Apr | 06-Apr | 06-Apr
CDUVDU26550 | Completed | Carryout Bundle Insertion | 14/04/2023 17:12:20 | 14/04/2023 17:12:24 | 14/04/2023 13:30:00 | 14/04/2023 21:30:00 | 01-EE-091B | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 0:00 |  | 8:00 | 14-Apr | 14-Apr | 14-Apr | 14-Apr
CDUVDU26910 | Completed | Channelhead Boxup | 15/04/2023 07:10:19 | 15/04/2023 07:10:32 | 14/04/2023 21:30:00 | 15/04/2023 03:30:00 | 01-EE-091B | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 14-Apr | 15-Apr | 15-Apr | 15-Apr
CDUVDU27130 | Completed | Test Ring Boxup | 16/04/2023 11:48:47 | 18/04/2023 11:12:49 | 15/04/2023 03:30:00 | 15/04/2023 11:30:00 | 01-EE-091B | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 47:24 | 39:24 |  | 15-Apr | 15-Apr | 16-Apr | 18-Apr
CDUVDU27470 | Completed | Carryout Shell Test | 17/04/2023 23:38:51 | 18/04/2023 17:42:04 | 15/04/2023 11:30:00 | 16/04/2023 02:30:00 | 01-EE-091B | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 18:03 | 3:03 |  | 15-Apr | 16-Apr | 17-Apr | 18-Apr
CDUVDU2750 | Completed | Pre Cleaning Inspection | 07/04/2023 07:36:19 | 07/04/2023 07:36:19 | 01/04/2023 12:30:00 | 01/04/2023 14:30:00 | 01-EE-091B | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  |  | 01-Apr | 01-Apr | 07-Apr | 07-Apr
CDUVDU27960 | Completed | Test Ring Drop Down | 19/04/2023 10:22:05 | 19/04/2023 10:22:12 | 16/04/2023 02:30:00 | 16/04/2023 08:30:00 | 01-EE-091B | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 16-Apr | 16-Apr | 19-Apr | 19-Apr
CDUVDU28140 | Completed | Floating Head Box-up | 19/04/2023 00:05:00 | 20/04/2023 02:58:00 | 16/04/2023 08:30:00 | 16/04/2023 14:30:00 | 01-EE-091B | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 26:53 | 20:53 |  | 16-Apr | 16-Apr | 19-Apr | 20-Apr
CDUVDU28370 | Completed | Tube Test | 20/04/2023 02:58:00 | 20/04/2023 02:58:00 | 16/04/2023 14:30:00 | 17/04/2023 05:30:00 | 01-EE-091B | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 15 | 15:00 | 0:00 |  |  | 16-Apr | 17-Apr | 20-Apr | 20-Apr
CDUVDU2850 | Completed | Bundle Shifting to Bay | 09/04/2023 07:28:44 | 09/04/2023 07:28:44 | 01/04/2023 14:30:00 | 01/04/2023 17:30:00 | 01-EE-091B | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  |  | 01-Apr | 01-Apr | 09-Apr | 09-Apr
CDUVDU28760 | Completed | Back Dome Boxup | 20/04/2023 02:58:00 | 20/04/2023 02:58:00 | 17/04/2023 05:30:00 | 17/04/2023 13:30:00 | 01-EE-091B | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 0:00 |  |  | 17-Apr | 17-Apr | 20-Apr | 20-Apr
CDUVDU28940 | Completed | Final Test | 20/04/2023 18:57:10 | 21/04/2023 06:43:47 | 17/04/2023 13:30:00 | 18/04/2023 04:30:00 | 01-EE-091B | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 11:47 |  | 3:13 | 17-Apr | 18-Apr | 20-Apr | 21-Apr
CDUVDU29300 | Completed | Deblinding | 22/04/2023 18:26:25 | 22/04/2023 18:26:31 | 18/04/2023 04:30:00 | 18/04/2023 12:30:00 | 01-EE-091B | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 18-Apr | 18-Apr | 22-Apr | 22-Apr
CDUVDU26570 | Completed | Hydrojetting of Tube Bundle | 09/04/2023 07:30:21 | 13/04/2023 05:29:22 | 14/04/2023 13:30:00 | 15/04/2023 07:30:00 | 01-EE-091D | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 18 | 18:00 | 93:59 | 75:59 |  | 14-Apr | 15-Apr | 09-Apr | 13-Apr
CDUVDU27310 | Completed | Air Drying | 18/04/2023 18:00:40 | 18/04/2023 18:00:50 | 15/04/2023 07:30:00 | 15/04/2023 15:30:00 | 01-EE-091D | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  | 8:00 | 15-Apr | 15-Apr | 18-Apr | 18-Apr
CDUVDU27630 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 18/04/2023 18:01:17 | 18/04/2023 18:01:23 | 15/04/2023 15:30:00 | 15/04/2023 21:30:00 | 01-EE-091D | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  | 6:00 | 15-Apr | 15-Apr | 18-Apr | 18-Apr
CDUVDU27780 | Completed | Shifting of bundle from bay | 18/04/2023 10:48:07 | 18/04/2023 17:57:18 | 15/04/2023 21:30:00 | 16/04/2023 00:30:00 | 01-EE-091D | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 7:09 | 4:09 |  | 15-Apr | 16-Apr | 18-Apr | 18-Apr
CDUVDU27880 | Completed | Carryout Bundle Insertion | 18/04/2023 19:30:06 | 18/04/2023 19:30:11 | 16/04/2023 00:30:00 | 16/04/2023 08:30:00 | 01-EE-091D | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 0:00 |  | 8:00 | 16-Apr | 16-Apr | 18-Apr | 18-Apr
CDUVDU28150 | Completed | Channelhead Boxup | 19/04/2023 06:53:13 | 19/04/2023 06:53:21 | 16/04/2023 08:30:00 | 16/04/2023 14:30:00 | 01-EE-091D | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 16-Apr | 16-Apr | 19-Apr | 19-Apr
CDUVDU28380 | Completed | Test Ring Boxup | 19/04/2023 18:17:54 | 19/04/2023 18:18:05 | 16/04/2023 14:30:00 | 16/04/2023 22:30:00 | 01-EE-091D | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  | 8:00 | 16-Apr | 16-Apr | 19-Apr | 19-Apr
CDUVDU28610 | Completed | Carryout Shell Test | 20/04/2023 02:51:00 | 20/04/2023 02:58:00 | 16/04/2023 22:30:00 | 17/04/2023 13:30:00 | 01-EE-091D | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 0:07 |  | 14:53 | 16-Apr | 17-Apr | 20-Apr | 20-Apr
CDUVDU28950 | Completed | Test Ring Drop Down | 21/04/2023 12:23:51 | 21/04/2023 19:00:28 | 17/04/2023 13:30:00 | 17/04/2023 19:30:00 | 01-EE-091D | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 6:37 | 0:37 |  | 17-Apr | 17-Apr | 21-Apr | 21-Apr
CDUVDU29100 | Completed | Floating Head Box-up | 21/04/2023 19:01:26 | 22/04/2023 18:27:16 | 17/04/2023 19:30:00 | 18/04/2023 01:30:00 | 01-EE-091D | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 23:26 | 17:26 |  | 17-Apr | 18-Apr | 21-Apr | 22-Apr
CDUVDU29190 | Completed | Tube Test | 22/04/2023 23:11:13 | 23/04/2023 06:45:54 | 18/04/2023 01:30:00 | 18/04/2023 16:30:00 | 01-EE-091D | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 15 | 15:00 | 7:35 |  | 7:25 | 18-Apr | 18-Apr | 22-Apr | 23-Apr
CDUVDU29490 | Completed | Back Dome Boxup | 23/04/2023 09:46:31 | 23/04/2023 18:11:00 | 18/04/2023 16:30:00 | 19/04/2023 00:30:00 | 01-EE-091D | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 8:24 | 0:24 |  | 18-Apr | 19-Apr | 23-Apr | 23-Apr
CDUVDU29640 | Completed | Final Test | 24/04/2023 00:41:59 | 24/04/2023 11:32:51 | 19/04/2023 00:30:00 | 19/04/2023 15:30:00 | 01-EE-091D | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 10:51 |  | 4:09 | 19-Apr | 19-Apr | 24-Apr | 24-Apr
CDUVDU29830 | Completed | Deblinding | 24/04/2023 18:28:40 | 25/04/2023 04:51:13 | 19/04/2023 15:30:00 | 19/04/2023 23:30:00 | 01-EE-091D | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 10:23 | 2:23 |  | 19-Apr | 19-Apr | 24-Apr | 25-Apr
CDUVDU3760 | Completed | Blinding As Per Blind List | 02/04/2023 06:34:33 | 02/04/2023 06:34:33 | 01/04/2023 14:30:00 | 01/04/2023 22:30:00 | 01-EE-091D | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  |  | 01-Apr | 01-Apr | 02-Apr | 02-Apr
CDUVDU4330 | Completed | Carryout Component Dropping | 03/04/2023 07:42:06 | 06/04/2023 07:46:52 | 01/04/2023 22:30:00 | 02/04/2023 06:30:00 | 01-EE-091D | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 72:05 | 64:05 |  | 01-Apr | 02-Apr | 03-Apr | 06-Apr
CDUVDU4860 | Completed | Carryout Bundle Pullout | 07/04/2023 19:10:46 | 08/04/2023 07:41:20 | 02/04/2023 06:30:00 | 02/04/2023 12:30:00 | 01-EE-091D | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 12:31 | 6:31 |  | 02-Apr | 02-Apr | 07-Apr | 08-Apr
CDUVDU5280 | Completed | Pre Cleaning Inspection | 08/04/2023 07:42:03 | 08/04/2023 07:42:03 | 02/04/2023 12:30:00 | 02/04/2023 14:30:00 | 01-EE-091D | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  |  | 02-Apr | 02-Apr | 08-Apr | 08-Apr
CDUVDU6020 | Completed | Bundle Shifting to Bay | 09/04/2023 07:30:21 | 09/04/2023 07:30:25 | 02/04/2023 14:30:00 | 02/04/2023 17:30:00 | 01-EE-091D | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 02-Apr | 02-Apr | 09-Apr | 09-Apr
CDUVDU30700 | Completed | Blinding As Per Blind List | 31/03/2023 00:31:00 | 31/03/2023 06:31:00 | 01/04/2023 15:00:00 | 01/04/2023 23:00:00 | 01-EE-101 | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 6:00 |  | 2:00 | 01-Apr | 01-Apr | 31-Mar | 31-Mar
CDUVDU30710 | Completed | Carryout Component Dropping | 31/03/2023 00:31:00 | 31/03/2023 06:31:00 | 01/04/2023 23:00:00 | 02/04/2023 07:00:00 | 01-EE-101 | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 6:00 |  | 2:00 | 01-Apr | 02-Apr | 31-Mar | 31-Mar
CDUVDU30720 | Completed | Carryout Bundle Pullout | 31/03/2023 00:31:00 | 31/03/2023 00:31:00 | 02/04/2023 07:00:00 | 02/04/2023 13:00:00 | 01-EE-101 | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 0:00 |  |  | 02-Apr | 02-Apr | 31-Mar | 31-Mar
CDUVDU30730 | Completed | Pre Cleaning Inspection | 31/03/2023 00:31:00 | 31/03/2023 00:31:00 | 02/04/2023 13:00:00 | 02/04/2023 15:00:00 | 01-EE-101 | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  |  | 02-Apr | 02-Apr | 31-Mar | 31-Mar
CDUVDU30740 | Completed | Bundle Shifting to Bay | 31/03/2023 00:31:00 | 31/03/2023 00:31:00 | 02/04/2023 15:00:00 | 02/04/2023 18:00:00 | 01-EE-101 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  |  | 02-Apr | 02-Apr | 31-Mar | 31-Mar
CDUVDU30750 | Completed | Hydrojetting of Tube Bundle | 31/03/2023 00:31:00 | 31/03/2023 00:31:00 | 02/04/2023 18:00:00 | 03/04/2023 07:00:00 | 01-EE-101 | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 13 | 13:00 | 0:00 |  |  | 02-Apr | 03-Apr | 31-Mar | 31-Mar
CDUVDU30760 | Completed | Air Drying | 17/04/2023 09:27:01 | 17/04/2023 09:27:06 | 03/04/2023 07:00:00 | 03/04/2023 13:00:00 | 01-EE-101 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 03-Apr | 03-Apr | 17-Apr | 17-Apr
CDUVDU30770 | Completed | Carryout Bundle Insertion | 17/04/2023 09:27:31 | 17/04/2023 09:27:42 | 03/04/2023 22:00:00 | 04/04/2023 06:00:00 | 01-EE-101 | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 0:00 |  | 8:00 | 03-Apr | 04-Apr | 17-Apr | 17-Apr
CDUVDU30780 | Completed | Channelhead Boxup | 17/04/2023 09:29:40 | 17/04/2023 09:29:45 | 04/04/2023 06:00:00 | 04/04/2023 12:00:00 | 01-EE-101 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 04-Apr | 04-Apr | 17-Apr | 17-Apr
CDUVDU30790 | Completed | Test Ring Boxup | 17/04/2023 09:31:07 | 17/04/2023 09:31:12 | 04/04/2023 12:00:00 | 04/04/2023 20:00:00 | 01-EE-101 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  | 8:00 | 04-Apr | 04-Apr | 17-Apr | 17-Apr
CDUVDU30800 | Completed | Carryout Shell Test | 17/04/2023 09:31:36 | 17/04/2023 09:31:41 | 04/04/2023 20:00:00 | 05/04/2023 11:00:00 | 01-EE-101 | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 0:00 |  | 15:00 | 04-Apr | 05-Apr | 17-Apr | 17-Apr
CDUVDU30810 | Completed | Test Ring Drop Down | 17/04/2023 09:31:58 | 18/04/2023 12:27:06 | 05/04/2023 11:00:00 | 05/04/2023 17:00:00 | 01-EE-101 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 26:55 | 20:55 |  | 05-Apr | 05-Apr | 17-Apr | 18-Apr
CDUVDU30820 | Completed | Floating Head Box-up | 20/04/2023 09:06:12 | 20/04/2023 09:06:26 | 05/04/2023 17:00:00 | 05/04/2023 23:00:00 | 01-EE-101 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 05-Apr | 05-Apr | 20-Apr | 20-Apr
CDUVDU30830 | Completed | Tube Test | 20/04/2023 11:15:33 | 20/04/2023 19:43:36 | 05/04/2023 23:00:00 | 06/04/2023 14:00:00 | 01-EE-101 | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 15 | 15:00 | 8:28 |  | 6:32 | 05-Apr | 06-Apr | 20-Apr | 20-Apr
CDUVDU30840 | Completed | Back Dome Boxup | 20/04/2023 19:43:55 | 21/04/2023 12:27:12 | 06/04/2023 14:00:00 | 06/04/2023 22:00:00 | 01-EE-101 | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 16:43 | 8:43 |  | 06-Apr | 06-Apr | 20-Apr | 21-Apr
CDUVDU30850 | Completed | Final Test | 22/04/2023 09:18:11 | 22/04/2023 09:18:32 | 06/04/2023 22:00:00 | 07/04/2023 13:00:00 | 01-EE-101 | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 0:00 |  | 15:00 | 06-Apr | 07-Apr | 22-Apr | 22-Apr
CDUVDU30860 | Completed | Deblinding | 22/04/2023 09:18:43 | 23/04/2023 19:11:39 | 07/04/2023 13:00:00 | 07/04/2023 21:00:00 | 01-EE-101 | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 33:53 | 25:53 |  | 07-Apr | 07-Apr | 22-Apr | 23-Apr
CDUVDU30870 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 17/04/2023 12:50:53 | 17/04/2023 12:50:56 | 03/04/2023 13:00:00 | 03/04/2023 19:00:00 | 01-EE-101 | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  | 6:00 | 03-Apr | 03-Apr | 17-Apr | 17-Apr
CDUVDU30880 | Completed | Shifting of bundle from bay | 18/04/2023 12:27:40 | 18/04/2023 12:27:45 | 03/04/2023 19:00:00 | 03/04/2023 22:00:00 | 01-EE-101 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 03-Apr | 03-Apr | 18-Apr | 18-Apr
CDUVDU17620 | Completed | Hydrojetting of Tube Bundle | 05/04/2023 18:19:00 | 06/04/2023 07:15:16 | 10/04/2023 00:30:00 | 11/04/2023 02:30:00 | 01-EE-040 | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 26 | 26:00 | 12:56 |  | 13:04 | 10-Apr | 11-Apr | 05-Apr | 06-Apr
CDUVDU20330 | Completed | Air Drying | 05/04/2023 23:15:00 | 06/04/2023 07:15:36 | 11/04/2023 02:30:00 | 11/04/2023 10:30:00 | 01-EE-040 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 8:01 | 0:01 |  | 11-Apr | 11-Apr | 05-Apr | 06-Apr
CDUVDU20990 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 05/04/2023 22:21:41 | 05/04/2023 22:21:41 | 11/04/2023 10:30:00 | 11/04/2023 16:30:00 | 01-EE-040 | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  |  | 11-Apr | 11-Apr | 05-Apr | 05-Apr
CDUVDU21660 | Completed | Shifting of bundle from bay | 06/04/2023 04:15:00 | 06/04/2023 07:16:07 | 11/04/2023 16:30:00 | 11/04/2023 19:30:00 | 01-EE-040 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 3:01 | 0:01 |  | 11-Apr | 11-Apr | 06-Apr | 06-Apr
CDUVDU22020 | Completed | Carryout Bundle Insertion | 06/04/2023 00:15:00 | 06/04/2023 07:16:00 | 11/04/2023 19:30:00 | 12/04/2023 03:30:00 | 01-EE-040 | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 7:01 |  | 0:59 | 11-Apr | 12-Apr | 06-Apr | 06-Apr
CDUVDU2230 | Completed | Blinding As Per Blind List | 31/03/2023 22:07:00 | 01/04/2023 01:07:00 | 31/03/2023 14:30:00 | 31/03/2023 22:30:00 | 01-EE-040 | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 3:00 |  | 5:00 | 31-Mar | 31-Mar | 31-Mar | 01-Apr
CDUVDU22800 | Completed | Channelhead Boxup | 08/04/2023 07:45:37 | 08/04/2023 07:45:37 | 12/04/2023 03:30:00 | 12/04/2023 09:30:00 | 01-EE-040 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 12-Apr | 12-Apr | 08-Apr | 08-Apr
CDUVDU23260 | Completed | Test Ring Boxup | 08/04/2023 15:51:00 | 08/04/2023 15:51:12 | 12/04/2023 09:30:00 | 12/04/2023 17:30:00 | 01-EE-040 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  | 8:00 | 12-Apr | 12-Apr | 08-Apr | 08-Apr
CDUVDU24010 | Completed | Carryout Shell Test | 09/04/2023 06:49:29 | 09/04/2023 06:49:29 | 12/04/2023 17:30:00 | 13/04/2023 08:30:00 | 01-EE-040 | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 0:00 |  |  | 12-Apr | 13-Apr | 09-Apr | 09-Apr
CDUVDU25140 | Completed | Test Ring Drop Down | 09/04/2023 10:17:38 | 09/04/2023 10:17:48 | 13/04/2023 08:30:00 | 13/04/2023 14:30:00 | 01-EE-040 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 13-Apr | 13-Apr | 09-Apr | 09-Apr
CDUVDU25460 | Completed | Floating Head Box-up | 09/04/2023 11:16:47 | 09/04/2023 11:16:47 | 13/04/2023 14:30:00 | 13/04/2023 20:30:00 | 01-EE-040 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 13-Apr | 13-Apr | 09-Apr | 09-Apr
CDUVDU2560 | Completed | Carryout Component Dropping | 01/04/2023 10:08:03 | 01/04/2023 15:55:48 | 31/03/2023 22:30:00 | 01/04/2023 06:30:00 | 01-EE-040 | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 5:48 |  | 2:12 | 31-Mar | 01-Apr | 01-Apr | 01-Apr
CDUVDU25760 | Completed | Tube Test | 09/04/2023 11:16:47 | 09/04/2023 11:16:47 | 13/04/2023 20:30:00 | 14/04/2023 11:30:00 | 01-EE-040 | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 15 | 15:00 | 0:00 |  |  | 13-Apr | 14-Apr | 09-Apr | 09-Apr
CDUVDU26510 | Completed | Back Dome Boxup | 09/04/2023 11:16:47 | 09/04/2023 11:16:47 | 14/04/2023 11:30:00 | 14/04/2023 19:30:00 | 01-EE-040 | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 0:00 |  |  | 14-Apr | 14-Apr | 09-Apr | 09-Apr
CDUVDU26870 | Completed | Final Test | 09/04/2023 11:16:47 | 09/04/2023 11:16:47 | 14/04/2023 19:30:00 | 15/04/2023 10:30:00 | 01-EE-040 | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 0:00 |  |  | 14-Apr | 15-Apr | 09-Apr | 09-Apr
CDUVDU2690 | Completed | Carryout Bundle Pullout | 01/04/2023 15:56:02 | 01/04/2023 15:56:07 | 01/04/2023 06:30:00 | 01/04/2023 12:30:00 | 01-EE-040 | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 0:00 |  | 6:00 | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU27440 | Completed | Deblinding | 14/04/2023 04:55:54 | 14/04/2023 04:56:03 | 15/04/2023 10:30:00 | 15/04/2023 18:30:00 | 01-EE-040 | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 15-Apr | 15-Apr | 14-Apr | 14-Apr
CDUVDU2970 | Completed | Pre Cleaning Inspection | 01/04/2023 16:41:24 | 01/04/2023 16:41:30 | 01/04/2023 12:30:00 | 01/04/2023 14:30:00 | 01-EE-040 | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  | 2:00 | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU3620 | Completed | Bundle Shifting to Bay | 03/04/2023 06:00:27 | 03/04/2023 06:00:27 | 01/04/2023 14:30:00 | 01/04/2023 17:30:00 | 01-EE-040 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  |  | 01-Apr | 01-Apr | 03-Apr | 03-Apr
CDUVDU16770 | Completed | Hydrojetting of Tube Bundle | 07/04/2023 00:59:00 | 08/04/2023 10:00:00 | 09/04/2023 15:30:00 | 09/04/2023 22:30:00 | 01-EE-027A | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 7 | 7:00 | 33:01 | 26:01 |  | 09-Apr | 09-Apr | 07-Apr | 08-Apr
CDUVDU17440 | Completed | Air Drying | 11/04/2023 17:26:03 | 11/04/2023 17:26:08 | 09/04/2023 22:30:00 | 10/04/2023 01:30:00 | 01-EE-027A | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 09-Apr | 10-Apr | 11-Apr | 11-Apr
CDUVDU17710 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 10/04/2023 03:05:23 | 10/04/2023 03:05:23 | 10/04/2023 01:30:00 | 10/04/2023 07:30:00 | 01-EE-027A | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  |  | 10-Apr | 10-Apr | 10-Apr | 10-Apr
CDUVDU18390 | Completed | Shifting of bundle from bay | 11/04/2023 17:26:15 | 11/04/2023 17:26:19 | 10/04/2023 07:30:00 | 10/04/2023 10:30:00 | 01-EE-027A | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 10-Apr | 10-Apr | 11-Apr | 11-Apr
CDUVDU18630 | Completed | Carryout Bundle Insertion | 11/04/2023 17:26:27 | 11/04/2023 17:42:59 | 10/04/2023 10:30:00 | 10/04/2023 16:30:00 | 01-EE-027A | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 6 | 6:00 | 0:17 |  | 5:43 | 10-Apr | 10-Apr | 11-Apr | 11-Apr
CDUVDU19190 | Completed | Channelhead Boxup | 11/04/2023 17:43:15 | 15/04/2023 03:34:17 | 10/04/2023 16:30:00 | 10/04/2023 22:30:00 | 01-EE-027A | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 81:51 | 75:51 |  | 10-Apr | 10-Apr | 11-Apr | 15-Apr
CDUVDU19740 | Completed | Test Ring Boxup | 14/04/2023 15:34:00 | 15/04/2023 01:00:00 | 10/04/2023 22:30:00 | 11/04/2023 06:30:00 | 01-EE-027A | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 9:26 | 1:26 |  | 10-Apr | 11-Apr | 14-Apr | 15-Apr
CDUVDU20660 | Completed | Carryout Shell Test | 15/04/2023 05:40:19 | 16/04/2023 06:41:15 | 11/04/2023 06:30:00 | 11/04/2023 14:30:00 | 01-EE-027A | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 8 | 8:00 | 25:01 | 17:01 |  | 11-Apr | 11-Apr | 15-Apr | 16-Apr
CDUVDU21560 | Completed | Test Ring Drop Down | 16/04/2023 00:59:30 | 16/04/2023 06:41:26 | 11/04/2023 14:30:00 | 11/04/2023 18:30:00 | 01-EE-027A | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 5:42 | 1:42 |  | 11-Apr | 11-Apr | 16-Apr | 16-Apr
CDUVDU21990 | Completed | Floating Head Box-up | 16/04/2023 17:34:23 | 17/04/2023 01:51:55 | 11/04/2023 18:30:00 | 11/04/2023 22:30:00 | 01-EE-027A | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 8:18 | 4:18 |  | 11-Apr | 11-Apr | 16-Apr | 17-Apr
CDUVDU22280 | Completed | Tube Test | 17/04/2023 01:52:10 | 18/04/2023 15:13:45 | 11/04/2023 22:30:00 | 12/04/2023 06:30:00 | 01-EE-027A | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 8 | 8:00 | 37:22 | 29:22 |  | 11-Apr | 12-Apr | 17-Apr | 18-Apr
CDUVDU23080 | Completed | Back Dome Boxup | 20/04/2023 12:15:59 | 20/04/2023 12:16:05 | 12/04/2023 06:30:00 | 12/04/2023 10:30:00 | 01-EE-027A | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  | 4:00 | 12-Apr | 12-Apr | 20-Apr | 20-Apr
CDUVDU23400 | Completed | Final Test | 20/04/2023 02:56:22 | 21/04/2023 09:16:11 | 12/04/2023 10:30:00 | 12/04/2023 18:30:00 | 01-EE-027A | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 8 | 8:00 | 30:20 | 22:20 |  | 12-Apr | 12-Apr | 20-Apr | 21-Apr
CDUVDU24150 | Completed | Deblinding | 21/04/2023 12:35:03 | 23/04/2023 09:41:33 | 12/04/2023 18:30:00 | 13/04/2023 00:30:00 | 01-EE-027A | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 6 | 6:00 | 45:07 | 39:07 |  | 12-Apr | 13-Apr | 21-Apr | 23-Apr
CDUVDU5920 | Completed | Blinding As Per Blind List | 02/04/2023 06:13:06 | 02/04/2023 06:13:10 | 02/04/2023 14:30:00 | 02/04/2023 20:30:00 | 01-EE-027A | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 6 | 6:00 | 0:00 |  | 6:00 | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU6310 | Completed | Carryout Component Dropping | 03/04/2023 04:52:21 | 03/04/2023 04:52:27 | 02/04/2023 20:30:00 | 03/04/2023 00:30:00 | 01-EE-027A | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 4 | 4:00 | 0:00 |  | 4:00 | 02-Apr | 03-Apr | 03-Apr | 03-Apr
CDUVDU6710 | Completed | Carryout Bundle Pullout | 05/04/2023 07:37:10 | 05/04/2023 07:37:14 | 03/04/2023 00:30:00 | 03/04/2023 06:30:00 | 01-EE-027A | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 0:00 |  | 6:00 | 03-Apr | 03-Apr | 05-Apr | 05-Apr
CDUVDU6970 | Completed | Pre Cleaning Inspection | 05/04/2023 22:25:38 | 05/04/2023 22:25:38 | 03/04/2023 06:30:00 | 03/04/2023 08:30:00 | 01-EE-027A | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  |  | 03-Apr | 03-Apr | 05-Apr | 05-Apr
CDUVDU7140 | Completed | Bundle Shifting to Bay | 06/04/2023 01:23:00 | 06/04/2023 07:23:22 | 03/04/2023 08:30:00 | 03/04/2023 11:30:00 | 01-EE-027A | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 6:00 | 3:00 |  | 03-Apr | 03-Apr | 06-Apr | 06-Apr
CDUVDU17450 | Completed | Hydrojetting of Tube Bundle | 08/04/2023 13:02:46 | 08/04/2023 13:02:50 | 09/04/2023 22:30:00 | 10/04/2023 05:30:00 | 01-EE-027B | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 7 | 7:00 | 0:00 |  | 7:00 | 09-Apr | 10-Apr | 08-Apr | 08-Apr
CDUVDU18200 | Completed | Air Drying | 11/04/2023 17:25:16 | 11/04/2023 17:25:21 | 10/04/2023 05:30:00 | 10/04/2023 08:30:00 | 01-EE-027B | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 10-Apr | 10-Apr | 11-Apr | 11-Apr
CDUVDU18460 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 10/04/2023 03:04:01 | 10/04/2023 03:04:01 | 10/04/2023 08:30:00 | 10/04/2023 14:30:00 | 01-EE-027B | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  |  | 10-Apr | 10-Apr | 10-Apr | 10-Apr
CDUVDU19050 | Completed | Shifting of bundle from bay | 11/04/2023 17:25:28 | 11/04/2023 17:25:36 | 10/04/2023 14:30:00 | 10/04/2023 17:30:00 | 01-EE-027B | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 10-Apr | 10-Apr | 11-Apr | 11-Apr
CDUVDU19290 | Completed | Carryout Bundle Insertion | 11/04/2023 17:25:46 | 11/04/2023 17:25:51 | 10/04/2023 17:30:00 | 10/04/2023 23:30:00 | 01-EE-027B | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 6 | 6:00 | 0:00 |  | 6:00 | 10-Apr | 10-Apr | 11-Apr | 11-Apr
CDUVDU19950 | Completed | Channelhead Boxup | 11/04/2023 17:43:26 | 11/04/2023 17:43:51 | 10/04/2023 23:30:00 | 11/04/2023 05:30:00 | 01-EE-027B | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 10-Apr | 11-Apr | 11-Apr | 11-Apr
CDUVDU20550 | Completed | Test Ring Boxup | 15/04/2023 03:35:01 | 15/04/2023 05:41:08 | 11/04/2023 05:30:00 | 11/04/2023 13:30:00 | 01-EE-027B | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 2:06 |  | 5:54 | 11-Apr | 11-Apr | 15-Apr | 15-Apr
CDUVDU21270 | Completed | Carryout Shell Test | 15/04/2023 05:41:21 | 16/04/2023 17:35:45 | 11/04/2023 13:30:00 | 11/04/2023 21:30:00 | 01-EE-027B | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 8 | 8:00 | 35:54 | 27:54 |  | 11-Apr | 11-Apr | 15-Apr | 16-Apr
CDUVDU22140 | Completed | Test Ring Drop Down | 16/04/2023 00:59:52 | 17/04/2023 17:22:23 | 11/04/2023 21:30:00 | 12/04/2023 01:30:00 | 01-EE-027B | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 40:23 | 36:23 |  | 11-Apr | 12-Apr | 16-Apr | 17-Apr
CDUVDU22460 | Completed | Floating Head Box-up | 16/04/2023 17:36:17 | 17/04/2023 17:22:43 | 12/04/2023 01:30:00 | 12/04/2023 05:30:00 | 01-EE-027B | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 23:46 | 19:46 |  | 12-Apr | 12-Apr | 16-Apr | 17-Apr
CDUVDU23000 | Completed | Tube Test | 17/04/2023 02:17:28 | 18/04/2023 15:14:31 | 12/04/2023 05:30:00 | 12/04/2023 13:30:00 | 01-EE-027B | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 8 | 8:00 | 36:57 | 28:57 |  | 12-Apr | 12-Apr | 17-Apr | 18-Apr
CDUVDU23640 | Completed | Back Dome Boxup | 20/04/2023 02:58:00 | 20/04/2023 02:58:00 | 12/04/2023 13:30:00 | 12/04/2023 17:30:00 | 01-EE-027B | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  |  | 12-Apr | 12-Apr | 20-Apr | 20-Apr
CDUVDU24030 | Completed | Final Test | 20/04/2023 02:58:00 | 21/04/2023 12:35:43 | 12/04/2023 17:30:00 | 13/04/2023 01:30:00 | 01-EE-027B | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 8 | 8:00 | 33:38 | 25:38 |  | 12-Apr | 13-Apr | 20-Apr | 21-Apr
CDUVDU24610 | Completed | Deblinding | 21/04/2023 12:35:54 | 23/04/2023 09:41:52 | 13/04/2023 01:30:00 | 13/04/2023 07:30:00 | 01-EE-027B | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 6 | 6:00 | 45:06 | 39:06 |  | 13-Apr | 13-Apr | 21-Apr | 23-Apr
CDUVDU5930 | Completed | Blinding As Per Blind List | 03/04/2023 04:55:17 | 03/04/2023 04:55:22 | 02/04/2023 14:30:00 | 02/04/2023 20:30:00 | 01-EE-027B | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 6 | 6:00 | 0:00 |  | 6:00 | 02-Apr | 02-Apr | 03-Apr | 03-Apr
CDUVDU6320 | Completed | Carryout Component Dropping | 03/04/2023 04:55:48 | 03/04/2023 04:55:53 | 02/04/2023 20:30:00 | 03/04/2023 00:30:00 | 01-EE-027B | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 4 | 4:00 | 0:00 |  | 4:00 | 02-Apr | 03-Apr | 03-Apr | 03-Apr
CDUVDU6720 | Completed | Carryout Bundle Pullout | 05/04/2023 07:37:44 | 05/04/2023 07:37:44 | 03/04/2023 00:30:00 | 03/04/2023 06:30:00 | 01-EE-027B | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 0:00 |  |  | 03-Apr | 03-Apr | 05-Apr | 05-Apr
CDUVDU6980 | Completed | Pre Cleaning Inspection | 05/04/2023 22:26:03 | 05/04/2023 22:26:03 | 03/04/2023 06:30:00 | 03/04/2023 08:30:00 | 01-EE-027B | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  |  | 03-Apr | 03-Apr | 05-Apr | 05-Apr
CDUVDU7150 | Completed | Bundle Shifting to Bay | 06/04/2023 01:24:00 | 06/04/2023 07:24:17 | 03/04/2023 08:30:00 | 03/04/2023 11:30:00 | 01-EE-027B | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 6:00 | 3:00 |  | 03-Apr | 03-Apr | 06-Apr | 06-Apr
CDU15610 | Completed | Blinding | 30/03/2023 05:22:15 | 30/03/2023 05:22:15 | 02/04/2023 14:30:00 | 03/04/2023 14:30:00 | 01-EE-059 | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 24 | 24:00 | 0:00 |  |  | 02-Apr | 03-Apr | 30-Mar | 30-Mar
CDU17890 | Completed | Opening of shell covers, dropping of channel head | 30/03/2023 05:22:15 | 30/03/2023 05:22:15 | 03/04/2023 14:30:00 | 04/04/2023 02:30:00 | 01-EE-059 | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 12 | 12:00 | 0:00 |  |  | 03-Apr | 04-Apr | 30-Mar | 30-Mar
CDU19020 | Completed | Tube bundle pull out | 30/03/2023 05:22:15 | 30/03/2023 05:22:15 | 04/04/2023 02:30:00 | 04/04/2023 14:30:00 | 01-EE-059 | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 12 | 12:00 | 0:00 |  |  | 04-Apr | 04-Apr | 30-Mar | 30-Mar
CDU19060 | Completed | UT Gauging | 30/03/2023 05:22:15 | 30/03/2023 05:22:15 | 04/04/2023 02:30:00 | 04/04/2023 14:30:00 | 01-EE-059 | EXCHANGER | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  |  | 04-Apr | 04-Apr | 30-Mar | 30-Mar
CDU20190 | Completed | Pre cleaning inspection | 30/03/2023 05:22:15 | 30/03/2023 05:22:15 | 04/04/2023 14:30:00 | 04/04/2023 18:30:00 | 01-EE-059 | EXCHANGER | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  |  | 04-Apr | 04-Apr | 30-Mar | 30-Mar
CDU20600 | Completed | Hydrojetting of tubes, channel head, channel covers, shell | 09/04/2023 11:16:55 | 10/04/2023 07:17:31 | 04/04/2023 18:30:00 | 05/04/2023 18:30:00 | 01-EE-059 | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 24 | 24:00 | 20:01 |  | 3:59 | 04-Apr | 05-Apr | 09-Apr | 10-Apr
CDU22550 | Completed | Post cleaning inspection | 10/04/2023 07:17:16 | 12/04/2023 16:39:24 | 05/04/2023 18:30:00 | 05/04/2023 21:30:00 | 01-EE-059 | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 3 | 3:00 | 57:22 | 54:22 |  | 05-Apr | 05-Apr | 10-Apr | 12-Apr
CDU22750 | Completed | Carry out RFET | 12/04/2023 16:41:48 | 12/04/2023 16:41:52 | 05/04/2023 21:30:00 | 06/04/2023 21:30:00 | 01-EE-059 | EXCHANGER | 100 | INSPECTION |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 05-Apr | 06-Apr | 12-Apr | 12-Apr
CDU24370 | Completed | Carry out Repair if Any | 12/04/2023 16:42:02 | 12/04/2023 16:42:07 | 06/04/2023 21:30:00 | 07/04/2023 21:30:00 | 01-EE-059 | EXCHANGER | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 06-Apr | 07-Apr | 12-Apr | 12-Apr
CDU25670 | Completed | Insertion of Tube bundle | 12/04/2023 16:42:16 | 12/04/2023 16:42:21 | 07/04/2023 21:30:00 | 08/04/2023 03:30:00 | 01-EE-059 | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 6 | 6:00 | 0:00 |  | 6:00 | 07-Apr | 08-Apr | 12-Apr | 12-Apr
CDU26070 | Completed | Shell Test | 12/04/2023 16:42:38 | 12/04/2023 16:42:43 | 08/04/2023 03:30:00 | 09/04/2023 03:30:00 | 01-EE-059 | EXCHANGER | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 08-Apr | 09-Apr | 12-Apr | 12-Apr
CDU27220 | Completed | Shell test inspection | 12/04/2023 16:42:58 | 12/04/2023 16:43:04 | 09/04/2023 03:30:00 | 09/04/2023 07:30:00 | 01-EE-059 | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 4 | 4:00 | 0:00 |  | 4:00 | 09-Apr | 09-Apr | 12-Apr | 12-Apr
CDU27340 | Completed | Tube test | 16/04/2023 19:16:47 | 16/04/2023 19:17:07 | 09/04/2023 07:30:00 | 10/04/2023 07:30:00 | 01-EE-059 | EXCHANGER | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 09-Apr | 10-Apr | 16-Apr | 16-Apr
CDU28110 | Completed | Tube test inspection | 16/04/2023 19:16:59 | 16/04/2023 19:17:12 | 10/04/2023 07:30:00 | 10/04/2023 11:30:00 | 01-EE-059 | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 4 | 4:00 | 0:00 |  | 4:00 | 10-Apr | 10-Apr | 16-Apr | 16-Apr
CDU28220 | Completed | Box Up Test | 17/04/2023 01:39:04 | 17/04/2023 01:39:07 | 10/04/2023 11:30:00 | 11/04/2023 11:30:00 | 01-EE-059 | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 24 | 24:00 | 0:00 |  | 24:00 | 10-Apr | 11-Apr | 17-Apr | 17-Apr
CDU28850 | Completed | Box Up Test Inspection | 18/04/2023 01:15:08 | 18/04/2023 01:15:13 | 11/04/2023 11:30:00 | 11/04/2023 15:30:00 | 01-EE-059 | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 4 | 4:00 | 0:00 |  | 4:00 | 11-Apr | 11-Apr | 18-Apr | 18-Apr
CDU28950 | Completed | Deblinding | 18/04/2023 15:16:37 | 18/04/2023 15:16:57 | 11/04/2023 15:30:00 | 12/04/2023 15:30:00 | 01-EE-059 | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  | 24:00 | 11-Apr | 12-Apr | 18-Apr | 18-Apr
CDUVDU11070 | Completed | Hydrojetting of Tube Bundle | 06/04/2023 06:56:01 | 07/04/2023 22:07:53 | 06/04/2023 05:30:00 | 07/04/2023 07:30:00 | 01-EE-006 | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 26 | 26:00 | 39:12 | 13:12 |  | 06-Apr | 07-Apr | 06-Apr | 07-Apr
CDUVDU12750 | Completed | Air Drying | 07/04/2023 22:07:53 | 07/04/2023 22:07:53 | 07/04/2023 07:30:00 | 07/04/2023 15:30:00 | 01-EE-006 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  |  | 07-Apr | 07-Apr | 07-Apr | 07-Apr
CDUVDU13220 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 07/04/2023 22:07:53 | 07/04/2023 22:07:53 | 07/04/2023 15:30:00 | 07/04/2023 21:30:00 | 01-EE-006 | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  |  | 07-Apr | 07-Apr | 07-Apr | 07-Apr
CDUVDU13600 | Completed | Shifting of bundle from bay | 08/04/2023 06:54:40 | 08/04/2023 06:54:54 | 07/04/2023 21:30:00 | 08/04/2023 00:30:00 | 01-EE-006 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 07-Apr | 08-Apr | 08-Apr | 08-Apr
CDUVDU13710 | Completed | Carryout Bundle Insertion | 08/04/2023 06:54:40 | 08/04/2023 06:54:54 | 08/04/2023 00:30:00 | 08/04/2023 08:30:00 | 01-EE-006 | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 0:00 |  | 8:00 | 08-Apr | 08-Apr | 08-Apr | 08-Apr
CDUVDU14240 | Completed | Channelhead Boxup | 08/04/2023 07:44:21 | 08/04/2023 07:44:21 | 08/04/2023 08:30:00 | 08/04/2023 14:30:00 | 01-EE-006 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 08-Apr | 08-Apr | 08-Apr | 08-Apr
CDUVDU14760 | Completed | Test Ring Boxup | 08/04/2023 07:44:21 | 08/04/2023 07:44:21 | 08/04/2023 14:30:00 | 08/04/2023 22:30:00 | 01-EE-006 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  |  | 08-Apr | 08-Apr | 08-Apr | 08-Apr
CDUVDU15270 | Completed | Carryout Shell Test | 09/04/2023 06:52:37 | 09/04/2023 14:53:48 | 08/04/2023 22:30:00 | 09/04/2023 13:30:00 | 01-EE-006 | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 8:01 |  | 6:59 | 08-Apr | 09-Apr | 09-Apr | 09-Apr
CDUVDU16540 | Completed | Test Ring Drop Down | 09/04/2023 15:04:40 | 10/04/2023 06:49:28 | 09/04/2023 13:30:00 | 09/04/2023 19:30:00 | 01-EE-006 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 15:45 | 9:45 |  | 09-Apr | 09-Apr | 09-Apr | 10-Apr
CDUVDU17130 | Completed | Floating Head Box-up | 10/04/2023 06:49:38 | 10/04/2023 09:56:52 | 09/04/2023 19:30:00 | 10/04/2023 01:30:00 | 01-EE-006 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 3:07 |  | 2:53 | 09-Apr | 10-Apr | 10-Apr | 10-Apr
CDUVDU17690 | Completed | Tube Test | 10/04/2023 10:00:49 | 10/04/2023 19:26:13 | 10/04/2023 01:30:00 | 10/04/2023 16:30:00 | 01-EE-006 | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 15 | 15:00 | 9:25 |  | 5:35 | 10-Apr | 10-Apr | 10-Apr | 10-Apr
CDUVDU19180 | Completed | Back Dome Boxup | 10/04/2023 19:26:40 | 11/04/2023 06:40:49 | 10/04/2023 16:30:00 | 11/04/2023 00:30:00 | 01-EE-006 | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 11:14 | 3:14 |  | 10-Apr | 11-Apr | 10-Apr | 11-Apr
CDUVDU20030 | Completed | Final Test | 11/04/2023 10:39:40 | 11/04/2023 17:34:58 | 11/04/2023 00:30:00 | 11/04/2023 15:30:00 | 01-EE-006 | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 6:55 |  | 8:05 | 11-Apr | 11-Apr | 11-Apr | 11-Apr
CDUVDU21600 | Completed | Deblinding | 14/04/2023 04:31:41 | 14/04/2023 04:31:44 | 11/04/2023 15:30:00 | 11/04/2023 23:30:00 | 01-EE-006 | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 11-Apr | 11-Apr | 14-Apr | 14-Apr
CDUVDU3490 | Completed | Blinding As Per Blind List | 31/03/2023 12:28:37 | 31/03/2023 21:09:00 | 01/04/2023 14:30:00 | 01/04/2023 22:30:00 | 01-EE-006 | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 8:40 | 0:40 |  | 01-Apr | 01-Apr | 31-Mar | 31-Mar
CDUVDU4130 | Completed | Carryout Component Dropping | 31/03/2023 12:34:50 | 01/04/2023 10:01:04 | 01/04/2023 22:30:00 | 02/04/2023 06:30:00 | 01-EE-006 | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 21:26 | 13:26 |  | 01-Apr | 02-Apr | 31-Mar | 01-Apr
CDUVDU6250 | Completed | Carryout Bundle Pullout | 01/04/2023 15:52:30 | 01/04/2023 15:52:35 | 02/04/2023 18:30:00 | 03/04/2023 00:30:00 | 01-EE-006 | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 0:00 |  | 6:00 | 02-Apr | 03-Apr | 01-Apr | 01-Apr
CDUVDU6700 | Completed | Pre Cleaning Inspection | 01/04/2023 16:40:18 | 01/04/2023 16:40:23 | 03/04/2023 00:30:00 | 03/04/2023 02:30:00 | 01-EE-006 | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  | 2:00 | 03-Apr | 03-Apr | 01-Apr | 01-Apr
CDUVDU6770 | Completed | Bundle Shifting to Bay | 02/04/2023 06:02:44 | 02/04/2023 06:02:49 | 03/04/2023 02:30:00 | 03/04/2023 05:30:00 | 01-EE-006 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 03-Apr | 03-Apr | 02-Apr | 02-Apr
CDUVDU12740 | Completed | Hydrojetting of Tube Bundle | 02/04/2023 06:03:29 | 11/04/2023 06:41:16 | 07/04/2023 07:30:00 | 08/04/2023 09:30:00 | 01-EE-007 | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 26 | 26:00 | 216:38 | 190:38 |  | 07-Apr | 08-Apr | 02-Apr | 11-Apr
CDUVDU14310 | Completed | Air Drying | 11/04/2023 07:40:18 | 11/04/2023 07:40:18 | 08/04/2023 09:30:00 | 08/04/2023 17:30:00 | 01-EE-007 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  |  | 08-Apr | 08-Apr | 11-Apr | 11-Apr
CDUVDU14960 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 11/04/2023 07:40:18 | 11/04/2023 07:40:18 | 08/04/2023 17:30:00 | 08/04/2023 23:30:00 | 01-EE-007 | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  |  | 08-Apr | 08-Apr | 11-Apr | 11-Apr
CDUVDU15360 | Completed | Shifting of bundle from bay | 12/04/2023 00:14:46 | 12/04/2023 00:14:46 | 08/04/2023 23:30:00 | 09/04/2023 02:30:00 | 01-EE-007 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  |  | 08-Apr | 09-Apr | 12-Apr | 12-Apr
CDUVDU15760 | Completed | Carryout Bundle Insertion | 12/04/2023 00:15:01 | 12/04/2023 07:47:19 | 09/04/2023 02:30:00 | 09/04/2023 10:30:00 | 01-EE-007 | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 7:32 |  | 0:28 | 09-Apr | 09-Apr | 12-Apr | 12-Apr
CDUVDU16330 | Completed | Channelhead Boxup | 12/04/2023 07:47:32 | 12/04/2023 07:49:16 | 09/04/2023 10:30:00 | 09/04/2023 16:30:00 | 01-EE-007 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:02 |  | 5:58 | 09-Apr | 09-Apr | 12-Apr | 12-Apr
CDUVDU16820 | Completed | Test Ring Boxup | 12/04/2023 07:49:29 | 12/04/2023 15:32:05 | 09/04/2023 16:30:00 | 10/04/2023 00:30:00 | 01-EE-007 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 7:43 |  | 0:17 | 09-Apr | 10-Apr | 12-Apr | 12-Apr
CDUVDU17600 | Completed | Carryout Shell Test | 12/04/2023 15:32:23 | 13/04/2023 16:54:44 | 10/04/2023 00:30:00 | 10/04/2023 15:30:00 | 01-EE-007 | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 25:22 | 10:22 |  | 10-Apr | 10-Apr | 12-Apr | 13-Apr
CDUVDU19090 | Completed | Test Ring Drop Down | 14/04/2023 04:32:28 | 14/04/2023 04:32:36 | 10/04/2023 15:30:00 | 10/04/2023 21:30:00 | 01-EE-007 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 10-Apr | 10-Apr | 14-Apr | 14-Apr
CDUVDU19650 | Completed | Floating Head Box-up | 14/04/2023 04:32:28 | 14/04/2023 07:58:15 | 10/04/2023 21:30:00 | 11/04/2023 03:30:00 | 01-EE-007 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 3:26 |  | 2:34 | 10-Apr | 11-Apr | 14-Apr | 14-Apr
CDUVDU20380 | Completed | Tube Test | 14/04/2023 10:59:18 | 15/04/2023 10:48:45 | 11/04/2023 03:30:00 | 11/04/2023 18:30:00 | 01-EE-007 | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 15 | 15:00 | 23:49 | 8:49 |  | 11-Apr | 11-Apr | 14-Apr | 15-Apr
CDUVDU21950 | Completed | Back Dome Boxup | 15/04/2023 17:17:14 | 15/04/2023 18:54:29 | 11/04/2023 18:30:00 | 12/04/2023 02:30:00 | 01-EE-007 | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 1:37 |  | 6:23 | 11-Apr | 12-Apr | 15-Apr | 15-Apr
CDUVDU22620 | Completed | Final Test | 15/04/2023 18:54:46 | 15/04/2023 18:54:50 | 12/04/2023 02:30:00 | 12/04/2023 17:30:00 | 01-EE-007 | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 0:00 |  | 15:00 | 12-Apr | 12-Apr | 15-Apr | 15-Apr
CDUVDU24000 | Completed | Deblinding | 17/04/2023 09:34:37 | 18/04/2023 00:19:51 | 12/04/2023 17:30:00 | 13/04/2023 01:30:00 | 01-EE-007 | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 14:45 | 6:45 |  | 12-Apr | 13-Apr | 17-Apr | 18-Apr
CDUVDU3470 | Completed | Blinding As Per Blind List | 31/03/2023 12:28:51 | 01/04/2023 04:05:37 | 01/04/2023 14:30:00 | 01/04/2023 22:30:00 | 01-EE-007 | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 15:37 | 7:37 |  | 01-Apr | 01-Apr | 31-Mar | 01-Apr
CDUVDU4110 | Completed | Carryout Component Dropping | 31/03/2023 12:32:28 | 31/03/2023 19:23:42 | 01/04/2023 22:30:00 | 02/04/2023 06:30:00 | 01-EE-007 | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 6:51 |  | 1:09 | 01-Apr | 02-Apr | 31-Mar | 31-Mar
CDUVDU4630 | Completed | Carryout Bundle Pullout | 01/04/2023 09:45:04 | 01/04/2023 15:54:27 | 02/04/2023 06:30:00 | 02/04/2023 12:30:00 | 01-EE-007 | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 6:09 | 0:09 |  | 02-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU5110 | Completed | Pre Cleaning Inspection | 01/04/2023 16:40:23 | 01/04/2023 16:40:30 | 02/04/2023 12:30:00 | 02/04/2023 14:30:00 | 01-EE-007 | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  | 2:00 | 02-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU5690 | Completed | Bundle Shifting to Bay | 02/04/2023 06:03:29 | 02/04/2023 06:03:33 | 02/04/2023 14:30:00 | 02/04/2023 17:30:00 | 01-EE-007 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU10090 | Completed | Carryout Shell Test | 07/04/2023 11:56:28 | 07/04/2023 18:48:36 | 05/04/2023 13:30:00 | 06/04/2023 04:30:00 | 01-EE-008 | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 6:52 |  | 8:08 | 05-Apr | 06-Apr | 07-Apr | 07-Apr
CDUVDU11010 | Completed | Test Ring Drop Down | 07/04/2023 18:49:01 | 07/04/2023 18:49:49 | 06/04/2023 04:30:00 | 06/04/2023 10:30:00 | 01-EE-008 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:01 |  | 5:59 | 06-Apr | 06-Apr | 07-Apr | 07-Apr
CDUVDU11270 | Completed | Floating Head Box-up | 08/04/2023 07:36:14 | 08/04/2023 07:36:14 | 06/04/2023 10:30:00 | 06/04/2023 16:30:00 | 01-EE-008 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 06-Apr | 06-Apr | 08-Apr | 08-Apr
CDUVDU11700 | Completed | Tube Test | 08/04/2023 18:42:13 | 08/04/2023 18:42:17 | 06/04/2023 16:30:00 | 07/04/2023 07:30:00 | 01-EE-008 | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 15 | 15:00 | 0:00 |  | 15:00 | 06-Apr | 07-Apr | 08-Apr | 08-Apr
CDUVDU12760 | Completed | Back Dome Boxup | 09/04/2023 07:19:59 | 09/04/2023 07:20:03 | 07/04/2023 07:30:00 | 07/04/2023 15:30:00 | 01-EE-008 | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 0:00 |  | 8:00 | 07-Apr | 07-Apr | 09-Apr | 09-Apr
CDUVDU13230 | Completed | Final Test | 09/04/2023 10:29:04 | 09/04/2023 17:03:46 | 07/04/2023 15:30:00 | 08/04/2023 06:30:00 | 01-EE-008 | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 6:35 |  | 8:25 | 07-Apr | 08-Apr | 09-Apr | 09-Apr
CDUVDU14070 | Completed | Deblinding | 18/04/2023 00:42:00 | 20/04/2023 02:58:00 | 08/04/2023 06:30:00 | 08/04/2023 14:30:00 | 01-EE-008 | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 50:16 | 42:16 |  | 08-Apr | 08-Apr | 18-Apr | 20-Apr
CDUVDU3500 | Completed | Blinding As Per Blind List | 02/04/2023 05:49:47 | 02/04/2023 05:49:47 | 01/04/2023 14:30:00 | 01/04/2023 22:30:00 | 01-EE-008 | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  |  | 01-Apr | 01-Apr | 02-Apr | 02-Apr
CDUVDU4140 | Completed | Carryout Component Dropping | 01/04/2023 10:06:02 | 01/04/2023 10:06:15 | 01/04/2023 22:30:00 | 02/04/2023 06:30:00 | 01-EE-008 | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  | 8:00 | 01-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU4650 | Completed | Carryout Bundle Pullout | 01/04/2023 16:04:14 | 01/04/2023 16:04:20 | 02/04/2023 06:30:00 | 02/04/2023 14:30:00 | 01-EE-008 | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 8 | 8:00 | 0:00 |  | 8:00 | 02-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU5710 | Completed | Pre Cleaning Inspection | 01/04/2023 16:44:34 | 02/04/2023 05:49:47 | 02/04/2023 14:30:00 | 02/04/2023 16:30:00 | 01-EE-008 | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 13:05 | 11:05 |  | 02-Apr | 02-Apr | 01-Apr | 02-Apr
CDUVDU6190 | Completed | Bundle Shifting to Bay | 02/04/2023 06:21:20 | 02/04/2023 06:21:25 | 02/04/2023 16:30:00 | 02/04/2023 20:30:00 | 01-EE-008 | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU6290 | Completed | Hydrojetting of Tube Bundle | 04/04/2023 07:29:41 | 04/04/2023 21:30:57 | 02/04/2023 20:30:00 | 03/04/2023 22:30:00 | 01-EE-008 | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 26 | 26:00 | 14:01 |  | 11:59 | 02-Apr | 03-Apr | 04-Apr | 04-Apr
CDUVDU8120 | Completed | Air Drying | 04/04/2023 21:30:57 | 04/04/2023 21:30:57 | 03/04/2023 22:30:00 | 04/04/2023 06:30:00 | 01-EE-008 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  |  | 03-Apr | 04-Apr | 04-Apr | 04-Apr
CDUVDU8460 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 04/04/2023 21:30:57 | 04/04/2023 21:30:57 | 04/04/2023 06:30:00 | 04/04/2023 12:30:00 | 01-EE-008 | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  |  | 04-Apr | 04-Apr | 04-Apr | 04-Apr
CDUVDU8690 | Completed | Shifting of bundle from bay | 05/04/2023 17:40:20 | 05/04/2023 17:40:27 | 04/04/2023 12:30:00 | 04/04/2023 15:30:00 | 01-EE-008 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 04-Apr | 04-Apr | 05-Apr | 05-Apr
CDUVDU9080 | Completed | Carryout Bundle Insertion | 05/04/2023 17:40:36 | 05/04/2023 17:40:42 | 04/04/2023 15:30:00 | 04/04/2023 23:30:00 | 01-EE-008 | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 0:00 |  | 8:00 | 04-Apr | 04-Apr | 05-Apr | 05-Apr
CDUVDU9350 | Completed | Channelhead Boxup | 07/04/2023 07:33:11 | 07/04/2023 07:33:42 | 04/04/2023 23:30:00 | 05/04/2023 05:30:00 | 01-EE-008 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:01 |  | 5:59 | 04-Apr | 05-Apr | 07-Apr | 07-Apr
CDUVDU9780 | Completed | Test Ring Boxup | 07/04/2023 07:33:58 | 07/04/2023 11:58:05 | 05/04/2023 05:30:00 | 05/04/2023 13:30:00 | 01-EE-008 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 4:24 |  | 3:36 | 05-Apr | 05-Apr | 07-Apr | 07-Apr
CDUVDU10310 | Completed | Shifting of bundle from bay | 05/04/2023 15:36:37 | 05/04/2023 15:36:49 | 05/04/2023 14:30:00 | 05/04/2023 17:30:00 | 01-EE-009A | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 05-Apr | 05-Apr | 05-Apr | 05-Apr
CDUVDU10500 | Completed | Carryout Bundle Insertion | 05/04/2023 15:37:01 | 05/04/2023 15:37:05 | 05/04/2023 17:30:00 | 06/04/2023 01:30:00 | 01-EE-009A | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 0:00 |  | 8:00 | 05-Apr | 06-Apr | 05-Apr | 05-Apr
CDUVDU10710 | Completed | Channelhead Boxup | 06/04/2023 07:43:18 | 06/04/2023 07:43:24 | 06/04/2023 01:30:00 | 06/04/2023 07:30:00 | 01-EE-009A | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 06-Apr | 06-Apr | 06-Apr | 06-Apr
CDUVDU11130 | Completed | Test Ring Boxup | 07/04/2023 07:09:15 | 07/04/2023 07:09:23 | 06/04/2023 07:30:00 | 06/04/2023 15:30:00 | 01-EE-009A | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  | 8:00 | 06-Apr | 06-Apr | 07-Apr | 07-Apr
CDUVDU11590 | Completed | Carryout Shell Test | 07/04/2023 07:09:45 | 07/04/2023 18:50:52 | 06/04/2023 15:30:00 | 07/04/2023 06:30:00 | 01-EE-009A | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 11:41 |  | 3:19 | 06-Apr | 07-Apr | 07-Apr | 07-Apr
CDUVDU12690 | Completed | Test Ring Drop Down | 07/04/2023 18:51:10 | 08/04/2023 07:24:13 | 07/04/2023 06:30:00 | 07/04/2023 12:30:00 | 01-EE-009A | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 12:33 | 6:33 |  | 07-Apr | 07-Apr | 07-Apr | 08-Apr
CDUVDU13000 | Completed | Floating Head Box-up | 08/04/2023 07:36:47 | 08/04/2023 07:36:47 | 07/04/2023 12:30:00 | 07/04/2023 18:30:00 | 01-EE-009A | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 07-Apr | 07-Apr | 08-Apr | 08-Apr
CDUVDU13430 | Completed | Tube Test | 09/04/2023 07:20:24 | 09/04/2023 17:04:52 | 07/04/2023 18:30:00 | 08/04/2023 09:30:00 | 01-EE-009A | EXCHANGER | 100 | INSPECTION | TUBE TEST |  | 15 | 15:00 | 9:44 |  | 5:16 | 07-Apr | 08-Apr | 09-Apr | 09-Apr
CDUVDU14320 | Completed | Back Dome Boxup | 10/04/2023 07:04:41 | 10/04/2023 10:20:29 | 08/04/2023 09:30:00 | 08/04/2023 17:30:00 | 01-EE-009A | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 3:16 |  | 4:44 | 08-Apr | 08-Apr | 10-Apr | 10-Apr
CDUVDU14980 | Completed | Final Test | 10/04/2023 10:51:19 | 10/04/2023 19:32:19 | 08/04/2023 17:30:00 | 09/04/2023 08:30:00 | 01-EE-009A | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 8:41 |  | 6:19 | 08-Apr | 09-Apr | 10-Apr | 10-Apr
CDUVDU16110 | Completed | Deblinding | 18/04/2023 09:44:00 | 20/04/2023 02:58:00 | 09/04/2023 08:30:00 | 09/04/2023 16:30:00 | 01-EE-009A | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 41:14 | 33:14 |  | 09-Apr | 09-Apr | 18-Apr | 20-Apr
CDUVDU3510 | Completed | Blinding As Per Blind List | 01/04/2023 04:14:00 | 01/04/2023 04:14:07 | 01/04/2023 14:30:00 | 01/04/2023 22:30:00 | 01-EE-009A | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 01-Apr | 01-Apr | 01-Apr | 01-Apr
CDUVDU4150 | Completed | Carryout Component Dropping | 31/03/2023 19:00:45 | 01/04/2023 10:07:28 | 01/04/2023 22:30:00 | 02/04/2023 06:30:00 | 01-EE-009A | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 15:07 | 7:07 |  | 01-Apr | 02-Apr | 31-Mar | 01-Apr
CDUVDU4660 | Completed | Carryout Bundle Pullout | 01/04/2023 16:05:57 | 01/04/2023 16:06:06 | 02/04/2023 06:30:00 | 02/04/2023 12:30:00 | 01-EE-009A | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 6 | 6:00 | 0:00 |  | 6:00 | 02-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU5140 | Completed | Pre Cleaning Inspection | 01/04/2023 16:39:39 | 02/04/2023 05:48:15 | 02/04/2023 12:30:00 | 02/04/2023 14:30:00 | 01-EE-009A | EXCHANGER | 100 | INSPECTION |  |  | 2 | 2:00 | 13:09 | 11:09 |  | 02-Apr | 02-Apr | 01-Apr | 02-Apr
CDUVDU5720 | Completed | Bundle Shifting to Bay | 02/04/2023 06:21:58 | 02/04/2023 06:21:58 | 02/04/2023 14:30:00 | 02/04/2023 17:30:00 | 01-EE-009A | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  |  | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU8130 | Completed | Hydrojetting of Tube Bundle | 02/04/2023 10:33:41 | 04/04/2023 07:30:30 | 03/04/2023 22:30:00 | 05/04/2023 00:30:00 | 01-EE-009A | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 26 | 26:00 | 44:57 | 18:57 |  | 03-Apr | 05-Apr | 02-Apr | 04-Apr
CDUVDU9440 | Completed | Air Drying | 04/04/2023 21:31:20 | 04/04/2023 21:31:20 | 05/04/2023 00:30:00 | 05/04/2023 08:30:00 | 01-EE-009A | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  |  | 05-Apr | 05-Apr | 04-Apr | 04-Apr
CDUVDU9900 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 04/04/2023 21:31:20 | 04/04/2023 21:31:20 | 05/04/2023 08:30:00 | 05/04/2023 14:30:00 | 01-EE-009A | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  |  | 05-Apr | 05-Apr | 04-Apr | 04-Apr
CDUVDU12350 | Completed | Hydrojetting of Tube & Component | 06/04/2023 07:48:53 | 06/04/2023 07:49:54 | 07/04/2023 01:30:00 | 07/04/2023 14:30:00 | 01-EE-055 | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 13 | 13:00 | 0:01 |  | 12:59 | 07-Apr | 07-Apr | 06-Apr | 06-Apr
CDUVDU13180 | Completed | Air Drying | 09/04/2023 07:33:49 | 09/04/2023 07:33:59 | 07/04/2023 14:30:00 | 07/04/2023 20:30:00 | 01-EE-055 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 07-Apr | 07-Apr | 09-Apr | 09-Apr
CDUVDU13560 | Completed | Post Cleaning Inspection | 09/04/2023 07:33:49 | 09/04/2023 07:33:59 | 07/04/2023 20:30:00 | 08/04/2023 00:30:00 | 01-EE-055 | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:00 |  | 4:00 | 07-Apr | 08-Apr | 09-Apr | 09-Apr
CDUVDU13730 | Completed | Channelhead Boxup | 14/04/2023 05:30:43 | 14/04/2023 05:31:41 | 08/04/2023 00:30:00 | 08/04/2023 08:30:00 | 01-EE-055 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:01 |  | 7:59 | 08-Apr | 08-Apr | 14-Apr | 14-Apr
CDUVDU14290 | Completed | Test Ring Boxup | 15/04/2023 05:57:09 | 18/04/2023 11:47:12 | 08/04/2023 08:30:00 | 08/04/2023 14:30:00 | 01-EE-055 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 77:50 | 71:50 |  | 08-Apr | 08-Apr | 15-Apr | 18-Apr
CDUVDU14820 | Completed | Carryout Shell Test | 19/04/2023 02:40:29 | 19/04/2023 18:24:25 | 08/04/2023 14:30:00 | 09/04/2023 05:30:00 | 01-EE-055 | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 15:44 | 0:44 |  | 08-Apr | 09-Apr | 19-Apr | 19-Apr
CDUVDU15940 | Completed | Test Ring Drop Down | 20/04/2023 02:54:37 | 20/04/2023 02:54:40 | 09/04/2023 05:30:00 | 09/04/2023 09:30:00 | 01-EE-055 | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 09-Apr | 09-Apr | 20-Apr | 20-Apr
CDUVDU16250 | Completed | Component Boxup | 20/04/2023 02:55:00 | 20/04/2023 02:55:07 | 09/04/2023 09:30:00 | 09/04/2023 15:30:00 | 01-EE-055 | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 6 | 6:00 | 0:00 |  | 6:00 | 09-Apr | 09-Apr | 20-Apr | 20-Apr
CDUVDU16790 | Completed | Final Test | 20/04/2023 02:55:19 | 20/04/2023 12:17:47 | 09/04/2023 15:30:00 | 10/04/2023 06:30:00 | 01-EE-055 | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 9:22 |  | 5:38 | 09-Apr | 10-Apr | 20-Apr | 20-Apr
CDUVDU18360 | Completed | Deblinding | 21/04/2023 12:35:23 | 23/04/2023 18:09:22 | 10/04/2023 06:30:00 | 10/04/2023 14:30:00 | 01-EE-055 | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 53:34 | 45:34 |  | 10-Apr | 10-Apr | 21-Apr | 23-Apr
CDUVDU6050 | Completed | Blinding As Per Blind List | 02/04/2023 05:34:08 | 02/04/2023 05:34:08 | 02/04/2023 14:30:00 | 02/04/2023 22:30:00 | 01-EE-055 | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  |  | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU6560 | Completed | Carryout Component Dropping | 02/04/2023 05:34:08 | 02/04/2023 05:34:08 | 02/04/2023 22:30:00 | 03/04/2023 06:30:00 | 01-EE-055 | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  |  | 02-Apr | 03-Apr | 02-Apr | 02-Apr
CDUVDU7060 | Completed | Pre Cleaning Inspection | 02/04/2023 11:43:27 | 02/04/2023 11:43:33 | 03/04/2023 06:30:00 | 03/04/2023 09:30:00 | 01-EE-055 | EXCHANGER | 100 | INSPECTION |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 03-Apr | 03-Apr | 02-Apr | 02-Apr
CDUVDU10380 | Completed | Post Cleaning Inspection | 14/04/2023 07:33:23 | 14/04/2023 07:33:31 | 05/04/2023 15:30:00 | 06/04/2023 03:30:00 | 01-EE-054A | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 12 | 12:00 | 0:00 |  | 12:00 | 05-Apr | 06-Apr | 14-Apr | 14-Apr
CDUVDU10930 | Completed | Channelhead Boxup | 16/04/2023 19:18:09 | 16/04/2023 19:18:18 | 06/04/2023 03:30:00 | 06/04/2023 11:30:00 | 01-EE-054A | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  | 8:00 | 06-Apr | 06-Apr | 16-Apr | 16-Apr
CDUVDU11350 | Completed | Test Ring Boxup | 17/04/2023 12:00:21 | 17/04/2023 12:12:29 | 06/04/2023 11:30:00 | 06/04/2023 17:30:00 | 01-EE-054A | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:12 |  | 5:48 | 06-Apr | 06-Apr | 17-Apr | 17-Apr
CDUVDU11790 | Completed | Carryout Shell Test | 18/04/2023 07:13:55 | 18/04/2023 07:14:04 | 06/04/2023 17:30:00 | 07/04/2023 08:30:00 | 01-EE-054A | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 0:00 |  | 15:00 | 06-Apr | 07-Apr | 18-Apr | 18-Apr
CDUVDU12820 | Completed | Test Ring Drop Down | 18/04/2023 15:22:57 | 18/04/2023 15:23:03 | 07/04/2023 08:30:00 | 07/04/2023 12:30:00 | 01-EE-054A | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 07-Apr | 07-Apr | 18-Apr | 18-Apr
CDUVDU13020 | Completed | Component Boxup | 19/04/2023 02:38:06 | 19/04/2023 02:38:15 | 07/04/2023 12:30:00 | 07/04/2023 19:30:00 | 01-EE-054A | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 7 | 7:00 | 0:00 |  | 7:00 | 07-Apr | 07-Apr | 19-Apr | 19-Apr
CDUVDU13480 | Completed | Final Test | 19/04/2023 02:38:26 | 21/04/2023 18:59:36 | 07/04/2023 19:30:00 | 08/04/2023 10:30:00 | 01-EE-054A | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 64:21 | 49:21 |  | 07-Apr | 08-Apr | 19-Apr | 21-Apr
CDUVDU14460 | Completed | Deblinding | 22/04/2023 23:55:16 | 23/04/2023 18:09:44 | 08/04/2023 10:30:00 | 08/04/2023 18:30:00 | 01-EE-054A | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 18:14 | 10:14 |  | 08-Apr | 08-Apr | 22-Apr | 23-Apr
CDUVDU3770 | Completed | Blinding As Per Blind List | 02/04/2023 05:32:10 | 02/04/2023 05:32:17 | 01/04/2023 14:30:00 | 02/04/2023 02:30:00 | 01-EE-054A | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 01-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU4530 | Completed | Carryout Component Dropping | 02/04/2023 05:32:10 | 03/04/2023 06:22:48 | 02/04/2023 02:30:00 | 02/04/2023 10:30:00 | 01-EE-054A | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 24:51 | 16:51 |  | 02-Apr | 02-Apr | 02-Apr | 03-Apr
CDUVDU5090 | Completed | Pre Cleaning Inspection | 03/04/2023 23:00:00 | 04/04/2023 04:59:00 | 02/04/2023 10:30:00 | 02/04/2023 16:30:00 | 01-EE-054A | EXCHANGER | 100 | INSPECTION |  |  | 6 | 6:00 | 5:59 |  | 0:01 | 02-Apr | 02-Apr | 03-Apr | 04-Apr
CDUVDU6210 | Completed | Hydrojetting of Tube & Component | 06/04/2023 07:46:18 | 06/04/2023 07:46:37 | 02/04/2023 16:30:00 | 04/04/2023 21:30:00 | 01-EE-054A | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 53 | 53:00 | 0:00 |  | 53:00 | 02-Apr | 04-Apr | 06-Apr | 06-Apr
CDUVDU9310 | Completed | Air Drying | 06/04/2023 07:46:18 | 06/04/2023 07:46:41 | 04/04/2023 21:30:00 | 05/04/2023 15:30:00 | 01-EE-054A | EXCHANGER | 100 | MECHANICAL |  |  | 18 | 18:00 | 0:00 |  | 18:00 | 04-Apr | 05-Apr | 06-Apr | 06-Apr
CDUVDU13190 | Completed | Hydrojetting of Tube & Component | 06/04/2023 07:50:26 | 08/04/2023 07:47:52 | 07/04/2023 14:30:00 | 08/04/2023 03:30:00 | 01-EE-056 | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 13 | 13:00 | 47:57 | 34:57 |  | 07-Apr | 08-Apr | 06-Apr | 08-Apr
CDUVDU13950 | Completed | Air Drying | 09/04/2023 07:34:27 | 11/04/2023 07:05:01 | 08/04/2023 03:30:00 | 08/04/2023 09:30:00 | 01-EE-056 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 47:31 | 41:31 |  | 08-Apr | 08-Apr | 09-Apr | 11-Apr
CDUVDU14360 | Completed | Post Cleaning Inspection | 09/04/2023 07:34:27 | 11/04/2023 07:05:01 | 08/04/2023 09:30:00 | 08/04/2023 13:30:00 | 01-EE-056 | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 47:31 | 43:31 |  | 08-Apr | 08-Apr | 09-Apr | 11-Apr
CDUVDU14610 | Completed | Channelhead Boxup | 13/04/2023 05:32:56 | 13/04/2023 05:33:00 | 08/04/2023 13:30:00 | 08/04/2023 21:30:00 | 01-EE-056 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  | 8:00 | 08-Apr | 08-Apr | 13-Apr | 13-Apr
CDUVDU15220 | Completed | Test Ring Boxup | 13/04/2023 12:23:54 | 13/04/2023 12:24:00 | 08/04/2023 21:30:00 | 09/04/2023 03:30:00 | 01-EE-056 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 08-Apr | 09-Apr | 13-Apr | 13-Apr
CDUVDU15820 | Completed | Carryout Shell Test | 13/04/2023 12:24:19 | 13/04/2023 12:25:04 | 09/04/2023 03:30:00 | 09/04/2023 18:30:00 | 01-EE-056 | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 0:01 |  | 14:59 | 09-Apr | 09-Apr | 13-Apr | 13-Apr
CDUVDU16950 | Completed | Test Ring Drop Down | 14/04/2023 05:57:00 | 14/04/2023 11:57:00 | 09/04/2023 18:30:00 | 09/04/2023 22:30:00 | 01-EE-056 | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 6:00 | 2:00 |  | 09-Apr | 09-Apr | 14-Apr | 14-Apr
CDUVDU17470 | Completed | Component Boxup | 14/04/2023 11:58:00 | 15/04/2023 05:58:00 | 09/04/2023 22:30:00 | 10/04/2023 04:30:00 | 01-EE-056 | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 6 | 6:00 | 18:00 | 12:00 |  | 09-Apr | 10-Apr | 14-Apr | 15-Apr
CDUVDU18100 | Completed | Final Test | 14/04/2023 17:58:00 | 15/04/2023 05:58:57 | 10/04/2023 04:30:00 | 10/04/2023 19:30:00 | 01-EE-056 | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 12:01 |  | 2:59 | 10-Apr | 10-Apr | 14-Apr | 15-Apr
CDUVDU19460 | Completed | Deblinding | 18/04/2023 07:17:30 | 18/04/2023 07:18:32 | 10/04/2023 19:30:00 | 11/04/2023 03:30:00 | 01-EE-056 | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:01 |  | 7:59 | 10-Apr | 11-Apr | 18-Apr | 18-Apr
CDUVDU6060 | Completed | Blinding As Per Blind List | 02/04/2023 05:34:32 | 02/04/2023 05:34:32 | 02/04/2023 14:30:00 | 02/04/2023 22:30:00 | 01-EE-056 | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  |  | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU6570 | Completed | Carryout Component Dropping | 02/04/2023 05:34:32 | 02/04/2023 05:34:32 | 02/04/2023 22:30:00 | 03/04/2023 06:30:00 | 01-EE-056 | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  |  | 02-Apr | 03-Apr | 02-Apr | 02-Apr
CDUVDU7070 | Completed | Pre Cleaning Inspection | 02/04/2023 11:44:12 | 02/04/2023 11:44:24 | 03/04/2023 06:30:00 | 03/04/2023 09:30:00 | 01-EE-056 | EXCHANGER | 100 | INSPECTION |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 03-Apr | 03-Apr | 02-Apr | 02-Apr
CDUVDU12340 | Completed | Air Drying | 06/04/2023 07:47:03 | 06/04/2023 07:48:12 | 07/04/2023 01:30:00 | 07/04/2023 19:30:00 | 01-EE-054B | EXCHANGER | 100 | MECHANICAL |  |  | 18 | 18:00 | 0:01 |  | 17:59 | 07-Apr | 07-Apr | 06-Apr | 06-Apr
CDUVDU13490 | Completed | Post Cleaning Inspection | 11/04/2023 07:03:55 | 14/04/2023 07:33:49 | 07/04/2023 19:30:00 | 08/04/2023 07:30:00 | 01-EE-054B | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 12 | 12:00 | 72:30 | 60:30 |  | 07-Apr | 08-Apr | 11-Apr | 14-Apr
CDUVDU14200 | Completed | Channelhead Boxup | 16/04/2023 19:18:45 | 16/04/2023 19:18:54 | 08/04/2023 07:30:00 | 08/04/2023 15:30:00 | 01-EE-054B | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  | 8:00 | 08-Apr | 08-Apr | 16-Apr | 16-Apr
CDUVDU14890 | Completed | Test Ring Boxup | 17/04/2023 12:01:17 | 17/04/2023 12:12:39 | 08/04/2023 15:30:00 | 08/04/2023 21:30:00 | 01-EE-054B | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:11 |  | 5:49 | 08-Apr | 08-Apr | 17-Apr | 17-Apr
CDUVDU15210 | Completed | Carryout Shell Test | 18/04/2023 11:45:44 | 18/04/2023 17:49:27 | 08/04/2023 21:30:00 | 09/04/2023 12:30:00 | 01-EE-054B | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 6:04 |  | 8:56 | 08-Apr | 09-Apr | 18-Apr | 18-Apr
CDUVDU16490 | Completed | Test Ring Drop Down | 18/04/2023 17:49:39 | 18/04/2023 17:49:47 | 09/04/2023 12:30:00 | 09/04/2023 18:30:00 | 01-EE-054B | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 09-Apr | 09-Apr | 18-Apr | 18-Apr
CDUVDU16940 | Completed | Component Boxup | 18/04/2023 17:50:08 | 19/04/2023 02:39:05 | 09/04/2023 18:30:00 | 10/04/2023 00:30:00 | 01-EE-054B | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 6 | 6:00 | 8:49 | 2:49 |  | 09-Apr | 10-Apr | 18-Apr | 19-Apr
CDUVDU17640 | Completed | Final Test | 19/04/2023 02:39:44 | 22/04/2023 18:16:07 | 10/04/2023 00:30:00 | 10/04/2023 15:30:00 | 01-EE-054B | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 87:36 | 72:36 |  | 10-Apr | 10-Apr | 19-Apr | 22-Apr
CDUVDU19130 | Completed | Deblinding | 22/04/2023 23:55:47 | 23/04/2023 18:09:54 | 10/04/2023 15:30:00 | 10/04/2023 23:30:00 | 01-EE-054B | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 18:14 | 10:14 |  | 10-Apr | 10-Apr | 22-Apr | 23-Apr
CDUVDU3780 | Completed | Blinding As Per Blind List | 02/04/2023 05:33:04 | 02/04/2023 05:33:12 | 01/04/2023 14:30:00 | 02/04/2023 02:30:00 | 01-EE-054B | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 01-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU4540 | Completed | Carryout Component Dropping | 02/04/2023 05:33:04 | 02/04/2023 17:04:24 | 02/04/2023 02:30:00 | 02/04/2023 10:30:00 | 01-EE-054B | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 11:31 | 3:31 |  | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU5100 | Completed | Pre Cleaning Inspection | 06/04/2023 07:47:03 | 06/04/2023 07:48:00 | 02/04/2023 10:30:00 | 02/04/2023 14:30:00 | 01-EE-054B | EXCHANGER | 100 | INSPECTION |  |  | 4 | 4:00 | 0:01 |  | 3:59 | 02-Apr | 02-Apr | 06-Apr | 06-Apr
CDUVDU9320 | Completed | Hydrojetting of Tube & Component | 06/04/2023 07:47:03 | 06/04/2023 07:48:08 | 04/04/2023 21:30:00 | 07/04/2023 01:30:00 | 01-EE-054B | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 52 | 52:00 | 0:01 |  | 51:59 | 04-Apr | 07-Apr | 06-Apr | 06-Apr
CDUVDU10460 | Completed | Final Test | 17/04/2023 01:42:00 | 17/04/2023 01:42:03 | 05/04/2023 16:30:00 | 06/04/2023 07:30:00 | 01-EE-024 | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 0:00 |  | 15:00 | 05-Apr | 06-Apr | 17-Apr | 17-Apr
CDUVDU11110 | Completed | Deblinding | 18/04/2023 09:47:43 | 18/04/2023 18:02:38 | 06/04/2023 07:30:00 | 06/04/2023 15:30:00 | 01-EE-024 | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 8:15 | 0:15 |  | 06-Apr | 06-Apr | 18-Apr | 18-Apr
CDUVDU5670 | Completed | Blinding As Per Blind List | 02/04/2023 06:34:55 | 02/04/2023 06:35:04 | 02/04/2023 14:30:00 | 02/04/2023 23:30:00 | 01-EE-024 | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 9 | 9:00 | 0:00 |  | 9:00 | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU6600 | Completed | Carryout Component Dropping | 09/04/2023 07:31:25 | 09/04/2023 07:31:37 | 02/04/2023 23:30:00 | 03/04/2023 08:30:00 | 01-EE-024 | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 9 | 9:00 | 0:00 |  | 9:00 | 02-Apr | 03-Apr | 09-Apr | 09-Apr
CDUVDU7130 | Completed | Pre Cleaning Inspection | 09/04/2023 07:31:25 | 09/04/2023 07:31:40 | 03/04/2023 08:30:00 | 03/04/2023 11:30:00 | 01-EE-024 | EXCHANGER | 100 | INSPECTION |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 03-Apr | 03-Apr | 09-Apr | 09-Apr
CDUVDU7450 | Completed | Hydrojetting of Tube & Component | 09/04/2023 07:31:25 | 09/04/2023 07:32:01 | 03/04/2023 11:30:00 | 03/04/2023 17:30:00 | 01-EE-024 | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 6 | 6:00 | 0:01 |  | 5:59 | 03-Apr | 03-Apr | 09-Apr | 09-Apr
CDUVDU7980 | Completed | Air Drying | 14/04/2023 07:32:28 | 14/04/2023 07:32:37 | 03/04/2023 17:30:00 | 03/04/2023 21:30:00 | 01-EE-024 | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 03-Apr | 03-Apr | 14-Apr | 14-Apr
CDUVDU8070 | Completed | Post Cleaning Inspection | 14/04/2023 07:32:28 | 14/04/2023 07:32:37 | 03/04/2023 21:30:00 | 04/04/2023 01:30:00 | 01-EE-024 | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:00 |  | 4:00 | 03-Apr | 04-Apr | 14-Apr | 14-Apr
CDUVDU8330 | Completed | Channelhead Boxup | 14/04/2023 17:52:00 | 15/04/2023 03:52:00 | 04/04/2023 01:30:00 | 04/04/2023 09:30:00 | 01-EE-024 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 10:00 | 2:00 |  | 04-Apr | 04-Apr | 14-Apr | 15-Apr
CDUVDU8620 | Completed | Test Ring Boxup | 15/04/2023 05:52:21 | 15/04/2023 17:28:09 | 04/04/2023 09:30:00 | 04/04/2023 15:30:00 | 01-EE-024 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 11:36 | 5:36 |  | 04-Apr | 04-Apr | 15-Apr | 15-Apr
CDUVDU9070 | Completed | Carryout Shell Test | 15/04/2023 17:28:25 | 15/04/2023 17:28:29 | 04/04/2023 15:30:00 | 05/04/2023 06:30:00 | 01-EE-024 | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 0:00 |  | 15:00 | 04-Apr | 05-Apr | 15-Apr | 15-Apr
CDUVDU9810 | Completed | Test Ring Drop Down | 17/04/2023 01:41:15 | 17/04/2023 01:41:19 | 05/04/2023 06:30:00 | 05/04/2023 10:30:00 | 01-EE-024 | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 05-Apr | 05-Apr | 17-Apr | 17-Apr
CDUVDU9960 | Completed | Component Boxup | 17/04/2023 01:41:32 | 17/04/2023 01:41:35 | 05/04/2023 10:30:00 | 05/04/2023 16:30:00 | 01-EE-024 | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 6 | 6:00 | 0:00 |  | 6:00 | 05-Apr | 05-Apr | 17-Apr | 17-Apr
CDUVDU10370 | Completed | Channelhead Boxup | 10/04/2023 07:16:23 | 10/04/2023 07:16:33 | 05/04/2023 15:30:00 | 05/04/2023 23:30:00 | 01-EE-028 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  | 8:00 | 05-Apr | 05-Apr | 10-Apr | 10-Apr
CDUVDU10630 | Completed | Test Ring Boxup | 10/04/2023 07:16:23 | 10/04/2023 07:16:33 | 05/04/2023 23:30:00 | 06/04/2023 05:30:00 | 01-EE-028 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 05-Apr | 06-Apr | 10-Apr | 10-Apr
CDUVDU11080 | Completed | Carryout Shell Test | 10/04/2023 07:16:23 | 10/04/2023 07:16:33 | 06/04/2023 05:30:00 | 06/04/2023 20:30:00 | 01-EE-028 | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 0:00 |  | 15:00 | 06-Apr | 06-Apr | 10-Apr | 10-Apr
CDUVDU11990 | Completed | Test Ring Drop Down | 13/04/2023 05:30:27 | 13/04/2023 05:30:48 | 06/04/2023 20:30:00 | 07/04/2023 00:30:00 | 01-EE-028 | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 06-Apr | 07-Apr | 13-Apr | 13-Apr
CDUVDU12270 | Completed | Component Boxup | 13/04/2023 05:30:27 | 15/04/2023 05:53:29 | 07/04/2023 00:30:00 | 07/04/2023 06:30:00 | 01-EE-028 | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 6 | 6:00 | 48:23 | 42:23 |  | 07-Apr | 07-Apr | 13-Apr | 15-Apr
CDUVDU12710 | Completed | Final Test | 14/04/2023 13:53:00 | 15/04/2023 05:54:30 | 07/04/2023 06:30:00 | 07/04/2023 21:30:00 | 01-EE-028 | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 16:02 | 1:02 |  | 07-Apr | 07-Apr | 14-Apr | 15-Apr
CDUVDU13610 | Completed | Deblinding | 20/04/2023 09:03:43 | 20/04/2023 09:03:54 | 07/04/2023 21:30:00 | 08/04/2023 05:30:00 | 01-EE-028 | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 07-Apr | 08-Apr | 20-Apr | 20-Apr
CDUVDU6030 | Completed | Blinding As Per Blind List | 02/04/2023 06:35:20 | 02/04/2023 06:35:26 | 02/04/2023 14:30:00 | 02/04/2023 22:30:00 | 01-EE-028 | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU6540 | Completed | Carryout Component Dropping | 03/04/2023 06:21:54 | 05/04/2023 17:17:41 | 02/04/2023 22:30:00 | 03/04/2023 06:30:00 | 01-EE-028 | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 58:56 | 50:56 |  | 02-Apr | 03-Apr | 03-Apr | 05-Apr
CDUVDU7040 | Completed | Pre Cleaning Inspection | 05/04/2023 22:25:06 | 05/04/2023 22:25:11 | 03/04/2023 06:30:00 | 03/04/2023 09:30:00 | 01-EE-028 | EXCHANGER | 100 | INSPECTION |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 03-Apr | 03-Apr | 05-Apr | 05-Apr
CDUVDU7990 | Completed | Hydrojetting of Tube & Component | 08/04/2023 17:44:28 | 10/04/2023 07:16:33 | 03/04/2023 17:30:00 | 04/04/2023 20:30:00 | 01-EE-028 | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 27 | 27:00 | 37:32 | 10:32 |  | 03-Apr | 04-Apr | 08-Apr | 10-Apr
CDUVDU9240 | Completed | Air Drying | 10/04/2023 07:16:23 | 10/04/2023 07:16:33 | 04/04/2023 20:30:00 | 05/04/2023 09:30:00 | 01-EE-028 | EXCHANGER | 100 | MECHANICAL |  |  | 13 | 13:00 | 0:00 |  | 13:00 | 04-Apr | 05-Apr | 10-Apr | 10-Apr
CDUVDU9920 | Completed | Post Cleaning Inspection | 10/04/2023 07:16:23 | 10/04/2023 07:16:33 | 05/04/2023 09:30:00 | 05/04/2023 15:30:00 | 01-EE-028 | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  | 6:00 | 05-Apr | 05-Apr | 10-Apr | 10-Apr
CDUVDU10540 | Completed | Test Ring Boxup | 16/04/2023 19:15:33 | 16/04/2023 19:16:08 | 05/04/2023 18:30:00 | 06/04/2023 00:30:00 | 01-EE-053 | EXCHANGER | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:01 |  | 5:59 | 05-Apr | 06-Apr | 16-Apr | 16-Apr
CDUVDU10680 | Completed | Carryout Shell Test | 16/04/2023 19:15:45 | 16/04/2023 19:16:13 | 06/04/2023 00:30:00 | 06/04/2023 15:30:00 | 01-EE-053 | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 0:00 |  | 15:00 | 06-Apr | 06-Apr | 16-Apr | 16-Apr
CDUVDU11650 | Completed | Test Ring Drop Down | 16/04/2023 19:15:55 | 16/04/2023 19:16:18 | 06/04/2023 15:30:00 | 06/04/2023 19:30:00 | 01-EE-053 | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 06-Apr | 06-Apr | 16-Apr | 16-Apr
CDUVDU11940 | Completed | Component Boxup | 18/04/2023 01:18:59 | 18/04/2023 01:19:03 | 06/04/2023 19:30:00 | 07/04/2023 01:30:00 | 01-EE-053 | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 6 | 6:00 | 0:00 |  | 6:00 | 06-Apr | 07-Apr | 18-Apr | 18-Apr
CDUVDU12330 | Completed | Final Test | 18/04/2023 01:19:26 | 18/04/2023 01:19:30 | 07/04/2023 01:30:00 | 07/04/2023 16:30:00 | 01-EE-053 | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 0:00 |  | 15:00 | 07-Apr | 07-Apr | 18-Apr | 18-Apr
CDUVDU13300 | Completed | Deblinding | 18/04/2023 15:17:48 | 18/04/2023 15:18:00 | 07/04/2023 16:30:00 | 08/04/2023 00:30:00 | 01-EE-053 | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 07-Apr | 08-Apr | 18-Apr | 18-Apr
CDUVDU6040 | Completed | Blinding As Per Blind List | 02/04/2023 06:36:17 | 02/04/2023 06:36:36 | 02/04/2023 14:30:00 | 02/04/2023 22:30:00 | 01-EE-053 | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU6550 | Completed | Carryout Component Dropping | 02/04/2023 06:36:17 | 02/04/2023 06:36:36 | 02/04/2023 22:30:00 | 03/04/2023 06:30:00 | 01-EE-053 | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  | 8:00 | 02-Apr | 03-Apr | 02-Apr | 02-Apr
CDUVDU7050 | Completed | Pre Cleaning Inspection | 02/04/2023 06:36:17 | 02/04/2023 06:36:36 | 03/04/2023 06:30:00 | 03/04/2023 09:30:00 | 01-EE-053 | EXCHANGER | 100 | INSPECTION |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 03-Apr | 03-Apr | 02-Apr | 02-Apr
CDUVDU9250 | Completed | Hydrojetting of Tube & Component | 02/04/2023 06:36:17 | 02/04/2023 06:36:36 | 04/04/2023 20:30:00 | 05/04/2023 02:30:00 | 01-EE-053 | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 6 | 6:00 | 0:00 |  | 6:00 | 04-Apr | 05-Apr | 02-Apr | 02-Apr
CDUVDU9600 | Completed | Air Drying | 02/04/2023 06:36:17 | 02/04/2023 06:36:36 | 05/04/2023 02:30:00 | 05/04/2023 06:30:00 | 01-EE-053 | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 05-Apr | 05-Apr | 02-Apr | 02-Apr
CDUVDU9820 | Completed | Post Cleaning Inspection | 02/04/2023 06:36:17 | 03/04/2023 06:22:25 | 05/04/2023 06:30:00 | 05/04/2023 10:30:00 | 01-EE-053 | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 23:46 | 19:46 |  | 05-Apr | 05-Apr | 02-Apr | 03-Apr
CDUVDU9990 | Completed | Channelhead Boxup | 16/04/2023 19:15:21 | 16/04/2023 19:16:03 | 05/04/2023 10:30:00 | 05/04/2023 18:30:00 | 01-EE-053 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:01 |  | 7:59 | 05-Apr | 05-Apr | 16-Apr | 16-Apr
CDUVDU10000 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 04/04/2023 08:02:37 | 04/04/2023 08:02:37 | 05/04/2023 10:30:00 | 05/04/2023 14:30:00 | 01-EE-052 | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:00 |  |  | 05-Apr | 05-Apr | 04-Apr | 04-Apr
CDUVDU10330 | Completed | Shifting of Bundle from HJ Bay | 04/04/2023 08:02:37 | 04/04/2023 08:02:37 | 05/04/2023 14:30:00 | 05/04/2023 18:30:00 | 01-EE-052 | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  |  | 05-Apr | 05-Apr | 04-Apr | 04-Apr
CDUVDU10550 | Completed | Carryout Bundle Insertion | 04/04/2023 08:02:37 | 04/04/2023 08:02:37 | 05/04/2023 18:30:00 | 06/04/2023 02:30:00 | 01-EE-052 | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 0:00 |  |  | 05-Apr | 06-Apr | 04-Apr | 04-Apr
CDUVDU10880 | Completed | Channelhead Boxup | 04/04/2023 19:21:50 | 04/04/2023 19:23:01 | 06/04/2023 02:30:00 | 06/04/2023 10:30:00 | 01-EE-052 | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:01 |  | 7:59 | 06-Apr | 06-Apr | 04-Apr | 04-Apr
CDUVDU11320 | Completed | Carryout Shell Test | 04/04/2023 19:23:20 | 04/04/2023 19:23:25 | 06/04/2023 10:30:00 | 07/04/2023 01:30:00 | 01-EE-052 | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 0:00 |  | 15:00 | 06-Apr | 07-Apr | 04-Apr | 04-Apr
CDUVDU12360 | Completed | Back Dome Boxup | 04/04/2023 19:23:33 | 04/04/2023 19:23:39 | 07/04/2023 01:30:00 | 07/04/2023 09:30:00 | 01-EE-052 | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 0:00 |  | 8:00 | 07-Apr | 07-Apr | 04-Apr | 04-Apr
CDUVDU12880 | Completed | Final Test | 04/04/2023 19:23:53 | 04/04/2023 19:23:57 | 07/04/2023 09:30:00 | 08/04/2023 00:30:00 | 01-EE-052 | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 0:00 |  | 15:00 | 07-Apr | 08-Apr | 04-Apr | 04-Apr
CDUVDU13740 | Completed | Deblinding | 16/04/2023 06:43:45 | 16/04/2023 06:43:56 | 08/04/2023 00:30:00 | 08/04/2023 08:30:00 | 01-EE-052 | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 08-Apr | 08-Apr | 16-Apr | 16-Apr
CDUVDU6080 | Completed | Blinding As Per Blind List | 31/03/2023 09:51:00 | 31/03/2023 15:52:00 | 02/04/2023 14:30:00 | 02/04/2023 22:30:00 | 01-EE-052 | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 6:01 |  | 1:59 | 02-Apr | 02-Apr | 31-Mar | 31-Mar
CDUVDU6590 | Completed | Carryout Component Dropping | 31/03/2023 12:52:00 | 31/03/2023 18:52:00 | 02/04/2023 22:30:00 | 03/04/2023 04:30:00 | 01-EE-052 | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 6 | 6:00 | 6:00 |  |  | 02-Apr | 03-Apr | 31-Mar | 31-Mar
CDUVDU6860 | Completed | Carryout Bundle Pullout | 31/03/2023 21:53:00 | 01/04/2023 09:53:52 | 03/04/2023 04:30:00 | 03/04/2023 12:30:00 | 01-EE-052 | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 8 | 8:00 | 12:01 | 4:01 |  | 03-Apr | 03-Apr | 31-Mar | 01-Apr
CDUVDU7610 | Completed | Pre Cleaning Inspection | 01/04/2023 10:04:20 | 01/04/2023 17:26:15 | 03/04/2023 12:30:00 | 03/04/2023 15:30:00 | 01-EE-052 | EXCHANGER | 100 | INSPECTION |  |  | 3 | 3:00 | 7:22 | 4:22 |  | 03-Apr | 03-Apr | 01-Apr | 01-Apr
CDUVDU7810 | Completed | Shifting of Bundle to HJ Bay | 02/04/2023 06:38:53 | 02/04/2023 06:38:56 | 03/04/2023 15:30:00 | 03/04/2023 19:30:00 | 01-EE-052 | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 03-Apr | 03-Apr | 02-Apr | 02-Apr
CDUVDU9480 | Completed | Hydrojetting of Tube Bundle | 03/04/2023 06:26:41 | 03/04/2023 10:30:14 | 05/04/2023 00:30:00 | 05/04/2023 07:30:00 | 01-EE-052 | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 7 | 7:00 | 4:04 |  | 2:56 | 05-Apr | 05-Apr | 03-Apr | 03-Apr
CDUVDU9850 | Completed | Air Drying | 04/04/2023 08:02:37 | 04/04/2023 08:02:37 | 05/04/2023 07:30:00 | 05/04/2023 10:30:00 | 01-EE-052 | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  |  | 05-Apr | 05-Apr | 04-Apr | 04-Apr
CDUVDU11240 | Completed | Hydrojetting of Tube Bundle | 09/04/2023 07:40:10 | 11/04/2023 03:17:25 | 06/04/2023 09:30:00 | 06/04/2023 15:30:00 | 01-EE-051B | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 6 | 6:00 | 43:37 | 37:37 |  | 06-Apr | 06-Apr | 09-Apr | 11-Apr
CDUVDU11660 | Completed | Air Drying | 11/04/2023 03:17:25 | 11/04/2023 03:17:25 | 06/04/2023 15:30:00 | 06/04/2023 18:30:00 | 01-EE-051B | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  |  | 06-Apr | 06-Apr | 11-Apr | 11-Apr
CDUVDU11890 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 11/04/2023 03:17:25 | 11/04/2023 03:17:25 | 06/04/2023 18:30:00 | 06/04/2023 22:30:00 | 01-EE-051B | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:00 |  |  | 06-Apr | 06-Apr | 11-Apr | 11-Apr
CDUVDU12200 | Completed | Shifting of Bundle from HJ Bay | 11/04/2023 07:31:49 | 11/04/2023 07:31:49 | 06/04/2023 22:30:00 | 07/04/2023 02:30:00 | 01-EE-051B | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  |  | 06-Apr | 07-Apr | 11-Apr | 11-Apr
CDUVDU12480 | Completed | Carryout Bundle Insertion | 11/04/2023 07:31:49 | 11/04/2023 07:31:49 | 07/04/2023 02:30:00 | 07/04/2023 10:30:00 | 01-EE-051B | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 0:00 |  |  | 07-Apr | 07-Apr | 11-Apr | 11-Apr
CDUVDU12930 | Completed | Channelhead Boxup | 12/04/2023 10:10:11 | 12/04/2023 10:10:17 | 07/04/2023 10:30:00 | 07/04/2023 18:30:00 | 01-EE-051B | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  | 8:00 | 07-Apr | 07-Apr | 12-Apr | 12-Apr
CDUVDU13450 | Completed | Carryout Shell Test | 12/04/2023 10:10:44 | 12/04/2023 18:36:41 | 07/04/2023 18:30:00 | 08/04/2023 09:30:00 | 01-EE-051B | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 8:26 |  | 6:34 | 07-Apr | 08-Apr | 12-Apr | 12-Apr
CDUVDU14370 | Completed | Back Dome Boxup | 15/04/2023 03:29:16 | 15/04/2023 03:29:26 | 08/04/2023 09:30:00 | 08/04/2023 17:30:00 | 01-EE-051B | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 0:00 |  | 8:00 | 08-Apr | 08-Apr | 15-Apr | 15-Apr
CDUVDU15000 | Completed | Final Test | 15/04/2023 03:29:42 | 15/04/2023 10:50:20 | 08/04/2023 17:30:00 | 09/04/2023 08:30:00 | 01-EE-051B | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 7:21 |  | 7:39 | 08-Apr | 09-Apr | 15-Apr | 15-Apr
CDUVDU16150 | Completed | Deblinding | 19/04/2023 02:42:04 | 19/04/2023 02:42:12 | 09/04/2023 08:30:00 | 09/04/2023 16:30:00 | 01-EE-051B | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 09-Apr | 09-Apr | 19-Apr | 19-Apr
CDUVDU6070 | Completed | Blinding As Per Blind List | 02/04/2023 05:42:35 | 02/04/2023 05:42:35 | 02/04/2023 14:30:00 | 02/04/2023 22:30:00 | 01-EE-051B | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  |  | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU6580 | Completed | Carryout Component Dropping | 01/04/2023 16:02:30 | 01/04/2023 16:02:38 | 02/04/2023 22:30:00 | 03/04/2023 04:30:00 | 01-EE-051B | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 6 | 6:00 | 0:00 |  | 6:00 | 02-Apr | 03-Apr | 01-Apr | 01-Apr
CDUVDU6850 | Completed | Carryout Bundle Pullout | 02/04/2023 05:42:35 | 02/04/2023 05:42:35 | 03/04/2023 04:30:00 | 03/04/2023 12:30:00 | 01-EE-051B | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 8 | 8:00 | 0:00 |  |  | 03-Apr | 03-Apr | 02-Apr | 02-Apr
CDUVDU7600 | Completed | Pre Cleaning Inspection | 02/04/2023 07:52:48 | 02/04/2023 07:52:48 | 03/04/2023 12:30:00 | 03/04/2023 15:30:00 | 01-EE-051B | EXCHANGER | 100 | INSPECTION |  |  | 3 | 3:00 | 0:00 |  |  | 03-Apr | 03-Apr | 02-Apr | 02-Apr
CDUVDU7800 | Completed | Shifting of Bundle to HJ Bay | 03/04/2023 06:26:03 | 03/04/2023 06:26:13 | 03/04/2023 15:30:00 | 03/04/2023 19:30:00 | 01-EE-051B | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 03-Apr | 03-Apr | 03-Apr | 03-Apr
CDUVDU10820 | Completed | Hydrojetting of Tube Bundle | 09/04/2023 07:39:16 | 11/04/2023 03:04:39 | 06/04/2023 02:30:00 | 06/04/2023 09:30:00 | 01-EE-051A | EXCHANGER | 100 | MECHANICAL | HYDROJETTING |  | 7 | 7:00 | 43:25 | 36:25 |  | 06-Apr | 06-Apr | 09-Apr | 11-Apr
CDUVDU11220 | Completed | Air Drying | 11/04/2023 03:04:59 | 11/04/2023 03:05:07 | 06/04/2023 09:30:00 | 06/04/2023 12:30:00 | 01-EE-051A | EXCHANGER | 100 | MECHANICAL |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 06-Apr | 06-Apr | 11-Apr | 11-Apr
CDUVDU11380 | Completed | Post Cleaning Inspection Of Bundle,Component And Shell | 11/04/2023 03:15:24 | 11/04/2023 03:17:01 | 06/04/2023 12:30:00 | 06/04/2023 16:30:00 | 01-EE-051A | EXCHANGER | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:02 |  | 3:58 | 06-Apr | 06-Apr | 11-Apr | 11-Apr
CDUVDU11750 | Completed | Shifting of Bundle from HJ Bay | 11/04/2023 07:31:31 | 11/04/2023 07:31:31 | 06/04/2023 16:30:00 | 06/04/2023 20:30:00 | 01-EE-051A | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  |  | 06-Apr | 06-Apr | 11-Apr | 11-Apr
CDUVDU11980 | Completed | Carryout Bundle Insertion | 11/04/2023 07:31:31 | 11/04/2023 07:31:31 | 06/04/2023 20:30:00 | 07/04/2023 04:30:00 | 01-EE-051A | EXCHANGER | 100 | MECHANICAL | BUNDLE INSERTION |  | 8 | 8:00 | 0:00 |  |  | 06-Apr | 07-Apr | 11-Apr | 11-Apr
CDUVDU12590 | Completed | Channelhead Boxup | 12/04/2023 10:06:59 | 12/04/2023 10:08:54 | 07/04/2023 04:30:00 | 07/04/2023 12:30:00 | 01-EE-051A | EXCHANGER | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:02 |  | 7:58 | 07-Apr | 07-Apr | 12-Apr | 12-Apr
CDUVDU12980 | Completed | Carryout Shell Test | 12/04/2023 10:09:09 | 12/04/2023 18:36:21 | 07/04/2023 12:30:00 | 08/04/2023 03:30:00 | 01-EE-051A | EXCHANGER | 100 | INSPECTION | SHELL TEST |  | 15 | 15:00 | 8:27 |  | 6:33 | 07-Apr | 08-Apr | 12-Apr | 12-Apr
CDUVDU13940 | Completed | Back Dome Boxup | 15/04/2023 03:28:25 | 15/04/2023 03:28:34 | 08/04/2023 03:30:00 | 08/04/2023 11:30:00 | 01-EE-051A | EXCHANGER | 100 | MECHANICAL | BOX UP | BOX UP | 8 | 8:00 | 0:00 |  | 8:00 | 08-Apr | 08-Apr | 15-Apr | 15-Apr
CDUVDU14470 | Completed | Final Test | 15/04/2023 03:28:25 | 15/04/2023 07:14:52 | 08/04/2023 11:30:00 | 09/04/2023 02:30:00 | 01-EE-051A | EXCHANGER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 3:46 |  | 11:14 | 08-Apr | 09-Apr | 15-Apr | 15-Apr
CDUVDU15750 | Completed | Deblinding | 19/04/2023 02:41:36 | 19/04/2023 02:41:45 | 09/04/2023 02:30:00 | 09/04/2023 10:30:00 | 01-EE-051A | EXCHANGER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 09-Apr | 09-Apr | 19-Apr | 19-Apr
CDUVDU5680 | Completed | Blinding As Per Blind List | 02/04/2023 05:42:19 | 02/04/2023 05:42:19 | 02/04/2023 14:30:00 | 02/04/2023 22:30:00 | 01-EE-051A | EXCHANGER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  |  | 02-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU6400 | Completed | Carryout Component Dropping | 01/04/2023 16:01:21 | 01/04/2023 16:01:33 | 02/04/2023 22:30:00 | 03/04/2023 04:30:00 | 01-EE-051A | EXCHANGER | 100 | MECHANICAL | OPENING | OPENING | 6 | 6:00 | 0:00 |  | 6:00 | 02-Apr | 03-Apr | 01-Apr | 01-Apr
CDUVDU6840 | Completed | Carryout Bundle Pullout | 02/04/2023 05:42:19 | 02/04/2023 05:42:19 | 03/04/2023 04:30:00 | 03/04/2023 12:30:00 | 01-EE-051A | EXCHANGER | 100 | MECHANICAL | BUNDLE PULL OUT |  | 8 | 8:00 | 0:00 |  |  | 03-Apr | 03-Apr | 02-Apr | 02-Apr
CDUVDU7470 | Completed | Pre Cleaning Inspection | 02/04/2023 07:52:23 | 02/04/2023 07:52:23 | 03/04/2023 12:30:00 | 03/04/2023 15:30:00 | 01-EE-051A | EXCHANGER | 100 | INSPECTION |  |  | 3 | 3:00 | 0:00 |  |  | 03-Apr | 03-Apr | 02-Apr | 02-Apr
CDUVDU7790 | Completed | Shifting of Bundle to HJ Bay | 03/04/2023 06:25:32 | 03/04/2023 06:25:42 | 03/04/2023 15:30:00 | 03/04/2023 19:30:00 | 01-EE-051A | EXCHANGER | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 03-Apr | 03-Apr | 03-Apr | 03-Apr
CDUVDU20930 | Not Started | All header and box emergency steam nozzle checking of FF-1& 2 in both convection and radiation section. |  |  | 11/04/2023 02:00:00 | 16/04/2023 02:00:00 | 01-FF-001 AND 002 | MECHANICAL JOBS | 0 | MECHANICAL |  |  | 120 | 120:00 | 0:00 |  |  | 11-Apr | 16-Apr | - Date check | - Date check
CDUVDU3440 | Completed | Painting of CC-001 ovehead lines | 27/03/2023 11:11:34 | 08/04/2023 15:14:47 | 01/04/2023 14:30:00 | 09/04/2023 02:30:00 | CIVIL JOBS | CIVIL JOBS | 100 | CIVIL |  |  | 180 | 180:00 | 292:03 | 112:03 |  | 01-Apr | 09-Apr | 27-Mar | 08-Apr
CDUVDU8110 | In Progress | Heat efficiency painting in 01-FF-01/02 wall | 03/04/2023 11:06:08 |  | 03/04/2023 14:00:00 | 11/04/2023 02:00:00 | CIVIL JOBS | CIVIL JOBS | 90 | CIVIL |  |  | 180 | 180:00 | 0:00 |  |  | 03-Apr | 11-Apr | 03-Apr | - Date check
CDUVDU9020 | In Progress | underground leakage arrest | 06/04/2023 17:18:14 |  | 04/04/2023 14:00:00 | 14/04/2023 14:00:00 | CIVIL JOBS | CIVIL JOBS | 90 | CIVIL |  |  | 240 | 240:00 | 0:00 |  |  | 04-Apr | 14-Apr | 06-Apr | - Date check
CDUVDU9030 | Completed | Staircase gratings check and repairing | 13/04/2023 18:00:59 | 26/04/2023 17:51:55 | 04/04/2023 14:00:00 | 14/04/2023 14:00:00 | CIVIL JOBS | CIVIL JOBS | 100 | CIVIL |  |  | 240 | 240:00 | 311:51 | 71:51 |  | 04-Apr | 14-Apr | 13-Apr | 26-Apr
CDUVDU8830 | Completed | Removal of CDU column old redundent line | 07/04/2023 20:08:19 | 23/04/2023 12:42:30 | 04/04/2023 14:00:00 | 06/04/2023 14:00:00 | SAFETY JOB | SAFETY JOBS | 100 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 48 | 48:00 | 376:34 | 328:34 |  | 04-Apr | 06-Apr | 07-Apr | 23-Apr
CDUVDU8930 | Completed | Provide end flange in nitogen header | 13/04/2023 09:37:23 | 13/04/2023 09:37:28 | 04/04/2023 14:00:00 | 09/04/2023 14:00:00 | SAFETY JOB | SAFETY JOBS | 100 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 120 | 120:00 | 0:00 |  | 120:00 | 04-Apr | 09-Apr | 13-Apr | 13-Apr
CDUVDU8840 | Completed | Removal of old crude booster pumpalong with cable trays and steam line | 08/04/2023 10:33:16 | 23/04/2023 12:43:29 | 04/04/2023 14:00:00 | 12/04/2023 18:00:00 | No Machine | No Machine Type | 100 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 196 | 196:00 | 362:10 | 166:10 |  | 04-Apr | 12-Apr | 08-Apr | 23-Apr
CDUVDU8841 | Completed | Removal of old crude booster pump foundation | 28/03/2023 09:13:57 | 27/04/2023 08:29:01 | 12/04/2023 18:00:00 | 21/04/2023 02:00:00 | SAFETY JOB | SAFETY JOBS | 100 | CIVIL | WORK COMPLETED | WORK COMPLETED | 200 | 200:00 | 719:15 | 519:15 |  | 12-Apr | 21-Apr | 28-Mar | 27-Apr
CDUVDU8850 | Completed | MP Steam header (east side), Emergency Steam line to FF0,Pass 1&4 line FF-01,4"-P-01-2149-A6N-IT,01-VV-008,OH VAPOURLINE | 17/04/2023 11:19:25 | 17/04/2023 11:19:39 | 04/04/2023 14:00:00 | 06/04/2023 06:00:00 | SAFETY JOB | SAFETY JOBS | 100 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 40 | 40:00 | 0:00 |  | 40:00 | 04-Apr | 06-Apr | 17-Apr | 17-Apr
CDUVDU8890 | Completed | Unchoking of Service water connection FF-01 | 17/04/2023 11:08:33 | 17/04/2023 11:17:36 | 04/04/2023 14:00:00 | 07/04/2023 14:00:00 | SAFETY JOB | SAFETY JOBS | 100 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 72 | 72:00 | 0:09 |  | 71:51 | 04-Apr | 07-Apr | 17-Apr | 17-Apr
CDUVDU8900 | Completed | Providing fire proofing up to top level in CDU air fin cooler | 19/04/2023 09:32:06 | 23/04/2023 12:46:06 | 04/04/2023 14:00:00 | 09/04/2023 14:00:00 | SAFETY JOB | SAFETY JOBS | 100 | CIVIL | WORK COMPLETED | WORK COMPLETED | 120 | 120:00 | 99:14 |  | 20:46 | 04-Apr | 09-Apr | 19-Apr | 23-Apr
CDUVDU8910 | In Progress | Providing auto sprinkler for LPG Reflux pump PA-12 A/B | 16/04/2023 11:20:07 |  | 04/04/2023 14:00:00 | 14/04/2023 14:00:00 | SAFETY JOB | SAFETY JOBS | 53 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 240 | 240:00 | 0:00 |  |  | 04-Apr | 14-Apr | 16-Apr | - Date check
A1030 | Completed | Providing 2nd layer protection at staircase VV-23 | 11/04/2023 15:24:21 | 13/04/2023 10:55:04 | 06/04/2023 22:00:00 | 22/04/2023 18:00:00 | SAFETY JOB | CIVIL JOBS | 100 | CIVIL | WORK COMPLETED | WORK COMPLETED | 380 | 380:00 | 43:31 |  | 336:29 | 06-Apr | 22-Apr | 11-Apr | 13-Apr
A1040 | Completed | Proper support to be provided for HN to SN manifold at B/L pipe rack. Presently it is tied with rope | 03/04/2023 11:06:19 | 03/04/2023 18:40:27 | 04/04/2023 14:00:00 | 20/04/2023 10:00:00 | SAFETY JOB | CIVIL JOBS | 100 | CIVIL | WORK COMPLETED | WORK COMPLETED | 380 | 380:00 | 7:34 |  | 372:26 | 04-Apr | 20-Apr | 03-Apr | 03-Apr
A1060 | Completed | Provision of safety guard in Monkey Ladder at Ejector platform CDU/VDU | 03/04/2023 11:06:31 | 03/04/2023 18:40:02 | 04/04/2023 14:00:00 | 20/04/2023 10:00:00 | SAFETY JOB | CIVIL JOBS | 100 | CIVIL | WORK COMPLETED | WORK COMPLETED | 380 | 380:00 | 7:34 |  | 372:26 | 04-Apr | 20-Apr | 03-Apr | 03-Apr
A1070 | Completed | Provision of Monkey ladder in safety guard of VV-105,14,13,103,101, 09 and 04 | 06/04/2023 14:51:11 | 11/04/2023 18:18:14 | 04/04/2023 14:00:00 | 22/04/2023 02:00:00 | SAFETY JOB | CIVIL JOBS | 100 | CIVIL | WORK COMPLETED | WORK COMPLETED | 420 | 420:00 | 123:27 |  | 296:33 | 04-Apr | 22-Apr | 06-Apr | 11-Apr
A1140 | Completed | Easy approach staircase to FF-1 burner platform from CCR side staircase | 11/04/2023 11:07:12 | 20/04/2023 16:12:26 | 04/04/2023 14:00:00 | 20/04/2023 10:00:00 | SAFETY JOB | CIVIL JOBS | 100 | CIVIL | WORK COMPLETED | WORK COMPLETED | 380 | 380:00 | 221:05 |  | 158:55 | 04-Apr | 20-Apr | 11-Apr | 20-Apr
A1150 | Completed | New monkey ladder for alternate escaped route at EE-61 and EE- 91 platform | 07/04/2023 11:59:22 | 26/04/2023 11:28:30 | 04/04/2023 14:00:00 | 22/04/2023 02:00:00 | SAFETY JOB | CIVIL JOBS | 100 | CIVIL | WORK COMPLETED | WORK COMPLETED | 420 | 420:00 | 455:29 | 35:29 |  | 04-Apr | 22-Apr | 07-Apr | 26-Apr
CDUVDU8920 | In Progress | Providing closed loop sampling for all sampling points | 06/04/2023 14:48:47 |  | 04/04/2023 14:00:00 | 22/04/2023 02:00:00 | SAFETY JOB | SAFETY JOBS | 16 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 420 | 420:00 | 0:00 |  |  | 04-Apr | 22-Apr | 06-Apr | - Date check
A1230 | In Progress | TSV outlet routing from OWS to Closed system (CBD) | 17/04/2023 12:02:43 |  | 10/04/2023 14:00:00 | 15/04/2023 14:00:00 | SAFETY JOB | SAFETY JOBS | 50 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 120 | 120:00 | 0:00 |  |  | 10-Apr | 15-Apr | 17-Apr | - Date check
A1000 | In Progress | Seal Plan Change of CDU VDU Pumps | 07/04/2023 19:30:00 |  | 07/04/2023 14:00:00 | 11/04/2023 14:00:00 | SEAL PLAN PUMPS | HOT JOB | 0.79681 | MECHANICAL |  |  | 96 | 96:00 | 0:00 |  |  | 07-Apr | 11-Apr | 07-Apr | - Date check
A1010 | Completed | ROV 1501 to be closed on actuation of CDU bottom level low low interlock | 18/04/2023 16:09:48 | 18/04/2023 16:10:48 | 11/04/2023 14:00:00 | 22/04/2023 14:00:00 | ROV 1501 | HOT JOB | 100 | MECHANICAL |  |  | 264 | 264:00 | 0:01 |  | 263:59 | 11-Apr | 22-Apr | 18-Apr | 18-Apr
CDUVDU20610 | Completed | Automatic fire water spray system installation for LPG pumps | 07/04/2023 09:19:41 | 18/04/2023 10:58:25 | 11/04/2023 06:00:00 | 17/04/2023 22:00:00 | MOC/V2/34 | MOC JOBS AFTER CUT OFF | 100 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 160 | 160:00 | 265:39 | 105:39 |  | 11-Apr | 17-Apr | 07-Apr | 18-Apr
CDUVDU29110 | In Progress | Provide double mechanical seal | 09/04/2023 09:17:59 |  | 17/04/2023 22:00:00 | 21/04/2023 22:00:00 | MOC/V2/31 | MOC JOBS AFTER CUT OFF | 0 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 96 | 96:00 | 0:00 |  |  | 17-Apr | 21-Apr | 09-Apr | - Date check
CDUVDU20590 | In Progress | Commissioning | 07/04/2023 09:19:16 |  | 11/04/2023 06:00:00 | 21/04/2023 06:00:00 | MOC/423 | MOC JOBS AFTER CUT OFF | 85 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 240 | 240:00 | 0:00 |  |  | 11-Apr | 21-Apr | 07-Apr | - Date check
CDUVDU8950 | In Progress | Additional facillity for corrosion inhibitor dosing to VDU Overhead | 09/04/2023 09:18:46 |  | 04/04/2023 14:00:00 | 09/04/2023 14:00:00 | MOC/V2/69 | MOC JOBS AFTER CUT OFF | 0 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 120 | 120:00 | 0:00 |  |  | 04-Apr | 09-Apr | 09-Apr | - Date check
CDUVDU16590 | Completed | TVS Outlet routing OWS to closed system(CBD) | 09/04/2023 09:19:02 | 24/04/2023 15:03:46 | 09/04/2023 14:00:00 | 16/04/2023 06:00:00 | MOC/V2/87 | MOC JOBS AFTER CUT OFF | 100 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 160 | 160:00 | 365:45 | 205:45 |  | 09-Apr | 16-Apr | 09-Apr | 24-Apr
A1200 | In Progress | Installation of 4 numbers of ultrasonic mass flow meters in Vacuum furnace Pass flow. | 09/04/2023 09:18:19 |  | 16/04/2023 06:00:00 | 21/04/2023 06:00:00 | MOC/V2/52 | MOC JOBS AFTER CUT OFF | 44 | INSTRUMENTATION | WORK COMPLETED | WORK COMPLETED | 120 | 120:00 | 0:00 |  |  | 16-Apr | 21-Apr | 09-Apr | - Date check
A1210 | In Progress | ROV1501 to be closed on actuation of CDU bottom Level Low Low interlock | 05/04/2023 12:13:31 |  | 16/04/2023 06:00:00 | 21/04/2023 06:00:00 | MOC/V2/85 | MOC JOBS AFTER CUT OFF | 90 | INSTRUMENTATION | WORK COMPLETED | WORK COMPLETED | 120 | 120:00 | 0:00 |  |  | 16-Apr | 21-Apr | 05-Apr | - Date check
A1160 | In Progress | Seal Plan change of CDU/VDU pumps to API plan 54 | 29/03/2023 09:02:00 |  | 16/04/2023 06:00:00 | 21/04/2023 06:00:00 | MOC/700 | MOC JOBS BEFORE CUT OFF | 93.0556 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 120 | 120:00 | 0:00 |  |  | 16-Apr | 21-Apr | 29-Mar | - Date check
CDUVDU16580 | Completed | Sampling point installation | 05/04/2023 19:18:51 | 18/04/2023 10:57:12 | 09/04/2023 14:00:00 | 16/04/2023 06:00:00 | MOC/20972 | MOC JOBS BEFORE CUT OFF | 100 | MECHANICAL |  |  | 160 | 160:00 | 303:38 | 143:38 |  | 09-Apr | 16-Apr | 05-Apr | 18-Apr
CDUVDU20600 | Completed | Sampling point with cooler installation in HGO,RCO,LVGO,MVGO,HVGO,VR | 06/04/2023 16:19:06 | 18/04/2023 10:57:18 | 11/04/2023 06:00:00 | 17/04/2023 22:00:00 | MOC/20972 | MOC JOBS BEFORE CUT OFF | 100 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 160 | 160:00 | 282:38 | 122:38 |  | 11-Apr | 17-Apr | 06-Apr | 18-Apr
CDUVDU8940 | Completed | Closed sample point installation | 05/04/2023 19:18:04 | 18/04/2023 10:58:03 | 04/04/2023 14:00:00 | 11/04/2023 06:00:00 | MOC/V2/26 | MOC JOBS BEFORE CUT OFF | 100 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 160 | 160:00 | 303:40 | 143:40 |  | 04-Apr | 11-Apr | 05-Apr | 18-Apr
A1170 | Completed | Fit and welding of flanges for installation of Flow Meter | 05/04/2023 12:06:10 | 18/04/2023 10:55:22 | 16/04/2023 06:00:00 | 18/04/2023 06:00:00 | MOC/20966 | MOC JOBS BEFORE CUT OFF | 100 | MECHANICAL |  |  | 48 | 48:00 | 310:49 | 262:49 |  | 16-Apr | 18-Apr | 05-Apr | 18-Apr
A1220 | Completed | Flow meter installation of PA-21A/B discharge to VR | 18/04/2023 10:56:05 | 18/04/2023 10:56:24 | 18/04/2023 06:00:00 | 22/04/2023 06:00:00 | MOC/20966 | MOC JOBS BEFORE CUT OFF | 100 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 96 | 96:00 | 0:00 |  | 96:00 | 18-Apr | 22-Apr | 18-Apr | 18-Apr
CDUVDU14630 | In Progress | Installation of remote operated HVLRM(2 Nos) | 06/04/2023 16:12:34 |  | 08/04/2023 14:00:00 | 18/04/2023 14:00:00 | MOC/611 | MOC JOBS BEFORE CUT OFF | 93.617 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 240 | 240:00 | 0:00 |  |  | 08-Apr | 18-Apr | 06-Apr | - Date check
A1180 | In Progress | Provision of minimum circulation flow in 01-PA-18A/B. | 05/04/2023 12:07:55 |  | 16/04/2023 06:00:00 | 21/04/2023 06:00:00 | MOC/V2/9 | MOC JOBS BEFORE CUT OFF | 63 | INSTRUMENTATION | WORK COMPLETED | WORK COMPLETED | 120 | 120:00 | 0:00 |  |  | 16-Apr | 21-Apr | 05-Apr | - Date check
A1190 | Completed | 01-PA-22A/B (VDU column bottom pump) replacement with New pumps | 04/04/2023 08:46:14 | 26/04/2023 17:03:36 | 16/04/2023 06:00:00 | 21/04/2023 06:00:00 | MOC/20835 | MOC JOBS BEFORE CUT OFF | 100 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 120 | 120:00 | 536:17 | 416:17 |  | 16-Apr | 21-Apr | 04-Apr | 26-Apr
CDUVDU26580 | Completed | Shifting of superheated steam temp indicator of FF-2 with new Temp Indicator | 07/04/2023 09:17:15 | 18/04/2023 10:56:49 | 09/04/2023 14:00:00 | 14/04/2023 14:00:00 | MOC/20967 | MOC JOBS BEFORE CUT OFF | 100 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 120 | 120:00 | 265:40 | 145:40 |  | 09-Apr | 14-Apr | 07-Apr | 18-Apr
CDUVDU16570 | Completed | Source water closed sampling point installation | 07/04/2023 09:21:35 | 18/04/2023 10:57:46 | 09/04/2023 14:00:00 | 16/04/2023 06:00:00 | MOC/20976 | MOC JOBS BEFORE CUT OFF | 100 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 160 | 160:00 | 265:36 | 105:36 |  | 09-Apr | 16-Apr | 07-Apr | 18-Apr
A1020 | In Progress | ICMS OVERHAULING | 29/03/2023 09:53:21 |  | 02/04/2023 08:00:00 | 20/04/2023 20:00:00 | ICMS O/H | ICMS O/H | 95 | PPM |  |  | 444 | 444:00 | 0:00 |  |  | 02-Apr | 20-Apr | 29-Mar | - Date check
A1080 | Completed | Scaffolding and Painting for CC-06 Overhead line | 27/03/2023 11:07:23 | 12/04/2023 11:47:35 | 26/03/2023 06:00:00 | 22/04/2023 18:00:00 | CIVIL JOBS | CIVIL JOBS | 100 | CIVIL |  |  | 660 | 660:00 | 384:40 |  | 275:20 | 26-Mar | 22-Apr | 27-Mar | 12-Apr
A1100 | Completed | New VR pump surface dressing /anchoring and grouting job. | 27/03/2023 11:08:53 | 27/04/2023 08:28:35 | 26/03/2023 06:00:00 | 15/04/2023 18:00:00 | CIVIL JOBS | CIVIL JOBS | 100 | CIVIL |  |  | 492 | 492:00 | 741:20 | 249:20 |  | 26-Mar | 15-Apr | 27-Mar | 27-Apr
A1110 | Completed | Replacement of damaged gratings of staircase of CC-001/006/005 & FF-1 & FF-2 | 10/04/2023 15:41:14 | 25/04/2023 16:14:49 | 04/04/2023 14:00:00 | 20/04/2023 10:00:00 | CIVIL JOBS | CIVIL JOBS | 100 | CIVIL |  |  | 380 | 380:00 | 360:34 |  | 19:26 | 04-Apr | 20-Apr | 10-Apr | 25-Apr
A1120 | Completed | EE-29A/B support & T structure repairing as per inspection | 10/04/2023 15:39:10 | 10/04/2023 19:18:08 | 04/04/2023 14:00:00 | 20/04/2023 10:00:00 | CIVIL JOBS | CIVIL JOBS | 100 | CIVIL |  |  | 380 | 380:00 | 3:39 |  | 376:21 | 04-Apr | 20-Apr | 10-Apr | 10-Apr
A1130 | Completed | RCC pavement dismantling/ Excavation and foundation job of new flushing oil pump as per MOC-2019-CDU-VDU-700 | 27/03/2023 11:09:04 | 04/04/2023 16:07:23 | 26/03/2023 06:00:00 | 06/04/2023 18:00:00 | CIVIL JOBS | CIVIL JOBS | 100 | CIVIL |  |  | 276 | 276:00 | 196:58 |  | 79:02 | 26-Mar | 06-Apr | 27-Mar | 04-Apr
CDUVDU1570 | Completed | Carry out blinding | 31/03/2023 09:26:23 | 04/04/2023 11:02:10 | 30/03/2023 06:00:00 | 31/03/2023 06:00:00 | 01-FF-001 | FURNACE | 100 | MECHANICAL | BLINDING | BLINDING | 24 | 24:00 | 97:36 | 73:36 |  | 30-Mar | 31-Mar | 31-Mar | 04-Apr
CDUVDU1950 | Completed | Carry out manway opening | 31/03/2023 09:27:38 | 01/04/2023 19:25:32 | 31/03/2023 06:00:00 | 31/03/2023 14:00:00 | 01-FF-001 | FURNACE | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 33:58 | 25:58 |  | 31-Mar | 31-Mar | 31-Mar | 01-Apr
CDUVDU21640 | In Progress | Carry out Process inspection of burners | 02/04/2023 16:33:00 |  | 11/04/2023 08:00:00 | 11/04/2023 12:00:00 | 01-FF-001 | FURNACE | 70 | TS |  |  | 4 | 4:00 | 0:00 |  |  | 11-Apr | 11-Apr | 02-Apr | - Date check
CDUVDU2450 | Completed | Carry out removal of burners | 31/03/2023 09:37:00 | 31/03/2023 09:37:12 | 31/03/2023 14:00:00 | 01/04/2023 08:00:00 | 01-FF-001 | FURNACE | 100 | MECHANICAL |  |  | 18 | 18:00 | 0:00 |  | 18:00 | 31-Mar | 01-Apr | 31-Mar | 31-Mar
CDUVDU3790 | In Progress | Carry out servicing of burners | 08/04/2023 11:11:14 |  | 01/04/2023 08:00:00 | 11/04/2023 08:00:00 | 01-FF-001 | FURNACE | 92 | MECHANICAL |  |  | 240 | 240:00 | 0:00 |  |  | 01-Apr | 11-Apr | 08-Apr | - Date check
CDUVDU1060 | Completed | Outlet coil support to be rectified | 17/04/2023 11:06:24 | 17/04/2023 11:16:32 | 31/03/2023 06:00:00 | 05/04/2023 06:00:00 | 01-FF-001 | FURNACE | 100 | MECHANICAL |  |  | 120 | 120:00 | 0:10 |  | 119:50 | 31-Mar | 05-Apr | 17-Apr | 17-Apr
CDUVDU10610 | Completed | Carry out Welding at ground level | 06/04/2023 10:52:17 | 09/04/2023 15:32:42 | 05/04/2023 14:00:00 | 06/04/2023 02:00:00 | 01-FF-001 | FURNACE | 100 | MECHANICAL |  |  | 12 | 12:00 | 76:40 | 64:40 |  | 05-Apr | 06-Apr | 06-Apr | 09-Apr
CDUVDU11260 | Completed | Carry out RT at ground level | 08/04/2023 15:11:13 | 09/04/2023 15:41:46 | 06/04/2023 02:00:00 | 06/04/2023 14:00:00 | 01-FF-001 | FURNACE | 100 | INSPECTION |  |  | 12 | 12:00 | 24:31 | 12:31 |  | 06-Apr | 06-Apr | 08-Apr | 09-Apr
CDUVDU12060 | Completed | PWHT | 17/04/2023 11:13:27 | 19/04/2023 10:10:56 | 06/04/2023 14:00:00 | 07/04/2023 06:00:00 | 01-FF-001 | FURNACE | 100 | INSPECTION |  |  | 16 | 16:00 | 46:57 | 30:57 |  | 06-Apr | 07-Apr | 17-Apr | 19-Apr
CDUVDU13060 | Completed | Carry out Hardness test | 18/04/2023 14:48:28 | 21/04/2023 19:41:10 | 07/04/2023 06:00:00 | 07/04/2023 08:00:00 | 01-FF-001 | FURNACE | 100 | INSPECTION |  |  | 2 | 2:00 | 76:53 | 74:53 |  | 07-Apr | 07-Apr | 18-Apr | 21-Apr
CDUVDU13250 | Completed | Removal of refractory for accessibilty of welding | 09/04/2023 15:33:37 | 09/04/2023 15:34:59 | 07/04/2023 08:00:00 | 07/04/2023 10:00:00 | 01-FF-001 | FURNACE | 100 | MECHANICAL |  |  | 2 | 2:00 | 0:01 |  | 1:59 | 07-Apr | 07-Apr | 09-Apr | 09-Apr
CDUVDU13400 | Completed | Carry out Erection of new tubes | 08/04/2023 10:14:15 | 09/04/2023 15:32:05 | 07/04/2023 10:00:00 | 07/04/2023 22:00:00 | 01-FF-001 | FURNACE | 100 | MECHANICAL |  |  | 12 | 12:00 | 29:18 | 17:18 |  | 07-Apr | 07-Apr | 08-Apr | 09-Apr
CDUVDU14020 | Completed | Carry out Fit up | 08/04/2023 15:15:14 | 13/04/2023 11:21:50 | 07/04/2023 22:00:00 | 08/04/2023 10:00:00 | 01-FF-001 | FURNACE | 100 | MECHANICAL | FIT UP |  | 12 | 12:00 | 116:07 | 104:07 |  | 07-Apr | 08-Apr | 08-Apr | 13-Apr
CDUVDU15020 | Completed | Carry out Pre heating and welding | 09/04/2023 15:24:43 | 18/04/2023 12:02:41 | 08/04/2023 10:00:00 | 09/04/2023 04:00:00 | 01-FF-001 | FURNACE | 100 | MECHANICAL | WELDING |  | 18 | 18:00 | 212:38 | 194:38 |  | 08-Apr | 09-Apr | 09-Apr | 18-Apr
CDUVDU16460 | Completed | Carry out RT | 17/04/2023 15:38:11 | 21/04/2023 19:41:29 | 09/04/2023 04:00:00 | 09/04/2023 16:00:00 | 01-FF-001 | FURNACE | 100 | INSPECTION |  |  | 12 | 12:00 | 100:03 | 88:03 |  | 09-Apr | 09-Apr | 17-Apr | 21-Apr
CDUVDU17570 | Completed | Carry out PWHT | 18/04/2023 14:48:43 | 21/04/2023 19:44:09 | 09/04/2023 16:00:00 | 10/04/2023 08:00:00 | 01-FF-001 | FURNACE | 100 | INSPECTION |  |  | 16 | 16:00 | 76:55 | 60:55 |  | 09-Apr | 10-Apr | 18-Apr | 21-Apr
CDUVDU19140 | Completed | Carry out hardness test | 22/04/2023 10:56:11 | 22/04/2023 10:56:19 | 10/04/2023 08:00:00 | 10/04/2023 10:00:00 | 01-FF-001 | FURNACE | 100 | INSPECTION | NDT |  | 2 | 2:00 | 0:00 |  | 2:00 | 10-Apr | 10-Apr | 22-Apr | 22-Apr
CDUVDU19340 | Completed | Carry out inspection by process and inspection | 20/04/2023 11:13:16 | 20/04/2023 11:13:27 | 10/04/2023 10:00:00 | 10/04/2023 14:00:00 | 01-FF-001 | FURNACE | 100 | TS | INSPECTION | INSPECTION | 4 | 4:00 | 0:00 |  | 4:00 | 10-Apr | 10-Apr | 20-Apr | 20-Apr
CDUVDU3800 | Completed | Entry | 02/04/2023 11:04:19 | 02/04/2023 16:40:25 | 01/04/2023 08:00:00 | 02/04/2023 02:00:00 | 01-FF-001 | FURNACE | 100 | MECHANICAL |  |  | 18 | 18:00 | 5:36 |  | 12:24 | 01-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU5010 | Completed | Carry out internal scaffolding upto arch section | 02/04/2023 18:47:55 | 06/04/2023 18:16:32 | 02/04/2023 02:00:00 | 03/04/2023 02:00:00 | 01-FF-001 | FURNACE | 100 | MECHANICAL |  |  | 24 | 24:00 | 95:29 | 71:29 |  | 02-Apr | 03-Apr | 02-Apr | 06-Apr
CDUVDU7370 | Completed | Carry out tube cleaning and elbows | 08/04/2023 19:09:36 | 14/04/2023 11:27:31 | 03/04/2023 02:00:00 | 04/04/2023 02:00:00 | 01-FF-001 | FURNACE | 100 | MECHANICAL | CLEANING |  | 24 | 24:00 | 136:18 | 112:18 |  | 03-Apr | 04-Apr | 08-Apr | 14-Apr
CDUVDU7380 | Completed | Carry out cutting of 2 Nos. tube | 04/04/2023 17:28:35 | 06/04/2023 10:59:08 | 03/04/2023 02:00:00 | 03/04/2023 14:00:00 | 01-FF-001 | FURNACE | 100 | MECHANICAL | CUTTING |  | 12 | 12:00 | 41:31 | 29:31 |  | 03-Apr | 03-Apr | 04-Apr | 06-Apr
CDUVDU8090 | Completed | Carry out Removal of tubes | 05/04/2023 16:02:19 | 05/04/2023 18:58:05 | 03/04/2023 14:00:00 | 04/04/2023 02:00:00 | 01-FF-001 | FURNACE | 100 | MECHANICAL |  |  | 12 | 12:00 | 2:56 |  | 9:04 | 03-Apr | 04-Apr | 05-Apr | 05-Apr
CDUVDU8630 | Completed | Carry out UT, DPT of TST points | 16/04/2023 10:08:18 | 16/04/2023 10:34:36 | 04/04/2023 02:00:00 | 04/04/2023 10:00:00 | 01-FF-001 | FURNACE | 100 | INSPECTION |  |  | 8 | 8:00 | 0:26 |  | 7:34 | 04-Apr | 04-Apr | 16-Apr | 16-Apr
CDUVDU8650 | Completed | Carry out Cutting and beveling of return bend of dismanteled tubes | 06/04/2023 09:24:30 | 06/04/2023 09:24:35 | 04/04/2023 02:00:00 | 04/04/2023 14:00:00 | 01-FF-001 | FURNACE | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:00 |  | 12:00 | 04-Apr | 04-Apr | 06-Apr | 06-Apr
CDUVDU9220 | Completed | Carry out insitu mettalography | 13/04/2023 18:53:06 | 20/04/2023 11:12:08 | 04/04/2023 10:00:00 | 05/04/2023 04:00:00 | 01-FF-001 | FURNACE | 100 | INSPECTION |  |  | 18 | 18:00 | 160:19 | 142:19 |  | 04-Apr | 05-Apr | 13-Apr | 20-Apr
CDUVDU9330 | Completed | Carry out fit up at ground level | 06/04/2023 10:51:30 | 09/04/2023 15:31:46 | 04/04/2023 14:00:00 | 05/04/2023 02:00:00 | 01-FF-001 | FURNACE | 100 | MECHANICAL |  |  | 12 | 12:00 | 76:40 | 64:40 |  | 04-Apr | 05-Apr | 06-Apr | 09-Apr
CDUVDU10570 | Completed | Carry out inspection | 16/04/2023 10:40:50 | 16/04/2023 10:40:54 | 05/04/2023 12:00:00 | 05/04/2023 16:00:00 | 01-FF-001 | FURNACE | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 05-Apr | 05-Apr | 16-Apr | 16-Apr
CDUVDU1960 | Completed | Carry out opening of side panels and manways | 02/04/2023 12:08:05 | 11/04/2023 11:12:06 | 31/03/2023 06:00:00 | 01/04/2023 06:00:00 | 01-FF-001 | FURNACE | 100 | MECHANICAL |  |  | 24 | 24:00 | 215:04 | 191:04 |  | 31-Mar | 01-Apr | 02-Apr | 11-Apr
CDUVDU19690 | Completed | Carry out Process inspection | 17/04/2023 17:32:04 | 19/04/2023 18:21:12 | 10/04/2023 14:00:00 | 10/04/2023 18:00:00 | 01-FF-001 | FURNACE | 100 | TS |  |  | 4 | 4:00 | 48:49 | 44:49 |  | 10-Apr | 10-Apr | 17-Apr | 19-Apr
CDUVDU2980 | Completed | Carry out tube cleaning and return elbows | 09/04/2023 15:34:36 | 18/04/2023 12:03:41 | 01/04/2023 06:00:00 | 02/04/2023 06:00:00 | 01-FF-001 | FURNACE | 100 | MECHANICAL |  |  | 24 | 24:00 | 212:29 | 188:29 |  | 01-Apr | 02-Apr | 09-Apr | 18-Apr
CDUVDU5320 | Completed | Carry out UT gauging of elbows and tubes | 09/04/2023 18:32:24 | 16/04/2023 10:57:48 | 02/04/2023 06:00:00 | 02/04/2023 18:00:00 | 01-FF-001 | FURNACE | 100 | INSPECTION |  |  | 12 | 12:00 | 160:25 | 148:25 |  | 02-Apr | 02-Apr | 09-Apr | 16-Apr
CDUVDU6750 | Completed | Carry out opening of TST flanges of I/L and O/L passes | 17/04/2023 15:39:16 | 19/04/2023 18:11:53 | 02/04/2023 18:00:00 | 03/04/2023 06:00:00 | 01-FF-001 | FURNACE | 100 | MECHANICAL |  |  | 12 | 12:00 | 50:33 | 38:33 |  | 02-Apr | 03-Apr | 17-Apr | 19-Apr
CDUVDU7620 | Completed | Carry out cleaning | 10/04/2023 11:40:10 | 18/04/2023 12:03:53 | 03/04/2023 06:00:00 | 03/04/2023 18:00:00 | 01-FF-001 | FURNACE | 100 | MECHANICAL |  |  | 12 | 12:00 | 192:24 | 180:24 |  | 03-Apr | 03-Apr | 10-Apr | 18-Apr
CDUVDU8340 | Completed | Carry out DPT of TST points | 20/04/2023 16:23:57 | 20/04/2023 16:24:15 | 03/04/2023 18:00:00 | 04/04/2023 00:00:00 | 01-FF-001 | FURNACE | 100 | INSPECTION |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 03-Apr | 04-Apr | 20-Apr | 20-Apr
CDUVDU8500 | Completed | Carry out internal scaffolding upto breech section | 17/04/2023 17:30:34 | 17/04/2023 17:30:39 | 04/04/2023 00:00:00 | 05/04/2023 00:00:00 | 01-FF-001 | FURNACE | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 04-Apr | 05-Apr | 17-Apr | 17-Apr
CDUVDU9860 | Completed | Carry out removal of refractory debris | 10/04/2023 11:39:34 | 18/04/2023 12:14:54 | 05/04/2023 00:00:00 | 05/04/2023 12:00:00 | 01-FF-001 | FURNACE | 100 | MECHANICAL |  |  | 12 | 12:00 | 192:35 | 180:35 |  | 05-Apr | 05-Apr | 10-Apr | 18-Apr
CDUVDU13620 | Completed | Carry out Inspection | 17/04/2023 17:32:56 | 17/04/2023 17:33:01 | 07/04/2023 14:00:00 | 07/04/2023 18:00:00 | 01-FF-001 | FURNACE | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 07-Apr | 07-Apr | 17-Apr | 17-Apr
CDUVDU13790 | In Progress | Carry out servicing of dampers and lovers | 16/04/2023 18:11:08 |  | 07/04/2023 18:00:00 | 12/04/2023 18:00:00 | 01-FF-001 | FURNACE | 81 | MECHANICAL |  |  | 120 | 120:00 | 0:00 |  |  | 07-Apr | 12-Apr | 16-Apr | - Date check
CDUVDU2460 | Completed | Carry out erection of scaffolding to access manways | 10/04/2023 11:30:43 | 13/04/2023 11:02:25 | 31/03/2023 14:00:00 | 01/04/2023 02:00:00 | 01-FF-001 | FURNACE | 100 | MECHANICAL |  |  | 12 | 12:00 | 71:32 | 59:32 |  | 31-Mar | 01-Apr | 10-Apr | 13-Apr
CDUVDU24620 | In Progress | Carry out Inspection by ops | 17/04/2023 17:34:19 |  | 12/04/2023 18:00:00 | 12/04/2023 21:00:00 | 01-FF-001 | FURNACE | 63 | OPERATION |  |  | 3 | 3:00 | 0:00 |  |  | 12-Apr | 12-Apr | 17-Apr | - Date check
CDUVDU2920 | Completed | Carry out manway opening | 13/04/2023 11:40:40 | 13/04/2023 11:40:54 | 01/04/2023 02:00:00 | 02/04/2023 02:00:00 | 01-FF-001 | FURNACE | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 01-Apr | 02-Apr | 13-Apr | 13-Apr
CDUVDU5020 | Completed | Entry | 13/04/2023 11:45:48 | 13/04/2023 11:45:53 | 02/04/2023 02:00:00 | 02/04/2023 14:00:00 | 01-FF-001 | FURNACE | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:00 |  | 12:00 | 02-Apr | 02-Apr | 13-Apr | 13-Apr
CDUVDU6380 | Completed | Carry out cleaning of internal surface of duct | 13/04/2023 15:44:06 | 25/04/2023 16:18:20 | 02/04/2023 14:00:00 | 07/04/2023 14:00:00 | 01-FF-001 | FURNACE | 100 | MECHANICAL |  |  | 120 | 120:00 | 288:34 | 168:34 |  | 02-Apr | 07-Apr | 13-Apr | 25-Apr
CDUVDU28210 | Completed | Carry out preperation of hydro test of pass # 1 and Pass # 2 | 13/04/2023 16:20:16 | 23/04/2023 18:16:58 | 16/04/2023 02:00:00 | 16/04/2023 14:00:00 | 01-FF-001 | FURNACE | 100 | MECHANICAL |  |  | 12 | 12:00 | 241:57 | 229:57 |  | 16-Apr | 16-Apr | 13-Apr | 23-Apr
CDUVDU28540 | Completed | Carry out hydro test of passes | 13/04/2023 16:21:20 | 24/04/2023 09:31:48 | 16/04/2023 14:00:00 | 17/04/2023 14:00:00 | 01-FF-001 | FURNACE | 100 | MECHANICAL | HYDRO TEST | HYDRO TEST | 24 | 24:00 | 257:10 | 233:10 |  | 16-Apr | 17-Apr | 13-Apr | 24-Apr
CDUVDU29120 | Completed | Carry out Inspection | 19/04/2023 18:25:13 | 24/04/2023 09:31:54 | 17/04/2023 14:00:00 | 17/04/2023 18:00:00 | 01-FF-001 | FURNACE | 100 | INSPECTION |  |  | 4 | 4:00 | 111:07 | 107:07 |  | 17-Apr | 17-Apr | 19-Apr | 24-Apr
CDUVDU11250 | Completed | Carry out application of refractory | 11/04/2023 13:51:46 | 27/04/2023 08:28:52 | 06/04/2023 02:00:00 | 11/04/2023 02:00:00 | 01-FF-001 | FURNACE | 100 | CIVIL |  |  | 120 | 120:00 | 378:37 | 258:37 |  | 06-Apr | 11-Apr | 11-Apr | 27-Apr
CDUVDU20900 | Not Started | Carry out final inspection |  |  | 11/04/2023 02:00:00 | 12/04/2023 02:00:00 | 01-FF-001 | FURNACE | 0 | INSPECTION |  |  | 24 | 24:00 | 0:00 |  |  | 11-Apr | 12-Apr | - Date check | - Date check
CDUVDU23310 | Not Started | Carry out box up of manway |  |  | 12/04/2023 02:00:00 | 12/04/2023 14:00:00 | 01-FF-001 | FURNACE | 0 | MECHANICAL |  |  | 12 | 12:00 | 0:00 |  |  | 12-Apr | 12-Apr | - Date check | - Date check
CDUVDU2470 | Completed | Carry out stack manway opening | 10/04/2023 11:35:32 | 13/04/2023 10:57:07 | 31/03/2023 14:00:00 | 01/04/2023 02:00:00 | 01-FF-001 | FURNACE | 100 | MECHANICAL |  |  | 12 | 12:00 | 71:22 | 59:22 |  | 31-Mar | 01-Apr | 10-Apr | 13-Apr
CDUVDU2471 | Completed | Stack painting using rope access technology through IRATA certified technician | 28/03/2023 12:55:41 | 08/04/2023 15:13:51 | 28/03/2023 06:00:00 | 07/04/2023 14:00:00 | 01-FF-001 | FURNACE | 100 | CIVIL |  |  | 248 | 248:00 | 266:18 | 18:18 |  | 28-Mar | 07-Apr | 28-Mar | 08-Apr
CDUVDU2930 | Completed | Carry out internal scaffolding upto damper | 16/04/2023 18:13:01 | 16/04/2023 18:13:06 | 01/04/2023 02:00:00 | 02/04/2023 02:00:00 | 01-FF-001 | FURNACE | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 01-Apr | 02-Apr | 16-Apr | 16-Apr
CDUVDU5030 | Completed | Carry out servicing of damper and power cylinder | 16/04/2023 18:13:24 | 20/04/2023 16:30:35 | 02/04/2023 02:00:00 | 04/04/2023 02:00:00 | 01-FF-001 | FURNACE | 100 | MECHANICAL |  |  | 48 | 48:00 | 94:17 | 46:17 |  | 02-Apr | 04-Apr | 16-Apr | 20-Apr
CDUVDU8640 | Completed | Carry out refractory cleaning | 16/04/2023 11:53:00 | 20/04/2023 16:30:29 | 04/04/2023 02:00:00 | 05/04/2023 02:00:00 | 01-FF-001 | FURNACE | 100 | CIVIL |  |  | 24 | 24:00 | 100:37 | 76:37 |  | 04-Apr | 05-Apr | 16-Apr | 20-Apr
CDUVDU9940 | Completed | Carry out inspection | 16/04/2023 18:13:55 | 17/04/2023 17:39:03 | 05/04/2023 02:00:00 | 06/04/2023 02:00:00 | 01-FF-001 | FURNACE | 100 | INSPECTION |  |  | 24 | 24:00 | 23:25 |  | 0:35 | 05-Apr | 06-Apr | 16-Apr | 17-Apr
CDUVDU29210 | Not Started | Carry out removal of internal scaffolding |  |  | 17/04/2023 18:00:00 | 18/04/2023 06:00:00 | 01-FF-001 | FURNACE | 0 | MECHANICAL |  |  | 12 | 12:00 | 0:00 |  |  | 17-Apr | 18-Apr | - Date check | - Date check
CDUVDU29400 | Not Started | Carry out fixing of burners |  |  | 18/04/2023 06:00:00 | 19/04/2023 00:00:00 | 01-FF-001 | FURNACE | 0 | MECHANICAL |  |  | 18 | 18:00 | 0:00 |  |  | 18-Apr | 19-Apr | - Date check | - Date check
CDUVDU29760 | In Progress | Carry out repair of damaged floor refractory | 18/04/2023 08:48:02 |  | 19/04/2023 00:00:00 | 19/04/2023 18:00:00 | 01-FF-001 | FURNACE | 0 | CIVIL |  |  | 18 | 18:00 | 0:00 |  |  | 19-Apr | 19-Apr | 18-Apr | - Date check
CDUVDU29990 | Not Started | Carry out allignment check of burners |  |  | 19/04/2023 18:00:00 | 20/04/2023 06:00:00 | 01-FF-001 | FURNACE | 0 | TS |  |  | 12 | 12:00 | 0:00 |  |  | 19-Apr | 20-Apr | - Date check | - Date check
CDUVDU30000 | Not Started | Carry out box of header panels of convection section |  |  | 19/04/2023 18:00:00 | 20/04/2023 12:00:00 | 01-FF-001 | FURNACE | 0 | MECHANICAL |  |  | 18 | 18:00 | 0:00 |  |  | 19-Apr | 20-Apr | - Date check | - Date check
CDUVDU30090 | Not Started | Carry out manway box up |  |  | 20/04/2023 12:00:00 | 21/04/2023 00:00:00 | 01-FF-001 | FURNACE | 0 | MECHANICAL | BOX UP | BOX UP | 12 | 12:00 | 0:00 |  |  | 20-Apr | 21-Apr | - Date check | - Date check
CDUVDU30140 | Not Started | Carry out deblinding |  |  | 21/04/2023 00:00:00 | 22/04/2023 00:00:00 | 01-FF-001 | FURNACE | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  |  | 21-Apr | 22-Apr | - Date check | - Date check
CDUVDU20160 | Completed | Carry out fixing of ceremic modules on roof plate | 19/04/2023 16:44:13 | 20/04/2023 16:25:38 | 10/04/2023 18:00:00 | 15/04/2023 18:00:00 | 01-FF-001 | FURNACE | 100 | CIVIL |  |  | 120 | 120:00 | 23:41 |  | 96:19 | 10-Apr | 15-Apr | 19-Apr | 20-Apr
CDUVDU22500 | Completed | Carry out refractory repairs as recommended | 08/04/2023 16:46:03 | 25/04/2023 16:20:19 | 11/04/2023 18:00:00 | 15/04/2023 18:00:00 | 01-FF-001 | FURNACE | 100 | CIVIL |  |  | 96 | 96:00 | 407:34 | 311:34 |  | 11-Apr | 15-Apr | 08-Apr | 25-Apr
CDUVDU27900 | Completed | Carry out inpection | 16/04/2023 10:42:17 | 16/04/2023 10:42:36 | 15/04/2023 18:00:00 | 16/04/2023 02:00:00 | 01-FF-001 | FURNACE | 100 | INSPECTION |  |  | 8 | 8:00 | 0:00 |  | 8:00 | 15-Apr | 16-Apr | 16-Apr | 16-Apr
CDUVDU10390 | Completed | Carry out removal of damaged refractory | 23/04/2023 12:51:44 | 23/04/2023 12:52:44 | 05/04/2023 08:00:00 | 05/04/2023 20:00:00 | 01-FF-001 | FURNACE | 100 | CIVIL |  |  | 12 | 12:00 | 0:01 |  | 11:59 | 05-Apr | 05-Apr | 23-Apr | 23-Apr
CDUVDU10940 | Completed | Application of refractory lining | 23/04/2023 12:51:44 | 23/04/2023 12:52:44 | 05/04/2023 20:00:00 | 06/04/2023 08:00:00 | 01-FF-001 | FURNACE | 100 | CIVIL |  |  | 12 | 12:00 | 0:01 |  | 11:59 | 05-Apr | 06-Apr | 23-Apr | 23-Apr
CDUVDU11670 | Completed | Carry out installation of liner plante and allignment | 23/04/2023 12:51:44 | 23/04/2023 12:52:44 | 06/04/2023 08:00:00 | 06/04/2023 14:00:00 | 01-FF-001 | FURNACE | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:01 |  | 5:59 | 06-Apr | 06-Apr | 23-Apr | 23-Apr
CDUVDU12070 | Completed | Carry out Testing with operations | 23/04/2023 12:51:44 | 23/04/2023 12:52:44 | 06/04/2023 14:00:00 | 07/04/2023 14:00:00 | 01-FF-001 | FURNACE | 100 | INSPECTION |  |  | 24 | 24:00 | 0:01 |  | 23:59 | 06-Apr | 07-Apr | 23-Apr | 23-Apr
CDUVDU1590 | Completed | Carry out Blinding | 23/04/2023 12:51:44 | 23/04/2023 12:52:44 | 30/03/2023 06:00:00 | 30/03/2023 18:00:00 | 01-FF-001 | FURNACE | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:01 |  | 11:59 | 30-Mar | 30-Mar | 23-Apr | 23-Apr
CDUVDU1780 | Completed | Removal of electrical connection of motor | 23/04/2023 12:51:44 | 23/04/2023 12:52:44 | 30/03/2023 18:00:00 | 31/03/2023 02:00:00 | 01-FF-001 | FURNACE | 100 | ELECTRICAL |  |  | 8 | 8:00 | 0:01 |  | 7:59 | 30-Mar | 31-Mar | 23-Apr | 23-Apr
CDUVDU1920 | Completed | Provide temperory support to soot blower base plate | 23/04/2023 12:51:44 | 23/04/2023 12:52:44 | 31/03/2023 02:00:00 | 31/03/2023 14:00:00 | 01-FF-001 | FURNACE | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:01 |  | 11:59 | 31-Mar | 31-Mar | 23-Apr | 23-Apr
CDUVDU2480 | Completed | Carry out removal of Top Cover | 23/04/2023 12:51:44 | 23/04/2023 12:52:44 | 31/03/2023 14:00:00 | 01/04/2023 02:00:00 | 01-FF-001 | FURNACE | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:01 |  | 11:59 | 31-Mar | 01-Apr | 23-Apr | 23-Apr
CDUVDU2940 | Completed | Retard Soot blower pipe manually | 23/04/2023 12:51:44 | 23/04/2023 12:52:44 | 01/04/2023 02:00:00 | 05/04/2023 02:00:00 | 01-FF-001 | FURNACE | 100 | MECHANICAL |  |  | 96 | 96:00 | 0:01 |  | 95:59 | 01-Apr | 05-Apr | 23-Apr | 23-Apr
CDUVDU4050 | Completed | Carry out Cleaning of Soot Blower Pipe | 23/04/2023 12:51:44 | 23/04/2023 12:52:44 | 01/04/2023 14:00:00 | 05/04/2023 14:00:00 | 01-FF-001 | FURNACE | 100 | MECHANICAL |  |  | 96 | 96:00 | 0:01 |  | 95:59 | 01-Apr | 05-Apr | 23-Apr | 23-Apr
CDUVDU5060 | Completed | Application of grease to chains, Gear box and make it operatable | 23/04/2023 12:51:44 | 23/04/2023 12:52:44 | 02/04/2023 02:00:00 | 06/04/2023 02:00:00 | 01-FF-001 | FURNACE | 100 | MECHANICAL |  |  | 96 | 96:00 | 0:01 |  | 95:59 | 02-Apr | 06-Apr | 23-Apr | 23-Apr
CDUVDU9950 | Completed | Carry out dismantle of liner plate | 23/04/2023 12:51:44 | 23/04/2023 12:52:44 | 05/04/2023 02:00:00 | 05/04/2023 08:00:00 | 01-FF-001 | FURNACE | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:01 |  | 5:59 | 05-Apr | 05-Apr | 23-Apr | 23-Apr
CDUVDU1580 | Completed | Carry out blinding | 31/03/2023 09:42:43 | 04/04/2023 11:02:33 | 30/03/2023 06:00:00 | 01/04/2023 06:00:00 | 01-FF-002 | FURNACE | 100 | MECHANICAL | BLINDING | BLINDING | 48 | 48:00 | 97:20 | 49:20 |  | 30-Mar | 01-Apr | 31-Mar | 04-Apr
CDUVDU24330 | In Progress | Carry out Process inspection of burners | 02/04/2023 16:33:32 |  | 12/04/2023 14:00:00 | 12/04/2023 18:00:00 | 01-FF-002 | FURNACE | 60 | TS |  |  | 4 | 4:00 | 0:00 |  |  | 12-Apr | 12-Apr | 02-Apr | - Date check
CDUVDU2990 | Completed | Carry out manway opening | 31/03/2023 17:33:25 | 01/04/2023 19:26:48 | 01/04/2023 06:00:00 | 01/04/2023 14:00:00 | 01-FF-002 | FURNACE | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 25:53 | 17:53 |  | 01-Apr | 01-Apr | 31-Mar | 01-Apr
CDUVDU4020 | Completed | Carry out removal of burners | 31/03/2023 17:33:53 | 31/03/2023 18:21:01 | 01/04/2023 14:00:00 | 02/04/2023 14:00:00 | 01-FF-002 | FURNACE | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:47 |  | 23:13 | 01-Apr | 02-Apr | 31-Mar | 31-Mar
CDUVDU6390 | In Progress | Carry out servicing of burners | 10/04/2023 10:54:53 |  | 02/04/2023 14:00:00 | 12/04/2023 14:00:00 | 01-FF-002 | FURNACE | 60 | MECHANICAL |  |  | 240 | 240:00 | 0:00 |  |  | 02-Apr | 12-Apr | 10-Apr | - Date check
CDUVDU10420 | Completed | Carry out fit up at ground level | 09/04/2023 15:51:17 | 16/04/2023 12:33:32 | 05/04/2023 08:00:00 | 06/04/2023 20:00:00 | 01-FF-002 | FURNACE | 100 | MECHANICAL |  |  | 36 | 36:00 | 164:42 | 128:42 |  | 05-Apr | 06-Apr | 09-Apr | 16-Apr
CDUVDU10950 | Completed | Carry out Welding at ground level | 09/04/2023 15:54:38 | 09/04/2023 15:54:43 | 05/04/2023 20:00:00 | 07/04/2023 08:00:00 | 01-FF-002 | FURNACE | 100 | MECHANICAL |  |  | 36 | 36:00 | 0:00 |  | 36:00 | 05-Apr | 07-Apr | 09-Apr | 09-Apr
CDUVDU13280 | Completed | Carry out RT at ground level | 09/04/2023 15:55:04 | 09/04/2023 15:55:11 | 07/04/2023 08:00:00 | 08/04/2023 02:00:00 | 01-FF-002 | FURNACE | 100 | INSPECTION |  |  | 18 | 18:00 | 0:00 |  | 18:00 | 07-Apr | 08-Apr | 09-Apr | 09-Apr
CDUVDU14410 | Completed | PWHT | 16/04/2023 11:21:57 | 16/04/2023 11:22:05 | 08/04/2023 02:00:00 | 08/04/2023 22:00:00 | 01-FF-002 | FURNACE | 100 | INSPECTION |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 08-Apr | 08-Apr | 16-Apr | 16-Apr
CDUVDU15950 | Completed | Carry out Hardness test | 17/04/2023 15:00:25 | 17/04/2023 15:00:30 | 08/04/2023 22:00:00 | 09/04/2023 00:00:00 | 01-FF-002 | FURNACE | 100 | INSPECTION |  |  | 2 | 2:00 | 0:00 |  | 2:00 | 08-Apr | 09-Apr | 17-Apr | 17-Apr
CDUVDU16070 | Completed | Removal of refractory for accessibilty of welding | 16/04/2023 11:13:31 | 16/04/2023 11:13:47 | 09/04/2023 00:00:00 | 09/04/2023 02:00:00 | 01-FF-002 | FURNACE | 100 | MECHANICAL |  |  | 2 | 2:00 | 0:00 |  | 2:00 | 09-Apr | 09-Apr | 16-Apr | 16-Apr
CDUVDU16280 | Completed | Carry out Erection of new tubes | 16/04/2023 11:14:43 | 16/04/2023 11:15:56 | 09/04/2023 02:00:00 | 09/04/2023 14:00:00 | 01-FF-002 | FURNACE | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:01 |  | 11:59 | 09-Apr | 09-Apr | 16-Apr | 16-Apr
CDUVDU17300 | Completed | Carry out Fit up | 16/04/2023 11:16:06 | 16/04/2023 11:16:12 | 09/04/2023 14:00:00 | 10/04/2023 08:00:00 | 01-FF-002 | FURNACE | 100 | MECHANICAL | FIT UP |  | 18 | 18:00 | 0:00 |  | 18:00 | 09-Apr | 10-Apr | 16-Apr | 16-Apr
CDUVDU19150 | Completed | Carry out Pre heating and welding | 16/04/2023 11:16:34 | 16/04/2023 11:16:40 | 10/04/2023 08:00:00 | 11/04/2023 04:00:00 | 01-FF-002 | FURNACE | 100 | MECHANICAL | WELDING |  | 20 | 20:00 | 0:00 |  | 20:00 | 10-Apr | 11-Apr | 16-Apr | 16-Apr
CDUVDU21190 | Completed | Carry out RT | 16/04/2023 11:17:18 | 16/04/2023 11:17:27 | 11/04/2023 04:00:00 | 11/04/2023 22:00:00 | 01-FF-002 | FURNACE | 100 | INSPECTION |  |  | 18 | 18:00 | 0:00 |  | 18:00 | 11-Apr | 11-Apr | 16-Apr | 16-Apr
CDUVDU23020 | Completed | Carry out PWHT | 16/04/2023 11:17:59 | 16/04/2023 11:18:03 | 11/04/2023 22:00:00 | 12/04/2023 16:00:00 | 01-FF-002 | FURNACE | 100 | INSPECTION |  |  | 18 | 18:00 | 0:00 |  | 18:00 | 11-Apr | 12-Apr | 16-Apr | 16-Apr
CDUVDU24560 | Completed | Carry out hardness test | 17/04/2023 15:00:43 | 17/04/2023 15:00:47 | 12/04/2023 16:00:00 | 12/04/2023 18:00:00 | 01-FF-002 | FURNACE | 100 | INSPECTION | NDT |  | 2 | 2:00 | 0:00 |  | 2:00 | 12-Apr | 12-Apr | 17-Apr | 17-Apr
CDUVDU24640 | Completed | Carry out inspection by process and inspection | 17/04/2023 15:27:57 | 18/04/2023 11:48:51 | 12/04/2023 18:00:00 | 12/04/2023 22:00:00 | 01-FF-002 | FURNACE | 100 | TS |  |  | 4 | 4:00 | 20:21 | 16:21 |  | 12-Apr | 12-Apr | 17-Apr | 18-Apr
CDUVDU4060 | Completed | Entry | 02/04/2023 11:05:11 | 02/04/2023 16:38:56 | 01/04/2023 14:00:00 | 02/04/2023 08:00:00 | 01-FF-002 | FURNACE | 100 | MECHANICAL |  |  | 18 | 18:00 | 5:34 |  | 12:26 | 01-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU6090 | Completed | Carry out internal scaffolding upto arch section | 02/04/2023 19:25:06 | 06/04/2023 09:25:45 | 02/04/2023 08:00:00 | 03/04/2023 02:00:00 | 01-FF-002 | FURNACE | 100 | MECHANICAL |  |  | 18 | 18:00 | 86:01 | 68:01 |  | 02-Apr | 03-Apr | 02-Apr | 06-Apr
CDUVDU7410 | Completed | Carry out tube cleaning and elbows | 09/04/2023 09:06:57 | 17/04/2023 15:03:02 | 03/04/2023 02:00:00 | 04/04/2023 02:00:00 | 01-FF-002 | FURNACE | 100 | MECHANICAL | CLEANING |  | 24 | 24:00 | 197:56 | 173:56 |  | 03-Apr | 04-Apr | 09-Apr | 17-Apr
CDUVDU7420 | Completed | Carry out cutting of 5 Nos. tube | 09/04/2023 09:08:32 | 09/04/2023 09:48:37 | 03/04/2023 02:00:00 | 03/04/2023 20:00:00 | 01-FF-002 | FURNACE | 100 | MECHANICAL | CUTTING |  | 18 | 18:00 | 0:40 |  | 17:20 | 03-Apr | 03-Apr | 09-Apr | 09-Apr
CDUVDU8360 | Completed | Carry out Removal of tubes | 09/04/2023 11:02:28 | 09/04/2023 11:02:34 | 03/04/2023 20:00:00 | 04/04/2023 14:00:00 | 01-FF-002 | FURNACE | 100 | MECHANICAL |  |  | 18 | 18:00 | 0:00 |  | 18:00 | 03-Apr | 04-Apr | 09-Apr | 09-Apr
CDUVDU8660 | Completed | Carry out UT, DPT of TST points | 16/04/2023 10:10:27 | 16/04/2023 10:34:53 | 04/04/2023 02:00:00 | 04/04/2023 10:00:00 | 01-FF-002 | FURNACE | 100 | INSPECTION |  |  | 8 | 8:00 | 0:24 |  | 7:36 | 04-Apr | 04-Apr | 16-Apr | 16-Apr
CDUVDU9230 | Completed | Carry out insitu mettalography | 16/04/2023 14:15:36 | 16/04/2023 14:33:27 | 04/04/2023 10:00:00 | 05/04/2023 04:00:00 | 01-FF-002 | FURNACE | 100 | INSPECTION |  |  | 18 | 18:00 | 0:18 |  | 17:42 | 04-Apr | 05-Apr | 16-Apr | 16-Apr
CDUVDU9340 | Completed | Carry out Cutting and beveling of return bend of dismanteled tubes | 09/04/2023 11:07:53 | 09/04/2023 14:39:15 | 04/04/2023 14:00:00 | 05/04/2023 08:00:00 | 01-FF-002 | FURNACE | 100 | MECHANICAL |  |  | 18 | 18:00 | 3:31 |  | 14:29 | 04-Apr | 05-Apr | 09-Apr | 09-Apr
CDUVDU10150 | Completed | Carry out inspection | 17/04/2023 11:13:05 | 17/04/2023 11:17:45 | 05/04/2023 06:00:00 | 05/04/2023 10:00:00 | 01-FF-002 | FURNACE | 100 | INSPECTION |  |  | 4 | 4:00 | 0:05 |  | 3:55 | 05-Apr | 05-Apr | 17-Apr | 17-Apr
CDUVDU11090 | Completed | Carry out RT | 16/04/2023 11:19:31 | 16/04/2023 11:19:48 | 05/04/2023 22:00:00 | 06/04/2023 18:00:00 | 01-FF-002 | FURNACE | 100 | INSPECTION |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 05-Apr | 06-Apr | 16-Apr | 16-Apr
CDUVDU12380 | Completed | PWHT | 16/04/2023 11:20:31 | 16/04/2023 11:20:40 | 06/04/2023 18:00:00 | 07/04/2023 14:00:00 | 01-FF-002 | FURNACE | 100 | INSPECTION |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 06-Apr | 07-Apr | 16-Apr | 16-Apr
CDUVDU13640 | Completed | Carry out Hardness test | 16/04/2023 14:16:36 | 16/04/2023 14:34:31 | 07/04/2023 14:00:00 | 07/04/2023 16:00:00 | 01-FF-002 | FURNACE | 100 | INSPECTION |  |  | 2 | 2:00 | 0:18 |  | 1:42 | 07-Apr | 07-Apr | 16-Apr | 16-Apr
CDUVDU24950 | Completed | Carry out Process inspection | 17/04/2023 15:29:43 | 17/04/2023 15:29:55 | 12/04/2023 22:00:00 | 13/04/2023 02:00:00 | 01-FF-002 | FURNACE | 100 | TS | INSPECTION | INSPECTION | 4 | 4:00 | 0:00 |  | 4:00 | 12-Apr | 13-Apr | 17-Apr | 17-Apr
CDUVDU3000 | Completed | Carry out opening of side panels and manways | 02/04/2023 12:02:14 | 08/04/2023 10:02:26 | 01/04/2023 06:00:00 | 02/04/2023 00:00:00 | 01-FF-002 | FURNACE | 100 | MECHANICAL |  |  | 18 | 18:00 | 142:00 | 124:00 |  | 01-Apr | 02-Apr | 02-Apr | 08-Apr
CDUVDU4870 | Completed | Carry out tube cleaning and return elbows | 09/04/2023 09:07:09 | 12/04/2023 11:36:39 | 02/04/2023 00:00:00 | 02/04/2023 12:00:00 | 01-FF-002 | FURNACE | 100 | MECHANICAL |  |  | 12 | 12:00 | 74:30 | 62:30 |  | 02-Apr | 02-Apr | 09-Apr | 12-Apr
CDUVDU6260 | Completed | Carry out UT gauging of elbows and tubes | 16/04/2023 10:53:50 | 16/04/2023 10:56:29 | 02/04/2023 12:00:00 | 03/04/2023 00:00:00 | 01-FF-002 | FURNACE | 100 | INSPECTION |  |  | 12 | 12:00 | 0:03 |  | 11:57 | 02-Apr | 03-Apr | 16-Apr | 16-Apr
CDUVDU6270 | Completed | Carry out cutting of 8 Nos. tube | 17/04/2023 15:00:56 | 17/04/2023 15:01:02 | 02/04/2023 12:00:00 | 03/04/2023 04:00:00 | 01-FF-002 | FURNACE | 100 | MECHANICAL |  |  | 16 | 16:00 | 0:00 |  | 16:00 | 02-Apr | 03-Apr | 17-Apr | 17-Apr
CDUVDU7080 | Completed | Carry out opening of TST flanges of I/L and O/L passes | 17/04/2023 15:28:51 | 17/04/2023 15:28:56 | 03/04/2023 00:00:00 | 03/04/2023 12:00:00 | 01-FF-002 | FURNACE | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:00 |  | 12:00 | 03-Apr | 03-Apr | 17-Apr | 17-Apr
CDUVDU7460 | Completed | Carry out beveling of return bend of dismanteled tubes | 17/04/2023 15:01:23 | 17/04/2023 15:01:28 | 03/04/2023 04:00:00 | 03/04/2023 22:00:00 | 01-FF-002 | FURNACE | 100 | MECHANICAL |  |  | 18 | 18:00 | 0:00 |  | 18:00 | 03-Apr | 03-Apr | 17-Apr | 17-Apr
CDUVDU8020 | Completed | Carry out DPT of TST points | 20/04/2023 16:31:29 | 20/04/2023 16:31:33 | 03/04/2023 12:00:00 | 04/04/2023 00:00:00 | 01-FF-002 | FURNACE | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  | 12:00 | 03-Apr | 04-Apr | 20-Apr | 20-Apr
CDUVDU8450 | Completed | Carry out fit up | 16/04/2023 11:18:19 | 16/04/2023 11:18:24 | 03/04/2023 22:00:00 | 04/04/2023 22:00:00 | 01-FF-002 | FURNACE | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 03-Apr | 04-Apr | 16-Apr | 16-Apr
CDUVDU8510 | Completed | Carry out internal scaffolding upto breech section | 16/04/2023 18:47:53 | 16/04/2023 18:47:58 | 04/04/2023 00:00:00 | 04/04/2023 18:00:00 | 01-FF-002 | FURNACE | 100 | MECHANICAL |  |  | 18 | 18:00 | 0:00 |  | 18:00 | 04-Apr | 04-Apr | 16-Apr | 16-Apr
CDUVDU9520 | Completed | Carry out removal of refractory debris | 16/04/2023 14:59:01 | 16/04/2023 15:00:08 | 04/04/2023 18:00:00 | 05/04/2023 06:00:00 | 01-FF-002 | FURNACE | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:01 |  | 11:59 | 04-Apr | 05-Apr | 16-Apr | 16-Apr
CDUVDU9800 | Completed | Carry out Welding | 16/04/2023 11:18:49 | 16/04/2023 11:18:55 | 04/04/2023 22:00:00 | 05/04/2023 22:00:00 | 01-FF-002 | FURNACE | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 04-Apr | 05-Apr | 16-Apr | 16-Apr
CDUVDU13630 | Completed | Carry out Inspection | 17/04/2023 15:30:59 | 17/04/2023 15:31:13 | 07/04/2023 14:00:00 | 07/04/2023 18:00:00 | 01-FF-002 | FURNACE | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 07-Apr | 07-Apr | 17-Apr | 17-Apr
CDUVDU13800 | Completed | Carry out servicing of dampers and lovers | 16/04/2023 18:48:33 | 17/04/2023 15:31:31 | 07/04/2023 18:00:00 | 12/04/2023 18:00:00 | 01-FF-002 | FURNACE | 100 | MECHANICAL |  |  | 120 | 120:00 | 20:43 |  | 99:17 | 07-Apr | 12-Apr | 16-Apr | 17-Apr
CDUVDU24630 | In Progress | Carry out Inspection by ops | 17/04/2023 15:31:54 |  | 12/04/2023 18:00:00 | 12/04/2023 21:00:00 | 01-FF-002 | FURNACE | 60 | OPERATION |  |  | 3 | 3:00 | 0:00 |  |  | 12-Apr | 12-Apr | 17-Apr | - Date check
CDUVDU4030 | Completed | Carry out erection of scaffolding to access manways | 11/04/2023 12:02:53 | 13/04/2023 11:00:14 | 01/04/2023 14:00:00 | 02/04/2023 02:00:00 | 01-FF-002 | FURNACE | 100 | MECHANICAL |  |  | 12 | 12:00 | 46:57 | 34:57 |  | 01-Apr | 02-Apr | 11-Apr | 13-Apr
CDUVDU5040 | Completed | Carry out manway opening | 13/04/2023 11:41:12 | 13/04/2023 11:41:17 | 02/04/2023 02:00:00 | 03/04/2023 02:00:00 | 01-FF-002 | FURNACE | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 02-Apr | 03-Apr | 13-Apr | 13-Apr
CDUVDU7390 | Completed | Entry | 13/04/2023 11:46:42 | 13/04/2023 11:46:47 | 03/04/2023 02:00:00 | 03/04/2023 14:00:00 | 01-FF-002 | FURNACE | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:00 |  | 12:00 | 03-Apr | 03-Apr | 13-Apr | 13-Apr
CDUVDU8080 | Completed | Carry out cleaning of internal surface of duct | 13/04/2023 15:44:39 | 23/04/2023 12:50:41 | 03/04/2023 14:00:00 | 07/04/2023 14:00:00 | 01-FF-002 | FURNACE | 100 | MECHANICAL |  |  | 96 | 96:00 | 237:06 | 141:06 |  | 03-Apr | 07-Apr | 13-Apr | 23-Apr
CDUVDU28650 | Completed | Carry out preperation of hydro test of pass # 1 and Pass # 2 | 12/04/2023 11:34:44 | 17/04/2023 15:34:06 | 16/04/2023 18:00:00 | 17/04/2023 06:00:00 | 01-FF-002 | FURNACE | 100 | MECHANICAL |  |  | 12 | 12:00 | 123:59 | 111:59 |  | 16-Apr | 17-Apr | 12-Apr | 17-Apr
CDUVDU28970 | Completed | Carry out hydro test of passes | 12/04/2023 11:35:01 | 21/04/2023 19:46:40 | 17/04/2023 06:00:00 | 18/04/2023 06:00:00 | 01-FF-002 | FURNACE | 100 | MECHANICAL | HYDRO TEST | HYDRO TEST | 24 | 24:00 | 224:12 | 200:12 |  | 17-Apr | 18-Apr | 12-Apr | 21-Apr
CDUVDU29410 | Completed | Carry out Inspection | 17/04/2023 15:34:28 | 19/04/2023 19:36:00 | 18/04/2023 06:00:00 | 18/04/2023 10:00:00 | 01-FF-002 | FURNACE | 100 | INSPECTION |  |  | 4 | 4:00 | 52:02 | 48:02 |  | 18-Apr | 18-Apr | 17-Apr | 19-Apr
CDUVDU12890 | Completed | Carry out refractory cleaning | 16/04/2023 11:53:08 | 26/04/2023 13:04:58 | 07/04/2023 02:00:00 | 08/04/2023 02:00:00 | 01-FF-002 | FURNACE | 100 | CIVIL |  |  | 24 | 24:00 | 241:12 | 217:12 |  | 07-Apr | 08-Apr | 16-Apr | 26-Apr
CDUVDU14400 | In Progress | Carry out inspection | 17/04/2023 15:35:30 |  | 08/04/2023 02:00:00 | 09/04/2023 02:00:00 | 01-FF-002 | FURNACE | 57 | INSPECTION |  |  | 24 | 24:00 | 0:00 |  |  | 08-Apr | 09-Apr | 17-Apr | - Date check
CDUVDU16270 | Completed | Carry out application of refractory | 17/04/2023 15:35:56 | 22/04/2023 19:30:47 | 09/04/2023 02:00:00 | 15/04/2023 18:00:00 | 01-FF-002 | FURNACE | 100 | CIVIL |  |  | 160 | 160:00 | 123:55 |  | 36:05 | 09-Apr | 15-Apr | 17-Apr | 22-Apr
CDUVDU27910 | Not Started | Carry out final inspection |  |  | 15/04/2023 18:00:00 | 16/04/2023 18:00:00 | 01-FF-002 | FURNACE | 0 | INSPECTION |  |  | 24 | 24:00 | 0:00 |  |  | 15-Apr | 16-Apr | - Date check | - Date check
CDUVDU28660 | Not Started | Carry out box up of manway |  |  | 16/04/2023 18:00:00 | 17/04/2023 06:00:00 | 01-FF-002 | FURNACE | 0 | MECHANICAL |  |  | 12 | 12:00 | 0:00 |  |  | 16-Apr | 17-Apr | - Date check | - Date check
CDUVDU4040 | Completed | Carry out stack manway opening | 07/04/2023 19:29:03 | 07/04/2023 19:29:18 | 01/04/2023 14:00:00 | 02/04/2023 02:00:00 | 01-FF-002 | FURNACE | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:00 |  | 12:00 | 01-Apr | 02-Apr | 07-Apr | 07-Apr
CDUVDU4041 | Completed | Stack painting using rope access technology through IRATA certified technician | 08/04/2023 10:00:47 | 16/04/2023 12:34:50 | 08/04/2023 14:00:00 | 21/04/2023 14:00:00 | 01-FF-002 | FURNACE | 100 | CIVIL |  |  | 312 | 312:00 | 194:34 |  | 117:26 | 08-Apr | 21-Apr | 08-Apr | 16-Apr
CDUVDU5050 | Completed | Carry out internal scaffolding upto damper | 08/04/2023 15:25:42 | 16/04/2023 09:56:09 | 02/04/2023 02:00:00 | 03/04/2023 02:00:00 | 01-FF-002 | FURNACE | 100 | MECHANICAL |  |  | 24 | 24:00 | 186:30 | 162:30 |  | 02-Apr | 03-Apr | 08-Apr | 16-Apr
CDUVDU7400 | In Progress | Carry out servicing of damper and power cylinder | 17/04/2023 15:35:01 |  | 03/04/2023 02:00:00 | 07/04/2023 02:00:00 | 01-FF-002 | FURNACE | 50 | MECHANICAL |  |  | 96 | 96:00 | 0:00 |  |  | 03-Apr | 07-Apr | 17-Apr | - Date check
CDUVDU29500 | Not Started | Carry out removal of internal scaffolding |  |  | 18/04/2023 10:00:00 | 18/04/2023 22:00:00 | 01-FF-002 | FURNACE | 0 | MECHANICAL |  |  | 12 | 12:00 | 0:00 |  |  | 18-Apr | 18-Apr | - Date check | - Date check
CDUVDU29700 | Not Started | Carry out fixing of burners |  |  | 18/04/2023 22:00:00 | 19/04/2023 22:00:00 | 01-FF-002 | FURNACE | 0 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  |  | 18-Apr | 19-Apr | - Date check | - Date check
CDUVDU29960 | Completed | Carry out repair of damaged floor refractory | 25/04/2023 08:38:37 | 26/04/2023 13:06:21 | 19/04/2023 22:00:00 | 20/04/2023 16:00:00 | 01-FF-002 | FURNACE | 100 | CIVIL |  |  | 18 | 18:00 | 28:28 | 10:28 |  | 19-Apr | 20-Apr | 25-Apr | 26-Apr
CDUVDU30070 | Not Started | Carry out allignment check of burners |  |  | 20/04/2023 16:00:00 | 21/04/2023 16:00:00 | 01-FF-002 | FURNACE | 0 | TS |  |  | 24 | 24:00 | 0:00 |  |  | 20-Apr | 21-Apr | - Date check | - Date check
CDUVDU30080 | Not Started | Carry out box of header panels of convection section |  |  | 20/04/2023 16:00:00 | 21/04/2023 10:00:00 | 01-FF-002 | FURNACE | 0 | MECHANICAL |  |  | 18 | 18:00 | 0:00 |  |  | 20-Apr | 21-Apr | - Date check | - Date check
CDUVDU30150 | Not Started | Carry out manway box up |  |  | 21/04/2023 16:00:00 | 22/04/2023 04:00:00 | 01-FF-002 | FURNACE | 0 | MECHANICAL | BOX UP | BOX UP | 12 | 12:00 | 0:00 |  |  | 21-Apr | 22-Apr | - Date check | - Date check
CDUVDU30170 | Not Started | Carry out deblinding |  |  | 22/04/2023 04:00:00 | 23/04/2023 04:00:00 | 01-FF-002 | FURNACE | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  |  | 22-Apr | 23-Apr | - Date check | - Date check
CDUVDU25200 | Completed | Carry out fixing of ceremic modules on roof plate | 17/04/2023 15:33:14 | 20/04/2023 16:33:02 | 13/04/2023 02:00:00 | 17/04/2023 02:00:00 | 01-FF-002 | FURNACE | 100 | CIVIL |  |  | 96 | 96:00 | 73:00 |  | 23:00 | 13-Apr | 17-Apr | 17-Apr | 20-Apr
CDUVDU26430 | Completed | Carry out refractory repairs as recommended | 18/04/2023 14:41:53 | 22/04/2023 12:20:58 | 14/04/2023 02:00:00 | 16/04/2023 14:00:00 | 01-FF-002 | FURNACE | 100 | CIVIL |  |  | 60 | 60:00 | 93:39 | 33:39 |  | 14-Apr | 16-Apr | 18-Apr | 22-Apr
CDUVDU28550 | Completed | Carry out inspection | 16/04/2023 10:44:36 | 16/04/2023 12:33:44 | 16/04/2023 14:00:00 | 16/04/2023 18:00:00 | 01-FF-002 | FURNACE | 100 | INSPECTION |  |  | 4 | 4:00 | 1:49 |  | 2:11 | 16-Apr | 16-Apr | 16-Apr | 16-Apr
CDUVDU13140 | Completed | Checking internal clearance, bearing condition | 31/03/2023 11:35:46 | 07/04/2023 19:04:20 | 07/04/2023 06:00:00 | 11/04/2023 06:00:00 | ID/FD FAN | ID/FD FAN | 100 | MECHANICAL |  |  | 96 | 96:00 | 175:29 | 79:29 |  | 07-Apr | 11-Apr | 31-Mar | 07-Apr
CDUVDU21460 | Completed | Overhauling of fan and motors | 04/04/2023 11:08:58 | 26/04/2023 12:41:56 | 11/04/2023 06:00:00 | 16/04/2023 06:00:00 | ID/FD FAN | ID/FD FAN | 100 | MECHANICAL |  |  | 120 | 120:00 | 529:33 | 409:33 |  | 11-Apr | 16-Apr | 04-Apr | 26-Apr
CDUVDU28340 | Completed | Checking of speed indication | 26/04/2023 12:44:38 | 26/04/2023 12:44:51 | 16/04/2023 06:00:00 | 17/04/2023 06:00:00 | ID/FD FAN | ID/FD FAN | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 16-Apr | 17-Apr | 26-Apr | 26-Apr
CDUVDU28980 | Completed | Box up | 26/04/2023 12:45:04 | 26/04/2023 12:45:09 | 17/04/2023 06:00:00 | 18/04/2023 06:00:00 | ID/FD FAN | ID/FD FAN | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 17-Apr | 18-Apr | 26-Apr | 26-Apr
CDUVDU29420 | In Progress | Alignment of fan and Deblinding | 26/04/2023 12:46:15 |  | 18/04/2023 06:00:00 | 19/04/2023 06:00:00 | ID/FD FAN | ID/FD FAN | 60 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  |  | 18-Apr | 19-Apr | 26-Apr | - Date check
CDUVDU3010 | Completed | Blinding & dropping of Fluid coupling and sent to Workshop | 31/03/2023 11:22:00 | 31/03/2023 11:22:18 | 01/04/2023 06:00:00 | 02/04/2023 06:00:00 | ID/FD FAN | ID/FD FAN | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 01-Apr | 02-Apr | 31-Mar | 31-Mar
CDUVDU5330 | Completed | Fluid coupling preventive checking at Workshop. | 31/03/2023 11:22:29 | 23/04/2023 12:54:25 | 02/04/2023 06:00:00 | 07/04/2023 06:00:00 | ID/FD FAN | ID/FD FAN | 100 | MECHANICAL |  |  | 120 | 120:00 | 553:32 | 433:32 |  | 02-Apr | 07-Apr | 31-Mar | 23-Apr
CDUVDU10230 | Completed | Inspection of the Internals & Fan Installation | 06/04/2023 10:37:42 | 12/04/2023 10:30:40 | 05/04/2023 06:00:00 | 13/04/2023 06:00:00 | 01-KA-02B | FD FAN | 100 | MECHANICAL |  |  | 192 | 192:00 | 143:53 |  | 48:07 | 05-Apr | 13-Apr | 06-Apr | 12-Apr
CDUVDU25400 | Completed | Casing Box-up | 12/04/2023 10:30:49 | 16/04/2023 12:01:58 | 13/04/2023 06:00:00 | 15/04/2023 06:00:00 | 01-KA-02B | FD FAN | 100 | MECHANICAL |  |  | 48 | 48:00 | 97:31 | 49:31 |  | 13-Apr | 15-Apr | 12-Apr | 16-Apr
CDUVDU27540 | Completed | Bearing Installation and fan alignment | 17/04/2023 15:56:11 | 25/04/2023 15:23:19 | 15/04/2023 06:00:00 | 18/04/2023 06:00:00 | 01-KA-02B | FD FAN | 100 | MECHANICAL |  |  | 72 | 72:00 | 191:27 | 119:27 |  | 15-Apr | 18-Apr | 17-Apr | 25-Apr
CDUVDU29430 | Completed | Auxiliary System Installation | 21/04/2023 19:08:52 | 25/04/2023 15:23:26 | 18/04/2023 06:00:00 | 19/04/2023 06:00:00 | 01-KA-02B | FD FAN | 100 | MECHANICAL |  |  | 24 | 24:00 | 92:15 | 68:15 |  | 18-Apr | 19-Apr | 21-Apr | 25-Apr
CDUVDU5340 | Completed | Removal of auxiliary systems | 31/03/2023 11:20:25 | 04/04/2023 18:07:45 | 02/04/2023 06:00:00 | 03/04/2023 06:00:00 | 01-KA-02B | FD FAN | 100 | MECHANICAL |  |  | 24 | 24:00 | 102:47 | 78:47 |  | 02-Apr | 03-Apr | 31-Mar | 04-Apr
CDUVDU7630 | Completed | Removal of Casing | 31/03/2023 11:24:14 | 04/04/2023 18:07:57 | 03/04/2023 06:00:00 | 05/04/2023 06:00:00 | 01-KA-02B | FD FAN | 100 | MECHANICAL |  |  | 48 | 48:00 | 102:44 | 54:44 |  | 03-Apr | 05-Apr | 31-Mar | 04-Apr
CDUVDU10160 | Completed | Provide Handlamp/ladder/scaffolfing for internal inspection | 31/03/2023 09:49:19 | 06/04/2023 17:39:07 | 05/04/2023 14:00:00 | 06/04/2023 14:00:00 | APH | APH | 100 | MECHANICAL |  |  | 24 | 24:00 | 151:50 | 127:50 |  | 05-Apr | 06-Apr | 31-Mar | 06-Apr
CDUVDU10220 | Completed | Insulation removal of Hot air and cold air duct for inspection | 06/04/2023 17:18:30 | 13/04/2023 11:56:21 | 05/04/2023 14:00:00 | 12/04/2023 06:00:00 | APH | APH | 100 | CIVIL |  |  | 160 | 160:00 | 162:38 | 2:38 |  | 05-Apr | 12-Apr | 06-Apr | 13-Apr
CDUVDU11450 | Completed | Cleaning and inspection of APH module | 01/04/2023 11:10:21 | 22/04/2023 19:34:48 | 06/04/2023 14:00:00 | 13/04/2023 06:00:00 | APH | APH | 100 | MECHANICAL |  |  | 160 | 160:00 | 512:24 | 352:24 |  | 06-Apr | 13-Apr | 01-Apr | 22-Apr
CDUVDU23050 | Completed | Carry out detail inspection of ducts | 06/04/2023 11:45:21 | 16/04/2023 11:16:22 | 12/04/2023 06:00:00 | 12/04/2023 18:00:00 | APH | APH | 100 | INSPECTION |  |  | 12 | 12:00 | 239:31 | 227:31 |  | 12-Apr | 12-Apr | 06-Apr | 16-Apr
CDUVDU24960 | Completed | Repair (if any) including refractory | 22/04/2023 12:22:46 | 22/04/2023 19:35:54 | 13/04/2023 06:00:00 | 19/04/2023 22:00:00 | APH | APH | 100 | MECHANICAL |  |  | 160 | 160:00 | 7:13 |  | 152:47 | 13-Apr | 19-Apr | 22-Apr | 22-Apr
CDUVDU29940 | Completed | Removing if Scaffolding and Lighting Arrangement | 22/04/2023 19:36:19 | 22/04/2023 19:36:24 | 19/04/2023 22:00:00 | 20/04/2023 22:00:00 | APH | APH | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 19-Apr | 20-Apr | 22-Apr | 22-Apr
CDUVDU30110 | In Progress | Box up | 23/04/2023 12:55:02 |  | 20/04/2023 22:00:00 | 21/04/2023 19:00:00 | APH | APH | 90 | MECHANICAL |  |  | 21 | 21:00 | 0:00 |  |  | 20-Apr | 21-Apr | 23-Apr | - Date check
CDUVDU8970 | Completed | Open all access doors | 29/03/2023 11:16:34 | 30/03/2023 15:23:41 | 04/04/2023 14:00:00 | 05/04/2023 14:00:00 | APH | APH | 100 | MECHANICAL |  |  | 24 | 24:00 | 28:07 | 4:07 |  | 04-Apr | 05-Apr | 29-Mar | 30-Mar
CDUVDU10960 | Completed | Carry out Cleaning of shell,tray and nozzles | 06/04/2023 16:21:23 | 14/04/2023 15:18:56 | 06/04/2023 04:30:00 | 09/04/2023 04:30:00 | 01-CC-002 | COLUMN | 100 | MECHANICAL | CLEANING |  | 72 | 72:00 | 190:58 | 118:58 |  | 06-Apr | 09-Apr | 06-Apr | 14-Apr
CDUVDU15860 | Completed | Carry out WFMPI, DP, UFD, of all weld joints internally and externally | 16/04/2023 14:17:42 | 16/04/2023 14:18:42 | 09/04/2023 04:30:00 | 11/04/2023 04:30:00 | 01-CC-002 | COLUMN | 100 | INSPECTION |  |  | 48 | 48:00 | 0:01 |  | 47:59 | 09-Apr | 11-Apr | 16-Apr | 16-Apr
CDUVDU1630 | Completed | Carry out blinding | 31/03/2023 10:38:51 | 03/04/2023 19:32:28 | 30/03/2023 14:30:00 | 31/03/2023 14:30:00 | 01-CC-002 | COLUMN | 100 | MECHANICAL | BLINDING | BLINDING | 24 | 24:00 | 80:54 | 56:54 |  | 30-Mar | 31-Mar | 31-Mar | 03-Apr
CDUVDU2010 | Completed | Carry out manway opening | 03/04/2023 19:33:13 | 03/04/2023 19:33:22 | 31/03/2023 14:30:00 | 01/04/2023 14:30:00 | 01-CC-002 | COLUMN | 100 | MECHANICAL | OPENING | OPENING | 24 | 24:00 | 0:00 |  | 24:00 | 31-Mar | 01-Apr | 03-Apr | 03-Apr
CDUVDU20460 | Completed | Carry out repair if any as per recommendation | 16/04/2023 19:27:44 | 16/04/2023 19:27:49 | 11/04/2023 04:30:00 | 13/04/2023 16:30:00 | 01-CC-002 | COLUMN | 100 | INSPECTION | REPAIR |  | 60 | 60:00 | 0:00 |  | 60:00 | 11-Apr | 13-Apr | 16-Apr | 16-Apr
CDUVDU25570 | Completed | Carry out Inspection by Inspection dept | 16/04/2023 19:27:57 | 16/04/2023 19:28:04 | 13/04/2023 16:30:00 | 13/04/2023 22:30:00 | 01-CC-002 | COLUMN | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:00 |  | 6:00 | 13-Apr | 13-Apr | 16-Apr | 16-Apr
CDUVDU25870 | Completed | Installation of Internal | 17/04/2023 11:29:33 | 17/04/2023 11:29:46 | 13/04/2023 22:30:00 | 14/04/2023 22:30:00 | 01-CC-002 | COLUMN | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 13-Apr | 14-Apr | 17-Apr | 17-Apr
CDUVDU26960 | Completed | Carry out TS Inspection | 19/04/2023 19:24:35 | 19/04/2023 19:24:39 | 14/04/2023 22:30:00 | 15/04/2023 04:30:00 | 01-CC-002 | COLUMN | 100 | TS |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 14-Apr | 15-Apr | 19-Apr | 19-Apr
CDUVDU27170 | Completed | Carry out removal of internal scaffolding | 17/04/2023 11:31:04 | 17/04/2023 11:31:10 | 15/04/2023 04:30:00 | 16/04/2023 04:30:00 | 01-CC-002 | COLUMN | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 15-Apr | 16-Apr | 17-Apr | 17-Apr
CDUVDU28020 | Completed | Carry out Tray manway box up | 19/04/2023 19:24:49 | 20/04/2023 14:52:02 | 16/04/2023 04:30:00 | 17/04/2023 04:30:00 | 01-CC-002 | COLUMN | 100 | MECHANICAL | TRAY MANWAY BOX UP |  | 24 | 24:00 | 19:27 |  | 4:33 | 16-Apr | 17-Apr | 19-Apr | 20-Apr
CDUVDU28750 | Completed | Carry out Manway box up with torquing | 20/04/2023 12:07:10 | 20/04/2023 19:35:28 | 17/04/2023 04:30:00 | 18/04/2023 04:30:00 | 01-CC-002 | COLUMN | 100 | MECHANICAL | BOX UP | BOX UP | 24 | 24:00 | 7:28 |  | 16:32 | 17-Apr | 18-Apr | 20-Apr | 20-Apr
CDUVDU29290 | In Progress | Carry out deblinding | 25/04/2023 11:27:04 |  | 18/04/2023 04:30:00 | 19/04/2023 04:30:00 | 01-CC-002 | COLUMN | 90 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  |  | 18-Apr | 19-Apr | 25-Apr | - Date check
CDUVDU3040 | Completed | Carry out preparation of air hose for ventilation and Hand lamp for lighting | 05/04/2023 10:38:24 | 06/04/2023 09:22:23 | 01/04/2023 14:30:00 | 01/04/2023 16:30:00 | 01-CC-002 | COLUMN | 100 | MECHANICAL |  |  | 2 | 2:00 | 22:44 | 20:44 |  | 01-Apr | 01-Apr | 05-Apr | 06-Apr
CDUVDU3080 | Completed | Insulation removal | 13/04/2023 15:47:50 | 20/04/2023 20:09:55 | 01/04/2023 14:30:00 | 02/04/2023 14:30:00 | 01-CC-002 | COLUMN | 100 | CIVIL |  |  | 24 | 24:00 | 172:22 | 148:22 |  | 01-Apr | 02-Apr | 13-Apr | 20-Apr
CDUVDU3860 | Completed | Entry | 06/04/2023 11:02:40 | 06/04/2023 11:02:45 | 01/04/2023 16:30:00 | 02/04/2023 04:30:00 | 01-CC-002 | COLUMN | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:00 |  | 12:00 | 01-Apr | 02-Apr | 06-Apr | 06-Apr
CDUVDU4560 | Completed | Carry out internal scaffolding on top and bottom | 16/04/2023 17:33:09 | 16/04/2023 17:33:14 | 02/04/2023 04:30:00 | 04/04/2023 04:30:00 | 01-CC-002 | COLUMN | 100 | MECHANICAL |  |  | 48 | 48:00 | 0:00 |  | 48:00 | 02-Apr | 04-Apr | 16-Apr | 16-Apr
CDUVDU5370 | Completed | Carry out UT Gauging | 16/04/2023 17:32:46 | 16/04/2023 17:32:50 | 02/04/2023 14:30:00 | 03/04/2023 14:30:00 | 01-CC-002 | COLUMN | 100 | INSPECTION |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 02-Apr | 03-Apr | 16-Apr | 16-Apr
CDUVDU8380 | Completed | Carry out tray manway opening | 06/04/2023 16:21:02 | 08/04/2023 17:18:21 | 04/04/2023 04:30:00 | 05/04/2023 04:30:00 | 01-CC-002 | COLUMN | 100 | MECHANICAL | TRAY MANWAY OPEN |  | 24 | 24:00 | 48:57 | 24:57 |  | 04-Apr | 05-Apr | 06-Apr | 08-Apr
CDUVDU9680 | Completed | Internal Removal | 17/04/2023 11:29:07 | 17/04/2023 11:29:12 | 05/04/2023 04:30:00 | 06/04/2023 04:30:00 | 01-CC-002 | COLUMN | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 05-Apr | 06-Apr | 17-Apr | 17-Apr
CDUVDU11000 | Completed | Internal Removal | 17/04/2023 11:31:53 | 17/04/2023 11:32:01 | 06/04/2023 04:30:00 | 07/04/2023 04:30:00 | 01-CC-003 | COLUMN | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 06-Apr | 07-Apr | 17-Apr | 17-Apr
CDUVDU12560 | Completed | Carry out Cleaning of shell and nozzles | 06/04/2023 16:23:39 | 14/04/2023 15:19:10 | 07/04/2023 04:30:00 | 10/04/2023 16:30:00 | 01-CC-003 | COLUMN | 100 | MECHANICAL | CLEANING |  | 84 | 84:00 | 190:56 | 106:56 |  | 07-Apr | 10-Apr | 06-Apr | 14-Apr
CDUVDU19160 | Completed | Carry out WFMPI, DP, UFD, of all weld joints internally and externally | 16/04/2023 14:20:41 | 16/04/2023 14:21:41 | 10/04/2023 16:30:00 | 12/04/2023 16:30:00 | 01-CC-003 | COLUMN | 100 | INSPECTION |  |  | 48 | 48:00 | 0:01 |  | 47:59 | 10-Apr | 12-Apr | 16-Apr | 16-Apr
CDUVDU2020 | Completed | Carry out blinding | 31/03/2023 10:39:19 | 03/04/2023 19:32:42 | 31/03/2023 14:30:00 | 01/04/2023 14:30:00 | 01-CC-003 | COLUMN | 100 | MECHANICAL | BLINDING | BLINDING | 24 | 24:00 | 80:53 | 56:53 |  | 31-Mar | 01-Apr | 31-Mar | 03-Apr
CDUVDU23930 | Completed | Carry out repair if any as per recommendation | 17/04/2023 11:32:43 | 19/04/2023 19:25:04 | 12/04/2023 16:30:00 | 15/04/2023 04:30:00 | 01-CC-003 | COLUMN | 100 | INSPECTION | REPAIR |  | 60 | 60:00 | 55:52 |  | 4:08 | 12-Apr | 15-Apr | 17-Apr | 19-Apr
CDUVDU27180 | Completed | Carry out Inspection by Inspection dept | 17/04/2023 11:32:59 | 17/04/2023 12:02:22 | 15/04/2023 04:30:00 | 15/04/2023 10:30:00 | 01-CC-003 | COLUMN | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:29 |  | 5:31 | 15-Apr | 15-Apr | 17-Apr | 17-Apr
CDUVDU27400 | Completed | Installation of Internal | 17/04/2023 11:32:16 | 17/04/2023 11:32:22 | 15/04/2023 10:30:00 | 16/04/2023 10:30:00 | 01-CC-003 | COLUMN | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 15-Apr | 16-Apr | 17-Apr | 17-Apr
CDUVDU28220 | Completed | Carry out TS Inspection | 19/04/2023 19:25:33 | 19/04/2023 19:25:39 | 16/04/2023 10:30:00 | 16/04/2023 16:30:00 | 01-CC-003 | COLUMN | 100 | TS |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 16-Apr | 16-Apr | 19-Apr | 19-Apr
CDUVDU28420 | Completed | Carry out removal of internal scaffolding | 17/04/2023 11:33:13 | 17/04/2023 11:33:20 | 16/04/2023 16:30:00 | 17/04/2023 16:30:00 | 01-CC-003 | COLUMN | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 16-Apr | 17-Apr | 17-Apr | 17-Apr
CDUVDU29010 | Completed | Carry out Tray manway box up | 19/04/2023 19:25:45 | 20/04/2023 14:52:13 | 17/04/2023 16:30:00 | 18/04/2023 16:30:00 | 01-CC-003 | COLUMN | 100 | MECHANICAL | TRAY MANWAY BOX UP |  | 24 | 24:00 | 19:26 |  | 4:34 | 17-Apr | 18-Apr | 19-Apr | 20-Apr
CDUVDU29470 | Completed | Carry out Manway box up with torquing | 20/04/2023 19:36:35 | 20/04/2023 19:36:40 | 18/04/2023 16:30:00 | 19/04/2023 16:30:00 | 01-CC-003 | COLUMN | 100 | MECHANICAL | BOX UP | BOX UP | 24 | 24:00 | 0:00 |  | 24:00 | 18-Apr | 19-Apr | 20-Apr | 20-Apr
CDUVDU29870 | In Progress | Carry out deblinding | 25/04/2023 11:27:11 |  | 19/04/2023 16:30:00 | 20/04/2023 16:30:00 | 01-CC-003 | COLUMN | 90 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  |  | 19-Apr | 20-Apr | 25-Apr | - Date check
CDUVDU3050 | Completed | Carry out manway opening | 03/04/2023 19:33:40 | 03/04/2023 19:33:44 | 01/04/2023 14:30:00 | 02/04/2023 14:30:00 | 01-CC-003 | COLUMN | 100 | MECHANICAL | OPENING | OPENING | 24 | 24:00 | 0:00 |  | 24:00 | 01-Apr | 02-Apr | 03-Apr | 03-Apr
CDUVDU3090 | Completed | Insulation removal | 13/04/2023 15:48:31 | 19/04/2023 19:27:13 | 01/04/2023 14:30:00 | 02/04/2023 14:30:00 | 01-CC-003 | COLUMN | 100 | CIVIL |  |  | 24 | 24:00 | 147:39 | 123:39 |  | 01-Apr | 02-Apr | 13-Apr | 19-Apr
CDUVDU5350 | Completed | Carry out preparation of air hose for ventilation and Hand lamp for lighting | 05/04/2023 10:40:25 | 05/04/2023 18:52:13 | 02/04/2023 14:30:00 | 02/04/2023 16:30:00 | 01-CC-003 | COLUMN | 100 | MECHANICAL |  |  | 2 | 2:00 | 8:12 | 6:12 |  | 02-Apr | 02-Apr | 05-Apr | 05-Apr
CDUVDU5380 | Completed | Carry out UT Gauging | 16/04/2023 12:09:41 | 16/04/2023 12:09:46 | 02/04/2023 14:30:00 | 03/04/2023 14:30:00 | 01-CC-003 | COLUMN | 100 | INSPECTION |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 02-Apr | 03-Apr | 16-Apr | 16-Apr
CDUVDU6140 | Completed | Entry | 06/04/2023 11:02:58 | 06/04/2023 11:03:04 | 02/04/2023 16:30:00 | 03/04/2023 04:30:00 | 01-CC-003 | COLUMN | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:00 |  | 12:00 | 02-Apr | 03-Apr | 06-Apr | 06-Apr
CDUVDU6780 | Completed | Carry out internal scaffolding on top and bottom | 16/04/2023 17:43:57 | 16/04/2023 17:44:02 | 03/04/2023 04:30:00 | 05/04/2023 04:30:00 | 01-CC-003 | COLUMN | 100 | MECHANICAL |  |  | 48 | 48:00 | 0:00 |  | 48:00 | 03-Apr | 05-Apr | 16-Apr | 16-Apr
CDUVDU9630 | Completed | Carry out tray manway opening | 06/04/2023 16:23:00 | 07/04/2023 19:17:50 | 05/04/2023 04:30:00 | 06/04/2023 04:30:00 | 01-CC-003 | COLUMN | 100 | MECHANICAL | TRAY MANWAY OPEN |  | 24 | 24:00 | 26:55 | 2:55 |  | 05-Apr | 06-Apr | 06-Apr | 07-Apr
CDUVDU10970 | Completed | Carry out tray manway opening | 06/04/2023 16:24:25 | 07/04/2023 19:18:18 | 06/04/2023 04:30:00 | 07/04/2023 04:30:00 | 01-CC-004 | COLUMN | 100 | MECHANICAL | TRAY MANWAY OPEN |  | 24 | 24:00 | 26:54 | 2:54 |  | 06-Apr | 07-Apr | 06-Apr | 07-Apr
CDUVDU12580 | Completed | Internal Removal | 17/04/2023 11:33:39 | 17/04/2023 11:33:44 | 07/04/2023 04:30:00 | 08/04/2023 04:30:00 | 01-CC-004 | COLUMN | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 07-Apr | 08-Apr | 17-Apr | 17-Apr
CDUVDU13970 | Completed | Carry out Cleaning of shell and nozzles | 06/04/2023 16:27:43 | 14/04/2023 15:19:23 | 08/04/2023 04:30:00 | 10/04/2023 16:30:00 | 01-CC-004 | COLUMN | 100 | MECHANICAL | CLEANING |  | 60 | 60:00 | 190:52 | 130:52 |  | 08-Apr | 10-Apr | 06-Apr | 14-Apr
CDUVDU19170 | Completed | Carry out WFMPI, DP, UFD, of all weld joints internally and externally | 16/04/2023 14:19:45 | 16/04/2023 14:20:45 | 10/04/2023 16:30:00 | 12/04/2023 16:30:00 | 01-CC-004 | COLUMN | 100 | INSPECTION |  |  | 48 | 48:00 | 0:01 |  | 47:59 | 10-Apr | 12-Apr | 16-Apr | 16-Apr
CDUVDU23940 | Completed | Carry out repair if any as per recommendation | 17/04/2023 11:34:01 | 19/04/2023 19:26:21 | 12/04/2023 16:30:00 | 15/04/2023 04:30:00 | 01-CC-004 | COLUMN | 100 | INSPECTION | REPAIR |  | 60 | 60:00 | 55:52 |  | 4:08 | 12-Apr | 15-Apr | 17-Apr | 19-Apr
CDUVDU27190 | Completed | Carry out Inspection by Inspection dept | 17/04/2023 11:34:24 | 17/04/2023 12:03:34 | 15/04/2023 04:30:00 | 15/04/2023 10:30:00 | 01-CC-004 | COLUMN | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:29 |  | 5:31 | 15-Apr | 15-Apr | 17-Apr | 17-Apr
CDUVDU27410 | Completed | Installation of Internal | 17/04/2023 11:34:40 | 17/04/2023 11:34:46 | 15/04/2023 10:30:00 | 16/04/2023 10:30:00 | 01-CC-004 | COLUMN | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 15-Apr | 16-Apr | 17-Apr | 17-Apr
CDUVDU28230 | Completed | Carry out TS Inspection | 19/04/2023 19:26:38 | 19/04/2023 19:26:43 | 16/04/2023 10:30:00 | 16/04/2023 16:30:00 | 01-CC-004 | COLUMN | 100 | TS |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 16-Apr | 16-Apr | 19-Apr | 19-Apr
CDUVDU28430 | Completed | Carry out removal of internal scaffolding | 17/04/2023 11:34:59 | 17/04/2023 11:35:09 | 16/04/2023 16:30:00 | 17/04/2023 16:30:00 | 01-CC-004 | COLUMN | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 16-Apr | 17-Apr | 17-Apr | 17-Apr
CDUVDU29020 | Completed | Carry out Tray manway box up | 19/04/2023 19:26:49 | 20/04/2023 14:52:25 | 17/04/2023 16:30:00 | 18/04/2023 16:30:00 | 01-CC-004 | COLUMN | 100 | MECHANICAL | TRAY MANWAY BOX UP |  | 24 | 24:00 | 19:26 |  | 4:34 | 17-Apr | 18-Apr | 19-Apr | 20-Apr
CDUVDU29480 | Completed | Carry out Manway box up with torquing | 20/04/2023 12:09:16 | 21/04/2023 19:22:17 | 18/04/2023 16:30:00 | 19/04/2023 16:30:00 | 01-CC-004 | COLUMN | 100 | MECHANICAL | BOX UP | BOX UP | 24 | 24:00 | 31:13 | 7:13 |  | 18-Apr | 19-Apr | 20-Apr | 21-Apr
CDUVDU29880 | In Progress | Carry out deblinding | 25/04/2023 11:27:19 |  | 19/04/2023 16:30:00 | 20/04/2023 16:30:00 | 01-CC-004 | COLUMN | 90 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  |  | 19-Apr | 20-Apr | 25-Apr | - Date check
CDUVDU3060 | Completed | Carry out blinding | 31/03/2023 10:39:37 | 03/04/2023 19:32:53 | 01/04/2023 14:30:00 | 02/04/2023 14:30:00 | 01-CC-004 | COLUMN | 100 | MECHANICAL | BLINDING | BLINDING | 24 | 24:00 | 80:53 | 56:53 |  | 01-Apr | 02-Apr | 31-Mar | 03-Apr
CDUVDU5360 | Completed | Carry out manway opening | 03/04/2023 19:34:17 | 03/04/2023 19:35:00 | 02/04/2023 14:30:00 | 03/04/2023 14:30:00 | 01-CC-004 | COLUMN | 100 | MECHANICAL | OPENING | OPENING | 24 | 24:00 | 0:01 |  | 23:59 | 02-Apr | 03-Apr | 03-Apr | 03-Apr
CDUVDU5390 | Completed | Insulation removal | 13/04/2023 15:48:10 | 20/04/2023 20:10:10 | 02/04/2023 14:30:00 | 03/04/2023 14:30:00 | 01-CC-004 | COLUMN | 100 | CIVIL |  |  | 24 | 24:00 | 172:22 | 148:22 |  | 02-Apr | 03-Apr | 13-Apr | 20-Apr
CDUVDU7640 | Completed | Carry out preparation of air hose for ventilation and Hand lamp for lighting | 05/04/2023 10:40:52 | 06/04/2023 11:03:25 | 03/04/2023 14:30:00 | 03/04/2023 16:30:00 | 01-CC-004 | COLUMN | 100 | MECHANICAL |  |  | 2 | 2:00 | 24:23 | 22:23 |  | 03-Apr | 03-Apr | 05-Apr | 06-Apr
CDUVDU7650 | Completed | Carry out UT Gauging | 16/04/2023 17:44:35 | 16/04/2023 17:44:41 | 03/04/2023 14:30:00 | 04/04/2023 14:30:00 | 01-CC-004 | COLUMN | 100 | INSPECTION |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 03-Apr | 04-Apr | 16-Apr | 16-Apr
CDUVDU7860 | Completed | Entry | 06/04/2023 11:03:42 | 06/04/2023 11:03:48 | 03/04/2023 16:30:00 | 04/04/2023 04:30:00 | 01-CC-004 | COLUMN | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:00 |  | 12:00 | 03-Apr | 04-Apr | 06-Apr | 06-Apr
CDUVDU8390 | Completed | Carry out internal scaffolding on top and bottom | 16/04/2023 17:44:58 | 16/04/2023 17:45:03 | 04/04/2023 04:30:00 | 06/04/2023 04:30:00 | 01-CC-004 | COLUMN | 100 | MECHANICAL |  |  | 48 | 48:00 | 0:00 |  | 48:00 | 04-Apr | 06-Apr | 16-Apr | 16-Apr
CDUVDU1430 | Completed | Carry out blinding | 30/03/2023 16:28:56 | 05/04/2023 11:35:47 | 30/03/2023 08:00:00 | 31/03/2023 08:00:00 | 01-CC-005 | COLUMN | 100 | MECHANICAL | BLINDING | BLINDING | 24 | 24:00 | 139:07 | 115:07 |  | 30-Mar | 31-Mar | 30-Mar | 05-Apr
CDUVDU14390 | Completed | Carry out WFMPI, DP, UFD, of all weld joints internally and externally | 16/04/2023 14:18:50 | 16/04/2023 14:19:50 | 08/04/2023 10:00:00 | 10/04/2023 10:00:00 | 01-CC-005 | COLUMN | 100 | INSPECTION |  |  | 48 | 48:00 | 0:01 |  | 47:59 | 08-Apr | 10-Apr | 16-Apr | 16-Apr
CDUVDU1820 | Completed | Carry out manway opening | 02/04/2023 14:51:25 | 03/04/2023 16:03:23 | 31/03/2023 08:00:00 | 01/04/2023 08:00:00 | 01-CC-005 | COLUMN | 100 | MECHANICAL | OPENING | OPENING | 24 | 24:00 | 25:12 | 1:12 |  | 31-Mar | 01-Apr | 02-Apr | 03-Apr
CDUVDU1840 | Completed | Insulation removal | 13/04/2023 09:24:39 | 13/04/2023 09:36:29 | 31/03/2023 08:00:00 | 01/04/2023 08:00:00 | 01-CC-005 | COLUMN | 100 | CIVIL |  |  | 24 | 24:00 | 0:12 |  | 23:48 | 31-Mar | 01-Apr | 13-Apr | 13-Apr
CDUVDU18550 | Completed | Carry out repair and replacement of fastner ( 36 nos.) if any as per recommendation | 17/04/2023 11:36:39 | 19/04/2023 19:29:46 | 10/04/2023 10:00:00 | 14/04/2023 10:00:00 | 01-CC-005 | COLUMN | 100 | INSPECTION | REPAIR |  | 96 | 96:00 | 55:53 |  | 40:07 | 10-Apr | 14-Apr | 17-Apr | 19-Apr
CDUVDU26420 | Completed | Carry out Inspection by Inspection dept | 17/04/2023 11:38:06 | 17/04/2023 12:05:19 | 14/04/2023 10:00:00 | 14/04/2023 16:00:00 | 01-CC-005 | COLUMN | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 0:27 |  | 5:33 | 14-Apr | 14-Apr | 17-Apr | 17-Apr
CDUVDU26750 | Completed | Installation of Internal | 17/04/2023 11:38:28 | 17/04/2023 11:38:33 | 14/04/2023 16:00:00 | 16/04/2023 04:00:00 | 01-CC-005 | COLUMN | 100 | MECHANICAL |  |  | 36 | 36:00 | 0:00 |  | 36:00 | 14-Apr | 16-Apr | 17-Apr | 17-Apr
CDUVDU2760 | Completed | Carry out preparation of air hose for ventilation and Hand lamp for lighting | 04/04/2023 12:40:17 | 04/04/2023 12:41:44 | 01/04/2023 08:00:00 | 01/04/2023 10:00:00 | 01-CC-005 | COLUMN | 100 | MECHANICAL |  |  | 2 | 2:00 | 0:01 |  | 1:59 | 01-Apr | 01-Apr | 04-Apr | 04-Apr
CDUVDU2770 | Completed | Carry out UT Gauging | 17/04/2023 11:12:00 | 17/04/2023 19:13:46 | 01/04/2023 08:00:00 | 02/04/2023 08:00:00 | 01-CC-005 | COLUMN | 100 | INSPECTION |  |  | 24 | 24:00 | 8:02 |  | 15:58 | 01-Apr | 02-Apr | 17-Apr | 17-Apr
CDUVDU27970 | Completed | Carry out TS Inspection | 19/04/2023 10:36:49 | 19/04/2023 10:36:54 | 16/04/2023 04:00:00 | 16/04/2023 10:00:00 | 01-CC-005 | COLUMN | 100 | TS |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 16-Apr | 16-Apr | 19-Apr | 19-Apr
CDUVDU28200 | Completed | Carry out removal of internal scaffolding | 19/04/2023 19:48:15 | 19/04/2023 19:48:20 | 16/04/2023 10:00:00 | 17/04/2023 10:00:00 | 01-CC-005 | COLUMN | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 16-Apr | 17-Apr | 19-Apr | 19-Apr
CDUVDU28850 | Completed | Carry out Tray manway box up | 19/04/2023 19:48:33 | 20/04/2023 07:13:15 | 17/04/2023 10:00:00 | 18/04/2023 10:00:00 | 01-CC-005 | COLUMN | 100 | MECHANICAL | TRAY MANWAY BOX UP |  | 24 | 24:00 | 11:25 |  | 12:35 | 17-Apr | 18-Apr | 19-Apr | 20-Apr
CDUVDU2910 | Completed | Entry | 04/04/2023 17:41:59 | 04/04/2023 18:56:49 | 01/04/2023 10:00:00 | 01/04/2023 22:00:00 | 01-CC-005 | COLUMN | 100 | MECHANICAL |  |  | 12 | 12:00 | 1:15 |  | 10:45 | 01-Apr | 01-Apr | 04-Apr | 04-Apr
CDUVDU29370 | Completed | Carry out Manway box up with torquing | 20/04/2023 07:12:10 | 21/04/2023 19:23:54 | 18/04/2023 10:00:00 | 19/04/2023 10:00:00 | 01-CC-005 | COLUMN | 100 | MECHANICAL | BOX UP | BOX UP | 24 | 24:00 | 36:12 | 12:12 |  | 18-Apr | 19-Apr | 20-Apr | 21-Apr
CDUVDU29770 | Completed | Carry out deblinding | 20/04/2023 07:12:22 | 24/04/2023 17:11:14 | 19/04/2023 10:00:00 | 20/04/2023 10:00:00 | 01-CC-005 | COLUMN | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 105:59 | 81:59 |  | 19-Apr | 20-Apr | 20-Apr | 24-Apr
CDUVDU4010 | Completed | Carry out internal scaffolding on top and bottom | 16/04/2023 10:16:57 | 16/04/2023 10:17:04 | 01/04/2023 22:00:00 | 02/04/2023 22:00:00 | 01-CC-005 | COLUMN | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 01-Apr | 02-Apr | 16-Apr | 16-Apr
CDUVDU6370 | Completed | Carry out tray manway opening | 05/04/2023 11:36:19 | 06/04/2023 11:09:30 | 02/04/2023 22:00:00 | 03/04/2023 22:00:00 | 01-CC-005 | COLUMN | 100 | MECHANICAL | TRAY MANWAY OPEN |  | 24 | 24:00 | 23:33 |  | 0:27 | 02-Apr | 03-Apr | 05-Apr | 06-Apr
CDUVDU8100 | Completed | Internal Removal | 17/04/2023 11:36:54 | 17/04/2023 11:36:59 | 03/04/2023 22:00:00 | 05/04/2023 10:00:00 | 01-CC-005 | COLUMN | 100 | MECHANICAL |  |  | 36 | 36:00 | 0:00 |  | 36:00 | 03-Apr | 05-Apr | 17-Apr | 17-Apr
CDUVDU9930 | Completed | Carry out Cleaning of shell and nozzles | 06/04/2023 18:03:03 | 15/04/2023 10:37:32 | 05/04/2023 10:00:00 | 08/04/2023 10:00:00 | 01-CC-005 | COLUMN | 100 | MECHANICAL | CLEANING |  | 72 | 72:00 | 208:34 | 136:34 |  | 05-Apr | 08-Apr | 06-Apr | 15-Apr
CDUVDU11690 | Completed | Carry out WFMPI, DP, UFD, of all weld joints internally and externally | 11/04/2023 05:34:11 | 17/04/2023 19:14:25 | 06/04/2023 16:30:00 | 08/04/2023 04:30:00 | 01-CC-006 | COLUMN | 100 | INSPECTION |  |  | 36 | 36:00 | 157:40 | 121:40 |  | 06-Apr | 08-Apr | 11-Apr | 17-Apr
CDUVDU13980 | Completed | Carry out wear plate repair | 16/04/2023 10:22:29 | 16/04/2023 10:22:34 | 08/04/2023 04:30:00 | 10/04/2023 16:30:00 | 01-CC-006 | COLUMN | 100 | INSPECTION | REPAIR |  | 60 | 60:00 | 0:00 |  | 60:00 | 08-Apr | 10-Apr | 16-Apr | 16-Apr
CDUVDU18050 | Completed | CT 4 deck plate spares replacement as per recommendation | 17/04/2023 11:40:02 | 17/04/2023 11:40:08 | 10/04/2023 04:30:00 | 16/04/2023 12:30:00 | 01-CC-006 | COLUMN | 100 | MECHANICAL |  |  | 152 | 152:00 | 0:00 |  | 152:00 | 10-Apr | 16-Apr | 17-Apr | 17-Apr
CDUVDU2030 | Completed | Carry out blinding | 27/03/2023 17:52:00 | 02/04/2023 09:54:04 | 31/03/2023 14:30:00 | 01/04/2023 08:30:00 | 01-CC-006 | COLUMN | 100 | MECHANICAL | BLINDING | BLINDING | 18 | 18:00 | 136:02 | 118:02 |  | 31-Mar | 01-Apr | 27-Mar | 02-Apr
CDUVDU2780 | Completed | Carry out manway opening | 01/04/2023 15:39:19 | 02/04/2023 09:55:40 | 01/04/2023 08:30:00 | 02/04/2023 02:30:00 | 01-CC-006 | COLUMN | 100 | MECHANICAL | OPENING | OPENING | 18 | 18:00 | 18:16 | 0:16 |  | 01-Apr | 02-Apr | 01-Apr | 02-Apr
CDUVDU28310 | Completed | Replacement of Packing | 08/04/2023 17:27:14 | 08/04/2023 18:44:34 | 16/04/2023 12:30:00 | 19/04/2023 00:30:00 | 01-CC-006 | COLUMN | 100 | MECHANICAL |  |  | 60 | 60:00 | 1:17 |  | 58:43 | 16-Apr | 19-Apr | 08-Apr | 08-Apr
CDUVDU29630 | Completed | Carry out Inspection by Inspection dept | 16/04/2023 10:25:19 | 17/04/2023 12:49:54 | 19/04/2023 00:30:00 | 19/04/2023 06:30:00 | 01-CC-006 | COLUMN | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 26:25 | 20:25 |  | 19-Apr | 19-Apr | 16-Apr | 17-Apr
CDUVDU29730 | Completed | Carry out inspection by TS | 18/04/2023 10:06:19 | 18/04/2023 10:06:27 | 19/04/2023 06:30:00 | 19/04/2023 12:30:00 | 01-CC-006 | COLUMN | 100 | TS |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 19-Apr | 19-Apr | 18-Apr | 18-Apr
CDUVDU29800 | Completed | Carry out removal of internal scaffolding | 18/04/2023 10:06:48 | 18/04/2023 10:12:09 | 19/04/2023 12:30:00 | 20/04/2023 08:30:00 | 01-CC-006 | COLUMN | 100 | MECHANICAL |  |  | 20 | 20:00 | 0:05 |  | 19:55 | 19-Apr | 20-Apr | 18-Apr | 18-Apr
CDUVDU30030 | Completed | Carry out Tray manway box up | 18/04/2023 10:12:20 | 18/04/2023 10:12:27 | 20/04/2023 08:30:00 | 21/04/2023 02:30:00 | 01-CC-006 | COLUMN | 100 | MECHANICAL | TRAY MANWAY BOX UP |  | 18 | 18:00 | 0:00 |  | 18:00 | 20-Apr | 21-Apr | 18-Apr | 18-Apr
CDUVDU30130 | Completed | Carry out Manway box up with torquing | 18/04/2023 14:55:17 | 19/04/2023 09:28:57 | 21/04/2023 02:30:00 | 21/04/2023 20:30:00 | 01-CC-006 | COLUMN | 100 | MECHANICAL | BOX UP | BOX UP | 18 | 18:00 | 18:34 | 0:34 |  | 21-Apr | 21-Apr | 18-Apr | 19-Apr
CDUVDU30160 | Completed | Carry out deblinding | 19/04/2023 00:04:14 | 20/04/2023 02:43:35 | 21/04/2023 20:30:00 | 22/04/2023 14:30:00 | 01-CC-006 | COLUMN | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 18 | 18:00 | 26:39 | 8:39 |  | 21-Apr | 22-Apr | 19-Apr | 20-Apr
CDUVDU4500 | Completed | Carry out preparation of air hose for ventilation and Hand lamp for lighting | 02/04/2023 09:59:26 | 03/04/2023 12:16:39 | 02/04/2023 02:30:00 | 02/04/2023 04:30:00 | 01-CC-006 | COLUMN | 100 | MECHANICAL |  |  | 2 | 2:00 | 26:17 | 24:17 |  | 02-Apr | 02-Apr | 02-Apr | 03-Apr
CDUVDU4570 | Completed | Entry | 03/04/2023 12:17:05 | 03/04/2023 12:17:27 | 02/04/2023 04:30:00 | 02/04/2023 10:30:00 | 01-CC-006 | COLUMN | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 02-Apr | 02-Apr | 03-Apr | 03-Apr
CDUVDU5070 | Completed | Carry out internal scaffolding on top and bottom | 04/04/2023 09:44:27 | 07/04/2023 18:32:32 | 02/04/2023 10:30:00 | 03/04/2023 04:30:00 | 01-CC-006 | COLUMN | 100 | MECHANICAL |  |  | 18 | 18:00 | 80:48 | 62:48 |  | 02-Apr | 03-Apr | 04-Apr | 07-Apr
CDUVDU6790 | Completed | Carry out tray manway opening | 05/04/2023 11:41:07 | 05/04/2023 19:13:45 | 03/04/2023 04:30:00 | 03/04/2023 16:30:00 | 01-CC-006 | COLUMN | 100 | MECHANICAL | TRAY MANWAY OPEN |  | 12 | 12:00 | 7:33 |  | 4:27 | 03-Apr | 03-Apr | 05-Apr | 05-Apr
CDUVDU7920 | Completed | Carry out dismantling of internals | 03/04/2023 17:03:35 | 05/04/2023 15:10:08 | 03/04/2023 16:30:00 | 05/04/2023 04:30:00 | 01-CC-006 | COLUMN | 100 | MECHANICAL |  |  | 36 | 36:00 | 46:07 | 10:07 |  | 03-Apr | 05-Apr | 03-Apr | 05-Apr
CDUVDU9640 | Completed | Carry out Cleaning of shell and nozzles | 05/04/2023 11:40:52 | 11/04/2023 05:33:30 | 05/04/2023 04:30:00 | 06/04/2023 16:30:00 | 01-CC-006 | COLUMN | 100 | MECHANICAL | CLEANING |  | 36 | 36:00 | 137:53 | 101:53 |  | 05-Apr | 06-Apr | 05-Apr | 11-Apr
CDUVDU12550 | Completed | Carry out Cleaning of shell and nozzles | 06/04/2023 16:20:02 | 24/04/2023 18:52:09 | 07/04/2023 04:30:00 | 10/04/2023 04:30:00 | 01-CC-001 | COLUMN | 100 | MECHANICAL | CLEANING |  | 72 | 72:00 | 434:32 | 362:32 |  | 07-Apr | 10-Apr | 06-Apr | 24-Apr
CDUVDU12570 | Completed | Cleaning of Packing and Trays | 16/04/2023 10:15:19 | 19/04/2023 19:49:36 | 07/04/2023 04:30:00 | 10/04/2023 04:30:00 | 01-CC-001 | COLUMN | 100 | MECHANICAL |  |  | 72 | 72:00 | 81:34 | 9:34 |  | 07-Apr | 10-Apr | 16-Apr | 19-Apr
CDUVDU1620 | Completed | Carry out blinding | 30/03/2023 19:50:28 | 04/04/2023 09:29:14 | 30/03/2023 14:30:00 | 31/03/2023 14:30:00 | 01-CC-001 | COLUMN | 100 | MECHANICAL | BLINDING | BLINDING | 24 | 24:00 | 109:39 | 85:39 |  | 30-Mar | 31-Mar | 30-Mar | 04-Apr
CDUVDU18040 | Completed | Carry out WFMPI, DP, UFD, of all weld joints internally and externally | 20/04/2023 12:03:17 | 20/04/2023 12:03:24 | 10/04/2023 04:30:00 | 12/04/2023 16:30:00 | 01-CC-001 | COLUMN | 100 | INSPECTION |  |  | 60 | 60:00 | 0:00 |  | 60:00 | 10-Apr | 12-Apr | 20-Apr | 20-Apr
CDUVDU18080 | Completed | Deatiled Inspection of Tray | 18/04/2023 12:23:04 | 23/04/2023 12:57:13 | 10/04/2023 04:30:00 | 11/04/2023 04:30:00 | 01-CC-001 | COLUMN | 100 | INSPECTION |  |  | 24 | 24:00 | 120:34 | 96:34 |  | 10-Apr | 11-Apr | 18-Apr | 23-Apr
CDUVDU2000 | Completed | Carry out manway opening | 04/04/2023 11:44:46 | 05/04/2023 10:31:25 | 31/03/2023 14:30:00 | 01/04/2023 14:30:00 | 01-CC-001 | COLUMN | 100 | MECHANICAL | OPENING | OPENING | 24 | 24:00 | 22:47 |  | 1:13 | 31-Mar | 01-Apr | 04-Apr | 05-Apr
CDUVDU23920 | Completed | Carry out repair and replacement of trays if any as per recommendation | 20/04/2023 12:08:00 | 20/04/2023 12:08:05 | 12/04/2023 16:30:00 | 15/04/2023 16:30:00 | 01-CC-001 | COLUMN | 100 | INSPECTION | REPAIR |  | 72 | 72:00 | 0:00 |  | 72:00 | 12-Apr | 15-Apr | 20-Apr | 20-Apr
CDUVDU23950 | Completed | Column shell weld build-up considering the grooving of the TSR regions & Inspection | 20/04/2023 12:07:10 | 20/04/2023 12:07:16 | 12/04/2023 16:30:00 | 13/04/2023 13:30:00 | 01-CC-001 | COLUMN | 100 | MECHANICAL |  |  | 21 | 21:00 | 0:00 |  | 21:00 | 12-Apr | 13-Apr | 20-Apr | 20-Apr
CDUVDU27640 | Completed | Carry out Inspection by Inspection dept | 20/04/2023 12:05:35 | 21/04/2023 09:20:54 | 15/04/2023 16:30:00 | 15/04/2023 22:30:00 | 01-CC-001 | COLUMN | 100 | INSPECTION | INSPECTION | INSPECTION | 6 | 6:00 | 21:15 | 15:15 |  | 15-Apr | 15-Apr | 20-Apr | 21-Apr
CDUVDU27790 | Completed | Carry out inspection by TS | 20/04/2023 12:04:38 | 24/04/2023 18:52:16 | 15/04/2023 22:30:00 | 16/04/2023 04:30:00 | 01-CC-001 | COLUMN | 100 | TS |  |  | 6 | 6:00 | 102:48 | 96:48 |  | 15-Apr | 16-Apr | 20-Apr | 24-Apr
CDUVDU28010 | Completed | Carry out removal of internal scaffolding | 20/04/2023 14:04:17 | 24/04/2023 18:52:26 | 16/04/2023 04:30:00 | 17/04/2023 04:30:00 | 01-CC-001 | COLUMN | 100 | MECHANICAL |  |  | 24 | 24:00 | 100:48 | 76:48 |  | 16-Apr | 17-Apr | 20-Apr | 24-Apr
CDUVDU28740 | Completed | Carry out Tray manway box up | 22/04/2023 19:06:41 | 24/04/2023 18:52:39 | 17/04/2023 04:30:00 | 18/04/2023 16:30:00 | 01-CC-001 | COLUMN | 100 | MECHANICAL | TRAY MANWAY BOX UP |  | 36 | 36:00 | 47:46 | 11:46 |  | 17-Apr | 18-Apr | 22-Apr | 24-Apr
CDUVDU29460 | Completed | Carry out Manway box up with torquing | 24/04/2023 18:52:50 | 25/04/2023 07:33:25 | 18/04/2023 16:30:00 | 19/04/2023 16:30:00 | 01-CC-001 | COLUMN | 100 | MECHANICAL | BOX UP | BOX UP | 24 | 24:00 | 12:41 |  | 11:19 | 18-Apr | 19-Apr | 24-Apr | 25-Apr
CDUVDU29860 | In Progress | Carry out deblinding | 24/04/2023 18:53:08 |  | 19/04/2023 16:30:00 | 20/04/2023 16:30:00 | 01-CC-001 | COLUMN | 90 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  |  | 19-Apr | 20-Apr | 24-Apr | - Date check
CDUVDU3030 | Completed | Carry out preparation of air hose for ventilation and Hand lamp for lighting | 05/04/2023 12:31:34 | 05/04/2023 18:48:52 | 01/04/2023 14:30:00 | 01/04/2023 16:30:00 | 01-CC-001 | COLUMN | 100 | MECHANICAL |  |  | 2 | 2:00 | 6:17 | 4:17 |  | 01-Apr | 01-Apr | 05-Apr | 05-Apr
CDUVDU3850 | Completed | Entry | 05/04/2023 18:51:33 | 06/04/2023 11:02:27 | 01/04/2023 16:30:00 | 02/04/2023 04:30:00 | 01-CC-001 | COLUMN | 100 | MECHANICAL |  |  | 12 | 12:00 | 16:11 | 4:11 |  | 01-Apr | 02-Apr | 05-Apr | 06-Apr
CDUVDU4550 | Completed | Carry out internal scaffolding on top and bottom and insulation removal | 07/04/2023 09:26:29 | 14/04/2023 16:57:32 | 02/04/2023 04:30:00 | 03/04/2023 16:30:00 | 01-CC-001 | COLUMN | 100 | CIVIL |  |  | 36 | 36:00 | 175:31 | 139:31 |  | 02-Apr | 03-Apr | 07-Apr | 14-Apr
CDUVDU7850 | Completed | Carry out tray manway opening | 06/04/2023 16:18:54 | 09/04/2023 09:49:44 | 03/04/2023 16:30:00 | 04/04/2023 16:30:00 | 01-CC-001 | COLUMN | 100 | MECHANICAL | TRAY MANWAY OPEN |  | 24 | 24:00 | 65:31 | 41:31 |  | 03-Apr | 04-Apr | 06-Apr | 09-Apr
CDUVDU7910 | Completed | Insulation removal | 15/04/2023 17:03:12 | 20/04/2023 19:16:32 | 03/04/2023 16:30:00 | 04/04/2023 16:30:00 | 01-CC-001 | COLUMN | 100 | CIVIL |  |  | 24 | 24:00 | 122:13 | 98:13 |  | 03-Apr | 04-Apr | 15-Apr | 20-Apr
CDUVDU9130 | Completed | Removal of Internals for detailed inspection | 10/04/2023 11:39:46 | 17/04/2023 19:20:21 | 04/04/2023 16:30:00 | 07/04/2023 04:30:00 | 01-CC-001 | COLUMN | 100 | MECHANICAL |  |  | 60 | 60:00 | 175:41 | 115:41 |  | 04-Apr | 07-Apr | 10-Apr | 17-Apr
CDUVDU9170 | Completed | Dismantle Distributor pipe | 17/04/2023 12:05:35 | 19/04/2023 19:49:21 | 04/04/2023 16:30:00 | 05/04/2023 10:30:00 | 01-CC-001 | COLUMN | 100 | MECHANICAL |  |  | 18 | 18:00 | 55:44 | 37:44 |  | 04-Apr | 05-Apr | 17-Apr | 19-Apr
CDUVDU9180 | Completed | Carry out UT Gauging | 19/04/2023 19:50:48 | 20/04/2023 17:26:36 | 04/04/2023 16:30:00 | 05/04/2023 16:30:00 | 01-CC-001 | COLUMN | 100 | INSPECTION |  |  | 24 | 24:00 | 21:36 |  | 2:24 | 04-Apr | 05-Apr | 19-Apr | 20-Apr
CDUVDU13960 | Completed | Carry Out Inspection | 20/04/2023 09:17:49 | 20/04/2023 09:17:53 | 08/04/2023 04:00:00 | 08/04/2023 08:00:00 | 01-VV-001 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 08-Apr | 08-Apr | 20-Apr | 20-Apr
CDUVDU14210 | Completed | Installation of Internals | 20/04/2023 09:18:04 | 20/04/2023 09:18:04 | 08/04/2023 08:00:00 | 09/04/2023 08:00:00 | 01-VV-001 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  |  | 08-Apr | 09-Apr | 20-Apr | 20-Apr
CDUVDU1450 | Completed | Blinding | 30/03/2023 05:28:16 | 30/03/2023 05:28:16 | 30/03/2023 08:00:00 | 31/03/2023 08:00:00 | 01-VV-001 | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 24 | 24:00 | 0:00 |  |  | 30-Mar | 31-Mar | 30-Mar | 30-Mar
CDUVDU16080 | Completed | Box up of manhole cover | 21/04/2023 18:43:54 | 22/04/2023 19:05:56 | 09/04/2023 08:00:00 | 09/04/2023 12:00:00 | 01-VV-001 | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 24:22 | 20:22 |  | 09-Apr | 09-Apr | 21-Apr | 22-Apr
CDUVDU16470 | In Progress | Deblinding | 21/04/2023 18:55:22 |  | 09/04/2023 12:00:00 | 10/04/2023 12:00:00 | 01-VV-001 | VESSEL | 90 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  |  | 09-Apr | 10-Apr | 21-Apr | - Date check
CDUVDU1850 | Completed | Opening of manhole cover | 30/03/2023 05:28:16 | 30/03/2023 05:28:16 | 31/03/2023 08:00:00 | 31/03/2023 16:00:00 | 01-VV-001 | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  |  | 31-Mar | 31-Mar | 30-Mar | 30-Mar
CDUVDU2300 | Completed | Manentry | 30/03/2023 05:28:16 | 30/03/2023 05:28:16 | 31/03/2023 16:00:00 | 31/03/2023 20:00:00 | 01-VV-001 | VESSEL | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  |  | 31-Mar | 31-Mar | 30-Mar | 30-Mar
CDUVDU2310 | Completed | UT Gauging | 30/03/2023 05:28:16 | 30/03/2023 05:28:16 | 31/03/2023 16:00:00 | 01/04/2023 04:00:00 | 01-VV-001 | VESSEL | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  |  | 31-Mar | 01-Apr | 30-Mar | 30-Mar
CDUVDU2390 | Completed | Pre-cleaning inspection | 30/03/2023 05:28:16 | 30/03/2023 05:28:16 | 31/03/2023 20:00:00 | 01/04/2023 00:00:00 | 01-VV-001 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  |  | 31-Mar | 01-Apr | 30-Mar | 30-Mar
CDUVDU2580 | Completed | Removal of Internals | 12/04/2023 11:52:54 | 12/04/2023 11:53:01 | 01/04/2023 00:00:00 | 02/04/2023 00:00:00 | 01-VV-001 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 01-Apr | 02-Apr | 12-Apr | 12-Apr
CDUVDU4350 | Completed | Internal cleaning | 05/04/2023 11:05:04 | 15/04/2023 17:08:19 | 02/04/2023 00:00:00 | 04/04/2023 00:00:00 | 01-VV-001 | VESSEL | 100 | MECHANICAL | CLEANING |  | 48 | 48:00 | 246:03 | 198:03 |  | 02-Apr | 04-Apr | 05-Apr | 15-Apr
CDUVDU8180 | Completed | Post cleaning inspection | 30/03/2023 05:28:16 | 15/04/2023 17:08:47 | 04/04/2023 00:00:00 | 04/04/2023 04:00:00 | 01-VV-001 | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 395:41 | 391:41 |  | 04-Apr | 04-Apr | 30-Mar | 15-Apr
CDUVDU8370 | Completed | Repair if any | 17/04/2023 11:48:02 | 17/04/2023 12:12:10 | 04/04/2023 04:00:00 | 08/04/2023 04:00:00 | 01-VV-001 | VESSEL | 100 | MECHANICAL | REPAIR |  | 96 | 96:00 | 0:24 |  | 95:36 | 04-Apr | 08-Apr | 17-Apr | 17-Apr
CDUVDU11370 | Completed | Internal cleaning | 29/03/2023 19:48:25 | 29/03/2023 19:48:25 | 06/04/2023 12:00:00 | 07/04/2023 12:00:00 | 01-VV-010 | VESSEL | 100 | MECHANICAL | CLEANING |  | 24 | 24:00 | 0:00 |  |  | 06-Apr | 07-Apr | 29-Mar | 29-Mar
CDUVDU12970 | Completed | Post cleaning inspection | 29/03/2023 19:48:25 | 29/03/2023 19:48:25 | 07/04/2023 12:00:00 | 07/04/2023 16:00:00 | 01-VV-010 | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:00 |  |  | 07-Apr | 07-Apr | 29-Mar | 29-Mar
CDUVDU13270 | Completed | Repair if any | 08/04/2023 11:40:23 | 08/04/2023 11:40:28 | 07/04/2023 16:00:00 | 09/04/2023 16:00:00 | 01-VV-010 | VESSEL | 100 | MECHANICAL | REPAIR |  | 48 | 48:00 | 0:00 |  | 48:00 | 07-Apr | 09-Apr | 08-Apr | 08-Apr
CDUVDU16810 | Completed | Carry Out Inspection | 08/04/2023 11:40:45 | 08/04/2023 11:40:50 | 09/04/2023 16:00:00 | 09/04/2023 20:00:00 | 01-VV-010 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 09-Apr | 09-Apr | 08-Apr | 08-Apr
CDUVDU17220 | Completed | Installation of Internals | 08/04/2023 11:41:13 | 08/04/2023 11:41:23 | 09/04/2023 20:00:00 | 10/04/2023 20:00:00 | 01-VV-010 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 09-Apr | 10-Apr | 08-Apr | 08-Apr
CDUVDU19490 | Completed | Box up of manhole cover | 08/04/2023 11:41:34 | 09/04/2023 19:21:04 | 10/04/2023 20:00:00 | 11/04/2023 00:00:00 | 01-VV-010 | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 31:39 | 27:40 |  | 10-Apr | 11-Apr | 08-Apr | 09-Apr
CDUVDU19990 | Completed | Deblinding | 09/04/2023 19:21:13 | 09/04/2023 19:21:18 | 11/04/2023 00:00:00 | 12/04/2023 00:00:00 | 01-VV-010 | VESSEL | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  | 24:00 | 11-Apr | 12-Apr | 09-Apr | 09-Apr
CDUVDU3820 | Completed | Blinding | 27/03/2023 10:04:01 | 29/03/2023 19:48:25 | 01/04/2023 16:30:00 | 02/04/2023 16:30:00 | 01-VV-010 | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 24 | 24:00 | 57:44 | 33:44 |  | 01-Apr | 02-Apr | 27-Mar | 29-Mar
CDUVDU6160 | Completed | Opening of manhole cover | 29/03/2023 19:48:25 | 29/03/2023 19:48:25 | 02/04/2023 16:30:00 | 03/04/2023 00:30:00 | 01-VV-010 | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  |  | 02-Apr | 03-Apr | 29-Mar | 29-Mar
CDUVDU6640 | Completed | Manentry | 29/03/2023 19:48:25 | 29/03/2023 19:48:25 | 03/04/2023 00:30:00 | 03/04/2023 04:30:00 | 01-VV-010 | VESSEL | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  |  | 03-Apr | 03-Apr | 29-Mar | 29-Mar
CDUVDU6650 | Completed | UT Gauging | 29/03/2023 19:48:25 | 29/03/2023 19:48:25 | 03/04/2023 00:30:00 | 03/04/2023 12:30:00 | 01-VV-010 | VESSEL | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  |  | 03-Apr | 03-Apr | 29-Mar | 29-Mar
CDUVDU6810 | Completed | Pre-cleaning inspection | 29/03/2023 19:48:25 | 29/03/2023 19:48:25 | 03/04/2023 04:30:00 | 03/04/2023 08:30:00 | 01-VV-010 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  |  | 03-Apr | 03-Apr | 29-Mar | 29-Mar
CDUVDU7100 | Completed | Removal of Internals | 29/03/2023 19:48:25 | 29/03/2023 19:48:25 | 03/04/2023 08:30:00 | 04/04/2023 08:30:00 | 01-VV-010 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  |  | 03-Apr | 04-Apr | 29-Mar | 29-Mar
CDUVDU10250 | Completed | Blinding | 10/04/2023 09:35:08 | 12/04/2023 11:23:25 | 05/04/2023 14:30:00 | 06/04/2023 14:30:00 | 01-VV-011 | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 24 | 24:00 | 49:48 | 25:48 |  | 05-Apr | 06-Apr | 10-Apr | 12-Apr
CDUVDU11530 | Completed | Opening of manhole cover | 11/04/2023 16:56:44 | 11/04/2023 16:56:49 | 06/04/2023 14:30:00 | 06/04/2023 22:30:00 | 01-VV-011 | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  | 8:00 | 06-Apr | 06-Apr | 11-Apr | 11-Apr
CDUVDU12110 | Completed | Manentry | 12/04/2023 11:37:15 | 12/04/2023 11:37:20 | 06/04/2023 22:30:00 | 07/04/2023 02:30:00 | 01-VV-011 | VESSEL | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 06-Apr | 07-Apr | 12-Apr | 12-Apr
CDUVDU12120 | Completed | UT Gauging | 12/04/2023 11:31:15 | 12/04/2023 11:31:22 | 06/04/2023 22:30:00 | 07/04/2023 10:30:00 | 01-VV-011 | VESSEL | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  | 12:00 | 06-Apr | 07-Apr | 12-Apr | 12-Apr
CDUVDU12450 | Completed | Pre-cleaning inspection | 11/04/2023 16:57:00 | 11/04/2023 19:57:00 | 07/04/2023 02:30:00 | 07/04/2023 06:30:00 | 01-VV-011 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 3:00 |  | 1:00 | 07-Apr | 07-Apr | 11-Apr | 11-Apr
CDUVDU12640 | Completed | Removal of Internals | 13/04/2023 07:57:00 | 14/04/2023 07:58:04 | 07/04/2023 06:30:00 | 08/04/2023 06:30:00 | 01-VV-011 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 24:01 | 0:01 |  | 07-Apr | 08-Apr | 13-Apr | 14-Apr
CDUVDU14040 | Completed | Internal cleaning | 12/04/2023 11:36:15 | 14/04/2023 12:21:25 | 08/04/2023 06:30:00 | 10/04/2023 18:30:00 | 01-VV-011 | VESSEL | 100 | MECHANICAL | CLEANING |  | 60 | 60:00 | 48:45 |  | 11:15 | 08-Apr | 10-Apr | 12-Apr | 14-Apr
CDUVDU19380 | Completed | Post cleaning inspection | 14/04/2023 12:22:25 | 14/04/2023 12:22:28 | 10/04/2023 18:30:00 | 10/04/2023 22:30:00 | 01-VV-011 | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:00 |  | 4:00 | 10-Apr | 10-Apr | 14-Apr | 14-Apr
CDUVDU19710 | Completed | Repair if any | 12/04/2023 11:31:35 | 12/04/2023 11:32:42 | 10/04/2023 22:30:00 | 12/04/2023 22:30:00 | 01-VV-011 | VESSEL | 100 | MECHANICAL | REPAIR |  | 48 | 48:00 | 0:01 |  | 47:59 | 10-Apr | 12-Apr | 12-Apr | 12-Apr
CDUVDU24370 | Completed | Carry Out Inspection | 12/04/2023 11:34:09 | 12/04/2023 11:34:14 | 12/04/2023 22:30:00 | 13/04/2023 02:30:00 | 01-VV-011 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 12-Apr | 13-Apr | 12-Apr | 12-Apr
CDUVDU24670 | Completed | Installation of Internals | 12/04/2023 11:34:32 | 17/04/2023 17:45:22 | 13/04/2023 02:30:00 | 14/04/2023 02:30:00 | 01-VV-011 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 126:11 | 102:11 |  | 13-Apr | 14-Apr | 12-Apr | 17-Apr
CDUVDU26040 | Completed | Box up of manhole cover | 20/04/2023 16:19:37 | 20/04/2023 16:19:42 | 14/04/2023 02:30:00 | 14/04/2023 06:30:00 | 01-VV-011 | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  | 4:00 | 14-Apr | 14-Apr | 20-Apr | 20-Apr
CDUVDU26270 | Completed | Deblinding | 22/04/2023 11:58:06 | 22/04/2023 11:58:11 | 14/04/2023 06:30:00 | 15/04/2023 06:30:00 | 01-VV-011 | VESSEL | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  | 24:00 | 14-Apr | 15-Apr | 22-Apr | 22-Apr
CDUVDU10430 | Completed | Opening of manhole cover | 04/04/2023 10:34:48 | 04/04/2023 10:34:54 | 05/04/2023 16:30:00 | 06/04/2023 00:30:00 | 01-VV-013 | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  | 8:00 | 05-Apr | 06-Apr | 04-Apr | 04-Apr
CDUVDU10640 | Completed | Manentry | 04/04/2023 21:43:49 | 04/04/2023 21:43:49 | 06/04/2023 00:30:00 | 06/04/2023 04:30:00 | 01-VV-013 | VESSEL | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  |  | 06-Apr | 06-Apr | 04-Apr | 04-Apr
CDUVDU10650 | Completed | UT Gauging | 04/04/2023 21:43:49 | 04/04/2023 21:43:49 | 06/04/2023 00:30:00 | 06/04/2023 12:30:00 | 01-VV-013 | VESSEL | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  |  | 06-Apr | 06-Apr | 04-Apr | 04-Apr
CDUVDU10980 | Completed | Pre-cleaning inspection | 04/04/2023 21:43:49 | 04/04/2023 21:43:49 | 06/04/2023 04:30:00 | 06/04/2023 08:30:00 | 01-VV-013 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  |  | 06-Apr | 06-Apr | 04-Apr | 04-Apr
CDUVDU11190 | Completed | Removal of Internals | 09/04/2023 14:39:06 | 09/04/2023 14:41:24 | 06/04/2023 08:30:00 | 07/04/2023 08:30:00 | 01-VV-013 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:02 |  | 23:58 | 06-Apr | 07-Apr | 09-Apr | 09-Apr
CDUVDU15420 | Completed | Internal cleaning | 10/04/2023 16:51:57 | 11/04/2023 18:07:20 | 09/04/2023 00:00:00 | 11/04/2023 00:00:00 | 01-VV-013 | VESSEL | 100 | MECHANICAL | CLEANING |  | 48 | 48:00 | 25:15 |  | 22:45 | 09-Apr | 11-Apr | 10-Apr | 11-Apr
CDUVDU20010 | Completed | Post cleaning inspection | 10/04/2023 03:02:37 | 10/04/2023 03:02:37 | 11/04/2023 00:00:00 | 11/04/2023 04:00:00 | 01-VV-013 | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:00 |  |  | 11-Apr | 11-Apr | 10-Apr | 10-Apr
CDUVDU20450 | Completed | Repair if any | 12/04/2023 12:14:41 | 12/04/2023 12:15:00 | 11/04/2023 04:00:00 | 13/04/2023 04:00:00 | 01-VV-013 | VESSEL | 100 | MECHANICAL | REPAIR |  | 48 | 48:00 | 0:00 |  | 48:00 | 11-Apr | 13-Apr | 12-Apr | 12-Apr
CDUVDU24810 | Completed | Carry Out Inspection | 12/04/2023 12:15:20 | 12/04/2023 12:15:27 | 13/04/2023 04:00:00 | 13/04/2023 08:00:00 | 01-VV-013 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 13-Apr | 13-Apr | 12-Apr | 12-Apr
CDUVDU25120 | Completed | Installation of Internals | 12/04/2023 12:15:55 | 12/04/2023 12:16:01 | 13/04/2023 08:00:00 | 14/04/2023 08:00:00 | 01-VV-013 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 13-Apr | 14-Apr | 12-Apr | 12-Apr
CDUVDU26340 | Completed | Box up of manhole cover | 12/04/2023 12:16:20 | 12/04/2023 12:16:49 | 14/04/2023 08:00:00 | 14/04/2023 12:00:00 | 01-VV-013 | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  | 4:00 | 14-Apr | 14-Apr | 12-Apr | 12-Apr
CDUVDU26530 | Completed | Deblinding | 17/04/2023 19:35:25 | 17/04/2023 19:35:29 | 14/04/2023 12:00:00 | 15/04/2023 12:00:00 | 01-VV-013 | VESSEL | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  | 24:00 | 14-Apr | 15-Apr | 17-Apr | 17-Apr
CDUVDU9110 | Completed | Blinding | 03/04/2023 17:34:20 | 03/04/2023 17:34:27 | 04/04/2023 16:30:00 | 05/04/2023 16:30:00 | 01-VV-013 | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 24 | 24:00 | 0:00 |  | 24:00 | 04-Apr | 05-Apr | 03-Apr | 03-Apr
CDUVDU10440 | Completed | Opening of manhole cover | 04/04/2023 10:33:51 | 04/04/2023 10:33:58 | 05/04/2023 16:30:00 | 06/04/2023 00:30:00 | 01-VV-014 | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  | 8:00 | 05-Apr | 06-Apr | 04-Apr | 04-Apr
CDUVDU10660 | Completed | Manentry | 04/04/2023 21:44:03 | 04/04/2023 21:44:03 | 06/04/2023 00:30:00 | 06/04/2023 04:30:00 | 01-VV-014 | VESSEL | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  |  | 06-Apr | 06-Apr | 04-Apr | 04-Apr
CDUVDU10670 | Completed | UT Gauging | 04/04/2023 21:44:03 | 04/04/2023 21:44:03 | 06/04/2023 00:30:00 | 06/04/2023 12:30:00 | 01-VV-014 | VESSEL | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  |  | 06-Apr | 06-Apr | 04-Apr | 04-Apr
CDUVDU10990 | Completed | Pre-cleaning inspection | 04/04/2023 21:44:03 | 04/04/2023 21:44:03 | 06/04/2023 04:30:00 | 06/04/2023 08:30:00 | 01-VV-014 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  |  | 06-Apr | 06-Apr | 04-Apr | 04-Apr
CDUVDU11200 | Completed | Removal of Internals | 11/04/2023 18:07:57 | 11/04/2023 18:08:02 | 06/04/2023 08:30:00 | 07/04/2023 08:30:00 | 01-VV-014 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 06-Apr | 07-Apr | 11-Apr | 11-Apr
CDUVDU19390 | Completed | Internal cleaning | 11/04/2023 18:08:10 | 11/04/2023 18:08:23 | 10/04/2023 18:30:00 | 12/04/2023 18:30:00 | 01-VV-014 | VESSEL | 100 | MECHANICAL | CLEANING |  | 48 | 48:00 | 0:00 |  | 48:00 | 10-Apr | 12-Apr | 11-Apr | 11-Apr
CDUVDU24100 | Completed | Post cleaning inspection | 10/04/2023 03:02:13 | 10/04/2023 03:02:13 | 12/04/2023 18:30:00 | 12/04/2023 22:30:00 | 01-VV-014 | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:00 |  |  | 12-Apr | 12-Apr | 10-Apr | 10-Apr
CDUVDU24380 | Completed | Repair if any | 12/04/2023 12:01:41 | 12/04/2023 12:01:45 | 12/04/2023 22:30:00 | 14/04/2023 22:30:00 | 01-VV-014 | VESSEL | 100 | MECHANICAL | REPAIR |  | 48 | 48:00 | 0:00 |  | 48:00 | 12-Apr | 14-Apr | 12-Apr | 12-Apr
CDUVDU26970 | Completed | Carry Out Inspection | 17/04/2023 11:14:31 | 17/04/2023 11:19:08 | 14/04/2023 22:30:00 | 15/04/2023 02:30:00 | 01-VV-014 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:05 |  | 3:55 | 14-Apr | 15-Apr | 17-Apr | 17-Apr
CDUVDU27080 | Completed | Installation of Internals | 17/04/2023 12:04:03 | 17/04/2023 12:04:16 | 15/04/2023 02:30:00 | 16/04/2023 02:30:00 | 01-VV-014 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 15-Apr | 16-Apr | 17-Apr | 17-Apr
CDUVDU27920 | Completed | Box up of manhole cover | 20/04/2023 16:19:05 | 20/04/2023 16:19:11 | 16/04/2023 02:30:00 | 16/04/2023 06:30:00 | 01-VV-014 | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  | 4:00 | 16-Apr | 16-Apr | 20-Apr | 20-Apr
CDUVDU28050 | Completed | Deblinding | 22/04/2023 11:58:39 | 22/04/2023 11:58:43 | 16/04/2023 06:30:00 | 17/04/2023 06:30:00 | 01-VV-014 | VESSEL | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  | 24:00 | 16-Apr | 17-Apr | 22-Apr | 22-Apr
CDUVDU9120 | Completed | Blinding | 03/04/2023 17:38:20 | 03/04/2023 17:38:56 | 04/04/2023 16:30:00 | 05/04/2023 16:30:00 | 01-VV-014 | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 24 | 24:00 | 0:01 |  | 23:59 | 04-Apr | 05-Apr | 03-Apr | 03-Apr
CDUVDU11960 | Completed | Internal cleaning | 06/04/2023 16:47:59 | 06/04/2023 16:48:20 | 06/04/2023 20:30:00 | 07/04/2023 20:30:00 | 01-VV-015 | VESSEL | 100 | MECHANICAL | CLEANING |  | 24 | 24:00 | 0:00 |  | 24:00 | 06-Apr | 07-Apr | 06-Apr | 06-Apr
CDUVDU13510 | Completed | Post cleaning inspection | 06/04/2023 16:48:41 | 06/04/2023 16:48:46 | 07/04/2023 20:30:00 | 08/04/2023 00:30:00 | 01-VV-015 | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:00 |  | 4:00 | 07-Apr | 08-Apr | 06-Apr | 06-Apr
CDUVDU13700 | Completed | Repair if any | 06/04/2023 16:49:01 | 06/04/2023 16:49:07 | 08/04/2023 00:30:00 | 10/04/2023 00:30:00 | 01-VV-015 | VESSEL | 100 | MECHANICAL | REPAIR |  | 48 | 48:00 | 0:00 |  | 48:00 | 08-Apr | 10-Apr | 06-Apr | 06-Apr
CDUVDU17590 | Completed | Carry Out Inspection | 06/04/2023 16:49:21 | 06/04/2023 16:49:29 | 10/04/2023 00:30:00 | 10/04/2023 04:30:00 | 01-VV-015 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 10-Apr | 10-Apr | 06-Apr | 06-Apr
CDUVDU18060 | Completed | Installation of Internals | 06/04/2023 16:49:38 | 06/04/2023 16:49:46 | 10/04/2023 04:30:00 | 11/04/2023 04:30:00 | 01-VV-015 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 10-Apr | 11-Apr | 06-Apr | 06-Apr
CDUVDU20470 | Completed | Box up of manhole cover | 06/04/2023 16:50:00 | 06/04/2023 16:50:08 | 11/04/2023 04:30:00 | 11/04/2023 08:30:00 | 01-VV-015 | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  | 4:00 | 11-Apr | 11-Apr | 06-Apr | 06-Apr
CDUVDU20770 | Completed | Hydro test | 20/04/2023 12:20:08 | 20/04/2023 12:20:13 | 11/04/2023 08:30:00 | 12/04/2023 08:30:00 | 01-VV-015 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 11-Apr | 12-Apr | 20-Apr | 20-Apr
CDUVDU23190 | Completed | Deblinding | 06/04/2023 16:50:22 | 06/04/2023 16:50:37 | 12/04/2023 08:30:00 | 13/04/2023 08:30:00 | 01-VV-015 | VESSEL | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  | 24:00 | 12-Apr | 13-Apr | 06-Apr | 06-Apr
CDUVDU3830 | Completed | Blinding | 27/03/2023 10:00:01 | 06/04/2023 16:46:28 | 01/04/2023 16:30:00 | 02/04/2023 16:30:00 | 01-VV-015 | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 24 | 24:00 | 246:46 | 222:46 |  | 01-Apr | 02-Apr | 27-Mar | 06-Apr
CDUVDU6170 | Completed | Opening of manhole cover | 06/04/2023 16:46:06 | 06/04/2023 16:46:19 | 02/04/2023 16:30:00 | 03/04/2023 00:30:00 | 01-VV-015 | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  | 8:00 | 02-Apr | 03-Apr | 06-Apr | 06-Apr
CDUVDU6660 | Completed | Manentry | 06/04/2023 16:46:39 | 06/04/2023 16:46:45 | 03/04/2023 00:30:00 | 03/04/2023 04:30:00 | 01-VV-015 | VESSEL | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 03-Apr | 03-Apr | 06-Apr | 06-Apr
CDUVDU6670 | Completed | UT Gauging | 11/04/2023 14:47:15 | 11/04/2023 14:47:20 | 03/04/2023 00:30:00 | 03/04/2023 12:30:00 | 01-VV-015 | VESSEL | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  | 12:00 | 03-Apr | 03-Apr | 11-Apr | 11-Apr
CDUVDU6820 | Completed | Pre-cleaning inspection | 06/04/2023 16:47:06 | 06/04/2023 16:47:13 | 03/04/2023 04:30:00 | 03/04/2023 08:30:00 | 01-VV-015 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 03-Apr | 03-Apr | 06-Apr | 06-Apr
CDUVDU7110 | Completed | Removal of Internals | 06/04/2023 16:47:37 | 06/04/2023 16:47:42 | 03/04/2023 08:30:00 | 04/04/2023 08:30:00 | 01-VV-015 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 03-Apr | 04-Apr | 06-Apr | 06-Apr
CDUVDU10260 | Completed | Blinding | 27/03/2023 07:18:00 | 27/03/2023 07:18:00 | 05/04/2023 14:30:00 | 06/04/2023 14:30:00 | 01-VV-018A | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 24 | 24:00 | 0:00 |  |  | 05-Apr | 06-Apr | 27-Mar | 27-Mar
CDUVDU11540 | Completed | Opening of manhole cover | 27/03/2023 07:18:00 | 27/03/2023 07:18:00 | 06/04/2023 14:30:00 | 06/04/2023 22:30:00 | 01-VV-018A | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  |  | 06-Apr | 06-Apr | 27-Mar | 27-Mar
CDUVDU12130 | Completed | Manentry | 29/03/2023 13:57:47 | 29/03/2023 13:57:51 | 06/04/2023 22:30:00 | 07/04/2023 02:30:00 | 01-VV-018A | VESSEL | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 06-Apr | 07-Apr | 29-Mar | 29-Mar
CDUVDU12140 | Completed | UT Gauging | 29/03/2023 23:05:16 | 29/03/2023 23:05:16 | 06/04/2023 22:30:00 | 07/04/2023 10:30:00 | 01-VV-018A | VESSEL | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  |  | 06-Apr | 07-Apr | 29-Mar | 29-Mar
CDUVDU12460 | Completed | Pre-cleaning inspection | 29/03/2023 13:58:05 | 29/03/2023 13:58:09 | 07/04/2023 02:30:00 | 07/04/2023 06:30:00 | 01-VV-018A | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 07-Apr | 07-Apr | 29-Mar | 29-Mar
CDUVDU12650 | Completed | Removal of Internals | 29/03/2023 23:05:16 | 29/03/2023 23:05:16 | 07/04/2023 06:30:00 | 08/04/2023 06:30:00 | 01-VV-018A | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  |  | 07-Apr | 08-Apr | 29-Mar | 29-Mar
CDUVDU14050 | Completed | Internal cleaning | 29/03/2023 23:05:16 | 29/03/2023 23:05:16 | 08/04/2023 06:30:00 | 10/04/2023 06:30:00 | 01-VV-018A | VESSEL | 100 | MECHANICAL | CLEANING |  | 48 | 48:00 | 0:00 |  |  | 08-Apr | 10-Apr | 29-Mar | 29-Mar
CDUVDU18310 | Completed | Post cleaning inspection | 29/03/2023 23:05:16 | 29/03/2023 23:05:16 | 10/04/2023 06:30:00 | 10/04/2023 10:30:00 | 01-VV-018A | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:00 |  |  | 10-Apr | 10-Apr | 29-Mar | 29-Mar
CDUVDU18570 | Completed | Repair if any | 06/04/2023 16:53:33 | 06/04/2023 16:53:43 | 10/04/2023 10:30:00 | 12/04/2023 10:30:00 | 01-VV-018A | VESSEL | 100 | MECHANICAL | REPAIR |  | 48 | 48:00 | 0:00 |  | 48:00 | 10-Apr | 12-Apr | 06-Apr | 06-Apr
CDUVDU23330 | Completed | Carry Out Inspection | 12/04/2023 12:22:59 | 12/04/2023 12:23:37 | 12/04/2023 10:30:00 | 12/04/2023 14:30:00 | 01-VV-018A | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:01 |  | 3:59 | 12-Apr | 12-Apr | 12-Apr | 12-Apr
CDUVDU23730 | Completed | Installation of Internals | 12/04/2023 12:23:56 | 12/04/2023 12:24:02 | 12/04/2023 14:30:00 | 13/04/2023 14:30:00 | 01-VV-018A | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 12-Apr | 13-Apr | 12-Apr | 12-Apr
CDUVDU25410 | Completed | Box up of manhole cover | 20/04/2023 09:22:20 | 20/04/2023 09:22:20 | 13/04/2023 14:30:00 | 13/04/2023 18:30:00 | 01-VV-018A | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  |  | 13-Apr | 13-Apr | 20-Apr | 20-Apr
CDUVDU25680 | Completed | Deblinding | 20/04/2023 09:22:28 | 20/04/2023 09:22:28 | 13/04/2023 18:30:00 | 14/04/2023 18:30:00 | 01-VV-018A | VESSEL | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  |  | 13-Apr | 14-Apr | 20-Apr | 20-Apr
CDUVDU10270 | Completed | Blinding | 11/04/2023 12:20:14 | 11/04/2023 12:20:20 | 05/04/2023 14:30:00 | 06/04/2023 14:30:00 | 01-VV-018B | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 24 | 24:00 | 0:00 |  | 24:00 | 05-Apr | 06-Apr | 11-Apr | 11-Apr
CDUVDU11550 | Completed | Opening of manhole cover | 16/04/2023 09:01:02 | 16/04/2023 09:01:09 | 06/04/2023 14:30:00 | 06/04/2023 22:30:00 | 01-VV-018B | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  | 8:00 | 06-Apr | 06-Apr | 16-Apr | 16-Apr
CDUVDU12150 | Completed | Manentry | 16/04/2023 12:23:38 | 16/04/2023 12:23:42 | 06/04/2023 22:30:00 | 07/04/2023 02:30:00 | 01-VV-018B | VESSEL | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 06-Apr | 07-Apr | 16-Apr | 16-Apr
CDUVDU12160 | Completed | UT Gauging | 16/04/2023 11:07:14 | 16/04/2023 11:07:24 | 06/04/2023 22:30:00 | 07/04/2023 10:30:00 | 01-VV-018B | VESSEL | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  | 12:00 | 06-Apr | 07-Apr | 16-Apr | 16-Apr
CDUVDU12470 | Completed | Pre-cleaning inspection | 16/04/2023 14:16:00 | 16/04/2023 14:34:03 | 07/04/2023 02:30:00 | 07/04/2023 06:30:00 | 01-VV-018B | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:18 |  | 3:42 | 07-Apr | 07-Apr | 16-Apr | 16-Apr
CDUVDU12660 | Completed | Removal of Internals | 22/04/2023 12:01:11 | 22/04/2023 12:01:16 | 07/04/2023 06:30:00 | 08/04/2023 06:30:00 | 01-VV-018B | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 07-Apr | 08-Apr | 22-Apr | 22-Apr
CDUVDU18320 | Completed | Internal cleaning | 22/04/2023 12:01:43 | 22/04/2023 12:01:43 | 10/04/2023 06:30:00 | 12/04/2023 06:30:00 | 01-VV-018B | VESSEL | 100 | MECHANICAL | CLEANING |  | 48 | 48:00 | 0:00 |  |  | 10-Apr | 12-Apr | 22-Apr | 22-Apr
CDUVDU23060 | Completed | Post cleaning inspection | 22/04/2023 12:01:43 | 22/04/2023 12:01:43 | 12/04/2023 06:30:00 | 12/04/2023 10:30:00 | 01-VV-018B | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:00 |  |  | 12-Apr | 12-Apr | 22-Apr | 22-Apr
CDUVDU23340 | Completed | Repair if any | 22/04/2023 12:01:43 | 22/04/2023 12:01:43 | 12/04/2023 10:30:00 | 14/04/2023 10:30:00 | 01-VV-018B | VESSEL | 100 | MECHANICAL | REPAIR |  | 48 | 48:00 | 0:00 |  |  | 12-Apr | 14-Apr | 22-Apr | 22-Apr
CDUVDU26440 | Completed | Carry Out Inspection | 22/04/2023 12:01:43 | 22/04/2023 12:01:43 | 14/04/2023 10:30:00 | 14/04/2023 14:30:00 | 01-VV-018B | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  |  | 14-Apr | 14-Apr | 22-Apr | 22-Apr
CDUVDU26600 | Completed | Installation of Internals | 22/04/2023 12:01:43 | 22/04/2023 12:01:43 | 14/04/2023 14:30:00 | 15/04/2023 14:30:00 | 01-VV-018B | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  |  | 14-Apr | 15-Apr | 22-Apr | 22-Apr
CDUVDU27550 | Completed | Box up of manhole cover | 23/04/2023 11:06:12 | 23/04/2023 11:06:12 | 15/04/2023 14:30:00 | 15/04/2023 18:30:00 | 01-VV-018B | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  |  | 15-Apr | 15-Apr | 23-Apr | 23-Apr
CDUVDU27660 | Completed | Deblinding | 23/04/2023 11:06:12 | 23/04/2023 11:06:12 | 15/04/2023 18:30:00 | 16/04/2023 18:30:00 | 01-VV-018B | VESSEL | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  |  | 15-Apr | 16-Apr | 23-Apr | 23-Apr
CDUVDU20020 | Completed | Internal cleaning | 16/04/2023 14:35:09 | 16/04/2023 14:35:14 | 11/04/2023 00:00:00 | 13/04/2023 00:00:00 | 01-VV-019 | VESSEL | 100 | MECHANICAL | CLEANING |  | 48 | 48:00 | 0:00 |  | 48:00 | 11-Apr | 13-Apr | 16-Apr | 16-Apr
CDUVDU24540 | Completed | Post cleaning inspection | 14/04/2023 12:21:43 | 14/04/2023 12:21:45 | 13/04/2023 00:00:00 | 13/04/2023 04:00:00 | 01-VV-019 | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:00 |  | 4:00 | 13-Apr | 13-Apr | 14-Apr | 14-Apr
CDUVDU24820 | Completed | Repair if any | 16/04/2023 14:35:21 | 16/04/2023 14:35:26 | 13/04/2023 04:00:00 | 15/04/2023 04:00:00 | 01-VV-019 | VESSEL | 100 | MECHANICAL | REPAIR |  | 48 | 48:00 | 0:00 |  | 48:00 | 13-Apr | 15-Apr | 16-Apr | 16-Apr
CDUVDU27160 | Completed | Carry Out Inspection | 16/04/2023 14:35:40 | 16/04/2023 14:35:44 | 15/04/2023 04:00:00 | 15/04/2023 08:00:00 | 01-VV-019 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 15-Apr | 15-Apr | 16-Apr | 16-Apr
CDUVDU27320 | Completed | Installation of Internals | 16/04/2023 14:35:54 | 16/04/2023 14:36:03 | 15/04/2023 08:00:00 | 16/04/2023 08:00:00 | 01-VV-019 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 15-Apr | 16-Apr | 16-Apr | 16-Apr
CDUVDU28120 | Completed | Box up of manhole cover | 16/04/2023 14:36:14 | 16/04/2023 14:36:22 | 16/04/2023 08:00:00 | 16/04/2023 12:00:00 | 01-VV-019 | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  | 4:00 | 16-Apr | 16-Apr | 16-Apr | 16-Apr
CDUVDU28280 | Completed | Deblinding | 20/04/2023 12:22:14 | 20/04/2023 12:22:18 | 16/04/2023 12:00:00 | 17/04/2023 12:00:00 | 01-VV-019 | VESSEL | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  | 24:00 | 16-Apr | 17-Apr | 20-Apr | 20-Apr
CDUVDU6100 | Completed | Blinding | 03/04/2023 17:41:47 | 04/04/2023 21:44:35 | 02/04/2023 16:30:00 | 03/04/2023 16:30:00 | 01-VV-019 | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 24 | 24:00 | 28:03 | 4:03 |  | 02-Apr | 03-Apr | 03-Apr | 04-Apr
CDUVDU7870 | Completed | Opening of manhole cover | 04/04/2023 10:36:00 | 04/04/2023 14:23:42 | 03/04/2023 16:30:00 | 04/04/2023 00:30:00 | 01-VV-019 | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 3:48 |  | 4:12 | 03-Apr | 04-Apr | 04-Apr | 04-Apr
CDUVDU8190 | Completed | Manentry | 04/04/2023 21:44:35 | 04/04/2023 21:44:35 | 04/04/2023 00:30:00 | 04/04/2023 04:30:00 | 01-VV-019 | VESSEL | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  |  | 04-Apr | 04-Apr | 04-Apr | 04-Apr
CDUVDU8200 | Completed | UT Gauging | 04/04/2023 21:44:35 | 04/04/2023 21:44:35 | 04/04/2023 00:30:00 | 04/04/2023 12:30:00 | 01-VV-019 | VESSEL | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  |  | 04-Apr | 04-Apr | 04-Apr | 04-Apr
CDUVDU8400 | Completed | Pre-cleaning inspection | 04/04/2023 21:44:35 | 04/04/2023 21:44:35 | 04/04/2023 04:30:00 | 04/04/2023 08:30:00 | 01-VV-019 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  |  | 04-Apr | 04-Apr | 04-Apr | 04-Apr
CDUVDU8520 | Completed | Removal of Internals | 16/04/2023 14:33:54 | 16/04/2023 14:34:46 | 04/04/2023 08:30:00 | 05/04/2023 08:30:00 | 01-VV-019 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:01 |  | 23:59 | 04-Apr | 05-Apr | 16-Apr | 16-Apr
CDUVDU24550 | Completed | Internal cleaning | 10/04/2023 17:52:46 | 10/04/2023 17:52:58 | 13/04/2023 00:00:00 | 14/04/2023 00:00:00 | 01-VV-020 | VESSEL | 100 | MECHANICAL | CLEANING |  | 24 | 24:00 | 0:00 |  | 24:00 | 13-Apr | 14-Apr | 10-Apr | 10-Apr
CDUVDU25940 | Completed | Post cleaning inspection | 07/04/2023 22:33:50 | 07/04/2023 22:33:50 | 14/04/2023 00:00:00 | 14/04/2023 04:00:00 | 01-VV-020 | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:00 |  |  | 14-Apr | 14-Apr | 07-Apr | 07-Apr
CDUVDU26180 | Completed | Repair if any | 10/04/2023 17:53:13 | 10/04/2023 17:53:21 | 14/04/2023 04:00:00 | 16/04/2023 04:00:00 | 01-VV-020 | VESSEL | 100 | MECHANICAL | REPAIR |  | 48 | 48:00 | 0:00 |  | 48:00 | 14-Apr | 16-Apr | 10-Apr | 10-Apr
CDUVDU27980 | Completed | Carry Out Inspection | 10/04/2023 17:53:44 | 10/04/2023 17:53:48 | 16/04/2023 04:00:00 | 16/04/2023 08:00:00 | 01-VV-020 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 16-Apr | 16-Apr | 10-Apr | 10-Apr
CDUVDU28130 | Completed | Installation of Internals | 10/04/2023 17:53:57 | 10/04/2023 17:54:01 | 16/04/2023 08:00:00 | 17/04/2023 08:00:00 | 01-VV-020 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 16-Apr | 17-Apr | 10-Apr | 10-Apr
CDUVDU28820 | Completed | Box up of manhole cover | 10/04/2023 17:54:09 | 10/04/2023 17:54:14 | 17/04/2023 08:00:00 | 17/04/2023 12:00:00 | 01-VV-020 | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  | 4:00 | 17-Apr | 17-Apr | 10-Apr | 10-Apr
CDUVDU28920 | Completed | Deblinding | 20/04/2023 12:22:57 | 20/04/2023 12:23:02 | 17/04/2023 12:00:00 | 18/04/2023 12:00:00 | 01-VV-020 | VESSEL | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  | 24:00 | 17-Apr | 18-Apr | 20-Apr | 20-Apr
CDUVDU6110 | Completed | Blinding | 04/04/2023 10:42:05 | 04/04/2023 10:42:12 | 02/04/2023 16:30:00 | 03/04/2023 16:30:00 | 01-VV-020 | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 24 | 24:00 | 0:00 |  | 24:00 | 02-Apr | 03-Apr | 04-Apr | 04-Apr
CDUVDU7880 | Completed | Opening of manhole cover | 04/04/2023 10:42:50 | 04/04/2023 14:24:10 | 03/04/2023 16:30:00 | 04/04/2023 00:30:00 | 01-VV-020 | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 3:41 |  | 4:19 | 03-Apr | 04-Apr | 04-Apr | 04-Apr
CDUVDU8210 | Completed | Manentry | 04/04/2023 21:27:54 | 04/04/2023 21:27:54 | 04/04/2023 00:30:00 | 04/04/2023 04:30:00 | 01-VV-020 | VESSEL | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  |  | 04-Apr | 04-Apr | 04-Apr | 04-Apr
CDUVDU8220 | Completed | UT Gauging | 04/04/2023 21:27:54 | 04/04/2023 21:27:54 | 04/04/2023 00:30:00 | 04/04/2023 12:30:00 | 01-VV-020 | VESSEL | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  |  | 04-Apr | 04-Apr | 04-Apr | 04-Apr
CDUVDU8410 | Completed | Pre-cleaning inspection | 04/04/2023 21:27:54 | 04/04/2023 21:27:54 | 04/04/2023 04:30:00 | 04/04/2023 08:30:00 | 01-VV-020 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  |  | 04-Apr | 04-Apr | 04-Apr | 04-Apr
CDUVDU8530 | Completed | Removal of Internals | 10/04/2023 17:52:28 | 10/04/2023 17:52:34 | 04/04/2023 08:30:00 | 05/04/2023 08:30:00 | 01-VV-020 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 04-Apr | 05-Apr | 10-Apr | 10-Apr
CDUVDU24110 | Completed | Internal cleaning | 11/04/2023 18:09:59 | 11/04/2023 18:10:03 | 12/04/2023 18:30:00 | 13/04/2023 18:30:00 | 01-VV-021 | VESSEL | 100 | MECHANICAL | CLEANING |  | 24 | 24:00 | 0:00 |  | 24:00 | 12-Apr | 13-Apr | 11-Apr | 11-Apr
CDUVDU25690 | Completed | Post cleaning inspection | 12/04/2023 12:02:55 | 12/04/2023 12:05:11 | 13/04/2023 18:30:00 | 13/04/2023 22:30:00 | 01-VV-021 | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:02 |  | 3:58 | 13-Apr | 13-Apr | 12-Apr | 12-Apr
CDUVDU25840 | Completed | Repair if any | 12/04/2023 12:05:29 | 12/04/2023 12:05:53 | 13/04/2023 22:30:00 | 15/04/2023 22:30:00 | 01-VV-021 | VESSEL | 100 | MECHANICAL | REPAIR |  | 48 | 48:00 | 0:00 |  | 48:00 | 13-Apr | 15-Apr | 12-Apr | 12-Apr
CDUVDU27800 | Completed | Carry Out Inspection | 12/04/2023 12:06:19 | 12/04/2023 12:06:38 | 15/04/2023 22:30:00 | 16/04/2023 02:30:00 | 01-VV-021 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 15-Apr | 16-Apr | 12-Apr | 12-Apr
CDUVDU27930 | Completed | Installation of Internals | 13/04/2023 19:38:01 | 13/04/2023 19:38:09 | 16/04/2023 02:30:00 | 17/04/2023 02:30:00 | 01-VV-021 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 16-Apr | 17-Apr | 13-Apr | 13-Apr
CDUVDU28670 | Completed | Box up of manhole cover | 13/04/2023 19:38:23 | 13/04/2023 19:38:29 | 17/04/2023 02:30:00 | 17/04/2023 06:30:00 | 01-VV-021 | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  | 4:00 | 17-Apr | 17-Apr | 13-Apr | 13-Apr
CDUVDU28780 | Completed | Deblinding | 13/04/2023 19:38:38 | 20/04/2023 12:23:34 | 17/04/2023 06:30:00 | 18/04/2023 06:30:00 | 01-VV-021 | VESSEL | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 160:45 | 136:45 |  | 17-Apr | 18-Apr | 13-Apr | 20-Apr
CDUVDU6120 | Completed | Blinding | 03/04/2023 17:53:28 | 05/04/2023 17:37:17 | 02/04/2023 16:30:00 | 03/04/2023 16:30:00 | 01-VV-021 | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 24 | 24:00 | 47:44 | 23:44 |  | 02-Apr | 03-Apr | 03-Apr | 05-Apr
CDUVDU7890 | Completed | Opening of manhole cover | 05/04/2023 17:38:03 | 05/04/2023 17:38:08 | 03/04/2023 16:30:00 | 04/04/2023 00:30:00 | 01-VV-021 | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  | 8:00 | 03-Apr | 04-Apr | 05-Apr | 05-Apr
CDUVDU8230 | Completed | Manentry | 08/04/2023 17:10:35 | 08/04/2023 17:10:41 | 04/04/2023 00:30:00 | 04/04/2023 04:30:00 | 01-VV-021 | VESSEL | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 04-Apr | 04-Apr | 08-Apr | 08-Apr
CDUVDU8240 | Completed | UT Gauging | 08/04/2023 17:11:54 | 08/04/2023 17:11:59 | 04/04/2023 00:30:00 | 04/04/2023 12:30:00 | 01-VV-021 | VESSEL | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  | 12:00 | 04-Apr | 04-Apr | 08-Apr | 08-Apr
CDUVDU8420 | Completed | Pre-cleaning inspection | 11/04/2023 18:08:53 | 11/04/2023 18:08:58 | 04/04/2023 04:30:00 | 04/04/2023 08:30:00 | 01-VV-021 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 04-Apr | 04-Apr | 11-Apr | 11-Apr
CDUVDU8540 | Completed | Removal of Internals | 11/04/2023 18:09:07 | 11/04/2023 18:09:15 | 04/04/2023 08:30:00 | 05/04/2023 08:30:00 | 01-VV-021 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 04-Apr | 05-Apr | 11-Apr | 11-Apr
CDUVDU1440 | Completed | Blinding | 31/03/2023 10:57:51 | 31/03/2023 15:52:18 | 30/03/2023 08:00:00 | 31/03/2023 08:00:00 | 01-VV-002 | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 24 | 24:00 | 4:54 |  | 19:06 | 30-Mar | 31-Mar | 31-Mar | 31-Mar
CDUVDU14900 | Completed | Carry Out Inspection | 19/04/2023 09:46:26 | 19/04/2023 09:46:30 | 08/04/2023 16:00:00 | 08/04/2023 20:00:00 | 01-VV-002 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 08-Apr | 08-Apr | 19-Apr | 19-Apr
CDUVDU15100 | Completed | Installation of Internals | 19/04/2023 09:47:08 | 19/04/2023 09:47:14 | 08/04/2023 20:00:00 | 09/04/2023 20:00:00 | 01-VV-002 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 08-Apr | 09-Apr | 19-Apr | 19-Apr
CDUVDU17190 | Completed | Box up of manhole cover | 20/04/2023 19:37:47 | 20/04/2023 19:37:52 | 09/04/2023 20:00:00 | 10/04/2023 00:00:00 | 01-VV-002 | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  | 4:00 | 09-Apr | 10-Apr | 20-Apr | 20-Apr
CDUVDU17580 | Completed | Hydrotest | 20/04/2023 09:21:07 | 20/04/2023 09:21:07 | 10/04/2023 00:00:00 | 11/04/2023 00:00:00 | 01-VV-002 | VESSEL | 100 | INSPECTION | FINAL TEST |  | 24 | 24:00 | 0:00 |  |  | 10-Apr | 11-Apr | 20-Apr | 20-Apr
CDUVDU1830 | Completed | Opening of manhole cover | 31/03/2023 19:17:54 | 31/03/2023 19:18:09 | 31/03/2023 08:00:00 | 31/03/2023 16:00:00 | 01-VV-002 | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  | 8:00 | 31-Mar | 31-Mar | 31-Mar | 31-Mar
CDUVDU20000 | Completed | Deblinding | 22/04/2023 11:59:32 | 22/04/2023 11:59:37 | 11/04/2023 00:00:00 | 12/04/2023 00:00:00 | 01-VV-002 | VESSEL | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  | 24:00 | 11-Apr | 12-Apr | 22-Apr | 22-Apr
CDUVDU2280 | Completed | Manentry | 01/04/2023 12:10:10 | 01/04/2023 12:10:16 | 31/03/2023 16:00:00 | 31/03/2023 20:00:00 | 01-VV-002 | VESSEL | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 31-Mar | 31-Mar | 01-Apr | 01-Apr
CDUVDU2290 | Completed | UT Gauging | 02/04/2023 05:52:54 | 02/04/2023 05:52:54 | 31/03/2023 16:00:00 | 01/04/2023 04:00:00 | 01-VV-002 | VESSEL | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  |  | 31-Mar | 01-Apr | 02-Apr | 02-Apr
CDUVDU2380 | Completed | Pre-cleaning inspection | 01/04/2023 12:29:28 | 01/04/2023 12:29:33 | 31/03/2023 20:00:00 | 01/04/2023 00:00:00 | 01-VV-002 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 31-Mar | 01-Apr | 01-Apr | 01-Apr
CDUVDU2570 | Completed | Removal of Internals | 12/04/2023 11:58:40 | 12/04/2023 11:58:48 | 01/04/2023 00:00:00 | 02/04/2023 00:00:00 | 01-VV-002 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 01-Apr | 02-Apr | 12-Apr | 12-Apr
CDUVDU4340 | Completed | Internal cleaning | 12/04/2023 11:59:09 | 17/04/2023 17:45:59 | 02/04/2023 00:00:00 | 04/04/2023 12:00:00 | 01-VV-002 | VESSEL | 100 | MECHANICAL | CLEANING |  | 60 | 60:00 | 125:47 | 65:47 |  | 02-Apr | 04-Apr | 12-Apr | 17-Apr
CDUVDU8670 | Completed | Post cleaning inspection | 17/04/2023 17:46:30 | 17/04/2023 17:46:40 | 04/04/2023 12:00:00 | 04/04/2023 16:00:00 | 01-VV-002 | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:00 |  | 4:00 | 04-Apr | 04-Apr | 17-Apr | 17-Apr
CDUVDU9100 | Completed | Repair if any | 19/04/2023 09:46:04 | 19/04/2023 09:46:08 | 04/04/2023 16:00:00 | 08/04/2023 16:00:00 | 01-VV-002 | VESSEL | 100 | MECHANICAL | REPAIR |  | 96 | 96:00 | 0:00 |  | 96:00 | 04-Apr | 08-Apr | 19-Apr | 19-Apr
CDUVDU25700 | Completed | Internal cleaning | 10/04/2023 19:37:15 | 10/04/2023 19:37:23 | 13/04/2023 18:30:00 | 14/04/2023 18:30:00 | 01-VV-022 | VESSEL | 100 | MECHANICAL | CLEANING |  | 24 | 24:00 | 0:00 |  | 24:00 | 13-Apr | 14-Apr | 10-Apr | 10-Apr
CDUVDU26830 | Completed | Post cleaning inspection | 10/04/2023 19:37:38 | 10/04/2023 19:37:44 | 14/04/2023 18:30:00 | 14/04/2023 22:30:00 | 01-VV-022 | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:00 |  | 4:00 | 14-Apr | 14-Apr | 10-Apr | 10-Apr
CDUVDU26980 | Completed | Repair if any | 10/04/2023 19:37:51 | 10/04/2023 19:37:56 | 14/04/2023 22:30:00 | 16/04/2023 22:30:00 | 01-VV-022 | VESSEL | 100 | MECHANICAL | REPAIR |  | 48 | 48:00 | 0:00 |  | 48:00 | 14-Apr | 16-Apr | 10-Apr | 10-Apr
CDUVDU28580 | Completed | Carry Out Inspection | 10/04/2023 19:38:13 | 10/04/2023 19:38:18 | 16/04/2023 22:30:00 | 17/04/2023 02:30:00 | 01-VV-022 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 16-Apr | 17-Apr | 10-Apr | 10-Apr
CDUVDU28680 | Completed | Installation of Internals | 10/04/2023 19:38:27 | 10/04/2023 19:38:32 | 17/04/2023 02:30:00 | 18/04/2023 02:30:00 | 01-VV-022 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 17-Apr | 18-Apr | 10-Apr | 10-Apr
CDUVDU29220 | Completed | Box up of manhole cover | 10/04/2023 19:38:40 | 10/04/2023 19:38:45 | 18/04/2023 02:30:00 | 18/04/2023 06:30:00 | 01-VV-022 | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  | 4:00 | 18-Apr | 18-Apr | 10-Apr | 10-Apr
CDUVDU29320 | Completed | Deblinding | 20/04/2023 12:23:12 | 20/04/2023 12:23:17 | 18/04/2023 06:30:00 | 19/04/2023 06:30:00 | 01-VV-022 | VESSEL | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  | 24:00 | 18-Apr | 19-Apr | 20-Apr | 20-Apr
CDUVDU6130 | Completed | Blinding | 02/04/2023 10:19:12 | 02/04/2023 10:28:38 | 02/04/2023 16:30:00 | 03/04/2023 16:30:00 | 01-VV-022 | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 24 | 24:00 | 0:09 |  | 23:51 | 02-Apr | 03-Apr | 02-Apr | 02-Apr
CDUVDU7900 | Completed | Opening of manhole cover | 03/04/2023 17:28:34 | 03/04/2023 17:28:41 | 03/04/2023 16:30:00 | 04/04/2023 00:30:00 | 01-VV-022 | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  | 8:00 | 03-Apr | 04-Apr | 03-Apr | 03-Apr
CDUVDU8250 | Completed | Manentry | 04/04/2023 21:28:32 | 04/04/2023 21:28:32 | 04/04/2023 00:30:00 | 04/04/2023 04:30:00 | 01-VV-022 | VESSEL | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  |  | 04-Apr | 04-Apr | 04-Apr | 04-Apr
CDUVDU8260 | Completed | UT Gauging | 04/04/2023 21:28:32 | 04/04/2023 21:28:32 | 04/04/2023 00:30:00 | 04/04/2023 12:30:00 | 01-VV-022 | VESSEL | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  |  | 04-Apr | 04-Apr | 04-Apr | 04-Apr
CDUVDU8430 | Completed | Pre-cleaning inspection | 04/04/2023 21:28:32 | 04/04/2023 21:28:32 | 04/04/2023 04:30:00 | 04/04/2023 08:30:00 | 01-VV-022 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  |  | 04-Apr | 04-Apr | 04-Apr | 04-Apr
CDUVDU8550 | Completed | Removal of Internals | 10/04/2023 19:37:01 | 10/04/2023 19:37:07 | 04/04/2023 08:30:00 | 05/04/2023 08:30:00 | 01-VV-022 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 04-Apr | 05-Apr | 10-Apr | 10-Apr
CDUVDU10450 | Completed | Pre-cleaning inspection | 07/04/2023 21:48:37 | 07/04/2023 21:48:37 | 05/04/2023 16:30:00 | 05/04/2023 20:30:00 | 01-VV-023 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  |  | 05-Apr | 05-Apr | 07-Apr | 07-Apr
CDUVDU10580 | Completed | Removal of Internals | 13/04/2023 19:39:09 | 13/04/2023 19:39:16 | 05/04/2023 20:30:00 | 06/04/2023 20:30:00 | 01-VV-023 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 05-Apr | 06-Apr | 13-Apr | 13-Apr
CDUVDU25950 | Completed | Internal cleaning | 13/04/2023 19:39:31 | 16/04/2023 18:54:29 | 14/04/2023 00:00:00 | 16/04/2023 12:00:00 | 01-VV-023 | VESSEL | 100 | MECHANICAL | CLEANING |  | 60 | 60:00 | 71:15 | 11:15 |  | 14-Apr | 16-Apr | 13-Apr | 16-Apr
CDUVDU28300 | Completed | Post cleaning inspection | 16/04/2023 18:54:45 | 16/04/2023 18:54:49 | 16/04/2023 12:00:00 | 16/04/2023 16:00:00 | 01-VV-023 | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:00 |  | 4:00 | 16-Apr | 16-Apr | 16-Apr | 16-Apr
CDUVDU28410 | Completed | Repair if any | 18/04/2023 11:17:44 | 18/04/2023 11:17:49 | 16/04/2023 16:00:00 | 18/04/2023 16:00:00 | 01-VV-023 | VESSEL | 100 | MECHANICAL | REPAIR |  | 48 | 48:00 | 0:00 |  | 48:00 | 16-Apr | 18-Apr | 18-Apr | 18-Apr
CDUVDU29450 | Completed | Carry Out Inspection | 18/04/2023 11:18:12 | 18/04/2023 11:18:20 | 18/04/2023 16:00:00 | 18/04/2023 20:00:00 | 01-VV-023 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 18-Apr | 18-Apr | 18-Apr | 18-Apr
CDUVDU29580 | Completed | Installation of Internals | 18/04/2023 11:18:55 | 18/04/2023 11:19:00 | 18/04/2023 20:00:00 | 19/04/2023 20:00:00 | 01-VV-023 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 18-Apr | 19-Apr | 18-Apr | 18-Apr
CDUVDU29910 | Completed | Box up of manhole cover | 18/04/2023 19:27:39 | 19/04/2023 17:47:51 | 19/04/2023 20:00:00 | 20/04/2023 00:00:00 | 01-VV-023 | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 22:20 | 18:20 |  | 19-Apr | 20-Apr | 18-Apr | 19-Apr
CDUVDU29970 | Completed | Deblinding | 19/04/2023 17:48:03 | 19/04/2023 17:48:08 | 20/04/2023 00:00:00 | 21/04/2023 00:00:00 | 01-VV-023 | VESSEL | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  | 24:00 | 20-Apr | 21-Apr | 19-Apr | 19-Apr
CDUVDU7930 | Completed | Blinding | 04/04/2023 19:37:14 | 05/04/2023 17:38:57 | 03/04/2023 16:30:00 | 04/04/2023 16:30:00 | 01-VV-023 | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 24 | 24:00 | 22:02 |  | 1:58 | 03-Apr | 04-Apr | 04-Apr | 05-Apr
CDUVDU9190 | Completed | Opening of manhole cover | 05/04/2023 17:39:06 | 05/04/2023 17:39:12 | 04/04/2023 16:30:00 | 05/04/2023 00:30:00 | 01-VV-023 | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  | 8:00 | 04-Apr | 05-Apr | 05-Apr | 05-Apr
CDUVDU9430 | Completed | Manentry | 07/04/2023 21:48:37 | 07/04/2023 21:48:37 | 05/04/2023 00:30:00 | 05/04/2023 04:30:00 | 01-VV-023 | VESSEL | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  |  | 05-Apr | 05-Apr | 07-Apr | 07-Apr
CDUVDU9690 | Completed | UT Gauging | 07/04/2023 21:48:37 | 07/04/2023 21:48:37 | 05/04/2023 04:30:00 | 05/04/2023 16:30:00 | 01-VV-023 | VESSEL | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  |  | 05-Apr | 05-Apr | 07-Apr | 07-Apr
CDUVDU23070 | Completed | Internal cleaning | 06/04/2023 16:52:00 | 06/04/2023 16:52:07 | 12/04/2023 06:30:00 | 13/04/2023 06:30:00 | 01-VV-024 | VESSEL | 100 | MECHANICAL | CLEANING |  | 24 | 24:00 | 0:00 |  | 24:00 | 12-Apr | 13-Apr | 06-Apr | 06-Apr
CDUVDU24980 | Completed | Post cleaning inspection | 06/04/2023 16:52:40 | 06/04/2023 16:53:04 | 13/04/2023 06:30:00 | 13/04/2023 10:30:00 | 01-VV-024 | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:00 |  | 4:00 | 13-Apr | 13-Apr | 06-Apr | 06-Apr
CDUVDU25230 | Completed | Repair if any | 18/04/2023 17:48:26 | 19/04/2023 09:33:43 | 13/04/2023 10:30:00 | 15/04/2023 10:30:00 | 01-VV-024 | VESSEL | 100 | MECHANICAL | REPAIR |  | 48 | 48:00 | 15:45 |  | 32:15 | 13-Apr | 15-Apr | 18-Apr | 19-Apr
CDUVDU27390 | Completed | Carry Out Inspection | 20/04/2023 14:25:04 | 20/04/2023 14:25:04 | 15/04/2023 10:30:00 | 15/04/2023 14:30:00 | 01-VV-024 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  |  | 15-Apr | 15-Apr | 20-Apr | 20-Apr
CDUVDU27560 | Completed | Installation of Internals | 20/04/2023 14:25:04 | 20/04/2023 14:25:04 | 15/04/2023 14:30:00 | 16/04/2023 14:30:00 | 01-VV-024 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  |  | 15-Apr | 16-Apr | 20-Apr | 20-Apr
CDUVDU28350 | Completed | Box up of manhole cover | 20/04/2023 14:25:04 | 22/04/2023 12:02:17 | 16/04/2023 14:30:00 | 16/04/2023 18:30:00 | 01-VV-024 | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 45:37 | 41:37 |  | 16-Apr | 16-Apr | 20-Apr | 22-Apr
CDUVDU28440 | Completed | Deblinding | 22/04/2023 12:02:33 | 22/04/2023 12:02:37 | 16/04/2023 18:30:00 | 17/04/2023 18:30:00 | 01-VV-024 | VESSEL | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  | 24:00 | 16-Apr | 17-Apr | 22-Apr | 22-Apr
CDUVDU7820 | Completed | Blinding | 27/03/2023 10:01:28 | 04/04/2023 21:29:01 | 03/04/2023 16:30:00 | 04/04/2023 16:30:00 | 01-VV-024 | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 24 | 24:00 | 203:28 | 179:28 |  | 03-Apr | 04-Apr | 27-Mar | 04-Apr
CDUVDU9140 | Completed | Opening of manhole cover | 04/04/2023 21:29:01 | 04/04/2023 21:29:01 | 04/04/2023 16:30:00 | 05/04/2023 00:30:00 | 01-VV-024 | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  |  | 04-Apr | 05-Apr | 04-Apr | 04-Apr
CDUVDU9370 | Completed | Manentry | 04/04/2023 21:29:01 | 04/04/2023 21:29:01 | 05/04/2023 00:30:00 | 05/04/2023 04:30:00 | 01-VV-024 | VESSEL | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  |  | 05-Apr | 05-Apr | 04-Apr | 04-Apr
CDUVDU9380 | Completed | UT Gauging | 04/04/2023 21:29:01 | 04/04/2023 21:29:01 | 05/04/2023 00:30:00 | 05/04/2023 12:30:00 | 01-VV-024 | VESSEL | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  |  | 05-Apr | 05-Apr | 04-Apr | 04-Apr
CDUVDU9650 | Completed | Pre-cleaning inspection | 04/04/2023 21:29:01 | 04/04/2023 21:29:01 | 05/04/2023 04:30:00 | 05/04/2023 08:30:00 | 01-VV-024 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  |  | 05-Apr | 05-Apr | 04-Apr | 04-Apr
CDUVDU9870 | Completed | Removal of Internals | 06/04/2023 16:51:45 | 06/04/2023 16:51:51 | 05/04/2023 08:30:00 | 06/04/2023 08:30:00 | 01-VV-024 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 05-Apr | 06-Apr | 06-Apr | 06-Apr
CDUVDU24990 | Completed | Internal cleaning | 16/04/2023 11:28:57 | 16/04/2023 11:29:05 | 13/04/2023 06:30:00 | 15/04/2023 18:30:00 | 01-VV-025 | VESSEL | 100 | MECHANICAL | CLEANING |  | 60 | 60:00 | 0:00 |  | 60:00 | 13-Apr | 15-Apr | 16-Apr | 16-Apr
CDUVDU27670 | Completed | Post cleaning inspection | 19/04/2023 10:37:11 | 19/04/2023 19:41:04 | 15/04/2023 18:30:00 | 15/04/2023 22:30:00 | 01-VV-025 | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 9:04 | 5:04 |  | 15-Apr | 15-Apr | 19-Apr | 19-Apr
CDUVDU27810 | Completed | Repair if any | 20/04/2023 09:24:17 | 20/04/2023 09:24:17 | 15/04/2023 22:30:00 | 17/04/2023 22:30:00 | 01-VV-025 | VESSEL | 100 | MECHANICAL | REPAIR |  | 48 | 48:00 | 0:00 |  |  | 15-Apr | 17-Apr | 20-Apr | 20-Apr
CDUVDU29140 | Completed | Carry Out Inspection | 20/04/2023 09:24:17 | 20/04/2023 09:24:17 | 17/04/2023 22:30:00 | 18/04/2023 02:30:00 | 01-VV-025 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  |  | 17-Apr | 18-Apr | 20-Apr | 20-Apr
CDUVDU29230 | Completed | Installation of Internals | 20/04/2023 09:24:17 | 20/04/2023 09:24:17 | 18/04/2023 02:30:00 | 19/04/2023 02:30:00 | 01-VV-025 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  |  | 18-Apr | 19-Apr | 20-Apr | 20-Apr
CDUVDU29650 | Completed | Box up of manhole cover | 20/04/2023 12:24:33 | 20/04/2023 16:18:42 | 19/04/2023 02:30:00 | 19/04/2023 06:30:00 | 01-VV-025 | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 3:54 |  | 0:06 | 19-Apr | 19-Apr | 20-Apr | 20-Apr
CDUVDU29710 | In Progress | Deblinding | 22/04/2023 11:36:15 |  | 19/04/2023 06:30:00 | 20/04/2023 06:30:00 | 01-VV-025 | VESSEL | 95 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  |  | 19-Apr | 20-Apr | 22-Apr | - Date check
CDUVDU7830 | Completed | Blinding | 31/03/2023 12:59:13 | 10/04/2023 14:51:35 | 03/04/2023 16:30:00 | 04/04/2023 16:30:00 | 01-VV-025 | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 24 | 24:00 | 241:52 | 217:52 |  | 03-Apr | 04-Apr | 31-Mar | 10-Apr
CDUVDU9150 | Completed | Opening of manhole cover | 13/04/2023 19:39:47 | 13/04/2023 19:39:53 | 04/04/2023 16:30:00 | 05/04/2023 00:30:00 | 01-VV-025 | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  | 8:00 | 04-Apr | 05-Apr | 13-Apr | 13-Apr
CDUVDU9390 | Completed | Manentry | 15/04/2023 10:31:10 | 15/04/2023 10:31:16 | 05/04/2023 00:30:00 | 05/04/2023 04:30:00 | 01-VV-025 | VESSEL | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 05-Apr | 05-Apr | 15-Apr | 15-Apr
CDUVDU9400 | Completed | UT Gauging | 19/04/2023 08:47:42 | 20/04/2023 09:23:53 | 05/04/2023 00:30:00 | 05/04/2023 12:30:00 | 01-VV-025 | VESSEL | 100 | INSPECTION |  |  | 12 | 12:00 | 24:36 | 12:36 |  | 05-Apr | 05-Apr | 19-Apr | 20-Apr
CDUVDU9660 | Completed | Pre-cleaning inspection | 16/04/2023 09:01:28 | 16/04/2023 09:01:33 | 05/04/2023 04:30:00 | 05/04/2023 08:30:00 | 01-VV-025 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 05-Apr | 05-Apr | 16-Apr | 16-Apr
CDUVDU9880 | Completed | Removal of Internals | 16/04/2023 11:28:44 | 16/04/2023 11:28:49 | 05/04/2023 08:30:00 | 06/04/2023 08:30:00 | 01-VV-025 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 05-Apr | 06-Apr | 16-Apr | 16-Apr
CDUVDU28290 | Completed | Internal cleaning | 13/04/2023 19:34:10 | 13/04/2023 19:34:26 | 16/04/2023 12:00:00 | 17/04/2023 12:00:00 | 01-VV-026 | VESSEL | 100 | MECHANICAL | CLEANING |  | 24 | 24:00 | 0:00 |  | 24:00 | 16-Apr | 17-Apr | 13-Apr | 13-Apr
CDUVDU28930 | Completed | Post cleaning inspection | 13/04/2023 19:34:43 | 13/04/2023 19:34:47 | 17/04/2023 12:00:00 | 17/04/2023 16:00:00 | 01-VV-026 | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:00 |  | 4:00 | 17-Apr | 17-Apr | 13-Apr | 13-Apr
CDUVDU29000 | Completed | Repair if any | 13/04/2023 19:34:54 | 13/04/2023 19:35:01 | 17/04/2023 16:00:00 | 19/04/2023 16:00:00 | 01-VV-026 | VESSEL | 100 | MECHANICAL | REPAIR |  | 48 | 48:00 | 0:00 |  | 48:00 | 17-Apr | 19-Apr | 13-Apr | 13-Apr
CDUVDU29850 | Completed | Carry Out Inspection | 13/04/2023 19:35:17 | 13/04/2023 19:35:22 | 19/04/2023 16:00:00 | 19/04/2023 20:00:00 | 01-VV-026 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 19-Apr | 19-Apr | 13-Apr | 13-Apr
CDUVDU29900 | Completed | Installation of Internals | 13/04/2023 19:35:30 | 13/04/2023 19:35:35 | 19/04/2023 20:00:00 | 20/04/2023 20:00:00 | 01-VV-026 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 19-Apr | 20-Apr | 13-Apr | 13-Apr
CDUVDU30100 | Completed | Box up of manhole cover | 13/04/2023 19:35:42 | 13/04/2023 19:35:46 | 20/04/2023 20:00:00 | 21/04/2023 00:00:00 | 01-VV-026 | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  | 4:00 | 20-Apr | 21-Apr | 13-Apr | 13-Apr
CDUVDU30120 | Completed | Deblinding | 22/04/2023 12:00:32 | 22/04/2023 12:00:38 | 21/04/2023 00:00:00 | 22/04/2023 00:00:00 | 01-VV-026 | VESSEL | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  | 24:00 | 21-Apr | 22-Apr | 22-Apr | 22-Apr
CDUVDU7840 | Completed | Blinding | 03/04/2023 17:56:54 | 03/04/2023 17:56:59 | 03/04/2023 16:30:00 | 04/04/2023 16:30:00 | 01-VV-026 | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 24 | 24:00 | 0:00 |  | 24:00 | 03-Apr | 04-Apr | 03-Apr | 03-Apr
CDUVDU9160 | Completed | Opening of manhole cover | 04/04/2023 16:31:27 | 04/04/2023 16:31:33 | 04/04/2023 16:30:00 | 05/04/2023 00:30:00 | 01-VV-026 | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  | 8:00 | 04-Apr | 05-Apr | 04-Apr | 04-Apr
CDUVDU9410 | Completed | Manentry | 04/04/2023 21:29:49 | 04/04/2023 21:29:49 | 05/04/2023 00:30:00 | 05/04/2023 04:30:00 | 01-VV-026 | VESSEL | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  |  | 05-Apr | 05-Apr | 04-Apr | 04-Apr
CDUVDU9420 | Completed | UT Gauging | 04/04/2023 21:29:49 | 04/04/2023 21:29:49 | 05/04/2023 00:30:00 | 05/04/2023 12:30:00 | 01-VV-026 | VESSEL | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  |  | 05-Apr | 05-Apr | 04-Apr | 04-Apr
CDUVDU9670 | Completed | Pre-cleaning inspection | 04/04/2023 21:29:49 | 04/04/2023 21:29:49 | 05/04/2023 04:30:00 | 05/04/2023 08:30:00 | 01-VV-026 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  |  | 05-Apr | 05-Apr | 04-Apr | 04-Apr
CDUVDU9890 | Completed | Removal of Internals | 13/04/2023 19:33:57 | 13/04/2023 19:34:02 | 05/04/2023 08:30:00 | 06/04/2023 08:30:00 | 01-VV-026 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 05-Apr | 06-Apr | 13-Apr | 13-Apr
CDUVDU11970 | Completed | Post cleaning inspection | 29/03/2023 23:07:39 | 29/03/2023 23:07:39 | 06/04/2023 20:30:00 | 07/04/2023 00:30:00 | 01-VV-012 | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:00 |  |  | 06-Apr | 07-Apr | 29-Mar | 29-Mar
CDUVDU12260 | Completed | Repair if any | 08/04/2023 11:34:14 | 08/04/2023 11:34:26 | 07/04/2023 00:30:00 | 09/04/2023 00:30:00 | 01-VV-012 | VESSEL | 100 | MECHANICAL | REPAIR |  | 48 | 48:00 | 0:00 |  | 48:00 | 07-Apr | 09-Apr | 08-Apr | 08-Apr
CDUVDU15430 | Completed | Carry Out Inspection | 08/04/2023 11:35:13 | 08/04/2023 11:35:20 | 09/04/2023 00:30:00 | 09/04/2023 04:30:00 | 01-VV-012 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 09-Apr | 09-Apr | 08-Apr | 08-Apr
CDUVDU15870 | Completed | Installation of Internals | 08/04/2023 11:34:37 | 08/04/2023 11:34:58 | 09/04/2023 04:30:00 | 10/04/2023 04:30:00 | 01-VV-012 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 09-Apr | 10-Apr | 08-Apr | 08-Apr
CDUVDU18070 | Completed | Box up of manhole cover | 08/04/2023 11:35:34 | 08/04/2023 11:35:39 | 10/04/2023 04:30:00 | 10/04/2023 08:30:00 | 01-VV-012 | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  | 4:00 | 10-Apr | 10-Apr | 08-Apr | 08-Apr
CDUVDU18440 | Completed | Deblinding | 08/04/2023 11:35:48 | 08/04/2023 11:35:56 | 10/04/2023 08:30:00 | 11/04/2023 08:30:00 | 01-VV-012 | VESSEL | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  | 24:00 | 10-Apr | 11-Apr | 08-Apr | 08-Apr
CDUVDU3840 | Completed | Blinding | 27/03/2023 10:05:03 | 29/03/2023 23:07:51 | 01/04/2023 16:30:00 | 02/04/2023 16:30:00 | 01-VV-012 | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 24 | 24:00 | 61:03 | 37:03 |  | 01-Apr | 02-Apr | 27-Mar | 29-Mar
CDUVDU6180 | Completed | Opening of manhole cover | 29/03/2023 23:07:39 | 29/03/2023 23:07:39 | 02/04/2023 16:30:00 | 03/04/2023 00:30:00 | 01-VV-012 | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  |  | 02-Apr | 03-Apr | 29-Mar | 29-Mar
CDUVDU6680 | Completed | Manentry | 29/03/2023 23:07:39 | 29/03/2023 23:07:39 | 03/04/2023 00:30:00 | 03/04/2023 04:30:00 | 01-VV-012 | VESSEL | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  |  | 03-Apr | 03-Apr | 29-Mar | 29-Mar
CDUVDU6690 | Completed | UT Gauging | 29/03/2023 23:07:39 | 29/03/2023 23:07:39 | 03/04/2023 00:30:00 | 03/04/2023 12:30:00 | 01-VV-012 | VESSEL | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  |  | 03-Apr | 03-Apr | 29-Mar | 29-Mar
CDUVDU6830 | Completed | Pre-cleaning inspection | 29/03/2023 23:07:39 | 29/03/2023 23:07:39 | 03/04/2023 04:30:00 | 03/04/2023 08:30:00 | 01-VV-012 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  |  | 03-Apr | 03-Apr | 29-Mar | 29-Mar
CDUVDU7120 | Completed | Removal of Internals | 29/03/2023 23:07:39 | 29/03/2023 23:07:39 | 03/04/2023 08:30:00 | 04/04/2023 08:30:00 | 01-VV-012 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  |  | 03-Apr | 04-Apr | 29-Mar | 29-Mar
CDUVDU8560 | Completed | Internal cleaning | 29/03/2023 23:07:39 | 29/03/2023 23:07:39 | 04/04/2023 08:30:00 | 06/04/2023 20:30:00 | 01-VV-012 | VESSEL | 100 | MECHANICAL | CLEANING |  | 60 | 60:00 | 0:00 |  |  | 04-Apr | 06-Apr | 29-Mar | 29-Mar
CDUVDU11520 | Completed | Blinding | 02/04/2023 09:36:57 | 02/04/2023 09:37:02 | 06/04/2023 14:30:00 | 07/04/2023 14:30:00 | 01-VV-027 | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 24 | 24:00 | 0:00 |  | 24:00 | 06-Apr | 07-Apr | 02-Apr | 02-Apr
CDUVDU13160 | Completed | Opening of manhole cover | 03/04/2023 17:49:57 | 03/04/2023 17:50:02 | 07/04/2023 14:30:00 | 07/04/2023 22:30:00 | 01-VV-027 | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  | 8:00 | 07-Apr | 07-Apr | 03-Apr | 03-Apr
CDUVDU13660 | Completed | Manentry | 04/04/2023 21:42:27 | 04/04/2023 21:42:27 | 07/04/2023 22:30:00 | 08/04/2023 02:30:00 | 01-VV-027 | VESSEL | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  |  | 07-Apr | 08-Apr | 04-Apr | 04-Apr
CDUVDU13670 | Completed | UT Gauging | 04/04/2023 21:42:27 | 04/04/2023 21:42:27 | 07/04/2023 22:30:00 | 08/04/2023 10:30:00 | 01-VV-027 | VESSEL | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  |  | 07-Apr | 08-Apr | 04-Apr | 04-Apr
CDUVDU13880 | Completed | Pre-cleaning inspection | 04/04/2023 21:42:27 | 04/04/2023 21:42:27 | 08/04/2023 02:30:00 | 08/04/2023 06:30:00 | 01-VV-027 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  |  | 08-Apr | 08-Apr | 04-Apr | 04-Apr
CDUVDU14060 | Completed | Removal of Internals | 07/04/2023 21:48:09 | 07/04/2023 21:48:09 | 08/04/2023 06:30:00 | 09/04/2023 06:30:00 | 01-VV-027 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  |  | 08-Apr | 09-Apr | 07-Apr | 07-Apr
CDUVDU26840 | Completed | Internal cleaning | 07/04/2023 21:48:09 | 07/04/2023 21:48:09 | 14/04/2023 18:30:00 | 15/04/2023 18:30:00 | 01-VV-027 | VESSEL | 100 | MECHANICAL | CLEANING |  | 24 | 24:00 | 0:00 |  |  | 14-Apr | 15-Apr | 07-Apr | 07-Apr
CDUVDU27680 | Completed | Post cleaning inspection | 07/04/2023 21:48:09 | 07/04/2023 21:48:09 | 15/04/2023 18:30:00 | 15/04/2023 22:30:00 | 01-VV-027 | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:00 |  |  | 15-Apr | 15-Apr | 07-Apr | 07-Apr
CDUVDU27820 | Completed | Repair if any | 09/04/2023 09:44:00 | 20/04/2023 09:19:44 | 15/04/2023 22:30:00 | 17/04/2023 22:30:00 | 01-VV-027 | VESSEL | 100 | MECHANICAL | REPAIR |  | 48 | 48:00 | 263:36 | 215:36 |  | 15-Apr | 17-Apr | 09-Apr | 20-Apr
CDUVDU29150 | Completed | Carry Out Inspection | 20/04/2023 09:20:13 | 20/04/2023 09:20:13 | 17/04/2023 22:30:00 | 18/04/2023 02:30:00 | 01-VV-027 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  |  | 17-Apr | 18-Apr | 20-Apr | 20-Apr
CDUVDU29240 | Completed | Installation of Internals | 20/04/2023 09:20:13 | 20/04/2023 09:20:13 | 18/04/2023 02:30:00 | 19/04/2023 02:30:00 | 01-VV-027 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  |  | 18-Apr | 19-Apr | 20-Apr | 20-Apr
CDUVDU29660 | Completed | Box up of manhole cover | 24/04/2023 17:31:15 | 24/04/2023 17:31:36 | 19/04/2023 02:30:00 | 19/04/2023 06:30:00 | 01-VV-027 | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  | 4:00 | 19-Apr | 19-Apr | 24-Apr | 24-Apr
CDUVDU29720 | Completed | Deblinding | 26/04/2023 17:25:07 | 26/04/2023 17:25:13 | 19/04/2023 06:30:00 | 20/04/2023 06:30:00 | 01-VV-027 | VESSEL | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  | 24:00 | 19-Apr | 20-Apr | 26-Apr | 26-Apr
CDUVDU13150 | Completed | Blinding | 27/03/2023 09:54:41 | 06/04/2023 17:21:21 | 07/04/2023 14:30:00 | 08/04/2023 02:30:00 | 01-WG-00-001A | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 247:27 | 235:27 |  | 07-Apr | 08-Apr | 27-Mar | 06-Apr
CDUVDU13890 | Completed | Opening of handhole | 06/04/2023 17:21:06 | 06/04/2023 17:21:11 | 08/04/2023 02:30:00 | 08/04/2023 10:30:00 | 01-WG-00-001A | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  | 8:00 | 08-Apr | 08-Apr | 06-Apr | 06-Apr
CDUVDU14440 | Completed | Pre-cleaning inspection | 06/04/2023 17:21:40 | 06/04/2023 17:21:45 | 08/04/2023 10:30:00 | 08/04/2023 14:30:00 | 01-WG-00-001A | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 08-Apr | 08-Apr | 06-Apr | 06-Apr
CDUVDU14450 | Completed | UT Gauging | 10/04/2023 17:54:45 | 10/04/2023 17:54:49 | 08/04/2023 10:30:00 | 08/04/2023 22:30:00 | 01-WG-00-001A | VESSEL | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  | 12:00 | 08-Apr | 08-Apr | 10-Apr | 10-Apr
CDUVDU14740 | Completed | Removal of Internals | 06/04/2023 17:21:55 | 06/04/2023 17:22:01 | 08/04/2023 14:30:00 | 09/04/2023 08:30:00 | 01-WG-00-001A | VESSEL | 100 | MECHANICAL |  |  | 18 | 18:00 | 0:00 |  | 18:00 | 08-Apr | 09-Apr | 06-Apr | 06-Apr
CDUVDU16100 | Completed | Internal cleaning | 06/04/2023 17:22:09 | 06/04/2023 17:22:27 | 09/04/2023 08:30:00 | 11/04/2023 20:30:00 | 01-WG-00-001A | VESSEL | 100 | MECHANICAL | CLEANING |  | 60 | 60:00 | 0:00 |  | 60:00 | 09-Apr | 11-Apr | 06-Apr | 06-Apr
CDUVDU22080 | Completed | Post cleaning inspection | 06/04/2023 17:22:44 | 06/04/2023 17:22:50 | 11/04/2023 20:30:00 | 12/04/2023 00:30:00 | 01-WG-00-001A | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:00 |  | 4:00 | 11-Apr | 12-Apr | 06-Apr | 06-Apr
CDUVDU22370 | Completed | Installation of Internals | 06/04/2023 17:23:03 | 06/04/2023 17:23:09 | 12/04/2023 00:30:00 | 12/04/2023 18:30:00 | 01-WG-00-001A | VESSEL | 100 | MECHANICAL |  |  | 18 | 18:00 | 0:00 |  | 18:00 | 12-Apr | 12-Apr | 06-Apr | 06-Apr
CDUVDU24120 | Completed | Box up of manhole cover | 06/04/2023 17:24:06 | 06/04/2023 17:24:12 | 12/04/2023 18:30:00 | 12/04/2023 22:30:00 | 01-WG-00-001A | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  | 4:00 | 12-Apr | 12-Apr | 06-Apr | 06-Apr
CDUVDU24360 | Completed | Deblinding | 06/04/2023 17:24:21 | 06/04/2023 17:24:28 | 12/04/2023 22:30:00 | 13/04/2023 10:30:00 | 01-WG-00-001A | VESSEL | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 12-Apr | 13-Apr | 06-Apr | 06-Apr
CDUVDU10350 | Completed | Carry out Inspection | 20/04/2023 16:53:04 | 20/04/2023 16:53:08 | 05/04/2023 15:30:00 | 06/04/2023 03:30:00 | CI/DE | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 12 | 12:00 | 0:00 |  | 12:00 | 05-Apr | 06-Apr | 20-Apr | 20-Apr
CDUVDU10900 | Completed | Carry out Hydro test | 18/04/2023 17:19:42 | 18/04/2023 17:20:42 | 06/04/2023 03:30:00 | 06/04/2023 15:30:00 | CI/DE | VESSEL | 100 | MECHANICAL | HYDRO TEST | HYDRO TEST | 12 | 12:00 | 0:01 |  | 11:59 | 06-Apr | 06-Apr | 18-Apr | 18-Apr
CDUVDU11570 | Completed | Carry out Box up | 20/04/2023 16:53:14 | 20/04/2023 16:53:19 | 06/04/2023 15:30:00 | 07/04/2023 03:30:00 | CI/DE | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 12 | 12:00 | 0:00 |  | 12:00 | 06-Apr | 07-Apr | 20-Apr | 20-Apr
CDUVDU12490 | Completed | Carry out Deblinding | 20/04/2023 16:53:29 | 20/04/2023 16:53:36 | 07/04/2023 03:30:00 | 07/04/2023 15:30:00 | CI/DE | VESSEL | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 07-Apr | 07-Apr | 20-Apr | 20-Apr
CDUVDU8060 | Completed | Carry out blinding | 13/04/2023 20:07:40 | 13/04/2023 20:08:40 | 03/04/2023 21:30:00 | 04/04/2023 09:30:00 | CI/DE | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 0:01 |  | 11:59 | 03-Apr | 04-Apr | 13-Apr | 13-Apr
CDUVDU8610 | Completed | Carry out handhole opening | 17/04/2023 11:07:41 | 20/04/2023 15:20:24 | 04/04/2023 09:30:00 | 04/04/2023 21:30:00 | CI/DE | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 12 | 12:00 | 76:13 | 64:13 |  | 04-Apr | 04-Apr | 17-Apr | 20-Apr
CDUVDU9290 | Completed | Carry out cleaning | 20/04/2023 16:52:47 | 20/04/2023 16:52:53 | 04/04/2023 21:30:00 | 05/04/2023 15:30:00 | CI/DE | VESSEL | 100 | MECHANICAL | CLEANING |  | 18 | 18:00 | 0:00 |  | 18:00 | 04-Apr | 05-Apr | 20-Apr | 20-Apr
CDUVDU14730 | Completed | Blinding | 27/03/2023 09:48:10 | 27/03/2023 11:40:12 | 08/04/2023 14:30:00 | 09/04/2023 02:30:00 | 01-WG-00-002A | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 1:52 |  | 10:08 | 08-Apr | 09-Apr | 27-Mar | 27-Mar
CDUVDU15720 | Completed | Opening of handhole | 27/03/2023 11:58:10 | 29/03/2023 13:59:36 | 09/04/2023 02:30:00 | 09/04/2023 10:30:00 | 01-WG-00-002A | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 50:01 | 42:01 |  | 09-Apr | 09-Apr | 27-Mar | 29-Mar
CDUVDU16310 | Completed | Pre-cleaning inspection | 29/03/2023 13:59:50 | 29/03/2023 13:59:54 | 09/04/2023 10:30:00 | 09/04/2023 14:30:00 | 01-WG-00-002A | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 09-Apr | 09-Apr | 29-Mar | 29-Mar
CDUVDU16320 | Completed | UT Gauging | 10/04/2023 17:55:28 | 10/04/2023 17:55:32 | 09/04/2023 10:30:00 | 09/04/2023 22:30:00 | 01-WG-00-002A | VESSEL | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  | 12:00 | 09-Apr | 09-Apr | 10-Apr | 10-Apr
CDUVDU16680 | Completed | Removal of Internals | 06/04/2023 16:55:15 | 06/04/2023 16:55:24 | 09/04/2023 14:30:00 | 10/04/2023 08:30:00 | 01-WG-00-002A | VESSEL | 100 | MECHANICAL |  |  | 18 | 18:00 | 0:00 |  | 18:00 | 09-Apr | 10-Apr | 06-Apr | 06-Apr
CDUVDU18450 | Completed | Internal cleaning | 06/04/2023 16:55:35 | 06/04/2023 16:56:02 | 10/04/2023 08:30:00 | 12/04/2023 20:30:00 | 01-WG-00-002A | VESSEL | 100 | MECHANICAL | CLEANING |  | 60 | 60:00 | 0:00 |  | 60:00 | 10-Apr | 12-Apr | 06-Apr | 06-Apr
CDUVDU24210 | Completed | Post cleaning inspection | 28/03/2023 14:32:51 | 28/03/2023 14:32:51 | 12/04/2023 20:30:00 | 13/04/2023 00:30:00 | 01-WG-00-002A | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:00 |  |  | 12-Apr | 13-Apr | 28-Mar | 28-Mar
CDUVDU24570 | Completed | Installation of Internals | 06/04/2023 16:56:14 | 06/04/2023 16:56:19 | 13/04/2023 00:30:00 | 13/04/2023 18:30:00 | 01-WG-00-002A | VESSEL | 100 | MECHANICAL |  |  | 18 | 18:00 | 0:00 |  | 18:00 | 13-Apr | 13-Apr | 06-Apr | 06-Apr
CDUVDU25710 | Completed | Box up of manhole cover | 06/04/2023 16:56:35 | 06/04/2023 16:56:39 | 13/04/2023 18:30:00 | 13/04/2023 22:30:00 | 01-WG-00-002A | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  | 4:00 | 13-Apr | 13-Apr | 06-Apr | 06-Apr
CDUVDU25830 | Completed | Deblinding | 06/04/2023 16:56:48 | 06/04/2023 16:56:55 | 13/04/2023 22:30:00 | 14/04/2023 10:30:00 | 01-WG-00-002A | VESSEL | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 13-Apr | 14-Apr | 06-Apr | 06-Apr
CDUVDU22570 | Completed | Blinding | 27/03/2023 09:22:26 | 06/04/2023 17:16:17 | 12/04/2023 02:30:00 | 12/04/2023 14:30:00 | 01-WG-00-006B | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 247:54 | 235:54 |  | 12-Apr | 12-Apr | 27-Mar | 06-Apr
CDUVDU23740 | Completed | Opening of manhole cover | 06/04/2023 17:16:05 | 06/04/2023 17:16:10 | 12/04/2023 14:30:00 | 12/04/2023 22:30:00 | 01-WG-00-006B | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  | 8:00 | 12-Apr | 12-Apr | 06-Apr | 06-Apr
CDUVDU24390 | Completed | Pre-cleaning inspection | 06/04/2023 17:16:35 | 06/04/2023 17:16:39 | 12/04/2023 22:30:00 | 13/04/2023 02:30:00 | 01-WG-00-006B | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 12-Apr | 13-Apr | 06-Apr | 06-Apr
CDUVDU24400 | Completed | UT Gauging | 16/04/2023 11:08:44 | 16/04/2023 11:08:55 | 12/04/2023 22:30:00 | 13/04/2023 10:30:00 | 01-WG-00-006B | VESSEL | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  | 12:00 | 12-Apr | 13-Apr | 16-Apr | 16-Apr
CDUVDU24680 | Completed | Removal of Internals | 06/04/2023 17:16:49 | 06/04/2023 17:16:54 | 13/04/2023 02:30:00 | 14/04/2023 02:30:00 | 01-WG-00-006B | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 13-Apr | 14-Apr | 06-Apr | 06-Apr
CDUVDU26050 | Completed | Internal cleaning | 06/04/2023 17:17:02 | 06/04/2023 17:17:10 | 14/04/2023 02:30:00 | 16/04/2023 14:30:00 | 01-WG-00-006B | VESSEL | 100 | MECHANICAL | CLEANING |  | 60 | 60:00 | 0:00 |  | 60:00 | 14-Apr | 16-Apr | 06-Apr | 06-Apr
CDUVDU28360 | Completed | Post cleaning inspection | 06/04/2023 17:17:29 | 06/04/2023 17:17:35 | 16/04/2023 14:30:00 | 16/04/2023 18:30:00 | 01-WG-00-006B | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:00 |  | 4:00 | 16-Apr | 16-Apr | 06-Apr | 06-Apr
CDUVDU28450 | Completed | Installation of Internals | 06/04/2023 17:17:44 | 06/04/2023 17:17:50 | 16/04/2023 18:30:00 | 17/04/2023 18:30:00 | 01-WG-00-006B | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 16-Apr | 17-Apr | 06-Apr | 06-Apr
CDUVDU29060 | Completed | Box up of manhole cover | 06/04/2023 17:17:58 | 06/04/2023 17:18:06 | 17/04/2023 18:30:00 | 17/04/2023 22:30:00 | 01-WG-00-006B | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  | 4:00 | 17-Apr | 17-Apr | 06-Apr | 06-Apr
CDUVDU29130 | Completed | Deblinding | 06/04/2023 17:18:14 | 06/04/2023 17:18:20 | 17/04/2023 22:30:00 | 18/04/2023 22:30:00 | 01-WG-00-006B | VESSEL | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  | 24:00 | 17-Apr | 18-Apr | 06-Apr | 06-Apr
CDUVDU24660 | Completed | Blinding | 27/03/2023 09:53:39 | 06/04/2023 16:58:49 | 13/04/2023 02:30:00 | 13/04/2023 14:30:00 | 01-WG-00-007B | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 247:05 | 235:05 |  | 13-Apr | 13-Apr | 27-Mar | 06-Apr
CDUVDU25420 | Completed | Opening of handhole | 06/04/2023 16:39:26 | 06/04/2023 16:39:32 | 13/04/2023 14:30:00 | 13/04/2023 22:30:00 | 01-WG-00-007B | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  | 8:00 | 13-Apr | 13-Apr | 06-Apr | 06-Apr
CDUVDU25850 | Completed | Pre-cleaning inspection | 06/04/2023 16:39:52 | 06/04/2023 16:39:58 | 13/04/2023 22:30:00 | 14/04/2023 02:30:00 | 01-WG-00-007B | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 13-Apr | 14-Apr | 06-Apr | 06-Apr
CDUVDU25860 | Completed | UT Gauging | 16/04/2023 11:08:32 | 16/04/2023 11:08:59 | 13/04/2023 22:30:00 | 14/04/2023 10:30:00 | 01-WG-00-007B | VESSEL | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  | 12:00 | 13-Apr | 14-Apr | 16-Apr | 16-Apr
CDUVDU26060 | Completed | Removal of Internals | 06/04/2023 16:41:14 | 06/04/2023 16:41:40 | 14/04/2023 02:30:00 | 15/04/2023 02:30:00 | 01-WG-00-007B | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 14-Apr | 15-Apr | 06-Apr | 06-Apr
CDUVDU27090 | Completed | Internal cleaning | 06/04/2023 16:42:17 | 06/04/2023 16:42:26 | 15/04/2023 02:30:00 | 17/04/2023 14:30:00 | 01-WG-00-007B | VESSEL | 100 | MECHANICAL | CLEANING |  | 60 | 60:00 | 0:00 |  | 60:00 | 15-Apr | 17-Apr | 06-Apr | 06-Apr
CDUVDU28990 | Completed | Post cleaning inspection | 06/04/2023 16:43:28 | 06/04/2023 16:44:06 | 17/04/2023 14:30:00 | 17/04/2023 18:30:00 | 01-WG-00-007B | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:01 |  | 3:59 | 17-Apr | 17-Apr | 06-Apr | 06-Apr
CDUVDU29070 | Completed | Installation of Internals | 06/04/2023 16:44:23 | 06/04/2023 16:44:28 | 17/04/2023 18:30:00 | 18/04/2023 18:30:00 | 01-WG-00-007B | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 17-Apr | 18-Apr | 06-Apr | 06-Apr
CDUVDU29520 | Completed | Box up of manhole cover | 06/04/2023 16:44:42 | 06/04/2023 16:44:49 | 18/04/2023 18:30:00 | 18/04/2023 22:30:00 | 01-WG-00-007B | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  | 4:00 | 18-Apr | 18-Apr | 06-Apr | 06-Apr
CDUVDU29600 | Completed | Deblinding | 06/04/2023 16:45:14 | 06/04/2023 16:45:22 | 18/04/2023 22:30:00 | 19/04/2023 22:30:00 | 01-WG-00-007B | VESSEL | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  | 24:00 | 18-Apr | 19-Apr | 06-Apr | 06-Apr
CDUVDU1020 | Completed | Blinding | 27/03/2023 10:03:01 | 29/03/2023 17:42:08 | 26/03/2023 06:00:00 | 27/03/2023 06:00:00 | 01-VV-047 | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 24 | 24:00 | 55:39 | 31:39 |  | 26-Mar | 27-Mar | 27-Mar | 29-Mar
CDUVDU1230 | Completed | Opening of manhole cover | 29/03/2023 17:42:51 | 29/03/2023 17:43:10 | 27/03/2023 06:00:00 | 27/03/2023 14:00:00 | 01-VV-047 | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  | 8:00 | 27-Mar | 27-Mar | 29-Mar | 29-Mar
CDUVDU1240 | Completed | Manentry | 02/04/2023 18:34:03 | 02/04/2023 18:34:09 | 27/03/2023 14:00:00 | 27/03/2023 18:00:00 | 01-VV-047 | VESSEL | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 27-Mar | 27-Mar | 02-Apr | 02-Apr
CDUVDU1250 | Completed | UT Gauging | 10/04/2023 14:53:38 | 10/04/2023 14:53:43 | 27/03/2023 14:00:00 | 28/03/2023 02:00:00 | 01-VV-047 | VESSEL | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  | 12:00 | 27-Mar | 28-Mar | 10-Apr | 10-Apr
CDUVDU1350 | Completed | Pre-cleaning inspection | 10/04/2023 14:54:55 | 10/04/2023 14:54:59 | 27/03/2023 18:00:00 | 27/03/2023 22:00:00 | 01-VV-047 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 27-Mar | 27-Mar | 10-Apr | 10-Apr
CDUVDU1360 | Completed | Removal of Internals | 03/04/2023 13:38:18 | 03/04/2023 13:38:46 | 27/03/2023 22:00:00 | 28/03/2023 22:00:00 | 01-VV-047 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 27-Mar | 28-Mar | 03-Apr | 03-Apr
CDUVDU1390 | Completed | Internal cleaning | 03/04/2023 13:38:28 | 03/04/2023 13:38:55 | 28/03/2023 22:00:00 | 31/03/2023 10:00:00 | 01-VV-047 | VESSEL | 100 | MECHANICAL | CLEANING |  | 60 | 60:00 | 0:00 |  | 60:00 | 28-Mar | 31-Mar | 03-Apr | 03-Apr
CDUVDU1910 | Completed | Post cleaning inspection | 10/04/2023 14:56:07 | 10/04/2023 14:56:11 | 31/03/2023 10:00:00 | 31/03/2023 14:00:00 | 01-VV-047 | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:00 |  | 4:00 | 31-Mar | 31-Mar | 10-Apr | 10-Apr
CDUVDU1940 | Completed | Bottom Dish Replacement & Repair | 03/04/2023 13:38:36 | 08/04/2023 08:50:27 | 31/03/2023 14:00:00 | 12/04/2023 20:00:00 | 01-VV-047 | VESSEL | 100 | MECHANICAL | REPAIR |  | 294 | 294:00 | 115:12 |  | 178:48 | 31-Mar | 12-Apr | 03-Apr | 08-Apr
CDUVDU24180 | Completed | Carry Out Inspection | 11/04/2023 18:06:03 | 11/04/2023 18:06:07 | 12/04/2023 20:00:00 | 13/04/2023 00:00:00 | 01-VV-047 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 12-Apr | 13-Apr | 11-Apr | 11-Apr
CDUVDU24530 | Completed | Installation of Internals | 07/04/2023 09:15:03 | 10/04/2023 09:11:17 | 13/04/2023 00:00:00 | 14/04/2023 00:00:00 | 01-VV-047 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 71:56 | 47:56 |  | 13-Apr | 14-Apr | 07-Apr | 10-Apr
CDUVDU25930 | Completed | Box up of manhole cover | 12/04/2023 08:05:12 | 12/04/2023 08:05:20 | 14/04/2023 00:00:00 | 14/04/2023 04:00:00 | 01-VV-047 | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  | 4:00 | 14-Apr | 14-Apr | 12-Apr | 12-Apr
CDUVDU26170 | Completed | Hydrotest | 12/04/2023 06:12:28 | 12/04/2023 06:12:28 | 14/04/2023 04:00:00 | 15/04/2023 04:00:00 | 01-VV-047 | VESSEL | 100 | INSPECTION | FINAL TEST |  | 24 | 24:00 | 0:00 |  |  | 14-Apr | 15-Apr | 12-Apr | 12-Apr
CDUVDU27150 | Completed | Deblinding | 22/04/2023 11:57:19 | 22/04/2023 11:57:25 | 15/04/2023 04:00:00 | 16/04/2023 04:00:00 | 01-VV-047 | VESSEL | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  | 24:00 | 15-Apr | 16-Apr | 22-Apr | 22-Apr
CDUVDU10340 | Completed | Carry out Hydro test | 18/04/2023 17:19:04 | 18/04/2023 17:20:04 | 05/04/2023 15:30:00 | 06/04/2023 03:30:00 | SEAL POT/ VOL BOTTLE | VESSEL | 100 | MECHANICAL | HYDRO TEST | HYDRO TEST | 12 | 12:00 | 0:01 |  | 11:59 | 05-Apr | 06-Apr | 18-Apr | 18-Apr
CDUVDU10890 | Completed | Carry out Box up | 23/04/2023 10:56:21 | 23/04/2023 10:56:21 | 06/04/2023 03:30:00 | 06/04/2023 15:30:00 | SEAL POT/ VOL BOTTLE | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 12 | 12:00 | 0:00 |  |  | 06-Apr | 06-Apr | 23-Apr | 23-Apr
CDUVDU11560 | Completed | Carry out Deblinding | 23/04/2023 10:56:21 | 23/04/2023 10:56:21 | 06/04/2023 15:30:00 | 07/04/2023 03:30:00 | SEAL POT/ VOL BOTTLE | VESSEL | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  |  | 06-Apr | 07-Apr | 23-Apr | 23-Apr
CDUVDU7180 | Completed | Carry out blinding | 13/04/2023 20:07:59 | 13/04/2023 20:08:59 | 03/04/2023 09:30:00 | 03/04/2023 21:30:00 | SEAL POT/ VOL BOTTLE | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 0:01 |  | 11:59 | 03-Apr | 03-Apr | 13-Apr | 13-Apr
CDUVDU8050 | Completed | Carry out handhole opening | 18/04/2023 16:08:49 | 20/04/2023 15:20:51 | 03/04/2023 21:30:00 | 04/04/2023 09:30:00 | SEAL POT/ VOL BOTTLE | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 12 | 12:00 | 47:12 | 35:12 |  | 03-Apr | 04-Apr | 18-Apr | 20-Apr
CDUVDU8600 | Completed | Carry out cleaning | 23/04/2023 10:56:21 | 23/04/2023 10:56:21 | 04/04/2023 09:30:00 | 05/04/2023 03:30:00 | SEAL POT/ VOL BOTTLE | VESSEL | 100 | MECHANICAL | CLEANING |  | 18 | 18:00 | 0:00 |  |  | 04-Apr | 05-Apr | 23-Apr | 23-Apr
CDUVDU9610 | Completed | Carry out Inspection | 23/04/2023 10:56:21 | 23/04/2023 10:56:21 | 05/04/2023 03:30:00 | 05/04/2023 15:30:00 | SEAL POT/ VOL BOTTLE | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 12 | 12:00 | 0:00 |  |  | 05-Apr | 05-Apr | 23-Apr | 23-Apr
CDUVDU13900 | Completed | Blinding | 27/03/2023 09:52:28 | 28/03/2023 20:48:00 | 08/04/2023 02:30:00 | 08/04/2023 14:30:00 | 01-WG-00-001B | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 34:56 | 22:56 |  | 08-Apr | 08-Apr | 27-Mar | 28-Mar
CDUVDU14750 | Completed | Opening of handhole | 06/04/2023 16:59:20 | 06/04/2023 16:59:27 | 08/04/2023 14:30:00 | 08/04/2023 22:30:00 | 01-WG-00-001B | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  | 8:00 | 08-Apr | 08-Apr | 06-Apr | 06-Apr
CDUVDU15250 | Completed | Pre-cleaning inspection | 06/04/2023 16:59:43 | 06/04/2023 16:59:58 | 08/04/2023 22:30:00 | 09/04/2023 02:30:00 | 01-WG-00-001B | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 08-Apr | 09-Apr | 06-Apr | 06-Apr
CDUVDU15260 | Completed | UT Gauging | 10/04/2023 17:55:08 | 10/04/2023 17:55:12 | 08/04/2023 22:30:00 | 09/04/2023 10:30:00 | 01-WG-00-001B | VESSEL | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  | 12:00 | 08-Apr | 09-Apr | 10-Apr | 10-Apr
CDUVDU15730 | Completed | Removal of Internals | 06/04/2023 17:00:25 | 06/04/2023 17:00:30 | 09/04/2023 02:30:00 | 09/04/2023 20:30:00 | 01-WG-00-001B | VESSEL | 100 | MECHANICAL |  |  | 18 | 18:00 | 0:00 |  | 18:00 | 09-Apr | 09-Apr | 06-Apr | 06-Apr
CDUVDU17230 | Completed | Internal cleaning | 06/04/2023 17:00:43 | 06/04/2023 17:00:48 | 09/04/2023 20:30:00 | 12/04/2023 08:30:00 | 01-WG-00-001B | VESSEL | 100 | MECHANICAL | CLEANING |  | 60 | 60:00 | 0:00 |  | 60:00 | 09-Apr | 12-Apr | 06-Apr | 06-Apr
CDUVDU23200 | Completed | Post cleaning inspection | 06/04/2023 17:01:05 | 06/04/2023 17:01:10 | 12/04/2023 08:30:00 | 12/04/2023 12:30:00 | 01-WG-00-001B | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:00 |  | 4:00 | 12-Apr | 12-Apr | 06-Apr | 06-Apr
CDUVDU23590 | Completed | Installation of Internals | 06/04/2023 17:01:21 | 06/04/2023 17:01:28 | 12/04/2023 12:30:00 | 13/04/2023 06:30:00 | 01-WG-00-001B | VESSEL | 100 | MECHANICAL |  |  | 18 | 18:00 | 0:00 |  | 18:00 | 12-Apr | 13-Apr | 06-Apr | 06-Apr
CDUVDU25000 | Completed | Box up of manhole cover | 06/04/2023 17:01:53 | 06/04/2023 17:01:59 | 13/04/2023 06:30:00 | 13/04/2023 10:30:00 | 01-WG-00-001B | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  | 4:00 | 13-Apr | 13-Apr | 06-Apr | 06-Apr
CDUVDU25240 | Completed | Deblinding | 06/04/2023 17:02:08 | 06/04/2023 17:02:21 | 13/04/2023 10:30:00 | 13/04/2023 22:30:00 | 01-WG-00-001B | VESSEL | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 13-Apr | 13-Apr | 06-Apr | 06-Apr
CDUVDU15740 | Completed | Blinding | 26/03/2023 19:28:00 | 27/03/2023 07:29:00 | 09/04/2023 02:30:00 | 09/04/2023 14:30:00 | 01-WG-00-002B | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 12:01 | 0:01 |  | 09-Apr | 09-Apr | 26-Mar | 27-Mar
CDUVDU16690 | Completed | Opening of handhole | 27/03/2023 09:50:15 | 29/03/2023 14:00:39 | 09/04/2023 14:30:00 | 09/04/2023 22:30:00 | 01-WG-00-002B | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 52:10 | 44:10 |  | 09-Apr | 09-Apr | 27-Mar | 29-Mar
CDUVDU17350 | Completed | Pre-cleaning inspection | 29/03/2023 14:00:52 | 29/03/2023 14:00:56 | 09/04/2023 22:30:00 | 10/04/2023 02:30:00 | 01-WG-00-002B | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 09-Apr | 10-Apr | 29-Mar | 29-Mar
CDUVDU17360 | Completed | UT Gauging | 10/04/2023 17:55:48 | 10/04/2023 17:55:53 | 09/04/2023 22:30:00 | 10/04/2023 10:30:00 | 01-WG-00-002B | VESSEL | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  | 12:00 | 09-Apr | 10-Apr | 10-Apr | 10-Apr
CDUVDU17810 | Completed | Removal of Internals | 06/04/2023 16:57:16 | 06/04/2023 16:57:22 | 10/04/2023 02:30:00 | 10/04/2023 20:30:00 | 01-WG-00-002B | VESSEL | 100 | MECHANICAL |  |  | 18 | 18:00 | 0:00 |  | 18:00 | 10-Apr | 10-Apr | 06-Apr | 06-Apr
CDUVDU19510 | Completed | Internal cleaning | 06/04/2023 16:57:28 | 06/04/2023 16:57:33 | 10/04/2023 20:30:00 | 13/04/2023 08:30:00 | 01-WG-00-002B | VESSEL | 100 | MECHANICAL | CLEANING |  | 60 | 60:00 | 0:00 |  | 60:00 | 10-Apr | 13-Apr | 06-Apr | 06-Apr
CDUVDU25130 | Completed | Post cleaning inspection | 28/03/2023 14:33:24 | 28/03/2023 14:33:24 | 13/04/2023 08:30:00 | 13/04/2023 12:30:00 | 01-WG-00-002B | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:00 |  |  | 13-Apr | 13-Apr | 28-Mar | 28-Mar
CDUVDU25320 | Completed | Installation of Internals | 06/04/2023 16:57:40 | 06/04/2023 16:57:46 | 13/04/2023 12:30:00 | 14/04/2023 06:30:00 | 01-WG-00-002B | VESSEL | 100 | MECHANICAL |  |  | 18 | 18:00 | 0:00 |  | 18:00 | 13-Apr | 14-Apr | 06-Apr | 06-Apr
CDUVDU26280 | Completed | Box up of manhole cover | 06/04/2023 16:57:57 | 06/04/2023 16:58:01 | 14/04/2023 06:30:00 | 14/04/2023 10:30:00 | 01-WG-00-002B | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  | 4:00 | 14-Apr | 14-Apr | 06-Apr | 06-Apr
CDUVDU26450 | Completed | Deblinding | 06/04/2023 16:58:14 | 06/04/2023 16:58:20 | 14/04/2023 10:30:00 | 15/04/2023 10:30:00 | 01-WG-00-002B | VESSEL | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  | 24:00 | 14-Apr | 15-Apr | 06-Apr | 06-Apr
CDUVDU16700 | Completed | Blinding | 27/03/2023 09:45:44 | 06/04/2023 17:02:43 | 09/04/2023 14:30:00 | 10/04/2023 02:30:00 | 01-WG-00-003A | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 247:17 | 235:17 |  | 09-Apr | 10-Apr | 27-Mar | 06-Apr
CDUVDU17820 | Completed | Opening of handhole | 06/04/2023 17:04:00 | 06/04/2023 17:04:12 | 10/04/2023 02:30:00 | 10/04/2023 10:30:00 | 01-WG-00-003A | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  | 8:00 | 10-Apr | 10-Apr | 06-Apr | 06-Apr
CDUVDU18580 | Completed | Pre-cleaning inspection | 28/03/2023 14:36:34 | 28/03/2023 14:36:34 | 10/04/2023 10:30:00 | 10/04/2023 14:30:00 | 01-WG-00-003A | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  |  | 10-Apr | 10-Apr | 28-Mar | 28-Mar
CDUVDU18590 | Completed | UT Gauging | 10/04/2023 17:56:18 | 10/04/2023 17:56:22 | 10/04/2023 10:30:00 | 10/04/2023 22:30:00 | 01-WG-00-003A | VESSEL | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  | 12:00 | 10-Apr | 10-Apr | 10-Apr | 10-Apr
CDUVDU19000 | Completed | Removal of Internals | 06/04/2023 17:04:21 | 06/04/2023 17:04:26 | 10/04/2023 14:30:00 | 11/04/2023 14:30:00 | 01-WG-00-003A | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 10-Apr | 11-Apr | 06-Apr | 06-Apr
CDUVDU21470 | Completed | Internal cleaning | 06/04/2023 17:04:36 | 06/04/2023 17:04:41 | 11/04/2023 14:30:00 | 14/04/2023 02:30:00 | 01-WG-00-003A | VESSEL | 100 | MECHANICAL | CLEANING |  | 60 | 60:00 | 0:00 |  | 60:00 | 11-Apr | 14-Apr | 06-Apr | 06-Apr
CDUVDU26070 | Completed | Post cleaning inspection | 28/03/2023 14:36:34 | 28/03/2023 14:36:34 | 14/04/2023 02:30:00 | 14/04/2023 06:30:00 | 01-WG-00-003A | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:00 |  |  | 14-Apr | 14-Apr | 28-Mar | 28-Mar
CDUVDU26290 | Completed | Installation of Internals | 06/04/2023 17:04:49 | 06/04/2023 17:05:00 | 14/04/2023 06:30:00 | 15/04/2023 06:30:00 | 01-WG-00-003A | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 14-Apr | 15-Apr | 06-Apr | 06-Apr
CDUVDU27240 | Completed | Box up of manhole cover | 06/04/2023 17:05:22 | 06/04/2023 17:05:29 | 15/04/2023 06:30:00 | 15/04/2023 10:30:00 | 01-WG-00-003A | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  | 4:00 | 15-Apr | 15-Apr | 06-Apr | 06-Apr
CDUVDU27420 | Completed | Deblinding | 06/04/2023 17:05:37 | 06/04/2023 17:05:42 | 15/04/2023 10:30:00 | 16/04/2023 10:30:00 | 01-WG-00-003A | VESSEL | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  | 24:00 | 15-Apr | 16-Apr | 06-Apr | 06-Apr
CDUVDU17830 | Completed | Blinding | 27/03/2023 09:47:14 | 06/04/2023 17:05:59 | 10/04/2023 02:30:00 | 10/04/2023 14:30:00 | 01-WG-00-003B | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 247:19 | 235:19 |  | 10-Apr | 10-Apr | 27-Mar | 06-Apr
CDUVDU19010 | Completed | Opening of handhole | 06/04/2023 17:06:27 | 06/04/2023 17:06:33 | 10/04/2023 14:30:00 | 10/04/2023 22:30:00 | 01-WG-00-003B | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  | 8:00 | 10-Apr | 10-Apr | 06-Apr | 06-Apr
CDUVDU19720 | Completed | Pre-cleaning inspection | 28/03/2023 14:35:49 | 28/03/2023 14:35:49 | 10/04/2023 22:30:00 | 11/04/2023 02:30:00 | 01-WG-00-003B | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  |  | 10-Apr | 11-Apr | 28-Mar | 28-Mar
CDUVDU19730 | Completed | UT Gauging | 06/04/2023 17:06:49 | 06/04/2023 17:06:56 | 10/04/2023 22:30:00 | 11/04/2023 10:30:00 | 01-WG-00-003B | VESSEL | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  | 12:00 | 10-Apr | 11-Apr | 06-Apr | 06-Apr
CDUVDU20260 | Completed | Removal of Internals | 06/04/2023 17:07:03 | 06/04/2023 17:07:10 | 11/04/2023 02:30:00 | 12/04/2023 02:30:00 | 01-WG-00-003B | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 11-Apr | 12-Apr | 06-Apr | 06-Apr
CDUVDU22580 | Completed | Internal cleaning | 06/04/2023 17:07:19 | 06/04/2023 17:07:26 | 12/04/2023 02:30:00 | 14/04/2023 14:30:00 | 01-WG-00-003B | VESSEL | 100 | MECHANICAL | CLEANING |  | 60 | 60:00 | 0:00 |  | 60:00 | 12-Apr | 14-Apr | 06-Apr | 06-Apr
CDUVDU26610 | Completed | Post cleaning inspection | 28/03/2023 14:35:49 | 28/03/2023 14:35:49 | 14/04/2023 14:30:00 | 14/04/2023 18:30:00 | 01-WG-00-003B | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:00 |  |  | 14-Apr | 14-Apr | 28-Mar | 28-Mar
CDUVDU26850 | Completed | Installation of Internals | 06/04/2023 17:07:35 | 06/04/2023 17:07:40 | 14/04/2023 18:30:00 | 15/04/2023 18:30:00 | 01-WG-00-003B | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 14-Apr | 15-Apr | 06-Apr | 06-Apr
CDUVDU27690 | Completed | Box up of manhole cover | 06/04/2023 17:07:50 | 06/04/2023 17:08:12 | 15/04/2023 18:30:00 | 15/04/2023 22:30:00 | 01-WG-00-003B | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  | 4:00 | 15-Apr | 15-Apr | 06-Apr | 06-Apr
CDUVDU27830 | Completed | Deblinding | 06/04/2023 17:08:27 | 06/04/2023 17:08:35 | 15/04/2023 22:30:00 | 16/04/2023 22:30:00 | 01-WG-00-003B | VESSEL | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  | 24:00 | 15-Apr | 16-Apr | 06-Apr | 06-Apr
CDUVDU19020 | Completed | Blinding | 27/03/2023 09:25:02 | 30/03/2023 05:22:49 | 10/04/2023 14:30:00 | 11/04/2023 02:30:00 | 01-WG-00-004A | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 67:58 | 55:58 |  | 10-Apr | 11-Apr | 27-Mar | 30-Mar
CDUVDU20270 | Completed | Opening of handhole | 30/03/2023 05:22:49 | 30/03/2023 05:22:49 | 11/04/2023 02:30:00 | 11/04/2023 10:30:00 | 01-WG-00-004A | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  |  | 11-Apr | 11-Apr | 30-Mar | 30-Mar
CDUVDU20940 | Completed | Pre-cleaning inspection | 30/03/2023 05:22:49 | 30/03/2023 05:22:49 | 11/04/2023 10:30:00 | 11/04/2023 14:30:00 | 01-WG-00-004A | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  |  | 11-Apr | 11-Apr | 30-Mar | 30-Mar
CDUVDU20950 | Completed | UT Gauging | 10/04/2023 17:56:42 | 10/04/2023 17:56:48 | 11/04/2023 10:30:00 | 11/04/2023 22:30:00 | 01-WG-00-004A | VESSEL | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  | 12:00 | 11-Apr | 11-Apr | 10-Apr | 10-Apr
CDUVDU21480 | Completed | Removal of Internals | 06/04/2023 17:11:47 | 06/04/2023 17:11:53 | 11/04/2023 14:30:00 | 12/04/2023 14:30:00 | 01-WG-00-004A | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 11-Apr | 12-Apr | 06-Apr | 06-Apr
CDUVDU23750 | Completed | Internal cleaning | 06/04/2023 17:12:06 | 06/04/2023 17:12:12 | 12/04/2023 14:30:00 | 15/04/2023 02:30:00 | 01-WG-00-004A | VESSEL | 100 | MECHANICAL | CLEANING |  | 60 | 60:00 | 0:00 |  | 60:00 | 12-Apr | 15-Apr | 06-Apr | 06-Apr
CDUVDU27100 | Completed | Post cleaning inspection | 28/03/2023 14:34:23 | 28/03/2023 14:34:23 | 15/04/2023 02:30:00 | 15/04/2023 06:30:00 | 01-WG-00-004A | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:00 |  |  | 15-Apr | 15-Apr | 28-Mar | 28-Mar
CDUVDU27250 | Completed | Installation of Internals | 06/04/2023 17:12:21 | 06/04/2023 17:12:30 | 15/04/2023 06:30:00 | 16/04/2023 06:30:00 | 01-WG-00-004A | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 15-Apr | 16-Apr | 06-Apr | 06-Apr
CDUVDU28060 | Completed | Box up of manhole cover | 06/04/2023 17:12:38 | 06/04/2023 17:12:43 | 16/04/2023 06:30:00 | 16/04/2023 10:30:00 | 01-WG-00-004A | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  | 4:00 | 16-Apr | 16-Apr | 06-Apr | 06-Apr
CDUVDU28240 | Completed | Deblinding | 06/04/2023 17:12:54 | 06/04/2023 17:13:02 | 16/04/2023 10:30:00 | 17/04/2023 10:30:00 | 01-WG-00-004A | VESSEL | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  | 24:00 | 16-Apr | 17-Apr | 06-Apr | 06-Apr
CDUVDU11870 | Completed | Post cleaning inspection | 12/04/2023 12:22:12 | 12/04/2023 12:22:18 | 06/04/2023 18:30:00 | 06/04/2023 22:30:00 | 01-VV-004 | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:00 |  | 4:00 | 06-Apr | 06-Apr | 12-Apr | 12-Apr
CDUVDU12100 | Completed | Repair if any | 15/04/2023 17:12:28 | 15/04/2023 17:12:33 | 06/04/2023 22:30:00 | 09/04/2023 10:30:00 | 01-VV-004 | VESSEL | 100 | MECHANICAL | REPAIR |  | 60 | 60:00 | 0:00 |  | 60:00 | 06-Apr | 09-Apr | 15-Apr | 15-Apr
CDUVDU16300 | Completed | Carry Out Inspection | 15/04/2023 17:13:00 | 15/04/2023 17:13:05 | 09/04/2023 10:30:00 | 09/04/2023 14:30:00 | 01-VV-004 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 09-Apr | 09-Apr | 15-Apr | 15-Apr
CDUVDU16670 | Completed | Installation of Internals | 17/04/2023 12:02:02 | 17/04/2023 12:12:49 | 09/04/2023 14:30:00 | 10/04/2023 14:30:00 | 01-VV-004 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:11 |  | 23:49 | 09-Apr | 10-Apr | 17-Apr | 17-Apr
CDUVDU18990 | Completed | Box up of manhole cover | 19/04/2023 19:22:41 | 19/04/2023 19:22:47 | 10/04/2023 14:30:00 | 10/04/2023 18:30:00 | 01-VV-004 | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  | 4:00 | 10-Apr | 10-Apr | 19-Apr | 19-Apr
CDUVDU19370 | Completed | Deblinding | 19/04/2023 19:22:56 | 23/04/2023 18:52:17 | 10/04/2023 18:30:00 | 11/04/2023 18:30:00 | 01-VV-004 | VESSEL | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 95:29 | 71:29 |  | 10-Apr | 11-Apr | 19-Apr | 23-Apr
CDUVDU1990 | Completed | Blinding | 30/03/2023 05:22:19 | 30/03/2023 05:22:19 | 31/03/2023 14:30:00 | 01/04/2023 14:30:00 | 01-VV-004 | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 24 | 24:00 | 0:00 |  |  | 31-Mar | 01-Apr | 30-Mar | 30-Mar
CDUVDU3070 | Completed | Opening of manhole cover | 30/03/2023 05:22:19 | 30/03/2023 05:22:19 | 01/04/2023 14:30:00 | 01/04/2023 22:30:00 | 01-VV-004 | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  |  | 01-Apr | 01-Apr | 30-Mar | 30-Mar
CDUVDU4080 | Completed | Manentry | 30/03/2023 05:22:19 | 30/03/2023 05:22:19 | 01/04/2023 22:30:00 | 02/04/2023 02:30:00 | 01-VV-004 | VESSEL | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  |  | 01-Apr | 02-Apr | 30-Mar | 30-Mar
CDUVDU4090 | Completed | UT Gauging | 30/03/2023 05:22:19 | 30/03/2023 05:22:19 | 01/04/2023 22:30:00 | 02/04/2023 10:30:00 | 01-VV-004 | VESSEL | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  |  | 01-Apr | 02-Apr | 30-Mar | 30-Mar
CDUVDU4510 | Completed | Pre-cleaning inspection | 30/03/2023 05:22:19 | 30/03/2023 05:22:19 | 02/04/2023 02:30:00 | 02/04/2023 06:30:00 | 01-VV-004 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  |  | 02-Apr | 02-Apr | 30-Mar | 30-Mar
CDUVDU4620 | Completed | Removal of Internals | 12/04/2023 12:21:28 | 12/04/2023 12:21:34 | 02/04/2023 06:30:00 | 03/04/2023 06:30:00 | 01-VV-004 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 02-Apr | 03-Apr | 12-Apr | 12-Apr
CDUVDU6880 | Completed | Internal cleaning | 12/04/2023 12:21:49 | 12/04/2023 12:21:56 | 03/04/2023 06:30:00 | 06/04/2023 18:30:00 | 01-VV-004 | VESSEL | 100 | MECHANICAL | CLEANING |  | 84 | 84:00 | 0:00 |  | 84:00 | 03-Apr | 06-Apr | 12-Apr | 12-Apr
CDUVDU20290 | Completed | Blinding | 27/03/2023 09:25:53 | 06/04/2023 17:09:00 | 11/04/2023 02:30:00 | 11/04/2023 14:30:00 | 01-WG-00-004B | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 247:43 | 235:43 |  | 11-Apr | 11-Apr | 27-Mar | 06-Apr
CDUVDU21500 | Completed | Opening of handhole | 06/04/2023 17:09:19 | 06/04/2023 17:09:25 | 11/04/2023 14:30:00 | 11/04/2023 22:30:00 | 01-WG-00-004B | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  | 8:00 | 11-Apr | 11-Apr | 06-Apr | 06-Apr
CDUVDU22230 | Completed | Pre-cleaning inspection | 28/03/2023 14:35:32 | 28/03/2023 14:35:32 | 11/04/2023 22:30:00 | 12/04/2023 02:30:00 | 01-WG-00-004B | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  |  | 11-Apr | 12-Apr | 28-Mar | 28-Mar
CDUVDU22240 | Completed | UT Gauging | 06/04/2023 17:09:40 | 06/04/2023 17:09:44 | 11/04/2023 22:30:00 | 12/04/2023 10:30:00 | 01-WG-00-004B | VESSEL | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  | 12:00 | 11-Apr | 12-Apr | 06-Apr | 06-Apr
CDUVDU22590 | Completed | Removal of Internals | 06/04/2023 17:09:51 | 06/04/2023 17:10:00 | 12/04/2023 02:30:00 | 13/04/2023 02:30:00 | 01-WG-00-004B | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 12-Apr | 13-Apr | 06-Apr | 06-Apr
CDUVDU24690 | Completed | Internal cleaning | 06/04/2023 17:10:13 | 06/04/2023 17:10:23 | 13/04/2023 02:30:00 | 15/04/2023 14:30:00 | 01-WG-00-004B | VESSEL | 100 | MECHANICAL | CLEANING |  | 60 | 60:00 | 0:00 |  | 60:00 | 13-Apr | 15-Apr | 06-Apr | 06-Apr
CDUVDU27570 | Completed | Post cleaning inspection | 28/03/2023 14:35:32 | 28/03/2023 14:35:32 | 15/04/2023 14:30:00 | 15/04/2023 18:30:00 | 01-WG-00-004B | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:00 |  |  | 15-Apr | 15-Apr | 28-Mar | 28-Mar
CDUVDU27700 | Completed | Installation of Internals | 06/04/2023 17:10:31 | 06/04/2023 17:10:35 | 15/04/2023 18:30:00 | 16/04/2023 18:30:00 | 01-WG-00-004B | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 15-Apr | 16-Apr | 06-Apr | 06-Apr
CDUVDU28460 | Completed | Box up of manhole cover | 06/04/2023 17:10:45 | 06/04/2023 17:10:51 | 16/04/2023 18:30:00 | 16/04/2023 22:30:00 | 01-WG-00-004B | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  | 4:00 | 16-Apr | 16-Apr | 06-Apr | 06-Apr
CDUVDU28590 | Completed | Deblinding | 06/04/2023 17:10:59 | 06/04/2023 17:11:05 | 16/04/2023 22:30:00 | 17/04/2023 22:30:00 | 01-WG-00-004B | VESSEL | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  | 24:00 | 16-Apr | 17-Apr | 06-Apr | 06-Apr
CDUVDU19030 | Completed | Blinding | 27/03/2023 09:23:22 | 06/04/2023 17:13:19 | 10/04/2023 14:30:00 | 11/04/2023 02:30:00 | 01-WG-00-005A | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 247:50 | 235:50 |  | 10-Apr | 11-Apr | 27-Mar | 06-Apr
CDUVDU20280 | Completed | Opening of handhole | 06/04/2023 17:13:39 | 06/04/2023 17:13:45 | 11/04/2023 02:30:00 | 11/04/2023 10:30:00 | 01-WG-00-005A | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  | 8:00 | 11-Apr | 11-Apr | 06-Apr | 06-Apr
CDUVDU20960 | Completed | Pre-cleaning inspection | 06/04/2023 17:14:02 | 06/04/2023 17:14:06 | 11/04/2023 10:30:00 | 11/04/2023 14:30:00 | 01-WG-00-005A | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 11-Apr | 11-Apr | 06-Apr | 06-Apr
CDUVDU20970 | Completed | UT Gauging | 10/04/2023 17:57:09 | 10/04/2023 17:57:13 | 11/04/2023 10:30:00 | 11/04/2023 22:30:00 | 01-WG-00-005A | VESSEL | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  | 12:00 | 11-Apr | 11-Apr | 10-Apr | 10-Apr
CDUVDU21490 | Completed | Removal of Internals | 06/04/2023 17:14:15 | 06/04/2023 17:14:21 | 11/04/2023 14:30:00 | 12/04/2023 14:30:00 | 01-WG-00-005A | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 11-Apr | 12-Apr | 06-Apr | 06-Apr
CDUVDU23760 | Completed | Internal cleaning | 06/04/2023 17:14:32 | 06/04/2023 17:14:40 | 12/04/2023 14:30:00 | 15/04/2023 02:30:00 | 01-WG-00-005A | VESSEL | 100 | MECHANICAL | CLEANING |  | 60 | 60:00 | 0:00 |  | 60:00 | 12-Apr | 15-Apr | 06-Apr | 06-Apr
CDUVDU27110 | Completed | Post cleaning inspection | 06/04/2023 17:14:53 | 06/04/2023 17:14:58 | 15/04/2023 02:30:00 | 15/04/2023 06:30:00 | 01-WG-00-005A | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:00 |  | 4:00 | 15-Apr | 15-Apr | 06-Apr | 06-Apr
CDUVDU27260 | Completed | Installation of Internals | 06/04/2023 17:15:14 | 06/04/2023 17:15:19 | 15/04/2023 06:30:00 | 16/04/2023 06:30:00 | 01-WG-00-005A | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 15-Apr | 16-Apr | 06-Apr | 06-Apr
CDUVDU28070 | Completed | Box up of manhole cover | 06/04/2023 17:15:06 | 06/04/2023 17:15:26 | 16/04/2023 06:30:00 | 16/04/2023 10:30:00 | 01-WG-00-005A | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  | 4:00 | 16-Apr | 16-Apr | 06-Apr | 06-Apr
CDUVDU28250 | Completed | Deblinding | 06/04/2023 17:15:38 | 06/04/2023 17:15:45 | 16/04/2023 10:30:00 | 17/04/2023 10:30:00 | 01-WG-00-005A | VESSEL | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  | 24:00 | 16-Apr | 17-Apr | 06-Apr | 06-Apr
CDUVDU20300 | Completed | Blinding | 11/04/2023 12:21:03 | 11/04/2023 12:21:08 | 11/04/2023 02:30:00 | 11/04/2023 14:30:00 | 01-WG-00-005B | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 11-Apr | 11-Apr | 11-Apr | 11-Apr
CDUVDU21510 | Completed | Opening of handhole | 17/04/2023 12:11:35 | 17/04/2023 16:48:46 | 11/04/2023 14:30:00 | 11/04/2023 22:30:00 | 01-WG-00-005B | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 4:37 |  | 3:23 | 11-Apr | 11-Apr | 17-Apr | 17-Apr
CDUVDU22250 | Completed | Pre-cleaning inspection | 17/04/2023 19:36:11 | 17/04/2023 19:36:15 | 11/04/2023 22:30:00 | 12/04/2023 02:30:00 | 01-WG-00-005B | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 11-Apr | 12-Apr | 17-Apr | 17-Apr
CDUVDU22260 | Completed | UT Gauging | 16/04/2023 11:08:07 | 16/04/2023 11:08:15 | 11/04/2023 22:30:00 | 12/04/2023 10:30:00 | 01-WG-00-005B | VESSEL | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  | 12:00 | 11-Apr | 12-Apr | 16-Apr | 16-Apr
CDUVDU22600 | Completed | Removal of Internals | 18/04/2023 17:41:06 | 18/04/2023 17:41:10 | 12/04/2023 02:30:00 | 13/04/2023 02:30:00 | 01-WG-00-005B | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 12-Apr | 13-Apr | 18-Apr | 18-Apr
CDUVDU24700 | Completed | Internal cleaning | 18/04/2023 17:41:22 | 19/04/2023 09:24:35 | 13/04/2023 02:30:00 | 15/04/2023 14:30:00 | 01-WG-00-005B | VESSEL | 100 | MECHANICAL | CLEANING |  | 60 | 60:00 | 15:43 |  | 44:17 | 13-Apr | 15-Apr | 18-Apr | 19-Apr
CDUVDU27580 | Completed | Post cleaning inspection | 20/04/2023 14:26:32 | 23/04/2023 11:07:21 | 15/04/2023 14:30:00 | 15/04/2023 18:30:00 | 01-WG-00-005B | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 68:41 | 64:41 |  | 15-Apr | 15-Apr | 20-Apr | 23-Apr
CDUVDU27710 | Completed | Installation of Internals | 20/04/2023 14:26:53 | 23/04/2023 11:07:21 | 15/04/2023 18:30:00 | 16/04/2023 18:30:00 | 01-WG-00-005B | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 68:40 | 44:40 |  | 15-Apr | 16-Apr | 20-Apr | 23-Apr
CDUVDU28470 | Completed | Box up of manhole cover | 23/04/2023 11:07:21 | 23/04/2023 11:07:21 | 16/04/2023 18:30:00 | 16/04/2023 22:30:00 | 01-WG-00-005B | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  |  | 16-Apr | 16-Apr | 23-Apr | 23-Apr
CDUVDU28600 | Completed | Deblinding | 23/04/2023 11:07:21 | 23/04/2023 11:07:21 | 16/04/2023 22:30:00 | 17/04/2023 22:30:00 | 01-WG-00-005B | VESSEL | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  |  | 16-Apr | 17-Apr | 23-Apr | 23-Apr
CDUVDU21520 | Completed | Blinding | 29/03/2023 19:44:56 | 29/03/2023 19:44:59 | 11/04/2023 14:30:00 | 12/04/2023 02:30:00 | 01-WG-00-006A | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 11-Apr | 12-Apr | 29-Mar | 29-Mar
CDUVDU22610 | Completed | Opening of handhole | 29/03/2023 19:44:28 | 29/03/2023 19:44:38 | 12/04/2023 02:30:00 | 12/04/2023 10:30:00 | 01-WG-00-006A | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  | 8:00 | 12-Apr | 12-Apr | 29-Mar | 29-Mar
CDUVDU23350 | Completed | Pre-cleaning inspection | 28/03/2023 14:37:19 | 28/03/2023 14:37:19 | 12/04/2023 10:30:00 | 12/04/2023 14:30:00 | 01-WG-00-006A | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  |  | 12-Apr | 12-Apr | 28-Mar | 28-Mar
CDUVDU23360 | Completed | UT Gauging | 29/03/2023 19:46:08 | 29/03/2023 19:46:08 | 12/04/2023 10:30:00 | 12/04/2023 22:30:00 | 01-WG-00-006A | VESSEL | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  |  | 12-Apr | 12-Apr | 29-Mar | 29-Mar
CDUVDU23770 | Completed | Removal of Internals | 29/03/2023 19:42:17 | 29/03/2023 19:42:29 | 12/04/2023 14:30:00 | 13/04/2023 14:30:00 | 01-WG-00-006A | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 12-Apr | 13-Apr | 29-Mar | 29-Mar
CDUVDU25430 | Completed | Internal cleaning | 29/03/2023 19:42:00 | 29/03/2023 19:42:04 | 13/04/2023 14:30:00 | 16/04/2023 02:30:00 | 01-WG-00-006A | VESSEL | 100 | MECHANICAL | CLEANING |  | 60 | 60:00 | 0:00 |  | 60:00 | 13-Apr | 16-Apr | 29-Mar | 29-Mar
CDUVDU27940 | Completed | Post cleaning inspection | 28/03/2023 14:37:19 | 28/03/2023 14:37:19 | 16/04/2023 02:30:00 | 16/04/2023 06:30:00 | 01-WG-00-006A | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:00 |  |  | 16-Apr | 16-Apr | 28-Mar | 28-Mar
CDUVDU28080 | Completed | Installation of Internals | 12/04/2023 12:25:46 | 12/04/2023 12:25:51 | 16/04/2023 06:30:00 | 17/04/2023 06:30:00 | 01-WG-00-006A | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 16-Apr | 17-Apr | 12-Apr | 12-Apr
CDUVDU28790 | Completed | Box up of manhole cover | 12/04/2023 12:26:09 | 12/04/2023 12:26:17 | 17/04/2023 06:30:00 | 17/04/2023 10:30:00 | 01-WG-00-006A | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  | 4:00 | 17-Apr | 17-Apr | 12-Apr | 12-Apr
CDUVDU28860 | Completed | Deblinding | 20/04/2023 09:10:23 | 20/04/2023 09:10:36 | 17/04/2023 10:30:00 | 18/04/2023 10:30:00 | 01-WG-00-006A | VESSEL | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  | 24:00 | 17-Apr | 18-Apr | 20-Apr | 20-Apr
CDUVDU23780 | Completed | Blinding | 08/04/2023 16:21:33 | 08/04/2023 16:21:38 | 12/04/2023 14:30:00 | 13/04/2023 02:30:00 | 01-WG-00-007A | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 12-Apr | 13-Apr | 08-Apr | 08-Apr
CDUVDU24710 | Completed | Opening of handhole | 08/04/2023 16:21:47 | 08/04/2023 16:21:52 | 13/04/2023 02:30:00 | 13/04/2023 10:30:00 | 01-WG-00-007A | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  | 8:00 | 13-Apr | 13-Apr | 08-Apr | 08-Apr
CDUVDU25250 | Completed | Pre-cleaning inspection | 08/04/2023 16:22:09 | 08/04/2023 16:22:15 | 13/04/2023 10:30:00 | 13/04/2023 14:30:00 | 01-WG-00-007A | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 13-Apr | 13-Apr | 08-Apr | 08-Apr
CDUVDU25260 | Completed | UT Gauging | 08/04/2023 16:22:50 | 08/04/2023 16:22:54 | 13/04/2023 10:30:00 | 13/04/2023 22:30:00 | 01-WG-00-007A | VESSEL | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  | 12:00 | 13-Apr | 13-Apr | 08-Apr | 08-Apr
CDUVDU25440 | Completed | Removal of Internals | 08/04/2023 16:23:11 | 08/04/2023 16:23:16 | 13/04/2023 14:30:00 | 14/04/2023 14:30:00 | 01-WG-00-007A | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 13-Apr | 14-Apr | 08-Apr | 08-Apr
CDUVDU26620 | Completed | Internal cleaning | 08/04/2023 16:23:25 | 08/04/2023 16:23:35 | 14/04/2023 14:30:00 | 17/04/2023 02:30:00 | 01-WG-00-007A | VESSEL | 100 | MECHANICAL | CLEANING |  | 60 | 60:00 | 0:00 |  | 60:00 | 14-Apr | 17-Apr | 08-Apr | 08-Apr
CDUVDU28690 | Completed | Post cleaning inspection | 08/04/2023 16:24:05 | 08/04/2023 16:24:10 | 17/04/2023 02:30:00 | 17/04/2023 06:30:00 | 01-WG-00-007A | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:00 |  | 4:00 | 17-Apr | 17-Apr | 08-Apr | 08-Apr
CDUVDU28800 | Completed | Installation of Internals | 08/04/2023 16:24:22 | 08/04/2023 16:24:27 | 17/04/2023 06:30:00 | 18/04/2023 06:30:00 | 01-WG-00-007A | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 17-Apr | 18-Apr | 08-Apr | 08-Apr
CDUVDU29330 | Completed | Box up of manhole cover | 08/04/2023 16:24:45 | 08/04/2023 16:24:52 | 18/04/2023 06:30:00 | 18/04/2023 10:30:00 | 01-WG-00-007A | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  | 4:00 | 18-Apr | 18-Apr | 08-Apr | 08-Apr
CDUVDU29380 | Completed | Deblinding | 20/04/2023 09:25:27 | 20/04/2023 09:25:27 | 18/04/2023 10:30:00 | 19/04/2023 10:30:00 | 01-WG-00-007A | VESSEL | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  |  | 18-Apr | 19-Apr | 20-Apr | 20-Apr
CDUVDU26080 | Completed | Blinding | 27/03/2023 09:21:56 | 30/03/2023 05:24:26 | 14/04/2023 02:30:00 | 14/04/2023 14:30:00 | 01-WG-00-008B | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 68:03 | 56:03 |  | 14-Apr | 14-Apr | 27-Mar | 30-Mar
CDUVDU26630 | Completed | Opening of manhole cover | 30/03/2023 05:24:26 | 30/03/2023 05:24:26 | 14/04/2023 14:30:00 | 14/04/2023 22:30:00 | 01-WG-00-008B | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  |  | 14-Apr | 14-Apr | 30-Mar | 30-Mar
CDUVDU26990 | Completed | Pre-cleaning inspection | 30/03/2023 05:24:26 | 30/03/2023 05:24:26 | 14/04/2023 22:30:00 | 15/04/2023 02:30:00 | 01-WG-00-008B | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  |  | 14-Apr | 15-Apr | 30-Mar | 30-Mar
CDUVDU27000 | Completed | UT Gauging | 10/04/2023 17:51:15 | 10/04/2023 17:51:19 | 14/04/2023 22:30:00 | 15/04/2023 10:30:00 | 01-WG-00-008B | VESSEL | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  | 12:00 | 14-Apr | 15-Apr | 10-Apr | 10-Apr
CDUVDU27120 | Completed | Removal of Internals | 06/04/2023 17:18:42 | 06/04/2023 17:18:46 | 15/04/2023 02:30:00 | 16/04/2023 02:30:00 | 01-WG-00-008B | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 15-Apr | 16-Apr | 06-Apr | 06-Apr
CDUVDU27950 | Completed | Internal cleaning | 06/04/2023 17:19:00 | 06/04/2023 17:19:06 | 16/04/2023 02:30:00 | 18/04/2023 14:30:00 | 01-WG-00-008B | VESSEL | 100 | MECHANICAL | CLEANING |  | 60 | 60:00 | 0:00 |  | 60:00 | 16-Apr | 18-Apr | 06-Apr | 06-Apr
CDUVDU29440 | Completed | Post cleaning inspection | 28/03/2023 14:34:46 | 28/03/2023 14:34:46 | 18/04/2023 14:30:00 | 18/04/2023 18:30:00 | 01-WG-00-008B | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:00 |  |  | 18-Apr | 18-Apr | 28-Mar | 28-Mar
CDUVDU29530 | Completed | Installation of Internals | 06/04/2023 17:19:16 | 06/04/2023 17:19:24 | 18/04/2023 18:30:00 | 19/04/2023 18:30:00 | 01-WG-00-008B | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 18-Apr | 19-Apr | 06-Apr | 06-Apr
CDUVDU29890 | Completed | Box up of manhole cover | 06/04/2023 17:19:32 | 06/04/2023 17:19:37 | 19/04/2023 18:30:00 | 19/04/2023 22:30:00 | 01-WG-00-008B | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  | 4:00 | 19-Apr | 19-Apr | 06-Apr | 06-Apr
CDUVDU29950 | Completed | Deblinding | 06/04/2023 17:19:44 | 06/04/2023 17:19:51 | 19/04/2023 22:30:00 | 20/04/2023 22:30:00 | 01-WG-00-008B | VESSEL | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  | 24:00 | 19-Apr | 20-Apr | 06-Apr | 06-Apr
CDUVDU25450 | Completed | Blinding | 27/03/2023 09:19:07 | 30/03/2023 05:25:21 | 13/04/2023 14:30:00 | 14/04/2023 02:30:00 | 01-WG-00-008A | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 68:06 | 56:06 |  | 13-Apr | 14-Apr | 27-Mar | 30-Mar
CDUVDU26090 | Completed | Opening of manhole cover | 30/03/2023 05:25:21 | 30/03/2023 05:25:21 | 14/04/2023 02:30:00 | 14/04/2023 10:30:00 | 01-WG-00-008A | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  |  | 14-Apr | 14-Apr | 30-Mar | 30-Mar
CDUVDU26460 | Completed | Pre-cleaning inspection | 30/03/2023 05:25:21 | 30/03/2023 05:25:21 | 14/04/2023 10:30:00 | 14/04/2023 14:30:00 | 01-WG-00-008A | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  |  | 14-Apr | 14-Apr | 30-Mar | 30-Mar
CDUVDU26470 | Completed | UT Gauging | 09/04/2023 19:20:20 | 09/04/2023 19:20:24 | 14/04/2023 10:30:00 | 14/04/2023 22:30:00 | 01-WG-00-008A | VESSEL | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  | 12:00 | 14-Apr | 14-Apr | 09-Apr | 09-Apr
CDUVDU26640 | Completed | Removal of Internals | 06/04/2023 17:25:18 | 06/04/2023 17:25:25 | 14/04/2023 14:30:00 | 15/04/2023 14:30:00 | 01-WG-00-008A | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 14-Apr | 15-Apr | 06-Apr | 06-Apr
CDUVDU27590 | Completed | Internal cleaning | 06/04/2023 17:25:32 | 06/04/2023 17:25:48 | 15/04/2023 14:30:00 | 18/04/2023 02:30:00 | 01-WG-00-008A | VESSEL | 100 | MECHANICAL | CLEANING |  | 60 | 60:00 | 0:00 |  | 60:00 | 15-Apr | 18-Apr | 06-Apr | 06-Apr
CDUVDU29250 | Completed | Post cleaning inspection | 28/03/2023 14:33:51 | 28/03/2023 14:33:51 | 18/04/2023 02:30:00 | 18/04/2023 06:30:00 | 01-WG-00-008A | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:00 |  |  | 18-Apr | 18-Apr | 28-Mar | 28-Mar
CDUVDU29340 | Completed | Installation of Internals | 06/04/2023 17:25:56 | 06/04/2023 17:26:02 | 18/04/2023 06:30:00 | 19/04/2023 06:30:00 | 01-WG-00-008A | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 18-Apr | 19-Apr | 06-Apr | 06-Apr
CDUVDU29740 | Completed | Box up of manhole cover | 06/04/2023 17:26:10 | 06/04/2023 17:26:15 | 19/04/2023 06:30:00 | 19/04/2023 10:30:00 | 01-WG-00-008A | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  | 4:00 | 19-Apr | 19-Apr | 06-Apr | 06-Apr
CDUVDU29780 | Completed | Deblinding | 20/04/2023 09:11:02 | 20/04/2023 09:11:20 | 19/04/2023 10:30:00 | 20/04/2023 10:30:00 | 01-WG-00-008A | VESSEL | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  | 24:00 | 19-Apr | 20-Apr | 20-Apr | 20-Apr
CDUVDU10010 | Completed | Post cleaning inspection | 13/04/2023 19:33:28 | 15/04/2023 17:15:54 | 05/04/2023 12:00:00 | 05/04/2023 16:00:00 | 01-VV-005 | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 45:42 | 41:42 |  | 05-Apr | 05-Apr | 13-Apr | 15-Apr
CDUVDU10400 | Completed | Repair if any | 19/04/2023 10:05:38 | 19/04/2023 10:05:43 | 05/04/2023 16:00:00 | 09/04/2023 16:00:00 | 01-VV-005 | VESSEL | 100 | MECHANICAL | REPAIR |  | 96 | 96:00 | 0:00 |  | 96:00 | 05-Apr | 09-Apr | 19-Apr | 19-Apr
CDUVDU16800 | Completed | Carry Out Inspection | 19/04/2023 10:06:23 | 19/04/2023 10:06:29 | 09/04/2023 16:00:00 | 09/04/2023 20:00:00 | 01-VV-005 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 09-Apr | 09-Apr | 19-Apr | 19-Apr
CDUVDU17200 | Completed | Installation of Internals | 19/04/2023 10:06:36 | 19/04/2023 10:06:40 | 09/04/2023 20:00:00 | 10/04/2023 20:00:00 | 01-VV-005 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 09-Apr | 10-Apr | 19-Apr | 19-Apr
CDUVDU19480 | Completed | Box up of manhole cover | 19/04/2023 11:24:18 | 20/04/2023 09:21:35 | 10/04/2023 20:00:00 | 11/04/2023 00:00:00 | 01-VV-005 | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 21:57 | 17:57 |  | 10-Apr | 11-Apr | 19-Apr | 20-Apr
CDUVDU19980 | Completed | Deblinding | 20/04/2023 09:09:19 | 22/04/2023 12:00:05 | 11/04/2023 00:00:00 | 12/04/2023 00:00:00 | 01-VV-005 | VESSEL | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 50:51 | 26:51 |  | 11-Apr | 12-Apr | 20-Apr | 22-Apr
CDUVDU2320 | Completed | Blinding | 31/03/2023 11:05:21 | 04/04/2023 11:26:01 | 31/03/2023 16:30:00 | 01/04/2023 16:30:00 | 01-VV-005 | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 24 | 24:00 | 96:21 | 72:21 |  | 31-Mar | 01-Apr | 31-Mar | 04-Apr
CDUVDU3870 | Completed | Opening of manhole cover | 02/04/2023 10:08:32 | 03/04/2023 11:33:43 | 01/04/2023 16:30:00 | 02/04/2023 00:30:00 | 01-VV-005 | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 25:25 | 17:25 |  | 01-Apr | 02-Apr | 02-Apr | 03-Apr
CDUVDU4360 | Completed | Manentry | 04/04/2023 21:43:32 | 04/04/2023 21:43:32 | 02/04/2023 00:30:00 | 02/04/2023 04:30:00 | 01-VV-005 | VESSEL | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  |  | 02-Apr | 02-Apr | 04-Apr | 04-Apr
CDUVDU4370 | Completed | UT Gauging | 04/04/2023 21:43:32 | 04/04/2023 21:43:32 | 02/04/2023 00:30:00 | 02/04/2023 12:30:00 | 01-VV-005 | VESSEL | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  |  | 02-Apr | 02-Apr | 04-Apr | 04-Apr
CDUVDU4580 | Completed | Pre-cleaning inspection | 04/04/2023 21:43:32 | 04/04/2023 21:43:32 | 02/04/2023 04:30:00 | 02/04/2023 08:30:00 | 01-VV-005 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  |  | 02-Apr | 02-Apr | 04-Apr | 04-Apr
CDUVDU4880 | Completed | Removal of Internals | 13/04/2023 10:07:39 | 13/04/2023 10:07:45 | 02/04/2023 08:30:00 | 03/04/2023 08:30:00 | 01-VV-005 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 02-Apr | 03-Apr | 13-Apr | 13-Apr
CDUVDU8680 | Completed | Internal cleaning | 13/04/2023 10:07:56 | 15/04/2023 17:15:23 | 04/04/2023 12:00:00 | 05/04/2023 12:00:00 | 01-VV-005 | VESSEL | 100 | MECHANICAL | CLEANING |  | 24 | 24:00 | 55:07 | 31:07 |  | 04-Apr | 05-Apr | 13-Apr | 15-Apr
CDUVDU10020 | Completed | Post cleaning inspection | 11/04/2023 05:48:53 | 11/04/2023 05:48:57 | 05/04/2023 12:00:00 | 05/04/2023 16:00:00 | 01-VV-006 | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:00 |  | 4:00 | 05-Apr | 05-Apr | 11-Apr | 11-Apr
CDUVDU10410 | Completed | Repair if any | 17/04/2023 12:09:52 | 17/04/2023 12:12:21 | 05/04/2023 16:00:00 | 07/04/2023 16:00:00 | 01-VV-006 | VESSEL | 100 | MECHANICAL | REPAIR |  | 48 | 48:00 | 0:02 |  | 47:58 | 05-Apr | 07-Apr | 17-Apr | 17-Apr
CDUVDU13260 | Completed | Carry Out Inspection | 18/04/2023 14:52:18 | 18/04/2023 14:52:24 | 07/04/2023 16:00:00 | 07/04/2023 20:00:00 | 01-VV-006 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 07-Apr | 07-Apr | 18-Apr | 18-Apr
CDUVDU13500 | Completed | Installation of Internals | 18/04/2023 14:52:31 | 18/04/2023 14:52:39 | 07/04/2023 20:00:00 | 08/04/2023 20:00:00 | 01-VV-006 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 07-Apr | 08-Apr | 18-Apr | 18-Apr
CDUVDU15110 | Completed | Box up of manhole cover | 18/04/2023 14:53:14 | 18/04/2023 17:08:58 | 08/04/2023 20:00:00 | 09/04/2023 00:00:00 | 01-VV-006 | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 2:16 |  | 1:44 | 08-Apr | 09-Apr | 18-Apr | 18-Apr
CDUVDU15400 | Completed | Deblinding | 18/04/2023 17:36:38 | 19/04/2023 09:26:46 | 09/04/2023 00:00:00 | 10/04/2023 00:00:00 | 01-VV-006 | VESSEL | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 15:50 |  | 8:10 | 09-Apr | 10-Apr | 18-Apr | 19-Apr
CDUVDU2330 | Completed | Blinding | 31/03/2023 11:09:33 | 04/04/2023 11:26:21 | 31/03/2023 16:30:00 | 01/04/2023 16:30:00 | 01-VV-006 | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 24 | 24:00 | 96:17 | 72:17 |  | 31-Mar | 01-Apr | 31-Mar | 04-Apr
CDUVDU3880 | Completed | Opening of manhole cover | 01/04/2023 17:54:02 | 01/04/2023 19:17:40 | 01/04/2023 16:30:00 | 02/04/2023 00:30:00 | 01-VV-006 | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 1:24 |  | 6:36 | 01-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU4380 | Completed | Manentry | 09/04/2023 18:36:44 | 09/04/2023 18:36:50 | 02/04/2023 00:30:00 | 02/04/2023 04:30:00 | 01-VV-006 | VESSEL | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 02-Apr | 02-Apr | 09-Apr | 09-Apr
CDUVDU4390 | Completed | UT Gauging | 09/04/2023 18:37:36 | 09/04/2023 18:37:41 | 02/04/2023 00:30:00 | 02/04/2023 12:30:00 | 01-VV-006 | VESSEL | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  | 12:00 | 02-Apr | 02-Apr | 09-Apr | 09-Apr
CDUVDU4590 | Completed | Pre-cleaning inspection | 03/04/2023 12:14:00 | 03/04/2023 14:14:00 | 02/04/2023 04:30:00 | 02/04/2023 08:30:00 | 01-VV-006 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 2:00 |  | 2:00 | 02-Apr | 02-Apr | 03-Apr | 03-Apr
CDUVDU4890 | Completed | Removal of Internals | 09/04/2023 18:37:00 | 09/04/2023 18:37:05 | 02/04/2023 08:30:00 | 03/04/2023 08:30:00 | 01-VV-006 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 02-Apr | 03-Apr | 09-Apr | 09-Apr
CDUVDU8170 | Completed | Internal cleaning | 09/04/2023 18:37:13 | 11/04/2023 05:48:44 | 04/04/2023 00:00:00 | 05/04/2023 12:00:00 | 01-VV-006 | VESSEL | 100 | MECHANICAL | CLEANING |  | 36 | 36:00 | 35:12 |  | 0:48 | 04-Apr | 05-Apr | 09-Apr | 11-Apr
CDUVDU10030 | Completed | Internal cleaning | 09/04/2023 09:47:26 | 09/04/2023 09:47:31 | 05/04/2023 12:00:00 | 07/04/2023 00:00:00 | 01-VV-007 | VESSEL | 100 | MECHANICAL | CLEANING |  | 36 | 36:00 | 0:00 |  | 36:00 | 05-Apr | 07-Apr | 09-Apr | 09-Apr
CDUVDU12240 | Completed | Post cleaning inspection | 07/04/2023 22:34:17 | 07/04/2023 22:34:17 | 07/04/2023 00:00:00 | 07/04/2023 04:00:00 | 01-VV-007 | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:00 |  |  | 07-Apr | 07-Apr | 07-Apr | 07-Apr
CDUVDU12540 | Completed | Repair if any | 09/04/2023 09:47:39 | 09/04/2023 09:47:44 | 07/04/2023 04:00:00 | 09/04/2023 04:00:00 | 01-VV-007 | VESSEL | 100 | MECHANICAL | REPAIR |  | 48 | 48:00 | 0:00 |  | 48:00 | 07-Apr | 09-Apr | 09-Apr | 09-Apr
CDUVDU15840 | Completed | Carry Out Inspection | 09/04/2023 09:48:02 | 09/04/2023 09:48:06 | 09/04/2023 04:00:00 | 09/04/2023 08:00:00 | 01-VV-007 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 09-Apr | 09-Apr | 09-Apr | 09-Apr
CDUVDU16060 | Completed | Installation of Internals | 09/04/2023 09:48:22 | 09/04/2023 09:48:33 | 09/04/2023 08:00:00 | 10/04/2023 08:00:00 | 01-VV-007 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 09-Apr | 10-Apr | 09-Apr | 09-Apr
CDUVDU18420 | Completed | Box up of manhole cover | 09/04/2023 09:48:43 | 09/04/2023 09:49:08 | 10/04/2023 08:00:00 | 10/04/2023 12:00:00 | 01-VV-007 | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  | 4:00 | 10-Apr | 10-Apr | 09-Apr | 09-Apr
CDUVDU18740 | Completed | Deblinding | 09/04/2023 10:47:47 | 09/04/2023 10:47:52 | 10/04/2023 12:00:00 | 11/04/2023 12:00:00 | 01-VV-007 | VESSEL | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  | 24:00 | 10-Apr | 11-Apr | 09-Apr | 09-Apr
CDUVDU2340 | Completed | Blinding | 30/03/2023 10:24:41 | 30/03/2023 14:45:45 | 31/03/2023 16:30:00 | 01/04/2023 16:30:00 | 01-VV-007 | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 24 | 24:00 | 4:21 |  | 19:39 | 31-Mar | 01-Apr | 30-Mar | 30-Mar
CDUVDU3890 | Completed | Opening of manhole cover | 01/04/2023 12:07:12 | 01/04/2023 12:07:29 | 01/04/2023 16:30:00 | 02/04/2023 00:30:00 | 01-VV-007 | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  | 8:00 | 01-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU4400 | Completed | Manentry | 09/04/2023 09:46:07 | 09/04/2023 09:46:29 | 02/04/2023 00:30:00 | 02/04/2023 04:30:00 | 01-VV-007 | VESSEL | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 02-Apr | 02-Apr | 09-Apr | 09-Apr
CDUVDU4410 | Completed | UT Gauging | 09/04/2023 09:46:55 | 09/04/2023 09:47:01 | 02/04/2023 00:30:00 | 02/04/2023 12:30:00 | 01-VV-007 | VESSEL | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  | 12:00 | 02-Apr | 02-Apr | 09-Apr | 09-Apr
CDUVDU4600 | Completed | Pre-cleaning inspection | 01/04/2023 16:52:13 | 01/04/2023 18:41:54 | 02/04/2023 04:30:00 | 02/04/2023 08:30:00 | 01-VV-007 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 1:50 |  | 2:10 | 02-Apr | 02-Apr | 01-Apr | 01-Apr
CDUVDU4900 | Completed | Removal of Internals | 09/04/2023 09:47:11 | 09/04/2023 09:47:17 | 02/04/2023 08:30:00 | 03/04/2023 08:30:00 | 01-VV-007 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 02-Apr | 03-Apr | 09-Apr | 09-Apr
CDUVDU10040 | Completed | Internal cleaning | 30/03/2023 05:26:56 | 30/03/2023 05:26:56 | 05/04/2023 12:00:00 | 06/04/2023 12:00:00 | 01-VV-008 | VESSEL | 100 | MECHANICAL | CLEANING |  | 24 | 24:00 | 0:00 |  |  | 05-Apr | 06-Apr | 30-Mar | 30-Mar
CDUVDU11360 | Completed | Post cleaning inspection | 30/03/2023 05:26:56 | 30/03/2023 05:26:56 | 06/04/2023 12:00:00 | 06/04/2023 16:00:00 | 01-VV-008 | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:00 |  |  | 06-Apr | 06-Apr | 30-Mar | 30-Mar
CDUVDU11680 | Completed | Repair if any | 13/04/2023 19:36:05 | 13/04/2023 19:36:09 | 06/04/2023 16:00:00 | 08/04/2023 16:00:00 | 01-VV-008 | VESSEL | 100 | MECHANICAL | REPAIR |  | 48 | 48:00 | 0:00 |  | 48:00 | 06-Apr | 08-Apr | 13-Apr | 13-Apr
CDUVDU14910 | Completed | Carry Out Inspection | 13/04/2023 19:36:22 | 13/04/2023 19:36:27 | 08/04/2023 16:00:00 | 08/04/2023 20:00:00 | 01-VV-008 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 08-Apr | 08-Apr | 13-Apr | 13-Apr
CDUVDU15120 | Completed | Installation of Internals | 13/04/2023 19:36:34 | 13/04/2023 19:36:38 | 08/04/2023 20:00:00 | 09/04/2023 20:00:00 | 01-VV-008 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 08-Apr | 09-Apr | 13-Apr | 13-Apr
CDUVDU17210 | Completed | Box up of manhole cover | 13/04/2023 19:36:46 | 13/04/2023 19:36:50 | 09/04/2023 20:00:00 | 10/04/2023 00:00:00 | 01-VV-008 | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  | 4:00 | 09-Apr | 10-Apr | 13-Apr | 13-Apr
CDUVDU17560 | Completed | Deblinding | 17/04/2023 17:41:07 | 17/04/2023 17:41:12 | 10/04/2023 00:00:00 | 11/04/2023 00:00:00 | 01-VV-008 | VESSEL | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  | 24:00 | 10-Apr | 11-Apr | 17-Apr | 17-Apr
CDUVDU3810 | Completed | Blinding | 28/03/2023 05:46:32 | 28/03/2023 05:46:52 | 01/04/2023 16:30:00 | 02/04/2023 16:30:00 | 01-VV-008 | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 24 | 24:00 | 0:00 |  | 24:00 | 01-Apr | 02-Apr | 28-Mar | 28-Mar
CDUVDU6150 | Completed | Opening of manhole cover | 28/03/2023 05:46:32 | 28/03/2023 05:46:52 | 02/04/2023 16:30:00 | 03/04/2023 00:30:00 | 01-VV-008 | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  | 8:00 | 02-Apr | 03-Apr | 28-Mar | 28-Mar
CDUVDU6620 | Completed | Manentry | 28/03/2023 05:46:32 | 28/03/2023 05:46:52 | 03/04/2023 00:30:00 | 03/04/2023 04:30:00 | 01-VV-008 | VESSEL | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 03-Apr | 03-Apr | 28-Mar | 28-Mar
CDUVDU6630 | Completed | UT Gauging | 28/03/2023 05:46:32 | 28/03/2023 05:46:52 | 03/04/2023 00:30:00 | 03/04/2023 12:30:00 | 01-VV-008 | VESSEL | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  | 12:00 | 03-Apr | 03-Apr | 28-Mar | 28-Mar
CDUVDU6800 | Completed | Pre-cleaning inspection | 28/03/2023 05:46:32 | 28/03/2023 05:46:52 | 03/04/2023 04:30:00 | 03/04/2023 08:30:00 | 01-VV-008 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 03-Apr | 03-Apr | 28-Mar | 28-Mar
CDUVDU7090 | Completed | Removal of Internals | 30/03/2023 05:26:56 | 30/03/2023 05:26:56 | 03/04/2023 08:30:00 | 04/04/2023 08:30:00 | 01-VV-008 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  |  | 03-Apr | 04-Apr | 30-Mar | 30-Mar
CDUVDU12250 | Completed | Internal cleaning | 28/03/2023 05:43:18 | 28/03/2023 05:43:30 | 07/04/2023 00:00:00 | 09/04/2023 00:00:00 | 01-VV-009 | VESSEL | 100 | MECHANICAL | CLEANING |  | 48 | 48:00 | 0:00 |  | 48:00 | 07-Apr | 09-Apr | 28-Mar | 28-Mar
CDUVDU15410 | Completed | Post cleaning inspection | 28/03/2023 05:43:18 | 28/03/2023 05:43:30 | 09/04/2023 00:00:00 | 09/04/2023 04:00:00 | 01-VV-009 | VESSEL | 100 | INSPECTION | INSPECTION | INSPECTION | 4 | 4:00 | 0:00 |  | 4:00 | 09-Apr | 09-Apr | 28-Mar | 28-Mar
CDUVDU15850 | Completed | Repair if any | 11/04/2023 17:59:23 | 11/04/2023 17:59:27 | 09/04/2023 04:00:00 | 11/04/2023 04:00:00 | 01-VV-009 | VESSEL | 100 | MECHANICAL | REPAIR |  | 48 | 48:00 | 0:00 |  | 48:00 | 09-Apr | 11-Apr | 11-Apr | 11-Apr
CDUVDU1610 | Completed | Blinding | 28/03/2023 05:42:43 | 28/03/2023 05:42:52 | 30/03/2023 14:30:00 | 31/03/2023 14:30:00 | 01-VV-009 | VESSEL | 100 | MECHANICAL | BLINDING | BLINDING | 24 | 24:00 | 0:00 |  | 24:00 | 30-Mar | 31-Mar | 28-Mar | 28-Mar
CDUVDU2040 | Completed | Opening of manhole cover | 28/03/2023 05:42:43 | 28/03/2023 05:42:52 | 31/03/2023 14:30:00 | 31/03/2023 22:30:00 | 01-VV-009 | VESSEL | 100 | MECHANICAL | OPENING | OPENING | 8 | 8:00 | 0:00 |  | 8:00 | 31-Mar | 31-Mar | 28-Mar | 28-Mar
CDUVDU20440 | Completed | Carry Out Inspection | 11/04/2023 18:06:38 | 11/04/2023 18:06:42 | 11/04/2023 04:00:00 | 11/04/2023 08:00:00 | 01-VV-009 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 11-Apr | 11-Apr | 11-Apr | 11-Apr
CDUVDU20750 | Completed | Installation of Internals | 11/04/2023 18:06:51 | 11/04/2023 18:06:57 | 11/04/2023 08:00:00 | 12/04/2023 08:00:00 | 01-VV-009 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 11-Apr | 12-Apr | 11-Apr | 11-Apr
CDUVDU23180 | Completed | Box up of manhole cover | 12/04/2023 12:10:35 | 12/04/2023 12:10:40 | 12/04/2023 08:00:00 | 12/04/2023 12:00:00 | 01-VV-009 | VESSEL | 100 | MECHANICAL | BOX UP | BOX UP | 4 | 4:00 | 0:00 |  | 4:00 | 12-Apr | 12-Apr | 12-Apr | 12-Apr
CDUVDU23580 | Completed | Deblinding | 12/04/2023 17:49:39 | 12/04/2023 17:49:49 | 12/04/2023 12:00:00 | 13/04/2023 12:00:00 | 01-VV-009 | VESSEL | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  | 24:00 | 12-Apr | 13-Apr | 12-Apr | 12-Apr
CDUVDU2510 | Completed | Manentry | 28/03/2023 05:42:43 | 28/03/2023 05:42:52 | 31/03/2023 22:30:00 | 01/04/2023 02:30:00 | 01-VV-009 | VESSEL | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 31-Mar | 01-Apr | 28-Mar | 28-Mar
CDUVDU2520 | Completed | UT Gauging | 28/03/2023 05:42:43 | 28/03/2023 05:42:52 | 31/03/2023 22:30:00 | 01/04/2023 10:30:00 | 01-VV-009 | VESSEL | 100 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  | 12:00 | 31-Mar | 01-Apr | 28-Mar | 28-Mar
CDUVDU2660 | Completed | Pre-cleaning inspection | 28/03/2023 05:42:43 | 28/03/2023 05:42:52 | 01/04/2023 02:30:00 | 01/04/2023 06:30:00 | 01-VV-009 | VESSEL | 100 | INSPECTION |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 01-Apr | 01-Apr | 28-Mar | 28-Mar
CDUVDU2680 | Completed | Removal of Internals | 28/03/2023 05:43:18 | 28/03/2023 05:43:30 | 01/04/2023 06:30:00 | 02/04/2023 06:30:00 | 01-VV-009 | VESSEL | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 01-Apr | 02-Apr | 28-Mar | 28-Mar
CDUVDU11460 | Completed | Hydrotest | 04/04/2023 14:34:50 | 04/04/2023 14:34:59 | 06/04/2023 14:00:00 | 07/04/2023 10:00:00 | DESLATER TO PMP - (HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | HYDRO TEST | HYDRO TEST | 20 | 20:00 | 0:00 |  | 20:00 | 06-Apr | 07-Apr | 04-Apr | 04-Apr
CDUVDU12900 | Completed | Hydrotest Witness | 04/04/2023 14:35:21 | 04/04/2023 14:35:25 | 07/04/2023 10:00:00 | 07/04/2023 13:00:00 | DESLATER TO PMP - (HT-UL) | HYDRO TEST LOOPS | 100 | INSPECTION |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 07-Apr | 07-Apr | 04-Apr | 04-Apr
CDUVDU13050 | Completed | Drainning of water | 04/04/2023 14:35:38 | 04/04/2023 14:35:44 | 07/04/2023 13:00:00 | 07/04/2023 19:00:00 | DESLATER TO PMP - (HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 07-Apr | 07-Apr | 04-Apr | 04-Apr
CDUVDU13460 | Completed | Deblinding & handover to Operation. | 04/04/2023 14:35:58 | 04/04/2023 14:36:32 | 07/04/2023 19:00:00 | 08/04/2023 07:00:00 | DESLATER TO PMP - (HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:01 |  | 11:59 | 07-Apr | 08-Apr | 04-Apr | 04-Apr
CDUVDU9000 | Completed | Blinding | 01/04/2023 12:49:12 | 04/04/2023 14:36:23 | 04/04/2023 14:00:00 | 05/04/2023 02:00:00 | DESLATER TO PMP - (HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 73:47 | 61:47 |  | 04-Apr | 05-Apr | 01-Apr | 04-Apr
CDUVDU9530 | Completed | Water filling | 04/04/2023 14:34:10 | 04/04/2023 14:34:17 | 05/04/2023 02:00:00 | 06/04/2023 02:00:00 | DESLATER TO PMP - (HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 05-Apr | 06-Apr | 04-Apr | 04-Apr
CDUVDU9540 | Completed | Insulation removal if required | 04/04/2023 14:34:25 | 04/04/2023 14:34:32 | 05/04/2023 02:00:00 | 06/04/2023 14:00:00 | DESLATER TO PMP - (HT-UL) | HYDRO TEST LOOPS | 100 | CIVIL |  |  | 36 | 36:00 | 0:00 |  | 36:00 | 05-Apr | 06-Apr | 04-Apr | 04-Apr
CDUVDU16620 | Completed | Blinding | 01/04/2023 12:51:15 | 06/04/2023 13:46:29 | 09/04/2023 14:00:00 | 10/04/2023 02:00:00 | HVGO TO EE-101-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 120:55 | 108:55 |  | 09-Apr | 10-Apr | 01-Apr | 06-Apr
CDUVDU17750 | Completed | Water filling | 10/04/2023 17:38:17 | 10/04/2023 17:38:23 | 10/04/2023 02:00:00 | 10/04/2023 22:00:00 | HVGO TO EE-101-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 10-Apr | 10-Apr | 10-Apr | 10-Apr
CDUVDU19700 | Completed | Insulation removal if required | 10/04/2023 17:38:31 | 10/04/2023 17:38:36 | 10/04/2023 22:00:00 | 11/04/2023 18:00:00 | HVGO TO EE-101-(HT-UL) | HYDRO TEST LOOPS | 100 | CIVIL |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 10-Apr | 11-Apr | 10-Apr | 10-Apr
CDUVDU21940 | Completed | Hydrotest | 10/04/2023 17:38:44 | 10/04/2023 17:38:48 | 11/04/2023 18:00:00 | 12/04/2023 14:00:00 | HVGO TO EE-101-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | HYDRO TEST | HYDRO TEST | 20 | 20:00 | 0:00 |  | 20:00 | 11-Apr | 12-Apr | 10-Apr | 10-Apr
CDUVDU23680 | Completed | Hydrotest Witness | 10/04/2023 17:39:24 | 10/04/2023 17:39:28 | 12/04/2023 14:00:00 | 12/04/2023 17:00:00 | HVGO TO EE-101-(HT-UL) | HYDRO TEST LOOPS | 100 | INSPECTION |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 12-Apr | 12-Apr | 10-Apr | 10-Apr
CDUVDU23980 | Completed | Drainning of water | 10/04/2023 17:39:35 | 10/04/2023 17:39:39 | 12/04/2023 17:00:00 | 12/04/2023 23:00:00 | HVGO TO EE-101-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 12-Apr | 12-Apr | 10-Apr | 10-Apr
CDUVDU24480 | Completed | Deblinding & handover to Operation. | 10/04/2023 17:39:47 | 10/04/2023 17:39:53 | 12/04/2023 23:00:00 | 13/04/2023 11:00:00 | HVGO TO EE-101-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 12-Apr | 13-Apr | 10-Apr | 10-Apr
CDUVDU17760 | Completed | Blinding | 01/04/2023 17:17:02 | 04/04/2023 18:33:45 | 10/04/2023 02:00:00 | 10/04/2023 14:00:00 | PA-11 TO LVGO-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 73:17 | 61:17 |  | 10-Apr | 10-Apr | 01-Apr | 04-Apr
CDUVDU18930 | Completed | Water filling | 04/04/2023 18:33:59 | 04/04/2023 18:34:04 | 10/04/2023 14:00:00 | 11/04/2023 10:00:00 | PA-11 TO LVGO-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 10-Apr | 11-Apr | 04-Apr | 04-Apr
CDUVDU20910 | Completed | Insulation removal if required | 04/04/2023 18:34:12 | 04/04/2023 18:34:17 | 11/04/2023 10:00:00 | 12/04/2023 06:00:00 | PA-11 TO LVGO-(HT-UL) | HYDRO TEST LOOPS | 100 | CIVIL |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 11-Apr | 12-Apr | 04-Apr | 04-Apr
CDUVDU23030 | Completed | Hydrotest | 04/04/2023 18:34:25 | 04/04/2023 18:34:31 | 12/04/2023 06:00:00 | 13/04/2023 02:00:00 | PA-11 TO LVGO-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | HYDRO TEST | HYDRO TEST | 20 | 20:00 | 0:00 |  | 20:00 | 12-Apr | 13-Apr | 04-Apr | 04-Apr
CDUVDU24650 | Completed | Hydrotest Witness | 04/04/2023 18:34:45 | 04/04/2023 18:34:50 | 13/04/2023 02:00:00 | 13/04/2023 05:00:00 | PA-11 TO LVGO-(HT-UL) | HYDRO TEST LOOPS | 100 | INSPECTION |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 13-Apr | 13-Apr | 04-Apr | 04-Apr
CDUVDU24890 | Completed | Drainning of water | 04/04/2023 18:34:57 | 04/04/2023 18:35:50 | 13/04/2023 05:00:00 | 13/04/2023 11:00:00 | PA-11 TO LVGO-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:01 |  | 5:59 | 13-Apr | 13-Apr | 04-Apr | 04-Apr
CDUVDU25290 | Completed | Deblinding & handover to Operation. | 04/04/2023 18:35:27 | 04/04/2023 18:35:34 | 13/04/2023 11:00:00 | 13/04/2023 23:00:00 | PA-11 TO LVGO-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 13-Apr | 13-Apr | 04-Apr | 04-Apr
CDUVDU18940 | Completed | Blinding | 01/04/2023 17:17:53 | 04/04/2023 18:36:28 | 10/04/2023 14:00:00 | 11/04/2023 02:00:00 | PA-11 TO MVGO-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 73:19 | 61:19 |  | 10-Apr | 11-Apr | 01-Apr | 04-Apr
CDUVDU20190 | Completed | Water filling | 04/04/2023 14:45:18 | 04/04/2023 14:45:26 | 11/04/2023 02:00:00 | 11/04/2023 22:00:00 | PA-11 TO MVGO-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 11-Apr | 11-Apr | 04-Apr | 04-Apr
CDUVDU22200 | Completed | Insulation removal if required | 04/04/2023 18:36:15 | 04/04/2023 18:36:21 | 11/04/2023 22:00:00 | 12/04/2023 18:00:00 | PA-11 TO MVGO-(HT-UL) | HYDRO TEST LOOPS | 100 | CIVIL |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 11-Apr | 12-Apr | 04-Apr | 04-Apr
CDUVDU24080 | Completed | Hydrotest | 04/04/2023 18:36:37 | 04/04/2023 18:36:42 | 12/04/2023 18:00:00 | 13/04/2023 14:00:00 | PA-11 TO MVGO-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | HYDRO TEST | HYDRO TEST | 20 | 20:00 | 0:00 |  | 20:00 | 12-Apr | 13-Apr | 04-Apr | 04-Apr
CDUVDU25390 | Completed | Hydrotest Witness | 04/04/2023 18:37:12 | 04/04/2023 18:37:20 | 13/04/2023 14:00:00 | 13/04/2023 17:00:00 | PA-11 TO MVGO-(HT-UL) | HYDRO TEST LOOPS | 100 | INSPECTION |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 13-Apr | 13-Apr | 04-Apr | 04-Apr
CDUVDU25600 | Completed | Drainning of water | 04/04/2023 18:37:28 | 04/04/2023 18:37:33 | 13/04/2023 17:00:00 | 13/04/2023 23:00:00 | PA-11 TO MVGO-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 13-Apr | 13-Apr | 04-Apr | 04-Apr
CDUVDU25890 | Completed | Deblinding & handover to Operation. | 04/04/2023 18:37:42 | 04/04/2023 18:37:50 | 13/04/2023 23:00:00 | 14/04/2023 11:00:00 | PA-11 TO MVGO-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 13-Apr | 14-Apr | 04-Apr | 04-Apr
CDUVDU20180 | Completed | Blinding | 01/04/2023 17:18:21 | 04/04/2023 18:38:27 | 11/04/2023 02:00:00 | 11/04/2023 14:00:00 | PA-11 TO HVGO-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 73:20 | 61:20 |  | 11-Apr | 11-Apr | 01-Apr | 04-Apr
CDUVDU21390 | Completed | Water filling | 04/04/2023 14:40:53 | 04/04/2023 18:38:34 | 11/04/2023 14:00:00 | 12/04/2023 10:00:00 | PA-11 TO HVGO-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL |  |  | 20 | 20:00 | 3:58 |  | 16:02 | 11-Apr | 12-Apr | 04-Apr | 04-Apr
CDUVDU23320 | Completed | Insulation removal if required | 04/04/2023 18:38:44 | 04/04/2023 18:38:51 | 12/04/2023 10:00:00 | 13/04/2023 06:00:00 | PA-11 TO HVGO-(HT-UL) | HYDRO TEST LOOPS | 100 | CIVIL |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 12-Apr | 13-Apr | 04-Apr | 04-Apr
CDUVDU24970 | Completed | Hydrotest | 04/04/2023 18:38:59 | 04/04/2023 18:39:03 | 13/04/2023 06:00:00 | 14/04/2023 02:00:00 | PA-11 TO HVGO-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | HYDRO TEST | HYDRO TEST | 20 | 20:00 | 0:00 |  | 20:00 | 13-Apr | 14-Apr | 04-Apr | 04-Apr
CDUVDU26030 | Completed | Hydrotest Witness | 04/04/2023 18:39:21 | 04/04/2023 18:39:26 | 14/04/2023 02:00:00 | 14/04/2023 05:00:00 | PA-11 TO HVGO-(HT-UL) | HYDRO TEST LOOPS | 100 | INSPECTION |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 14-Apr | 14-Apr | 04-Apr | 04-Apr
CDUVDU26220 | Completed | Drainning of water | 04/04/2023 18:39:33 | 04/04/2023 18:39:38 | 14/04/2023 05:00:00 | 14/04/2023 11:00:00 | PA-11 TO HVGO-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 14-Apr | 14-Apr | 04-Apr | 04-Apr
CDUVDU26490 | Completed | Deblinding & handover to Operation. | 04/04/2023 18:39:47 | 04/04/2023 18:39:52 | 14/04/2023 11:00:00 | 14/04/2023 23:00:00 | PA-11 TO HVGO-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 14-Apr | 14-Apr | 04-Apr | 04-Apr
CDUVDU21400 | Completed | Blinding | 01/04/2023 12:51:53 | 01/04/2023 12:51:59 | 11/04/2023 14:00:00 | 12/04/2023 02:00:00 | FG TO VV-23-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 11-Apr | 12-Apr | 01-Apr | 01-Apr
CDUVDU22520 | Completed | Water filling | 10/04/2023 17:40:20 | 10/04/2023 17:40:25 | 12/04/2023 02:00:00 | 12/04/2023 22:00:00 | FG TO VV-23-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 12-Apr | 12-Apr | 10-Apr | 10-Apr
CDUVDU24340 | Completed | Insulation removal if required | 10/04/2023 17:40:40 | 10/04/2023 17:40:46 | 12/04/2023 22:00:00 | 13/04/2023 18:00:00 | FG TO VV-23-(HT-UL) | HYDRO TEST LOOPS | 100 | CIVIL |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 12-Apr | 13-Apr | 10-Apr | 10-Apr
CDUVDU25660 | Completed | Hydrotest | 10/04/2023 17:40:54 | 10/04/2023 17:41:00 | 13/04/2023 18:00:00 | 14/04/2023 14:00:00 | FG TO VV-23-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | HYDRO TEST | HYDRO TEST | 20 | 20:00 | 0:00 |  | 20:00 | 13-Apr | 14-Apr | 10-Apr | 10-Apr
CDUVDU26590 | Completed | Hydrotest Witness | 10/04/2023 17:41:13 | 10/04/2023 17:41:17 | 14/04/2023 14:00:00 | 14/04/2023 17:00:00 | FG TO VV-23-(HT-UL) | HYDRO TEST LOOPS | 100 | INSPECTION |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 14-Apr | 14-Apr | 10-Apr | 10-Apr
CDUVDU26780 | Completed | Drainning of water | 10/04/2023 17:41:24 | 10/04/2023 17:41:29 | 14/04/2023 17:00:00 | 14/04/2023 23:00:00 | FG TO VV-23-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 14-Apr | 14-Apr | 10-Apr | 10-Apr
CDUVDU27020 | Completed | Deblinding & handover to Operation. | 10/04/2023 17:41:37 | 10/04/2023 17:41:43 | 14/04/2023 23:00:00 | 15/04/2023 11:00:00 | FG TO VV-23-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 14-Apr | 15-Apr | 10-Apr | 10-Apr
CDUVDU22530 | Completed | Blinding | 04/04/2023 18:40:11 | 04/04/2023 18:40:16 | 12/04/2023 02:00:00 | 12/04/2023 14:00:00 | PA-11 TO LGO-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 12-Apr | 12-Apr | 04-Apr | 04-Apr
CDUVDU23690 | Completed | Water filling | 04/04/2023 18:40:24 | 04/04/2023 18:40:29 | 12/04/2023 14:00:00 | 13/04/2023 10:00:00 | PA-11 TO LGO-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 12-Apr | 13-Apr | 04-Apr | 04-Apr
CDUVDU25210 | Completed | Insulation removal if required | 04/04/2023 18:40:38 | 04/04/2023 18:40:42 | 13/04/2023 10:00:00 | 14/04/2023 06:00:00 | PA-11 TO LGO-(HT-UL) | HYDRO TEST LOOPS | 100 | CIVIL |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 13-Apr | 14-Apr | 04-Apr | 04-Apr
CDUVDU26250 | Completed | Hydrotest | 04/04/2023 18:40:50 | 04/04/2023 18:41:02 | 14/04/2023 06:00:00 | 15/04/2023 02:00:00 | PA-11 TO LGO-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | HYDRO TEST | HYDRO TEST | 20 | 20:00 | 0:00 |  | 20:00 | 14-Apr | 15-Apr | 04-Apr | 04-Apr
CDUVDU27070 | Completed | Hydrotest Witness | 04/04/2023 18:41:18 | 04/04/2023 18:41:22 | 15/04/2023 02:00:00 | 15/04/2023 05:00:00 | PA-11 TO LGO-(HT-UL) | HYDRO TEST LOOPS | 100 | INSPECTION |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 15-Apr | 15-Apr | 04-Apr | 04-Apr
CDUVDU27220 | Completed | Drainning of water | 04/04/2023 18:41:29 | 04/04/2023 18:41:34 | 15/04/2023 05:00:00 | 15/04/2023 11:00:00 | PA-11 TO LGO-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 15-Apr | 15-Apr | 04-Apr | 04-Apr
CDUVDU27450 | Completed | Deblinding & handover to Operation. | 04/04/2023 18:41:42 | 04/04/2023 18:41:49 | 15/04/2023 11:00:00 | 15/04/2023 23:00:00 | PA-11 TO LGO-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 15-Apr | 15-Apr | 04-Apr | 04-Apr
CDUVDU13830 | Completed | Blinding | 10/04/2023 17:42:25 | 10/04/2023 17:42:31 | 08/04/2023 02:00:00 | 08/04/2023 14:00:00 | VV-023 TO KERO-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 08-Apr | 08-Apr | 10-Apr | 10-Apr
CDUVDU14660 | Completed | Water filling | 10/04/2023 17:42:38 | 10/04/2023 17:42:43 | 08/04/2023 14:00:00 | 09/04/2023 10:00:00 | VV-023 TO KERO-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 08-Apr | 09-Apr | 10-Apr | 10-Apr
CDUVDU16290 | Completed | Insulation removal if required | 10/04/2023 17:42:50 | 10/04/2023 17:42:54 | 09/04/2023 10:00:00 | 10/04/2023 06:00:00 | VV-023 TO KERO-(HT-UL) | HYDRO TEST LOOPS | 100 | CIVIL |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 09-Apr | 10-Apr | 10-Apr | 10-Apr
CDUVDU18300 | Completed | Hydrotest | 10/04/2023 17:43:02 | 10/04/2023 17:43:08 | 10/04/2023 06:00:00 | 11/04/2023 02:00:00 | VV-023 TO KERO-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | HYDRO TEST | HYDRO TEST | 20 | 20:00 | 0:00 |  | 20:00 | 10-Apr | 11-Apr | 10-Apr | 10-Apr
CDUVDU20200 | Completed | Hydrotest Witness | 10/04/2023 17:43:25 | 10/04/2023 17:43:40 | 11/04/2023 02:00:00 | 11/04/2023 05:00:00 | VV-023 TO KERO-(HT-UL) | HYDRO TEST LOOPS | 100 | INSPECTION |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 11-Apr | 11-Apr | 10-Apr | 10-Apr
CDUVDU20500 | Completed | Drainning of water | 10/04/2023 17:43:52 | 10/04/2023 17:43:57 | 11/04/2023 05:00:00 | 11/04/2023 11:00:00 | VV-023 TO KERO-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 11-Apr | 11-Apr | 10-Apr | 10-Apr
CDUVDU21140 | Completed | Deblinding & handover to Operation. | 10/04/2023 17:44:15 | 10/04/2023 17:44:21 | 11/04/2023 11:00:00 | 11/04/2023 23:00:00 | VV-023 TO KERO-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 11-Apr | 11-Apr | 10-Apr | 10-Apr
CDUVDU10170 | Completed | Water filling | 19/04/2023 10:57:13 | 19/04/2023 10:57:17 | 05/04/2023 14:00:00 | 07/04/2023 02:00:00 | USN TO B/L- (HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL |  |  | 36 | 36:00 | 0:00 |  | 36:00 | 05-Apr | 07-Apr | 19-Apr | 19-Apr
CDUVDU10180 | Completed | Insulation removal if required | 19/04/2023 10:57:33 | 19/04/2023 10:57:38 | 05/04/2023 14:00:00 | 07/04/2023 02:00:00 | USN TO B/L- (HT-UL) | HYDRO TEST LOOPS | 100 | CIVIL |  |  | 36 | 36:00 | 0:00 |  | 36:00 | 05-Apr | 07-Apr | 19-Apr | 19-Apr
CDUVDU12390 | Completed | Hydrotest | 19/04/2023 10:56:50 | 19/04/2023 10:56:58 | 07/04/2023 02:00:00 | 08/04/2023 02:00:00 | USN TO B/L- (HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | HYDRO TEST | HYDRO TEST | 24 | 24:00 | 0:00 |  | 24:00 | 07-Apr | 08-Apr | 19-Apr | 19-Apr
CDUVDU13810 | Completed | Hydrotest Witness | 19/04/2023 10:57:52 | 19/04/2023 10:57:57 | 08/04/2023 02:00:00 | 08/04/2023 05:00:00 | USN TO B/L- (HT-UL) | HYDRO TEST LOOPS | 100 | INSPECTION |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 08-Apr | 08-Apr | 19-Apr | 19-Apr
CDUVDU14000 | Completed | Drainning of water | 19/04/2023 10:58:13 | 19/04/2023 10:58:17 | 08/04/2023 05:00:00 | 08/04/2023 13:00:00 | USN TO B/L- (HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  | 8:00 | 08-Apr | 08-Apr | 19-Apr | 19-Apr
CDUVDU14570 | Completed | Deblinding & handover to Operation. | 19/04/2023 11:03:09 | 19/04/2023 11:03:15 | 08/04/2023 13:00:00 | 09/04/2023 01:00:00 | USN TO B/L- (HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 08-Apr | 09-Apr | 19-Apr | 19-Apr
CDUVDU9550 | Completed | Blinding | 01/04/2023 12:49:46 | 06/04/2023 13:46:21 | 05/04/2023 02:00:00 | 05/04/2023 14:00:00 | USN TO B/L- (HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 120:57 | 108:57 |  | 05-Apr | 05-Apr | 01-Apr | 06-Apr
CDUVDU10190 | Completed | Blinding | 18/04/2023 10:23:41 | 18/04/2023 10:23:46 | 05/04/2023 14:00:00 | 06/04/2023 02:00:00 | CC-06 TO PMP-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 05-Apr | 06-Apr | 18-Apr | 18-Apr
CDUVDU10760 | Completed | Water filling | 18/04/2023 10:23:55 | 18/04/2023 10:24:02 | 06/04/2023 02:00:00 | 06/04/2023 22:00:00 | CC-06 TO PMP-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 06-Apr | 06-Apr | 18-Apr | 18-Apr
CDUVDU12080 | Completed | Insulation removal if required | 18/04/2023 10:24:10 | 18/04/2023 10:24:15 | 06/04/2023 22:00:00 | 07/04/2023 18:00:00 | CC-06 TO PMP-(HT-UL) | HYDRO TEST LOOPS | 100 | CIVIL |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 06-Apr | 07-Apr | 18-Apr | 18-Apr
CDUVDU13410 | Completed | Hydrotest | 18/04/2023 10:24:25 | 18/04/2023 10:24:30 | 07/04/2023 18:00:00 | 08/04/2023 14:00:00 | CC-06 TO PMP-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | HYDRO TEST | HYDRO TEST | 20 | 20:00 | 0:00 |  | 20:00 | 07-Apr | 08-Apr | 18-Apr | 18-Apr
CDUVDU14640 | Completed | Hydrotest Witness | 18/04/2023 10:24:58 | 18/04/2023 10:25:45 | 08/04/2023 14:00:00 | 08/04/2023 17:00:00 | CC-06 TO PMP-(HT-UL) | HYDRO TEST LOOPS | 100 | INSPECTION |  |  | 3 | 3:00 | 0:01 |  | 2:59 | 08-Apr | 08-Apr | 18-Apr | 18-Apr
CDUVDU14940 | Completed | Drainning of water | 18/04/2023 10:25:57 | 18/04/2023 10:26:32 | 08/04/2023 17:00:00 | 08/04/2023 23:00:00 | CC-06 TO PMP-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:01 |  | 5:59 | 08-Apr | 08-Apr | 18-Apr | 18-Apr
CDUVDU15340 | Completed | Deblinding & handover to Operation. | 18/04/2023 10:26:44 | 18/04/2023 10:26:51 | 08/04/2023 23:00:00 | 09/04/2023 11:00:00 | CC-06 TO PMP-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 08-Apr | 09-Apr | 18-Apr | 18-Apr
CDUVDU10770 | Completed | Blinding | 10/04/2023 17:47:50 | 10/04/2023 17:47:56 | 06/04/2023 02:00:00 | 06/04/2023 14:00:00 | MVGO FV TO LGO FV-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 06-Apr | 06-Apr | 10-Apr | 10-Apr
CDUVDU11470 | Completed | Water filling | 10/04/2023 17:48:07 | 10/04/2023 17:48:12 | 06/04/2023 14:00:00 | 07/04/2023 10:00:00 | MVGO FV TO LGO FV-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 06-Apr | 07-Apr | 10-Apr | 10-Apr
CDUVDU12910 | Completed | Insulation removal if required | 10/04/2023 17:48:22 | 10/04/2023 17:48:32 | 07/04/2023 10:00:00 | 08/04/2023 06:00:00 | MVGO FV TO LGO FV-(HT-UL) | HYDRO TEST LOOPS | 100 | CIVIL |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 07-Apr | 08-Apr | 10-Apr | 10-Apr
CDUVDU14030 | Completed | Hydrotest | 10/04/2023 17:48:41 | 10/04/2023 17:48:46 | 08/04/2023 06:00:00 | 09/04/2023 02:00:00 | MVGO FV TO LGO FV-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | HYDRO TEST | HYDRO TEST | 20 | 20:00 | 0:00 |  | 20:00 | 08-Apr | 09-Apr | 10-Apr | 10-Apr
CDUVDU15640 | Completed | Hydrotest Witness | 10/04/2023 17:49:00 | 19/04/2023 10:55:42 | 09/04/2023 02:00:00 | 09/04/2023 05:00:00 | MVGO FV TO LGO FV-(HT-UL) | HYDRO TEST LOOPS | 100 | INSPECTION |  |  | 3 | 3:00 | 209:07 | 206:07 |  | 09-Apr | 09-Apr | 10-Apr | 19-Apr
CDUVDU15910 | Completed | Drainning of water | 19/04/2023 10:55:56 | 19/04/2023 10:56:05 | 09/04/2023 05:00:00 | 09/04/2023 11:00:00 | MVGO FV TO LGO FV-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 09-Apr | 09-Apr | 19-Apr | 19-Apr
CDUVDU16400 | Completed | Deblinding & handover to Operation. | 19/04/2023 10:56:20 | 19/04/2023 10:56:26 | 09/04/2023 11:00:00 | 09/04/2023 23:00:00 | MVGO FV TO LGO FV-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 09-Apr | 09-Apr | 19-Apr | 19-Apr
CDUVDU11480 | Completed | Blinding | 15/04/2023 18:51:05 | 15/04/2023 18:51:11 | 06/04/2023 14:00:00 | 07/04/2023 02:00:00 | VV-047 TO PV-5303-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 06-Apr | 07-Apr | 15-Apr | 15-Apr
CDUVDU12400 | Completed | Water filling | 15/04/2023 18:51:20 | 15/04/2023 18:51:25 | 07/04/2023 02:00:00 | 07/04/2023 22:00:00 | VV-047 TO PV-5303-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 07-Apr | 07-Apr | 15-Apr | 15-Apr
CDUVDU13650 | Completed | Insulation removal if required | 15/04/2023 18:51:33 | 15/04/2023 18:51:38 | 07/04/2023 22:00:00 | 08/04/2023 18:00:00 | VV-047 TO PV-5303-(HT-UL) | HYDRO TEST LOOPS | 100 | CIVIL |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 07-Apr | 08-Apr | 15-Apr | 15-Apr
CDUVDU15030 | Completed | Hydrotest | 15/04/2023 18:51:45 | 15/04/2023 18:51:50 | 08/04/2023 18:00:00 | 09/04/2023 14:00:00 | VV-047 TO PV-5303-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | HYDRO TEST | HYDRO TEST | 20 | 20:00 | 0:00 |  | 20:00 | 08-Apr | 09-Apr | 15-Apr | 15-Apr
CDUVDU16600 | Completed | Hydrotest Witness | 15/04/2023 18:52:16 | 15/04/2023 18:52:21 | 09/04/2023 14:00:00 | 09/04/2023 17:00:00 | VV-047 TO PV-5303-(HT-UL) | HYDRO TEST LOOPS | 100 | INSPECTION |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 09-Apr | 09-Apr | 15-Apr | 15-Apr
CDUVDU16850 | Completed | Drainning of water | 15/04/2023 18:52:32 | 15/04/2023 18:52:37 | 09/04/2023 17:00:00 | 09/04/2023 23:00:00 | VV-047 TO PV-5303-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 09-Apr | 09-Apr | 15-Apr | 15-Apr
CDUVDU17500 | Completed | Deblinding & handover to Operation. | 15/04/2023 18:52:47 | 15/04/2023 18:52:54 | 09/04/2023 23:00:00 | 10/04/2023 11:00:00 | VV-047 TO PV-5303-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 09-Apr | 10-Apr | 15-Apr | 15-Apr
CDUVDU12410 | Completed | Blinding | 08/04/2023 11:01:16 | 08/04/2023 11:01:21 | 07/04/2023 02:00:00 | 07/04/2023 14:00:00 | LGO TO CC-06-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 07-Apr | 07-Apr | 08-Apr | 08-Apr
CDUVDU13080 | Completed | Water filling | 08/04/2023 11:01:29 | 08/04/2023 11:01:34 | 07/04/2023 14:00:00 | 08/04/2023 10:00:00 | LGO TO CC-06-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 07-Apr | 08-Apr | 08-Apr | 08-Apr
CDUVDU14420 | Completed | Insulation removal if required | 08/04/2023 11:01:43 | 08/04/2023 11:01:48 | 08/04/2023 10:00:00 | 09/04/2023 06:00:00 | LGO TO CC-06-(HT-UL) | HYDRO TEST LOOPS | 100 | CIVIL |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 08-Apr | 09-Apr | 08-Apr | 08-Apr
CDUVDU15960 | Completed | Hydrotest | 08/04/2023 11:01:55 | 08/04/2023 11:02:00 | 09/04/2023 06:00:00 | 10/04/2023 02:00:00 | LGO TO CC-06-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | HYDRO TEST | HYDRO TEST | 20 | 20:00 | 0:00 |  | 20:00 | 09-Apr | 10-Apr | 08-Apr | 08-Apr
CDUVDU17740 | Completed | Hydrotest Witness | 08/04/2023 11:02:16 | 08/04/2023 11:02:20 | 10/04/2023 02:00:00 | 10/04/2023 05:00:00 | LGO TO CC-06-(HT-UL) | HYDRO TEST LOOPS | 100 | INSPECTION |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 10-Apr | 10-Apr | 08-Apr | 08-Apr
CDUVDU18160 | Completed | Drainning of water | 08/04/2023 11:02:29 | 08/04/2023 11:02:33 | 10/04/2023 05:00:00 | 10/04/2023 11:00:00 | LGO TO CC-06-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 10-Apr | 10-Apr | 08-Apr | 08-Apr
CDUVDU18650 | Completed | Deblinding & handover to Operation. | 08/04/2023 11:02:40 | 08/04/2023 11:02:47 | 10/04/2023 11:00:00 | 10/04/2023 23:00:00 | LGO TO CC-06-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 10-Apr | 10-Apr | 08-Apr | 08-Apr
CDUVDU13090 | Completed | Blinding | 14/04/2023 09:22:23 | 14/04/2023 09:22:32 | 07/04/2023 14:00:00 | 08/04/2023 02:00:00 | VR QUENCH-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 07-Apr | 08-Apr | 14-Apr | 14-Apr
CDUVDU13820 | Completed | Water filling | 14/04/2023 09:23:07 | 14/04/2023 09:23:14 | 08/04/2023 02:00:00 | 08/04/2023 22:00:00 | VR QUENCH-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 08-Apr | 08-Apr | 14-Apr | 14-Apr
CDUVDU15230 | Completed | Insulation removal if required | 14/04/2023 09:23:46 | 14/04/2023 09:24:14 | 08/04/2023 22:00:00 | 09/04/2023 18:00:00 | VR QUENCH-(HT-UL) | HYDRO TEST LOOPS | 100 | CIVIL |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 08-Apr | 09-Apr | 14-Apr | 14-Apr
CDUVDU16920 | Completed | Hydrotest | 14/04/2023 09:24:25 | 14/04/2023 09:24:31 | 09/04/2023 18:00:00 | 10/04/2023 14:00:00 | VR QUENCH-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | HYDRO TEST | HYDRO TEST | 20 | 20:00 | 0:00 |  | 20:00 | 09-Apr | 10-Apr | 14-Apr | 14-Apr
CDUVDU18920 | Completed | Hydrotest Witness | 14/04/2023 09:24:47 | 14/04/2023 09:24:52 | 10/04/2023 14:00:00 | 10/04/2023 17:00:00 | VR QUENCH-(HT-UL) | HYDRO TEST LOOPS | 100 | INSPECTION |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 10-Apr | 10-Apr | 14-Apr | 14-Apr
CDUVDU19250 | Completed | Drainning of water | 14/04/2023 09:25:07 | 14/04/2023 09:25:14 | 10/04/2023 17:00:00 | 10/04/2023 23:00:00 | VR QUENCH-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 10-Apr | 10-Apr | 14-Apr | 14-Apr
CDUVDU19900 | Completed | Deblinding & handover to Operation. | 14/04/2023 09:25:25 | 14/04/2023 09:25:32 | 10/04/2023 23:00:00 | 11/04/2023 11:00:00 | VR QUENCH-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 10-Apr | 11-Apr | 14-Apr | 14-Apr
CDUVDU14650 | Completed | Blinding | 04/04/2023 18:31:32 | 04/04/2023 18:31:37 | 08/04/2023 14:00:00 | 09/04/2023 02:00:00 | LPG TO CC-005-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 08-Apr | 09-Apr | 04-Apr | 04-Apr
CDUVDU15650 | Completed | Water filling | 04/04/2023 18:31:45 | 04/04/2023 18:31:50 | 09/04/2023 02:00:00 | 09/04/2023 22:00:00 | LPG TO CC-005-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 09-Apr | 09-Apr | 04-Apr | 04-Apr
CDUVDU17310 | Completed | Insulation removal if required | 04/04/2023 18:31:58 | 04/04/2023 18:32:03 | 09/04/2023 22:00:00 | 10/04/2023 18:00:00 | LPG TO CC-005-(HT-UL) | HYDRO TEST LOOPS | 100 | CIVIL |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 09-Apr | 10-Apr | 04-Apr | 04-Apr
CDUVDU19350 | Completed | Hydrotest | 04/04/2023 18:32:15 | 04/04/2023 18:32:20 | 10/04/2023 18:00:00 | 11/04/2023 14:00:00 | LPG TO CC-005-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | HYDRO TEST | HYDRO TEST | 20 | 20:00 | 0:00 |  | 20:00 | 10-Apr | 11-Apr | 04-Apr | 04-Apr
CDUVDU21380 | Completed | Hydrotest Witness | 04/04/2023 18:32:34 | 04/04/2023 18:32:38 | 11/04/2023 14:00:00 | 11/04/2023 17:00:00 | LPG TO CC-005-(HT-UL) | HYDRO TEST LOOPS | 100 | INSPECTION |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 11-Apr | 11-Apr | 04-Apr | 04-Apr
CDUVDU21870 | Completed | Drainning of water | 04/04/2023 18:32:45 | 04/04/2023 18:32:51 | 11/04/2023 17:00:00 | 11/04/2023 23:00:00 | LPG TO CC-005-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 11-Apr | 11-Apr | 04-Apr | 04-Apr
CDUVDU22310 | Completed | Deblinding & handover to Operation. | 04/04/2023 18:33:00 | 04/04/2023 18:33:06 | 11/04/2023 23:00:00 | 12/04/2023 11:00:00 | LPG TO CC-005-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 11-Apr | 12-Apr | 04-Apr | 04-Apr
CDUVDU15660 | Completed | Blinding | 01/04/2023 17:03:48 | 01/04/2023 17:03:55 | 09/04/2023 02:00:00 | 09/04/2023 14:00:00 | HOT HN TO DHDT-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 09-Apr | 09-Apr | 01-Apr | 01-Apr
CDUVDU16610 | Completed | Water filling | 10/04/2023 17:44:52 | 10/04/2023 17:44:57 | 09/04/2023 14:00:00 | 10/04/2023 10:00:00 | HOT HN TO DHDT-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 09-Apr | 10-Apr | 10-Apr | 10-Apr
CDUVDU18560 | Completed | Insulation removal if required | 10/04/2023 17:45:04 | 10/04/2023 17:45:10 | 10/04/2023 10:00:00 | 11/04/2023 06:00:00 | HOT HN TO DHDT-(HT-UL) | HYDRO TEST LOOPS | 100 | CIVIL |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 10-Apr | 11-Apr | 10-Apr | 10-Apr
CDUVDU20620 | Completed | Hydrotest | 10/04/2023 17:45:21 | 10/04/2023 17:45:26 | 11/04/2023 06:00:00 | 12/04/2023 02:00:00 | HOT HN TO DHDT-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | HYDRO TEST | HYDRO TEST | 20 | 20:00 | 0:00 |  | 20:00 | 11-Apr | 12-Apr | 10-Apr | 10-Apr
CDUVDU22510 | Completed | Hydrotest Witness | 10/04/2023 17:46:01 | 10/04/2023 17:46:15 | 12/04/2023 02:00:00 | 12/04/2023 05:00:00 | HOT HN TO DHDT-(HT-UL) | HYDRO TEST LOOPS | 100 | INSPECTION |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 12-Apr | 12-Apr | 10-Apr | 10-Apr
CDUVDU22960 | Completed | Drainning of water | 10/04/2023 17:46:27 | 10/04/2023 17:46:31 | 12/04/2023 05:00:00 | 12/04/2023 11:00:00 | HOT HN TO DHDT-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 12-Apr | 12-Apr | 10-Apr | 10-Apr
CDUVDU23540 | Completed | Deblinding & handover to Operation. | 10/04/2023 17:46:40 | 10/04/2023 17:46:45 | 12/04/2023 11:00:00 | 12/04/2023 23:00:00 | HOT HN TO DHDT-(HT-UL) | HYDRO TEST LOOPS | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 12-Apr | 12-Apr | 10-Apr | 10-Apr
CDUVDU10780 | Completed | Insulation removal if required | 21/04/2023 14:25:24 | 21/04/2023 14:28:59 | 06/04/2023 02:00:00 | 07/04/2023 14:00:00 | L-113(HT-INSP/MOC) | HYDRO TEST LOOPS | 100 | CIVIL |  |  | 36 | 36:00 | 0:04 |  | 35:56 | 06-Apr | 07-Apr | 21-Apr | 21-Apr
CDUVDU13100 | Not Started | Hydrotest |  |  | 07/04/2023 14:00:00 | 08/04/2023 10:00:00 | L-113(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | HYDRO TEST | HYDRO TEST | 20 | 20:00 | 0:00 |  |  | 07-Apr | 08-Apr | - Date check | - Date check
CDUVDU14430 | Not Started | Hydrotest Witness |  |  | 08/04/2023 10:00:00 | 08/04/2023 13:00:00 | L-113(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | INSPECTION |  |  | 3 | 3:00 | 0:00 |  |  | 08-Apr | 08-Apr | - Date check | - Date check
CDUVDU14580 | Not Started | Drainning of water |  |  | 08/04/2023 13:00:00 | 08/04/2023 19:00:00 | L-113(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 08-Apr | 08-Apr | - Date check | - Date check
CDUVDU15070 | Not Started | Deblinding & handover to Operation. |  |  | 08/04/2023 19:00:00 | 09/04/2023 07:00:00 | L-113(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  |  | 08-Apr | 09-Apr | - Date check | - Date check
CDUVDU9010 | Completed | Blinding | 13/04/2023 12:14:13 | 13/04/2023 12:14:17 | 04/04/2023 14:00:00 | 05/04/2023 02:00:00 | L-113(HT-INSP/MOC) | HYDRO TEST LOOPS | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 04-Apr | 05-Apr | 13-Apr | 13-Apr
CDUVDU9560 | Not Started | Water filling |  |  | 05/04/2023 02:00:00 | 06/04/2023 02:00:00 | L-113(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  |  | 05-Apr | 06-Apr | - Date check | - Date check
CDUVDU30280 | Not Started | Blinding |  |  | 09/04/2023 14:00:00 | 10/04/2023 02:00:00 | L-4B(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 0:00 |  |  | 09-Apr | 10-Apr | - Date check | - Date check
CDUVDU30290 | Not Started | Water filling |  |  | 10/04/2023 02:00:00 | 12/04/2023 02:00:00 | L-4B(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 48 | 48:00 | 0:00 |  |  | 10-Apr | 12-Apr | - Date check | - Date check
CDUVDU30300 | Completed | Insulation removal if required | 21/04/2023 14:27:33 | 21/04/2023 14:34:50 | 10/04/2023 02:00:00 | 12/04/2023 02:00:00 | L-4B(HT-INSP/MOC) | HYDRO TEST LOOPS | 100 | CIVIL |  |  | 48 | 48:00 | 0:07 |  | 47:53 | 10-Apr | 12-Apr | 21-Apr | 21-Apr
CDUVDU30310 | Not Started | Hydrotest |  |  | 12/04/2023 02:00:00 | 13/04/2023 02:00:00 | L-4B(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | HYDRO TEST | HYDRO TEST | 24 | 24:00 | 0:00 |  |  | 12-Apr | 13-Apr | - Date check | - Date check
CDUVDU30320 | Not Started | Drainning of water |  |  | 13/04/2023 05:00:00 | 13/04/2023 13:00:00 | L-4B(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  |  | 13-Apr | 13-Apr | - Date check | - Date check
CDUVDU30330 | Not Started | Deblinding & handover to Operation. |  |  | 13/04/2023 13:00:00 | 14/04/2023 01:00:00 | L-4B(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  |  | 13-Apr | 14-Apr | - Date check | - Date check
CDUVDU30340 | Not Started | Hydrotest Witness |  |  | 13/04/2023 02:00:00 | 13/04/2023 05:00:00 | L-4B(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | INSPECTION |  |  | 3 | 3:00 | 0:00 |  |  | 13-Apr | 13-Apr | - Date check | - Date check
CDUVDU30350 | Not Started | Blinding |  |  | 10/04/2023 02:00:00 | 10/04/2023 14:00:00 | VV-004-PSV1602(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 0:00 |  |  | 10-Apr | 10-Apr | - Date check | - Date check
CDUVDU30360 | Not Started | Water filling |  |  | 10/04/2023 14:00:00 | 11/04/2023 10:00:00 | VV-004-PSV1602(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 20 | 20:00 | 0:00 |  |  | 10-Apr | 11-Apr | - Date check | - Date check
CDUVDU30370 | Completed | Insulation removal if required | 21/04/2023 14:27:48 | 21/04/2023 14:35:07 | 10/04/2023 14:00:00 | 11/04/2023 10:00:00 | VV-004-PSV1602(HT-INSP/MOC) | HYDRO TEST LOOPS | 100 | CIVIL |  |  | 20 | 20:00 | 0:07 |  | 19:53 | 10-Apr | 11-Apr | 21-Apr | 21-Apr
CDUVDU30380 | Not Started | Hydrotest |  |  | 11/04/2023 10:00:00 | 12/04/2023 06:00:00 | VV-004-PSV1602(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | HYDRO TEST | HYDRO TEST | 20 | 20:00 | 0:00 |  |  | 11-Apr | 12-Apr | - Date check | - Date check
CDUVDU30390 | Not Started | Drainning of water |  |  | 12/04/2023 09:00:00 | 12/04/2023 15:00:00 | VV-004-PSV1602(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 12-Apr | 12-Apr | - Date check | - Date check
CDUVDU30400 | Not Started | Deblinding & handover to Operation. |  |  | 12/04/2023 15:00:00 | 13/04/2023 03:00:00 | VV-004-PSV1602(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  |  | 12-Apr | 13-Apr | - Date check | - Date check
CDUVDU30410 | Not Started | Hydrotest Witness |  |  | 12/04/2023 06:00:00 | 12/04/2023 09:00:00 | VV-004-PSV1602(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | INSPECTION |  |  | 3 | 3:00 | 0:00 |  |  | 12-Apr | 12-Apr | - Date check | - Date check
CDUVDU30420 | Completed | Blinding | 19/04/2023 11:39:34 | 19/04/2023 11:43:26 | 10/04/2023 14:00:00 | 11/04/2023 02:00:00 | EE-056-VV-006(HT-INSP/MOC) | HYDRO TEST LOOPS | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 0:04 |  | 11:56 | 10-Apr | 11-Apr | 19-Apr | 19-Apr
CDUVDU30430 | Completed | Water filling | 19/04/2023 12:21:49 | 19/04/2023 12:21:52 | 11/04/2023 02:00:00 | 11/04/2023 22:00:00 | EE-056-VV-006(HT-INSP/MOC) | HYDRO TEST LOOPS | 100 | MECHANICAL |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 11-Apr | 11-Apr | 19-Apr | 19-Apr
CDUVDU30440 | Completed | Insulation removal if required | 19/04/2023 12:22:06 | 19/04/2023 12:22:11 | 11/04/2023 02:00:00 | 11/04/2023 22:00:00 | EE-056-VV-006(HT-INSP/MOC) | HYDRO TEST LOOPS | 100 | CIVIL |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 11-Apr | 11-Apr | 19-Apr | 19-Apr
CDUVDU30450 | Completed | Hydrotest | 19/04/2023 12:22:23 | 19/04/2023 12:22:28 | 11/04/2023 22:00:00 | 12/04/2023 18:00:00 | EE-056-VV-006(HT-INSP/MOC) | HYDRO TEST LOOPS | 100 | MECHANICAL | HYDRO TEST | HYDRO TEST | 20 | 20:00 | 0:00 |  | 20:00 | 11-Apr | 12-Apr | 19-Apr | 19-Apr
CDUVDU30460 | Completed | Drainning of water | 19/04/2023 12:22:41 | 19/04/2023 12:22:45 | 12/04/2023 21:00:00 | 13/04/2023 03:00:00 | EE-056-VV-006(HT-INSP/MOC) | HYDRO TEST LOOPS | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  | 6:00 | 12-Apr | 13-Apr | 19-Apr | 19-Apr
CDUVDU30470 | Completed | Deblinding & handover to Operation. | 19/04/2023 12:23:21 | 19/04/2023 12:23:25 | 13/04/2023 03:00:00 | 13/04/2023 15:00:00 | EE-056-VV-006(HT-INSP/MOC) | HYDRO TEST LOOPS | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 13-Apr | 13-Apr | 19-Apr | 19-Apr
CDUVDU30480 | Completed | Hydrotest Witness | 19/04/2023 12:23:05 | 19/04/2023 12:23:09 | 12/04/2023 18:00:00 | 12/04/2023 21:00:00 | EE-056-VV-006(HT-INSP/MOC) | HYDRO TEST LOOPS | 100 | INSPECTION |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 12-Apr | 12-Apr | 19-Apr | 19-Apr
CDUVDU30490 | Completed | Blinding | 26/04/2023 13:55:05 | 26/04/2023 13:55:05 | 11/04/2023 02:00:00 | 11/04/2023 14:00:00 | L-72(HT-INSP/MOC) | HYDRO TEST LOOPS | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 0:00 |  |  | 11-Apr | 11-Apr | 26-Apr | 26-Apr
CDUVDU30500 | Completed | Water filling | 26/04/2023 13:55:05 | 26/04/2023 13:55:05 | 11/04/2023 14:00:00 | 13/04/2023 02:00:00 | L-72(HT-INSP/MOC) | HYDRO TEST LOOPS | 100 | MECHANICAL |  |  | 36 | 36:00 | 0:00 |  |  | 11-Apr | 13-Apr | 26-Apr | 26-Apr
CDUVDU30510 | Completed | Insulation removal if required | 21/04/2023 14:28:01 | 21/04/2023 14:35:22 | 11/04/2023 14:00:00 | 13/04/2023 02:00:00 | L-72(HT-INSP/MOC) | HYDRO TEST LOOPS | 100 | CIVIL |  |  | 36 | 36:00 | 0:07 |  | 35:53 | 11-Apr | 13-Apr | 21-Apr | 21-Apr
CDUVDU30520 | Completed | Hydrotest | 26/04/2023 13:55:05 | 26/04/2023 13:55:05 | 13/04/2023 02:00:00 | 14/04/2023 02:00:00 | L-72(HT-INSP/MOC) | HYDRO TEST LOOPS | 100 | MECHANICAL | HYDRO TEST | HYDRO TEST | 24 | 24:00 | 0:00 |  |  | 13-Apr | 14-Apr | 26-Apr | 26-Apr
CDUVDU30530 | Not Started | Drainning of water |  |  | 14/04/2023 05:00:00 | 14/04/2023 13:00:00 | L-72(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  |  | 14-Apr | 14-Apr | - Date check | - Date check
CDUVDU30540 | Not Started | Deblinding & handover to Operation. |  |  | 14/04/2023 13:00:00 | 15/04/2023 01:00:00 | L-72(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  |  | 14-Apr | 15-Apr | - Date check | - Date check
CDUVDU30550 | Not Started | Hydrotest Witness |  |  | 14/04/2023 02:00:00 | 14/04/2023 05:00:00 | L-72(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | INSPECTION |  |  | 3 | 3:00 | 0:00 |  |  | 14-Apr | 14-Apr | - Date check | - Date check
CDUVDU30560 | Not Started | Blinding |  |  | 11/04/2023 14:00:00 | 12/04/2023 02:00:00 | L-129PA(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 0:00 |  |  | 11-Apr | 12-Apr | - Date check | - Date check
CDUVDU30570 | Not Started | Water filling |  |  | 12/04/2023 02:00:00 | 12/04/2023 22:00:00 | L-129PA(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 20 | 20:00 | 0:00 |  |  | 12-Apr | 12-Apr | - Date check | - Date check
CDUVDU30580 | Completed | Insulation removal if required | 21/04/2023 14:28:13 | 22/04/2023 14:28:06 | 12/04/2023 02:00:00 | 12/04/2023 22:00:00 | L-129PA(HT-INSP/MOC) | HYDRO TEST LOOPS | 100 | CIVIL |  |  | 20 | 20:00 | 24:00 | 4:00 |  | 12-Apr | 12-Apr | 21-Apr | 22-Apr
CDUVDU30590 | Not Started | Hydrotest |  |  | 12/04/2023 22:00:00 | 13/04/2023 18:00:00 | L-129PA(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | HYDRO TEST | HYDRO TEST | 20 | 20:00 | 0:00 |  |  | 12-Apr | 13-Apr | - Date check | - Date check
CDUVDU30600 | Not Started | Drainning of water |  |  | 13/04/2023 21:00:00 | 14/04/2023 03:00:00 | L-129PA(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 13-Apr | 14-Apr | - Date check | - Date check
CDUVDU30610 | Not Started | Deblinding & handover to Operation. |  |  | 14/04/2023 03:00:00 | 14/04/2023 15:00:00 | L-129PA(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  |  | 14-Apr | 14-Apr | - Date check | - Date check
CDUVDU30620 | Not Started | Hydrotest Witness |  |  | 13/04/2023 18:00:00 | 13/04/2023 21:00:00 | L-129PA(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | INSPECTION |  |  | 3 | 3:00 | 0:00 |  |  | 13-Apr | 13-Apr | - Date check | - Date check
CDUVDU30630 | Not Started | Blinding |  |  | 12/04/2023 02:00:00 | 12/04/2023 14:00:00 | L-116(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 0:00 |  |  | 12-Apr | 12-Apr | - Date check | - Date check
CDUVDU30640 | Not Started | Water filling |  |  | 12/04/2023 14:00:00 | 13/04/2023 10:00:00 | L-116(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 20 | 20:00 | 0:00 |  |  | 12-Apr | 13-Apr | - Date check | - Date check
CDUVDU30650 | Completed | Insulation removal if required | 21/04/2023 14:28:28 | 21/04/2023 14:29:40 | 12/04/2023 14:00:00 | 13/04/2023 10:00:00 | L-116(HT-INSP/MOC) | HYDRO TEST LOOPS | 100 | CIVIL |  |  | 20 | 20:00 | 0:01 |  | 19:59 | 12-Apr | 13-Apr | 21-Apr | 21-Apr
CDUVDU30660 | Not Started | Hydrotest |  |  | 13/04/2023 10:00:00 | 14/04/2023 06:00:00 | L-116(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | HYDRO TEST | HYDRO TEST | 20 | 20:00 | 0:00 |  |  | 13-Apr | 14-Apr | - Date check | - Date check
CDUVDU30670 | Not Started | Drainning of water |  |  | 14/04/2023 09:00:00 | 14/04/2023 15:00:00 | L-116(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 14-Apr | 14-Apr | - Date check | - Date check
CDUVDU30680 | Not Started | Deblinding & handover to Operation. |  |  | 14/04/2023 15:00:00 | 15/04/2023 03:00:00 | L-116(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  |  | 14-Apr | 15-Apr | - Date check | - Date check
CDUVDU30690 | Not Started | Hydrotest Witness |  |  | 14/04/2023 06:00:00 | 14/04/2023 09:00:00 | L-116(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | INSPECTION |  |  | 3 | 3:00 | 0:00 |  |  | 14-Apr | 14-Apr | - Date check | - Date check
CDUVDU15710 | Not Started | Blinding |  |  | 09/04/2023 02:00:00 | 09/04/2023 14:00:00 | L-91(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 0:00 |  |  | 09-Apr | 09-Apr | - Date check | - Date check
CDUVDU16650 | Not Started | Water filling |  |  | 09/04/2023 14:00:00 | 10/04/2023 14:00:00 | L-91(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  |  | 09-Apr | 10-Apr | - Date check | - Date check
CDUVDU16660 | Completed | Insulation removal if required | 21/04/2023 14:27:19 | 21/04/2023 14:34:34 | 09/04/2023 14:00:00 | 11/04/2023 14:00:00 | L-91(HT-INSP/MOC) | HYDRO TEST LOOPS | 100 | CIVIL |  |  | 48 | 48:00 | 0:07 |  | 47:53 | 09-Apr | 11-Apr | 21-Apr | 21-Apr
CDUVDU20250 | Not Started | Hydrotest |  |  | 11/04/2023 14:00:00 | 12/04/2023 10:00:00 | L-91(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | HYDRO TEST | HYDRO TEST | 20 | 20:00 | 0:00 |  |  | 11-Apr | 12-Apr | - Date check | - Date check
CDUVDU22220 | Not Started | Hydrotest Witness |  |  | 12/04/2023 10:00:00 | 12/04/2023 13:00:00 | L-91(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | INSPECTION |  |  | 3 | 3:00 | 0:00 |  |  | 12-Apr | 12-Apr | - Date check | - Date check
CDUVDU22430 | Not Started | Drainning of water |  |  | 12/04/2023 13:00:00 | 12/04/2023 19:00:00 | L-91(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 12-Apr | 12-Apr | - Date check | - Date check
CDUVDU23120 | Not Started | Deblinding & handover to Operation. |  |  | 12/04/2023 19:00:00 | 13/04/2023 07:00:00 | L-91(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  |  | 12-Apr | 13-Apr | - Date check | - Date check
CDUVDU10200 | Not Started | Water filling |  |  | 05/04/2023 14:00:00 | 07/04/2023 02:00:00 | L-114(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 36 | 36:00 | 0:00 |  |  | 05-Apr | 07-Apr | - Date check | - Date check
CDUVDU12420 | Completed | Insulation removal if required | 21/04/2023 14:26:15 | 21/04/2023 14:33:22 | 07/04/2023 02:00:00 | 08/04/2023 14:00:00 | L-114(HT-INSP/MOC) | HYDRO TEST LOOPS | 100 | CIVIL |  |  | 36 | 36:00 | 0:07 |  | 35:53 | 07-Apr | 08-Apr | 21-Apr | 21-Apr
CDUVDU14670 | Not Started | Hydrotest |  |  | 08/04/2023 14:00:00 | 09/04/2023 14:00:00 | L-114(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | HYDRO TEST | HYDRO TEST | 24 | 24:00 | 0:00 |  |  | 08-Apr | 09-Apr | - Date check | - Date check
CDUVDU16630 | Not Started | Hydrotest Witness |  |  | 09/04/2023 14:00:00 | 09/04/2023 17:00:00 | L-114(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | INSPECTION |  |  | 3 | 3:00 | 0:00 |  |  | 09-Apr | 09-Apr | - Date check | - Date check
CDUVDU16860 | Not Started | Drainning of water |  |  | 09/04/2023 17:00:00 | 10/04/2023 01:00:00 | L-114(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  |  | 09-Apr | 10-Apr | - Date check | - Date check
CDUVDU17660 | Not Started | Deblinding & handover to Operation. |  |  | 10/04/2023 01:00:00 | 10/04/2023 13:00:00 | L-114(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  |  | 10-Apr | 10-Apr | - Date check | - Date check
CDUVDU9570 | Completed | Blinding | 19/04/2023 10:29:38 | 20/04/2023 09:32:54 | 05/04/2023 02:00:00 | 05/04/2023 14:00:00 | L-114(HT-INSP/MOC) | HYDRO TEST LOOPS | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 23:03 | 11:03 |  | 05-Apr | 05-Apr | 19-Apr | 20-Apr
CDUVDU10210 | Not Started | Blinding |  |  | 05/04/2023 14:00:00 | 06/04/2023 02:00:00 | VV-008 OVHD(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 0:00 |  |  | 05-Apr | 06-Apr | - Date check | - Date check
CDUVDU10790 | Not Started | Water filling |  |  | 06/04/2023 02:00:00 | 06/04/2023 22:00:00 | VV-008 OVHD(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 20 | 20:00 | 0:00 |  |  | 06-Apr | 06-Apr | - Date check | - Date check
CDUVDU12090 | Completed | Insulation removal if required | 21/04/2023 14:25:57 | 21/04/2023 14:29:56 | 06/04/2023 22:00:00 | 07/04/2023 18:00:00 | VV-008 OVHD(HT-INSP/MOC) | HYDRO TEST LOOPS | 100 | CIVIL |  |  | 20 | 20:00 | 0:04 |  | 19:56 | 06-Apr | 07-Apr | 21-Apr | 21-Apr
CDUVDU13420 | Not Started | Hydrotest |  |  | 07/04/2023 18:00:00 | 08/04/2023 14:00:00 | VV-008 OVHD(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | HYDRO TEST | HYDRO TEST | 20 | 20:00 | 0:00 |  |  | 07-Apr | 08-Apr | - Date check | - Date check
CDUVDU14680 | Not Started | Hydrotest Witness |  |  | 08/04/2023 14:00:00 | 08/04/2023 17:00:00 | VV-008 OVHD(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | INSPECTION |  |  | 3 | 3:00 | 0:00 |  |  | 08-Apr | 08-Apr | - Date check | - Date check
CDUVDU14950 | Not Started | Drainning of water |  |  | 08/04/2023 17:00:00 | 08/04/2023 23:00:00 | VV-008 OVHD(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 08-Apr | 08-Apr | - Date check | - Date check
CDUVDU15350 | Not Started | Deblinding & handover to Operation. |  |  | 08/04/2023 23:00:00 | 09/04/2023 11:00:00 | VV-008 OVHD(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  |  | 08-Apr | 09-Apr | - Date check | - Date check
CDUVDU10800 | Completed | Blinding | 26/04/2023 17:11:53 | 26/04/2023 17:12:12 | 06/04/2023 02:00:00 | 06/04/2023 14:00:00 | L-16(HT-INSP/MOC) | HYDRO TEST LOOPS | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 06-Apr | 06-Apr | 26-Apr | 26-Apr
CDUVDU11490 | Completed | Water filling | 26/04/2023 17:12:21 | 26/04/2023 17:12:26 | 06/04/2023 14:00:00 | 08/04/2023 02:00:00 | L-16(HT-INSP/MOC) | HYDRO TEST LOOPS | 100 | MECHANICAL |  |  | 36 | 36:00 | 0:00 |  | 36:00 | 06-Apr | 08-Apr | 26-Apr | 26-Apr
CDUVDU11500 | Completed | Insulation removal if required | 21/04/2023 14:25:42 | 21/04/2023 14:29:17 | 06/04/2023 14:00:00 | 08/04/2023 02:00:00 | L-16(HT-INSP/MOC) | HYDRO TEST LOOPS | 100 | CIVIL |  |  | 36 | 36:00 | 0:04 |  | 35:56 | 06-Apr | 08-Apr | 21-Apr | 21-Apr
CDUVDU13840 | Completed | Hydrotest | 26/04/2023 17:12:37 | 26/04/2023 17:12:41 | 08/04/2023 02:00:00 | 08/04/2023 22:00:00 | L-16(HT-INSP/MOC) | HYDRO TEST LOOPS | 100 | MECHANICAL | HYDRO TEST | HYDRO TEST | 20 | 20:00 | 0:00 |  | 20:00 | 08-Apr | 08-Apr | 26-Apr | 26-Apr
CDUVDU15240 | Completed | Hydrotest Witness | 26/04/2023 17:12:50 | 26/04/2023 17:12:56 | 08/04/2023 22:00:00 | 09/04/2023 01:00:00 | L-16(HT-INSP/MOC) | HYDRO TEST LOOPS | 100 | INSPECTION |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 08-Apr | 09-Apr | 26-Apr | 26-Apr
CDUVDU15600 | Completed | Drainning of water | 26/04/2023 17:13:03 | 26/04/2023 17:13:07 | 09/04/2023 01:00:00 | 09/04/2023 09:00:00 | L-16(HT-INSP/MOC) | HYDRO TEST LOOPS | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  | 8:00 | 09-Apr | 09-Apr | 26-Apr | 26-Apr
CDUVDU16200 | Completed | Deblinding & handover to Operation. | 26/04/2023 17:13:16 | 26/04/2023 17:13:22 | 09/04/2023 09:00:00 | 09/04/2023 21:00:00 | L-16(HT-INSP/MOC) | HYDRO TEST LOOPS | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 09-Apr | 09-Apr | 26-Apr | 26-Apr
CDUVDU11510 | Completed | Blinding | 18/04/2023 10:27:26 | 18/04/2023 10:27:32 | 06/04/2023 14:00:00 | 07/04/2023 02:00:00 | L-30(HT-INSP/MOC) | HYDRO TEST LOOPS | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 06-Apr | 07-Apr | 18-Apr | 18-Apr
CDUVDU12430 | Completed | Water filling | 18/04/2023 10:27:43 | 18/04/2023 10:27:49 | 07/04/2023 02:00:00 | 08/04/2023 14:00:00 | L-30(HT-INSP/MOC) | HYDRO TEST LOOPS | 100 | MECHANICAL |  |  | 36 | 36:00 | 0:00 |  | 36:00 | 07-Apr | 08-Apr | 18-Apr | 18-Apr
CDUVDU14690 | Completed | Insulation removal if required | 18/04/2023 10:27:57 | 18/04/2023 10:28:23 | 08/04/2023 14:00:00 | 10/04/2023 02:00:00 | L-30(HT-INSP/MOC) | HYDRO TEST LOOPS | 100 | CIVIL |  |  | 36 | 36:00 | 0:00 |  | 36:00 | 08-Apr | 10-Apr | 18-Apr | 18-Apr
CDUVDU17770 | Completed | Hydrotest | 18/04/2023 10:28:39 | 18/04/2023 10:28:56 | 10/04/2023 02:00:00 | 11/04/2023 02:00:00 | L-30(HT-INSP/MOC) | HYDRO TEST LOOPS | 100 | MECHANICAL | HYDRO TEST | HYDRO TEST | 24 | 24:00 | 0:00 |  | 24:00 | 10-Apr | 11-Apr | 18-Apr | 18-Apr
CDUVDU20210 | Completed | Hydrotest Witness | 18/04/2023 10:29:11 | 18/04/2023 10:29:16 | 11/04/2023 02:00:00 | 11/04/2023 05:00:00 | L-30(HT-INSP/MOC) | HYDRO TEST LOOPS | 100 | INSPECTION |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 11-Apr | 11-Apr | 18-Apr | 18-Apr
CDUVDU20510 | Completed | Drainning of water | 18/04/2023 10:29:25 | 18/04/2023 10:29:31 | 11/04/2023 05:00:00 | 11/04/2023 13:00:00 | L-30(HT-INSP/MOC) | HYDRO TEST LOOPS | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  | 8:00 | 11-Apr | 11-Apr | 18-Apr | 18-Apr
CDUVDU21230 | Completed | Deblinding & handover to Operation. | 18/04/2023 10:29:44 | 18/04/2023 10:29:51 | 11/04/2023 13:00:00 | 12/04/2023 01:00:00 | L-30(HT-INSP/MOC) | HYDRO TEST LOOPS | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 11-Apr | 12-Apr | 18-Apr | 18-Apr
CDUVDU12440 | Completed | Blinding | 19/04/2023 10:28:55 | 19/04/2023 11:15:51 | 07/04/2023 02:00:00 | 07/04/2023 14:00:00 | L-152(HT-INSP/MOC) | HYDRO TEST LOOPS | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 0:47 |  | 11:13 | 07-Apr | 07-Apr | 19-Apr | 19-Apr
CDUVDU13110 | In Progress | Water filling | 19/04/2023 11:16:06 |  | 07/04/2023 14:00:00 | 08/04/2023 14:00:00 | L-152(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  |  | 07-Apr | 08-Apr | 19-Apr | - Date check
CDUVDU13120 | Completed | Insulation removal if required | 20/04/2023 16:14:00 | 20/04/2023 16:14:19 | 07/04/2023 14:00:00 | 09/04/2023 02:00:00 | L-152(HT-INSP/MOC) | HYDRO TEST LOOPS | 100 | CIVIL |  |  | 36 | 36:00 | 0:00 |  | 36:00 | 07-Apr | 09-Apr | 20-Apr | 20-Apr
CDUVDU15670 | Not Started | Hydrotest |  |  | 09/04/2023 02:00:00 | 09/04/2023 22:00:00 | L-152(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | HYDRO TEST | HYDRO TEST | 20 | 20:00 | 0:00 |  |  | 09-Apr | 09-Apr | - Date check | - Date check
CDUVDU17320 | Not Started | Hydrotest Witness |  |  | 09/04/2023 22:00:00 | 10/04/2023 01:00:00 | L-152(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | INSPECTION |  |  | 3 | 3:00 | 0:00 |  |  | 09-Apr | 10-Apr | - Date check | - Date check
CDUVDU17670 | Not Started | Drainning of water |  |  | 10/04/2023 01:00:00 | 10/04/2023 07:00:00 | L-152(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 10-Apr | 10-Apr | - Date check | - Date check
CDUVDU18370 | Not Started | Deblinding & handover to Operation. |  |  | 10/04/2023 07:00:00 | 10/04/2023 19:00:00 | L-152(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  |  | 10-Apr | 10-Apr | - Date check | - Date check
CDUVDU13130 | Not Started | Blinding |  |  | 07/04/2023 14:00:00 | 08/04/2023 02:00:00 | L-125(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 0:00 |  |  | 07-Apr | 08-Apr | - Date check | - Date check
CDUVDU13850 | Not Started | Water filling |  |  | 08/04/2023 02:00:00 | 09/04/2023 02:00:00 | L-125(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  |  | 08-Apr | 09-Apr | - Date check | - Date check
CDUVDU13860 | Completed | Insulation removal if required | 21/04/2023 14:26:29 | 21/04/2023 14:33:37 | 08/04/2023 02:00:00 | 09/04/2023 02:00:00 | L-125(HT-INSP/MOC) | HYDRO TEST LOOPS | 100 | CIVIL |  |  | 24 | 24:00 | 0:07 |  | 23:53 | 08-Apr | 09-Apr | 21-Apr | 21-Apr
CDUVDU15680 | Not Started | Hydrotest |  |  | 09/04/2023 02:00:00 | 09/04/2023 22:00:00 | L-125(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | HYDRO TEST | HYDRO TEST | 20 | 20:00 | 0:00 |  |  | 09-Apr | 09-Apr | - Date check | - Date check
CDUVDU17330 | Not Started | Hydrotest Witness |  |  | 09/04/2023 22:00:00 | 10/04/2023 01:00:00 | L-125(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | INSPECTION |  |  | 3 | 3:00 | 0:00 |  |  | 09-Apr | 10-Apr | - Date check | - Date check
CDUVDU17680 | Not Started | Drainning of water |  |  | 10/04/2023 01:00:00 | 10/04/2023 09:00:00 | L-125(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  |  | 10-Apr | 10-Apr | - Date check | - Date check
CDUVDU18480 | Not Started | Deblinding & handover to Operation. |  |  | 10/04/2023 09:00:00 | 10/04/2023 21:00:00 | L-125(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  |  | 10-Apr | 10-Apr | - Date check | - Date check
CDUVDU14700 | Not Started | Blinding |  |  | 08/04/2023 14:00:00 | 09/04/2023 02:00:00 | L-165(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 0:00 |  |  | 08-Apr | 09-Apr | - Date check | - Date check
CDUVDU15690 | Not Started | Water filling |  |  | 09/04/2023 02:00:00 | 09/04/2023 22:00:00 | L-165(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 20 | 20:00 | 0:00 |  |  | 09-Apr | 09-Apr | - Date check | - Date check
CDUVDU15700 | Completed | Insulation removal if required | 21/04/2023 14:27:04 | 21/04/2023 14:34:16 | 09/04/2023 02:00:00 | 09/04/2023 22:00:00 | L-165(HT-INSP/MOC) | HYDRO TEST LOOPS | 100 | CIVIL |  |  | 20 | 20:00 | 0:07 |  | 19:53 | 09-Apr | 09-Apr | 21-Apr | 21-Apr
CDUVDU17340 | Not Started | Hydrotest |  |  | 09/04/2023 22:00:00 | 10/04/2023 18:00:00 | L-165(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | HYDRO TEST | HYDRO TEST | 20 | 20:00 | 0:00 |  |  | 09-Apr | 10-Apr | - Date check | - Date check
CDUVDU19360 | Not Started | Hydrotest Witness |  |  | 10/04/2023 18:00:00 | 10/04/2023 21:00:00 | L-165(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | INSPECTION |  |  | 3 | 3:00 | 0:00 |  |  | 10-Apr | 10-Apr | - Date check | - Date check
CDUVDU19640 | Not Started | Drainning of water |  |  | 10/04/2023 21:00:00 | 11/04/2023 03:00:00 | L-165(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 10-Apr | 11-Apr | - Date check | - Date check
CDUVDU20370 | Not Started | Deblinding & handover to Operation. |  |  | 11/04/2023 03:00:00 | 11/04/2023 15:00:00 | L-165(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  |  | 11-Apr | 11-Apr | - Date check | - Date check
CDUVDU30210 | In Progress | Blinding | 23/04/2023 09:34:38 |  | 08/04/2023 02:00:00 | 08/04/2023 14:00:00 | L-107(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 0:00 |  |  | 08-Apr | 08-Apr | 23-Apr | - Date check
CDUVDU30220 | In Progress | Water filling | 23/04/2023 09:34:50 |  | 08/04/2023 14:00:00 | 10/04/2023 14:00:00 | L-107(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 48 | 48:00 | 0:00 |  |  | 08-Apr | 10-Apr | 23-Apr | - Date check
CDUVDU30230 | Completed | Insulation removal if required | 21/04/2023 14:26:48 | 25/04/2023 08:39:14 | 08/04/2023 14:00:00 | 10/04/2023 14:00:00 | L-107(HT-INSP/MOC) | HYDRO TEST LOOPS | 100 | CIVIL |  |  | 48 | 48:00 | 90:12 | 42:12 |  | 08-Apr | 10-Apr | 21-Apr | 25-Apr
CDUVDU30240 | In Progress | Hydrotest | 23/04/2023 09:35:08 |  | 10/04/2023 14:00:00 | 11/04/2023 14:00:00 | L-107(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | HYDRO TEST | HYDRO TEST | 24 | 24:00 | 0:00 |  |  | 10-Apr | 11-Apr | 23-Apr | - Date check
CDUVDU30250 | In Progress | Drainning of water | 23/04/2023 09:35:31 |  | 11/04/2023 17:00:00 | 12/04/2023 03:00:00 | L-107(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 10 | 10:00 | 0:00 |  |  | 11-Apr | 12-Apr | 23-Apr | - Date check
CDUVDU30260 | In Progress | Deblinding & handover to Operation. | 23/04/2023 09:35:48 |  | 12/04/2023 03:00:00 | 12/04/2023 15:00:00 | L-107(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  |  | 12-Apr | 12-Apr | 23-Apr | - Date check
CDUVDU30270 | In Progress | Hydrotest Witness | 23/04/2023 09:36:00 |  | 11/04/2023 14:00:00 | 11/04/2023 17:00:00 | L-107(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | INSPECTION |  |  | 3 | 3:00 | 0:00 |  |  | 11-Apr | 11-Apr | 23-Apr | - Date check
CDUVDU11950 | In Progress | Inspection activities | 25/04/2023 16:06:40 |  | 06/04/2023 20:00:00 | 10/04/2023 08:00:00 | "2""-P-01-2015-A6N" | INSP RECOMM | 0 | INSPECTION |  |  | 84 | 84:00 | 0:00 |  |  | 06-Apr | 10-Apr | 25-Apr | - Date check
CDUVDU18400 | Not Started | HT preparation |  |  | 10/04/2023 08:00:00 | 11/04/2023 04:00:00 | "2""-P-01-2015-A6N" | INSP RECOMM | 0 | MECHANICAL |  |  | 20 | 20:00 | 0:00 |  |  | 10-Apr | 11-Apr | - Date check | - Date check
CDUVDU20420 | Not Started | Hydrotest Witness |  |  | 11/04/2023 04:00:00 | 12/04/2023 00:00:00 | "2""-P-01-2015-A6N" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 20 | 20:00 | 0:00 |  |  | 11-Apr | 12-Apr | - Date check | - Date check
CDUVDU22350 | Not Started | Draining |  |  | 12/04/2023 00:00:00 | 12/04/2023 12:00:00 | "2""-P-01-2015-A6N" | INSP RECOMM | 0 | MECHANICAL |  |  | 12 | 12:00 | 0:00 |  |  | 12-Apr | 12-Apr | - Date check | - Date check
CDUVDU23560 | Not Started | De-blinding and hand-over |  |  | 12/04/2023 12:00:00 | 13/04/2023 08:00:00 | "2""-P-01-2015-A6N" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 20 | 20:00 | 0:00 |  |  | 12-Apr | 13-Apr | - Date check | - Date check
CDUVDU8730 | Completed | Blinding | 13/04/2023 09:24:19 | 13/04/2023 09:24:23 | 04/04/2023 14:00:00 | 05/04/2023 02:00:00 | "2""-P-01-2015-A6N" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 04-Apr | 05-Apr | 13-Apr | 13-Apr
CDUVDU9500 | In Progress | Cutting, grinding, fit-up, welding and NDT (133 ID) | 17/04/2023 15:21:54 |  | 05/04/2023 02:00:00 | 06/04/2023 20:00:00 | "2""-P-01-2015-A6N" | INSP RECOMM | 60.1504 | MECHANICAL |  |  | 42 | 42:00 | 0:00 |  |  | 05-Apr | 06-Apr | 17-Apr | - Date check
CDUVDU14150 | Completed | Blinding | 08/04/2023 10:05:00 | 08/04/2023 10:05:04 | 08/04/2023 07:00:00 | 09/04/2023 01:00:00 | "4""-P-01-2301-A1A" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 18 | 18:00 | 0:00 |  | 18:00 | 08-Apr | 09-Apr | 08-Apr | 08-Apr
CDUVDU15490 | Completed | Cutting, grinding, fit-up, welding and NDT | 08/04/2023 10:05:16 | 08/04/2023 10:05:27 | 09/04/2023 01:00:00 | 09/04/2023 22:00:00 | "4""-P-01-2301-A1A" | INSP RECOMM | 100 | MECHANICAL |  |  | 21 | 21:00 | 0:00 |  | 21:00 | 09-Apr | 09-Apr | 08-Apr | 08-Apr
CDUVDU16190 | Completed | Inspection activities | 19/04/2023 11:38:03 | 19/04/2023 11:38:08 | 09/04/2023 09:00:00 | 10/04/2023 05:00:00 | "4""-P-01-2301-A1A" | INSP RECOMM | 100 | INSPECTION |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 09-Apr | 10-Apr | 19-Apr | 19-Apr
CDUVDU18150 | Completed | HT preparation | 19/04/2023 11:38:19 | 19/04/2023 11:38:19 | 10/04/2023 05:00:00 | 10/04/2023 17:00:00 | "4""-P-01-2301-A1A" | INSP RECOMM | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:00 |  |  | 10-Apr | 10-Apr | 19-Apr | 19-Apr
CDUVDU19240 | Completed | Hydrotest Witness | 19/04/2023 11:38:19 | 19/04/2023 11:38:19 | 10/04/2023 17:00:00 | 10/04/2023 23:00:00 | "4""-P-01-2301-A1A" | INSP RECOMM | 100 | INSPECTION | HYDRO TEST | HYDRO TEST | 6 | 6:00 | 0:00 |  |  | 10-Apr | 10-Apr | 19-Apr | 19-Apr
CDUVDU19790 | Completed | Draining | 23/04/2023 12:14:52 | 23/04/2023 12:14:52 | 10/04/2023 23:00:00 | 11/04/2023 09:00:00 | "4""-P-01-2301-A1A" | INSP RECOMM | 100 | MECHANICAL |  |  | 10 | 10:00 | 0:00 |  |  | 10-Apr | 11-Apr | 23-Apr | 23-Apr
CDUVDU20860 | Completed | De-blinding and hand-over | 23/04/2023 12:15:04 | 23/04/2023 12:15:10 | 11/04/2023 09:00:00 | 12/04/2023 03:00:00 | "4""-P-01-2301-A1A" | INSP RECOMM | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 18 | 18:00 | 0:00 |  | 18:00 | 11-Apr | 12-Apr | 23-Apr | 23-Apr
CDUVDU15500 | Completed | Blinding | 18/04/2023 10:43:55 | 18/04/2023 10:44:00 | 09/04/2023 01:00:00 | 09/04/2023 19:00:00 | "4""-P-01-2305-A1A" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 18 | 18:00 | 0:00 |  | 18:00 | 09-Apr | 09-Apr | 18-Apr | 18-Apr
CDUVDU16970 | Completed | Cutting, grinding, fit-up, welding and NDT | 18/04/2023 10:44:08 | 18/04/2023 10:44:13 | 09/04/2023 19:00:00 | 10/04/2023 16:00:00 | "4""-P-01-2305-A1A" | INSP RECOMM | 100 | MECHANICAL |  |  | 21 | 21:00 | 0:00 |  | 21:00 | 09-Apr | 10-Apr | 18-Apr | 18-Apr
CDUVDU17860 | Completed | Inspection activities | 18/04/2023 10:44:43 | 18/04/2023 10:45:28 | 10/04/2023 03:00:00 | 10/04/2023 23:00:00 | "4""-P-01-2305-A1A" | INSP RECOMM | 100 | INSPECTION |  |  | 20 | 20:00 | 0:01 |  | 19:59 | 10-Apr | 10-Apr | 18-Apr | 18-Apr
CDUVDU19800 | Completed | HT preparation | 23/04/2023 12:15:50 | 23/04/2023 12:15:50 | 10/04/2023 23:00:00 | 11/04/2023 11:00:00 | "4""-P-01-2305-A1A" | INSP RECOMM | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:00 |  |  | 10-Apr | 11-Apr | 23-Apr | 23-Apr
CDUVDU21040 | Completed | Hydrotest Witness | 23/04/2023 12:15:50 | 23/04/2023 12:15:50 | 11/04/2023 11:00:00 | 11/04/2023 17:00:00 | "4""-P-01-2305-A1A" | INSP RECOMM | 100 | INSPECTION | HYDRO TEST | HYDRO TEST | 6 | 6:00 | 0:00 |  |  | 11-Apr | 11-Apr | 23-Apr | 23-Apr
CDUVDU21710 | Completed | Draining | 23/04/2023 12:15:50 | 23/04/2023 12:15:50 | 11/04/2023 17:00:00 | 12/04/2023 03:00:00 | "4""-P-01-2305-A1A" | INSP RECOMM | 100 | MECHANICAL |  |  | 10 | 10:00 | 0:00 |  |  | 11-Apr | 12-Apr | 23-Apr | 23-Apr
CDUVDU22690 | Completed | De-blinding and hand-over | 23/04/2023 12:15:50 | 23/04/2023 12:15:50 | 12/04/2023 03:00:00 | 12/04/2023 21:00:00 | "4""-P-01-2305-A1A" | INSP RECOMM | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 18 | 18:00 | 0:00 |  |  | 12-Apr | 12-Apr | 23-Apr | 23-Apr
CDUVDU15510 | Completed | Blinding | 19/04/2023 10:29:48 | 23/04/2023 12:16:52 | 09/04/2023 01:00:00 | 09/04/2023 19:00:00 | "2""-P-01-1740-A1A-N" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 18 | 18:00 | 97:47 | 79:47 |  | 09-Apr | 09-Apr | 19-Apr | 23-Apr
CDUVDU16980 | Completed | Cutting, grinding, fit-up, welding and NDT | 23/04/2023 12:16:52 | 23/04/2023 12:16:52 | 09/04/2023 19:00:00 | 10/04/2023 16:00:00 | "2""-P-01-1740-A1A-N" | INSP RECOMM | 100 | MECHANICAL |  |  | 21 | 21:00 | 0:00 |  |  | 09-Apr | 10-Apr | 23-Apr | 23-Apr
CDUVDU17870 | Completed | Inspection activities | 23/04/2023 12:16:52 | 23/04/2023 12:16:52 | 10/04/2023 03:00:00 | 10/04/2023 23:00:00 | "2""-P-01-1740-A1A-N" | INSP RECOMM | 100 | INSPECTION |  |  | 20 | 20:00 | 0:00 |  |  | 10-Apr | 10-Apr | 23-Apr | 23-Apr
CDUVDU19810 | Completed | HT preparation | 23/04/2023 12:16:52 | 23/04/2023 12:16:52 | 10/04/2023 23:00:00 | 11/04/2023 11:00:00 | "2""-P-01-1740-A1A-N" | INSP RECOMM | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:00 |  |  | 10-Apr | 11-Apr | 23-Apr | 23-Apr
CDUVDU21050 | Completed | Hydrotest Witness | 23/04/2023 12:16:52 | 23/04/2023 12:16:52 | 11/04/2023 11:00:00 | 11/04/2023 17:00:00 | "2""-P-01-1740-A1A-N" | INSP RECOMM | 100 | INSPECTION | HYDRO TEST | HYDRO TEST | 6 | 6:00 | 0:00 |  |  | 11-Apr | 11-Apr | 23-Apr | 23-Apr
CDUVDU21720 | Completed | Draining | 23/04/2023 12:16:52 | 23/04/2023 12:16:52 | 11/04/2023 17:00:00 | 12/04/2023 03:00:00 | "2""-P-01-1740-A1A-N" | INSP RECOMM | 100 | MECHANICAL |  |  | 10 | 10:00 | 0:00 |  |  | 11-Apr | 12-Apr | 23-Apr | 23-Apr
CDUVDU22700 | Completed | De-blinding and hand-over | 23/04/2023 12:16:52 | 23/04/2023 12:16:52 | 12/04/2023 03:00:00 | 12/04/2023 21:00:00 | "2""-P-01-1740-A1A-N" | INSP RECOMM | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 18 | 18:00 | 0:00 |  |  | 12-Apr | 12-Apr | 23-Apr | 23-Apr
CDUVDU14520 | Completed | Cutting, grinding, fit-up, welding and NDT (24 ID) | 25/04/2023 17:05:31 | 26/04/2023 16:53:14 | 08/04/2023 12:00:00 | 10/04/2023 04:00:00 | "4""-P-01-2149-A6N" | INSP RECOMM | 100 | MECHANICAL |  |  | 40 | 40:00 | 23:48 |  | 16:12 | 08-Apr | 10-Apr | 25-Apr | 26-Apr
CDUVDU18000 | Not Started | Inspection activities |  |  | 10/04/2023 04:00:00 | 11/04/2023 20:00:00 | "4""-P-01-2149-A6N" | INSP RECOMM | 0 | INSPECTION |  |  | 40 | 40:00 | 0:00 |  |  | 10-Apr | 11-Apr | - Date check | - Date check
CDUVDU22060 | Not Started | HT preparation |  |  | 11/04/2023 20:00:00 | 12/04/2023 16:00:00 | "4""-P-01-2149-A6N" | INSP RECOMM | 0 | MECHANICAL |  |  | 20 | 20:00 | 0:00 |  |  | 11-Apr | 12-Apr | - Date check | - Date check
CDUVDU23910 | Not Started | Hydrotest Witness |  |  | 12/04/2023 16:00:00 | 13/04/2023 04:00:00 | "4""-P-01-2149-A6N" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 12 | 12:00 | 0:00 |  |  | 12-Apr | 13-Apr | - Date check | - Date check
CDUVDU24800 | Not Started | Draining |  |  | 13/04/2023 04:00:00 | 13/04/2023 16:00:00 | "4""-P-01-2149-A6N" | INSP RECOMM | 0 | MECHANICAL |  |  | 12 | 12:00 | 0:00 |  |  | 13-Apr | 13-Apr | - Date check | - Date check
CDUVDU25530 | Not Started | De-blinding and hand-over |  |  | 13/04/2023 16:00:00 | 14/04/2023 12:00:00 | "4""-P-01-2149-A6N" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 20 | 20:00 | 0:00 |  |  | 13-Apr | 14-Apr | - Date check | - Date check
CDUVDU9720 | Completed | Blinding | 25/04/2023 17:04:59 | 25/04/2023 17:05:20 | 05/04/2023 05:00:00 | 06/04/2023 01:00:00 | "4""-P-01-2149-A6N" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 20 | 20:00 | 0:00 |  | 20:00 | 05-Apr | 06-Apr | 25-Apr | 25-Apr
CDUVDU10050 | Completed | Cutting, grinding, fit-up | 20/04/2023 16:55:35 | 20/04/2023 16:55:35 | 05/04/2023 13:00:00 | 06/04/2023 05:00:00 | "12""-P-01-1204-B1A" | INSP RECOMM | 100 | MECHANICAL |  |  | 16 | 16:00 | 0:00 |  |  | 05-Apr | 06-Apr | 20-Apr | 20-Apr
CDUVDU11030 | Completed | Pre-heating, welding and pre SR radiography (4 ID) | 20/04/2023 16:55:35 | 20/04/2023 16:55:35 | 06/04/2023 05:00:00 | 07/04/2023 01:00:00 | "12""-P-01-1204-B1A" | INSP RECOMM | 100 | MECHANICAL |  |  | 20 | 20:00 | 0:00 |  |  | 06-Apr | 07-Apr | 20-Apr | 20-Apr
CDUVDU11330 | Completed | Inspection activities | 20/04/2023 16:55:35 | 20/04/2023 16:55:35 | 06/04/2023 11:00:00 | 07/04/2023 07:00:00 | "12""-P-01-1204-B1A" | INSP RECOMM | 100 | INSPECTION |  |  | 20 | 20:00 | 0:00 |  |  | 06-Apr | 07-Apr | 20-Apr | 20-Apr
CDUVDU12720 | Completed | Post SR and radiography | 20/04/2023 16:55:35 | 20/04/2023 16:55:35 | 07/04/2023 07:00:00 | 08/04/2023 03:00:00 | "12""-P-01-1204-B1A" | INSP RECOMM | 100 | INSPECTION |  |  | 20 | 20:00 | 0:00 |  |  | 07-Apr | 08-Apr | 20-Apr | 20-Apr
CDUVDU13920 | Completed | HT preparation | 20/04/2023 16:55:35 | 20/04/2023 16:55:35 | 08/04/2023 03:00:00 | 08/04/2023 15:00:00 | "12""-P-01-1204-B1A" | INSP RECOMM | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:00 |  |  | 08-Apr | 08-Apr | 20-Apr | 20-Apr
CDUVDU15010 | Completed | Hydrotest Witness | 20/04/2023 16:55:35 | 20/04/2023 16:55:35 | 08/04/2023 18:00:00 | 08/04/2023 21:00:00 | "12""-P-01-1204-B1A" | INSP RECOMM | 100 | INSPECTION | HYDRO TEST | HYDRO TEST | 3 | 3:00 | 0:00 |  |  | 08-Apr | 08-Apr | 20-Apr | 20-Apr
CDUVDU15180 | Completed | Draining | 20/04/2023 16:55:35 | 20/04/2023 16:55:35 | 08/04/2023 21:00:00 | 09/04/2023 03:00:00 | "12""-P-01-1204-B1A" | INSP RECOMM | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 08-Apr | 09-Apr | 20-Apr | 20-Apr
CDUVDU15780 | Completed | De-blinding and hand-over | 20/04/2023 16:55:35 | 20/04/2023 16:55:35 | 09/04/2023 03:00:00 | 09/04/2023 11:00:00 | "12""-P-01-1204-B1A" | INSP RECOMM | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:00 |  |  | 09-Apr | 09-Apr | 20-Apr | 20-Apr
CDUVDU9730 | Completed | Blinding | 20/04/2023 16:55:35 | 20/04/2023 16:55:35 | 05/04/2023 05:00:00 | 05/04/2023 13:00:00 | "12""-P-01-1204-B1A" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  |  | 05-Apr | 05-Apr | 20-Apr | 20-Apr
CDUVDU11050 | Completed | Cutting, grinding, fit-up, welding and NDT(4 ID) | 26/04/2023 12:27:16 | 26/04/2023 12:28:16 | 06/04/2023 05:00:00 | 07/04/2023 01:00:00 | "4""-P-01-4102-A1A" | INSP RECOMM | 100 | MECHANICAL |  |  | 20 | 20:00 | 0:01 |  | 19:59 | 06-Apr | 07-Apr | 26-Apr | 26-Apr
CDUVDU12730 | Completed | Inspection activities | 26/04/2023 12:27:16 | 26/04/2023 12:28:16 | 07/04/2023 07:00:00 | 08/04/2023 03:00:00 | "4""-P-01-4102-A1A" | INSP RECOMM | 100 | INSPECTION |  |  | 20 | 20:00 | 0:01 |  | 19:59 | 07-Apr | 08-Apr | 26-Apr | 26-Apr
CDUVDU14830 | Completed | HT preparation | 26/04/2023 12:27:16 | 26/04/2023 12:28:16 | 08/04/2023 15:00:00 | 09/04/2023 03:00:00 | "4""-P-01-4102-A1A" | INSP RECOMM | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:01 |  | 11:59 | 08-Apr | 09-Apr | 26-Apr | 26-Apr
CDUVDU15790 | Completed | Hydrotest Witness | 26/04/2023 12:27:16 | 26/04/2023 12:28:16 | 09/04/2023 03:00:00 | 09/04/2023 07:00:00 | "4""-P-01-4102-A1A" | INSP RECOMM | 100 | INSPECTION | HYDRO TEST | HYDRO TEST | 4 | 4:00 | 0:01 |  | 3:59 | 09-Apr | 09-Apr | 26-Apr | 26-Apr
CDUVDU15990 | Completed | Draining | 26/04/2023 12:27:16 | 26/04/2023 12:28:16 | 09/04/2023 07:00:00 | 09/04/2023 13:00:00 | "4""-P-01-4102-A1A" | INSP RECOMM | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:01 |  | 5:59 | 09-Apr | 09-Apr | 26-Apr | 26-Apr
CDUVDU16520 | Completed | De-blinding and hand-over | 26/04/2023 12:27:16 | 26/04/2023 12:28:16 | 09/04/2023 13:00:00 | 09/04/2023 21:00:00 | "4""-P-01-4102-A1A" | INSP RECOMM | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:01 |  | 7:59 | 09-Apr | 09-Apr | 26-Apr | 26-Apr
CDUVDU9760 | Completed | Blinding | 26/04/2023 12:27:16 | 26/04/2023 12:28:16 | 05/04/2023 05:00:00 | 05/04/2023 13:00:00 | "4""-P-01-4102-A1A" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:01 |  | 7:59 | 05-Apr | 05-Apr | 26-Apr | 26-Apr
CDUVDU11040 | Completed | Cutting, grinding, fit-up | 26/04/2023 12:27:38 | 26/04/2023 12:28:38 | 06/04/2023 05:00:00 | 06/04/2023 21:00:00 | "3""-P-01-4024-A1A" | INSP RECOMM | 100 | MECHANICAL |  |  | 16 | 16:00 | 0:01 |  | 15:59 | 06-Apr | 06-Apr | 26-Apr | 26-Apr
CDUVDU12280 | Completed | Pre-heating, welding and pre SR radiography (4 ID) | 26/04/2023 12:27:38 | 26/04/2023 12:28:38 | 07/04/2023 01:00:00 | 07/04/2023 21:00:00 | "3""-P-01-4024-A1A" | INSP RECOMM | 100 | MECHANICAL |  |  | 20 | 20:00 | 0:01 |  | 19:59 | 07-Apr | 07-Apr | 26-Apr | 26-Apr
CDUVDU13570 | Completed | Inspection activities | 26/04/2023 12:27:38 | 26/04/2023 12:28:38 | 07/04/2023 21:00:00 | 08/04/2023 17:00:00 | "3""-P-01-4024-A1A" | INSP RECOMM | 100 | INSPECTION |  |  | 20 | 20:00 | 0:01 |  | 19:59 | 07-Apr | 08-Apr | 26-Apr | 26-Apr
CDUVDU14920 | Completed | Post SR and radiography | 26/04/2023 12:27:38 | 26/04/2023 12:28:38 | 08/04/2023 17:00:00 | 09/04/2023 13:00:00 | "3""-P-01-4024-A1A" | INSP RECOMM | 100 | INSPECTION |  |  | 20 | 20:00 | 0:01 |  | 19:59 | 08-Apr | 09-Apr | 26-Apr | 26-Apr
CDUVDU16500 | Completed | HT preparation | 26/04/2023 12:27:38 | 26/04/2023 12:28:38 | 09/04/2023 13:00:00 | 10/04/2023 01:00:00 | "3""-P-01-4024-A1A" | INSP RECOMM | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:01 |  | 11:59 | 09-Apr | 10-Apr | 26-Apr | 26-Apr
CDUVDU17650 | Completed | Hydrotest Witness | 26/04/2023 12:27:38 | 26/04/2023 12:28:38 | 10/04/2023 01:00:00 | 10/04/2023 04:00:00 | "3""-P-01-4024-A1A" | INSP RECOMM | 100 | INSPECTION | HYDRO TEST | HYDRO TEST | 3 | 3:00 | 0:01 |  | 2:59 | 10-Apr | 10-Apr | 26-Apr | 26-Apr
CDUVDU18010 | Completed | Draining | 26/04/2023 12:27:38 | 26/04/2023 12:28:38 | 10/04/2023 04:00:00 | 10/04/2023 10:00:00 | "3""-P-01-4024-A1A" | INSP RECOMM | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:01 |  | 5:59 | 10-Apr | 10-Apr | 26-Apr | 26-Apr
CDUVDU18540 | Completed | De-blinding and hand-over | 26/04/2023 12:27:38 | 26/04/2023 12:28:38 | 10/04/2023 10:00:00 | 10/04/2023 18:00:00 | "3""-P-01-4024-A1A" | INSP RECOMM | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:01 |  | 7:59 | 10-Apr | 10-Apr | 26-Apr | 26-Apr
CDUVDU9740 | Completed | Blinding | 26/04/2023 12:27:38 | 26/04/2023 12:28:38 | 05/04/2023 05:00:00 | 05/04/2023 13:00:00 | "3""-P-01-4024-A1A" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:01 |  | 7:59 | 05-Apr | 05-Apr | 26-Apr | 26-Apr
CDUVDU12000 | Completed | Cutting, grinding, fit-up | 26/04/2023 12:27:57 | 26/04/2023 12:28:57 | 06/04/2023 21:00:00 | 07/04/2023 05:00:00 | "1.5""-P-01-4107-A1A" | INSP RECOMM | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:01 |  | 7:59 | 06-Apr | 07-Apr | 26-Apr | 26-Apr
CDUVDU13580 | Completed | Pre-heating, welding and pre SR radiography (2 ID) | 26/04/2023 12:27:57 | 26/04/2023 12:28:57 | 07/04/2023 21:00:00 | 08/04/2023 17:00:00 | "1.5""-P-01-4107-A1A" | INSP RECOMM | 100 | MECHANICAL |  |  | 20 | 20:00 | 0:01 |  | 19:59 | 07-Apr | 08-Apr | 26-Apr | 26-Apr
CDUVDU14930 | Completed | Inspection activities | 26/04/2023 12:27:57 | 26/04/2023 12:28:57 | 08/04/2023 17:00:00 | 09/04/2023 13:00:00 | "1.5""-P-01-4107-A1A" | INSP RECOMM | 100 | INSPECTION |  |  | 20 | 20:00 | 0:01 |  | 19:59 | 08-Apr | 09-Apr | 26-Apr | 26-Apr
CDUVDU16510 | Completed | Post SR and radiography | 26/04/2023 12:27:57 | 26/04/2023 12:28:57 | 09/04/2023 13:00:00 | 10/04/2023 09:00:00 | "1.5""-P-01-4107-A1A" | INSP RECOMM | 100 | INSPECTION |  |  | 20 | 20:00 | 0:01 |  | 19:59 | 09-Apr | 10-Apr | 26-Apr | 26-Apr
CDUVDU18470 | Completed | HT preparation | 26/04/2023 12:27:57 | 26/04/2023 12:28:57 | 10/04/2023 09:00:00 | 10/04/2023 21:00:00 | "1.5""-P-01-4107-A1A" | INSP RECOMM | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:01 |  | 11:59 | 10-Apr | 10-Apr | 26-Apr | 26-Apr
CDUVDU19560 | Completed | Hydrotest Witness | 26/04/2023 12:27:57 | 26/04/2023 12:28:57 | 10/04/2023 21:00:00 | 11/04/2023 00:00:00 | "1.5""-P-01-4107-A1A" | INSP RECOMM | 100 | INSPECTION | HYDRO TEST | HYDRO TEST | 3 | 3:00 | 0:01 |  | 2:59 | 10-Apr | 11-Apr | 26-Apr | 26-Apr
CDUVDU19970 | Completed | Draining | 26/04/2023 12:27:57 | 26/04/2023 12:28:57 | 11/04/2023 00:00:00 | 11/04/2023 06:00:00 | "1.5""-P-01-4107-A1A" | INSP RECOMM | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:01 |  | 5:59 | 11-Apr | 11-Apr | 26-Apr | 26-Apr
CDUVDU20580 | Completed | De-blinding and hand-over | 26/04/2023 12:27:57 | 26/04/2023 12:28:57 | 11/04/2023 06:00:00 | 11/04/2023 14:00:00 | "1.5""-P-01-4107-A1A" | INSP RECOMM | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:01 |  | 7:59 | 11-Apr | 11-Apr | 26-Apr | 26-Apr
CDUVDU9750 | Completed | Blinding | 26/04/2023 12:27:57 | 26/04/2023 12:28:57 | 05/04/2023 05:00:00 | 05/04/2023 13:00:00 | "1.5""-P-01-4107-A1A" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:01 |  | 7:59 | 05-Apr | 05-Apr | 26-Apr | 26-Apr
CDUVDU10070 | Completed | Blinding | 15/04/2023 15:17:12 | 15/04/2023 15:17:22 | 05/04/2023 13:00:00 | 05/04/2023 21:00:00 | "3""-P-01-4021-A1A" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 05-Apr | 05-Apr | 15-Apr | 15-Apr
CDUVDU12600 | Completed | Cutting, grinding, fit-up, welding and radiography (4 ID) | 15/04/2023 15:17:29 | 15/04/2023 15:17:42 | 07/04/2023 05:00:00 | 08/04/2023 01:00:00 | "3""-P-01-4021-A1A" | INSP RECOMM | 100 | MECHANICAL |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 07-Apr | 08-Apr | 15-Apr | 15-Apr
CDUVDU13930 | Completed | Inspection activities | 15/04/2023 15:18:00 | 15/04/2023 15:18:04 | 08/04/2023 03:00:00 | 08/04/2023 23:00:00 | "3""-P-01-4021-A1A" | INSP RECOMM | 100 | INSPECTION |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 08-Apr | 08-Apr | 15-Apr | 15-Apr
CDUVDU30900 | Not Started | HT preparation |  |  | 08/04/2023 23:00:00 | 09/04/2023 11:00:00 | "3""-P-01-4021-A1A" | INSP RECOMM | 0 | MECHANICAL |  |  | 12 | 12:00 | 0:00 |  |  | 08-Apr | 09-Apr | - Date check | - Date check
CDUVDU30910 | Not Started | Hydrotest Witness |  |  | 09/04/2023 16:00:00 | 09/04/2023 19:00:00 | "3""-P-01-4021-A1A" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 3 | 3:00 | 0:00 |  |  | 09-Apr | 09-Apr | - Date check | - Date check
CDUVDU30920 | Not Started | Draining |  |  | 09/04/2023 19:00:00 | 10/04/2023 01:00:00 | "3""-P-01-4021-A1A" | INSP RECOMM | 0 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 09-Apr | 10-Apr | - Date check | - Date check
CDUVDU30930 | Not Started | De-blinding and hand-over |  |  | 10/04/2023 01:00:00 | 10/04/2023 09:00:00 | "3""-P-01-4021-A1A" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:00 |  |  | 10-Apr | 10-Apr | - Date check | - Date check
CDUVDU11800 | Not Started | Inspection activities |  |  | 06/04/2023 18:00:00 | 10/04/2023 06:00:00 | "4""-P-01-2132-B1N" | INSP RECOMM | 0 | INSPECTION |  |  | 84 | 84:00 | 0:00 |  |  | 06-Apr | 10-Apr | - Date check | - Date check
CDUVDU18260 | Not Started | HT preparation |  |  | 10/04/2023 06:00:00 | 11/04/2023 02:00:00 | "4""-P-01-2132-B1N" | INSP RECOMM | 0 | MECHANICAL |  |  | 20 | 20:00 | 0:00 |  |  | 10-Apr | 11-Apr | - Date check | - Date check
CDUVDU20140 | Not Started | Hydrotest Witness |  |  | 11/04/2023 02:00:00 | 11/04/2023 14:00:00 | "4""-P-01-2132-B1N" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 12 | 12:00 | 0:00 |  |  | 11-Apr | 11-Apr | - Date check | - Date check
CDUVDU21330 | Not Started | Draining |  |  | 11/04/2023 14:00:00 | 12/04/2023 10:00:00 | "4""-P-01-2132-B1N" | INSP RECOMM | 0 | MECHANICAL |  |  | 20 | 20:00 | 0:00 |  |  | 11-Apr | 12-Apr | - Date check | - Date check
CDUVDU23290 | Not Started | De-blinding and hand-over |  |  | 12/04/2023 10:00:00 | 13/04/2023 01:00:00 | "4""-P-01-2132-B1N" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 15 | 15:00 | 0:00 |  |  | 12-Apr | 13-Apr | - Date check | - Date check
CDUVDU8740 | Completed | Blinding | 17/04/2023 15:22:12 | 20/04/2023 09:30:53 | 04/04/2023 14:00:00 | 05/04/2023 02:00:00 | "4""-P-01-2132-B1N" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 66:09 | 54:09 |  | 04-Apr | 05-Apr | 17-Apr | 20-Apr
CDUVDU9510 | In Progress | Cutting, grinding, fit-up, welding and NDT(32 ID) | 26/04/2023 18:42:37 |  | 05/04/2023 02:00:00 | 06/04/2023 18:00:00 | "4""-P-01-2132-B1N" | INSP RECOMM | 50 | MECHANICAL |  |  | 40 | 40:00 | 0:00 |  |  | 05-Apr | 06-Apr | 26-Apr | - Date check
CDUVDU10060 | Completed | Blinding | 26/04/2023 12:31:14 | 26/04/2023 12:32:14 | 05/04/2023 13:00:00 | 05/04/2023 21:00:00 | "3""-P-01-4010-A1A" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:01 |  | 7:59 | 05-Apr | 05-Apr | 26-Apr | 26-Apr
CDUVDU13750 | Completed | Cutting, grinding, fit-up, welding and radiography (8 ID) | 26/04/2023 12:31:14 | 26/04/2023 12:32:14 | 08/04/2023 01:00:00 | 08/04/2023 21:00:00 | "3""-P-01-4010-A1A" | INSP RECOMM | 100 | MECHANICAL |  |  | 20 | 20:00 | 0:01 |  | 19:59 | 08-Apr | 08-Apr | 26-Apr | 26-Apr
CDUVDU15330 | Completed | Inspection activities | 26/04/2023 12:31:14 | 26/04/2023 12:32:14 | 08/04/2023 23:00:00 | 09/04/2023 19:00:00 | "3""-P-01-4010-A1A" | INSP RECOMM | 100 | INSPECTION |  |  | 20 | 20:00 | 0:01 |  | 19:59 | 08-Apr | 09-Apr | 26-Apr | 26-Apr
CDUVDU16960 | Completed | HT preparation | 26/04/2023 12:31:14 | 26/04/2023 12:32:14 | 09/04/2023 19:00:00 | 10/04/2023 07:00:00 | "3""-P-01-4010-A1A" | INSP RECOMM | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:01 |  | 11:59 | 09-Apr | 10-Apr | 26-Apr | 26-Apr
CDUVDU21690 | Completed | Hydrotest Witness | 26/04/2023 12:31:14 | 26/04/2023 12:32:14 | 10/04/2023 07:00:00 | 10/04/2023 11:00:00 | "3""-P-01-4010-A1A" | INSP RECOMM | 100 | INSPECTION | HYDRO TEST | HYDRO TEST | 4 | 4:00 | 0:01 |  | 3:59 | 10-Apr | 10-Apr | 26-Apr | 26-Apr
CDUVDU22290 | Completed | Draining | 26/04/2023 12:31:14 | 26/04/2023 12:32:14 | 10/04/2023 11:00:00 | 10/04/2023 17:00:00 | "3""-P-01-4010-A1A" | INSP RECOMM | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:01 |  | 5:59 | 10-Apr | 10-Apr | 26-Apr | 26-Apr
CDUVDU23090 | Completed | De-blinding and hand-over | 26/04/2023 12:31:14 | 26/04/2023 12:32:14 | 10/04/2023 17:00:00 | 11/04/2023 01:00:00 | "3""-P-01-4010-A1A" | INSP RECOMM | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:01 |  | 7:59 | 10-Apr | 11-Apr | 26-Apr | 26-Apr
CDUVDU10520 | Completed | Blinding | 08/04/2023 09:48:24 | 08/04/2023 09:48:30 | 05/04/2023 18:00:00 | 06/04/2023 02:00:00 | "10""-P-01-1525-B1A-IH" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 05-Apr | 06-Apr | 08-Apr | 08-Apr
CDUVDU15390 | Completed | Cutting, grinding, fit-up, welding and NDT (4 ID) | 08/04/2023 09:48:44 | 15/04/2023 15:19:19 | 09/04/2023 00:00:00 | 09/04/2023 20:00:00 | "10""-P-01-1525-B1A-IH" | INSP RECOMM | 100 | MECHANICAL |  |  | 20 | 20:00 | 173:31 | 153:31 |  | 09-Apr | 09-Apr | 08-Apr | 15-Apr
CDUVDU17290 | Completed | Inspection activities | 15/04/2023 15:19:45 | 15/04/2023 15:19:51 | 09/04/2023 22:00:00 | 10/04/2023 18:00:00 | "10""-P-01-1525-B1A-IH" | INSP RECOMM | 100 | INSPECTION |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 09-Apr | 10-Apr | 15-Apr | 15-Apr
CDUVDU19470 | Completed | HT preparation | 25/04/2023 16:48:40 | 25/04/2023 16:48:40 | 10/04/2023 20:00:00 | 11/04/2023 08:00:00 | "10""-P-01-1525-B1A-IH" | INSP RECOMM | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:00 |  |  | 10-Apr | 11-Apr | 25-Apr | 25-Apr
CDUVDU22120 | Completed | Hydrotest Witness | 25/04/2023 16:48:40 | 25/04/2023 16:48:40 | 11/04/2023 08:00:00 | 11/04/2023 11:00:00 | "10""-P-01-1525-B1A-IH" | INSP RECOMM | 100 | INSPECTION | HYDRO TEST | HYDRO TEST | 3 | 3:00 | 0:00 |  |  | 11-Apr | 11-Apr | 25-Apr | 25-Apr
CDUVDU22360 | Completed | Draining | 25/04/2023 16:48:40 | 25/04/2023 16:48:40 | 11/04/2023 11:00:00 | 11/04/2023 17:00:00 | "10""-P-01-1525-B1A-IH" | INSP RECOMM | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 11-Apr | 11-Apr | 25-Apr | 25-Apr
CDUVDU23820 | Completed | De-blinding and hand-over | 25/04/2023 16:48:40 | 25/04/2023 16:48:40 | 11/04/2023 17:00:00 | 12/04/2023 01:00:00 | "10""-P-01-1525-B1A-IH" | INSP RECOMM | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:00 |  |  | 11-Apr | 12-Apr | 25-Apr | 25-Apr
CDUVDU10740 | Completed | Blinding | 08/04/2023 15:57:46 | 08/04/2023 15:57:55 | 06/04/2023 02:00:00 | 06/04/2023 10:00:00 | "10""-P-01-1526-B1A-IH" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 06-Apr | 06-Apr | 08-Apr | 08-Apr
CDUVDU17170 | Completed | Cutting, grinding, fit-up, welding and NDT (8 ID) | 08/04/2023 15:58:11 | 15/04/2023 15:20:28 | 09/04/2023 20:00:00 | 10/04/2023 16:00:00 | "10""-P-01-1526-B1A-IH" | INSP RECOMM | 100 | MECHANICAL |  |  | 20 | 20:00 | 167:22 | 147:22 |  | 09-Apr | 10-Apr | 08-Apr | 15-Apr
CDUVDU19320 | Completed | Inspection activities | 15/04/2023 15:20:50 | 15/04/2023 15:20:55 | 10/04/2023 18:00:00 | 11/04/2023 14:00:00 | "10""-P-01-1526-B1A-IH" | INSP RECOMM | 100 | INSPECTION |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 10-Apr | 11-Apr | 15-Apr | 15-Apr
CDUVDU21340 | Completed | HT preparation | 25/04/2023 16:49:07 | 25/04/2023 16:49:07 | 11/04/2023 14:00:00 | 12/04/2023 02:00:00 | "10""-P-01-1526-B1A-IH" | INSP RECOMM | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:00 |  |  | 11-Apr | 12-Apr | 25-Apr | 25-Apr
CDUVDU22490 | Completed | Hydrotest Witness | 25/04/2023 16:49:07 | 25/04/2023 16:49:07 | 12/04/2023 02:00:00 | 12/04/2023 07:00:00 | "10""-P-01-1526-B1A-IH" | INSP RECOMM | 100 | INSPECTION | HYDRO TEST | HYDRO TEST | 5 | 5:00 | 0:00 |  |  | 12-Apr | 12-Apr | 25-Apr | 25-Apr
CDUVDU23100 | Completed | Draining | 25/04/2023 16:49:07 | 25/04/2023 16:49:07 | 12/04/2023 07:00:00 | 12/04/2023 13:00:00 | "10""-P-01-1526-B1A-IH" | INSP RECOMM | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 12-Apr | 12-Apr | 25-Apr | 25-Apr
CDUVDU24430 | Completed | De-blinding and hand-over | 25/04/2023 16:49:07 | 25/04/2023 16:49:07 | 12/04/2023 13:00:00 | 12/04/2023 21:00:00 | "10""-P-01-1526-B1A-IH" | INSP RECOMM | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:00 |  |  | 12-Apr | 12-Apr | 25-Apr | 25-Apr
CDUVDU11170 | Completed | Blinding | 07/04/2023 19:42:32 | 08/04/2023 09:50:38 | 06/04/2023 08:00:00 | 06/04/2023 15:00:00 | "6""-P-01-1621-B1A-N" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 7 | 7:00 | 14:08 | 7:08 |  | 06-Apr | 06-Apr | 07-Apr | 08-Apr
CDUVDU19330 | Completed | Cutting, grinding, fit-up, welding and NDT (4 ID) | 08/04/2023 09:50:51 | 08/04/2023 09:51:55 | 10/04/2023 18:00:00 | 11/04/2023 14:00:00 | "6""-P-01-1621-B1A-N" | INSP RECOMM | 100 | MECHANICAL |  |  | 20 | 20:00 | 0:01 |  | 19:59 | 10-Apr | 11-Apr | 08-Apr | 08-Apr
CDUVDU21350 | Completed | Inspection activities | 15/04/2023 15:22:59 | 15/04/2023 15:23:11 | 11/04/2023 14:00:00 | 12/04/2023 08:00:00 | "6""-P-01-1621-B1A-N" | INSP RECOMM | 100 | INSPECTION |  |  | 18 | 18:00 | 0:00 |  | 18:00 | 11-Apr | 12-Apr | 15-Apr | 15-Apr
CDUVDU23430 | Completed | HT preparation | 19/04/2023 11:30:58 | 19/04/2023 11:31:02 | 12/04/2023 11:00:00 | 12/04/2023 23:00:00 | "6""-P-01-1621-B1A-N" | INSP RECOMM | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:00 |  | 12:00 | 12-Apr | 12-Apr | 19-Apr | 19-Apr
CDUVDU24440 | Completed | Hydrotest Witness | 19/04/2023 11:31:15 | 19/04/2023 11:31:21 | 12/04/2023 23:00:00 | 13/04/2023 04:00:00 | "6""-P-01-1621-B1A-N" | INSP RECOMM | 100 | INSPECTION | HYDRO TEST | HYDRO TEST | 5 | 5:00 | 0:00 |  | 5:00 | 12-Apr | 13-Apr | 19-Apr | 19-Apr
CDUVDU25030 | Completed | Draining | 23/04/2023 11:51:53 | 23/04/2023 11:51:53 | 13/04/2023 07:00:00 | 16/04/2023 15:00:00 | "6""-P-01-1621-B1A-N" | INSP RECOMM | 100 | MECHANICAL |  |  | 80 | 80:00 | 0:00 |  |  | 13-Apr | 16-Apr | 23-Apr | 23-Apr
CDUVDU28390 | Completed | De-blinding and hand-over | 23/04/2023 11:51:53 | 23/04/2023 11:51:53 | 16/04/2023 15:00:00 | 16/04/2023 23:00:00 | "6""-P-01-1621-B1A-N" | INSP RECOMM | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:00 |  |  | 16-Apr | 16-Apr | 23-Apr | 23-Apr
CDUVDU11180 | Completed | Blinding | 07/04/2023 19:44:15 | 07/04/2023 19:44:25 | 06/04/2023 08:00:00 | 06/04/2023 16:00:00 | "2"" CBD FROM 1622" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 06-Apr | 06-Apr | 07-Apr | 07-Apr
CDUVDU21360 | Completed | Cutting, grinding, fit-up, welding and NDT (4 ID) | 07/04/2023 19:44:49 | 08/04/2023 16:00:26 | 11/04/2023 14:00:00 | 12/04/2023 10:00:00 | "2"" CBD FROM 1622" | INSP RECOMM | 100 | MECHANICAL |  |  | 20 | 20:00 | 20:16 | 0:16 |  | 11-Apr | 12-Apr | 07-Apr | 08-Apr
CDUVDU23300 | Completed | Inspection activities | 15/04/2023 15:24:03 | 15/04/2023 15:24:15 | 12/04/2023 10:00:00 | 13/04/2023 06:00:00 | "2"" CBD FROM 1622" | INSP RECOMM | 100 | INSPECTION |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 12-Apr | 13-Apr | 15-Apr | 15-Apr
CDUVDU25150 | Completed | HT preparation | 19/04/2023 11:31:13 | 19/04/2023 11:32:13 | 13/04/2023 09:00:00 | 13/04/2023 21:00:00 | "2"" CBD FROM 1622" | INSP RECOMM | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:01 |  | 11:59 | 13-Apr | 13-Apr | 19-Apr | 19-Apr
CDUVDU25800 | Completed | Hydrotest Witness | 19/04/2023 11:31:47 | 19/04/2023 11:32:47 | 13/04/2023 21:00:00 | 14/04/2023 03:00:00 | "2"" CBD FROM 1622" | INSP RECOMM | 100 | INSPECTION | HYDRO TEST | HYDRO TEST | 6 | 6:00 | 0:01 |  | 5:59 | 13-Apr | 14-Apr | 19-Apr | 19-Apr
CDUVDU28480 | Completed | Draining | 19/04/2023 11:32:02 | 19/04/2023 11:33:02 | 16/04/2023 19:00:00 | 17/04/2023 03:00:00 | "2"" CBD FROM 1622" | INSP RECOMM | 100 | MECHANICAL |  |  | 8 | 8:00 | 0:01 |  | 7:59 | 16-Apr | 17-Apr | 19-Apr | 19-Apr
CDUVDU28710 | Completed | De-blinding and hand-over | 19/04/2023 11:32:29 | 19/04/2023 11:33:29 | 17/04/2023 03:00:00 | 17/04/2023 11:00:00 | "2"" CBD FROM 1622" | INSP RECOMM | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:01 |  | 7:59 | 17-Apr | 17-Apr | 19-Apr | 19-Apr
CDUVDU11400 | Completed | Blinding | 26/04/2023 12:32:24 | 26/04/2023 12:33:24 | 06/04/2023 13:00:00 | 06/04/2023 21:00:00 | "4""-P-01-2217-B1N-1T" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:01 |  | 7:59 | 06-Apr | 06-Apr | 26-Apr | 26-Apr
CDUVDU23570 | Completed | Cutting, grinding, fit-up, welding and NDT (16 ID) | 26/04/2023 12:32:24 | 26/04/2023 12:33:24 | 12/04/2023 12:00:00 | 13/04/2023 08:00:00 | "4""-P-01-2217-B1N-1T" | INSP RECOMM | 100 | MECHANICAL |  |  | 20 | 20:00 | 0:01 |  | 19:59 | 12-Apr | 13-Apr | 26-Apr | 26-Apr
CDUVDU25080 | Completed | Inspection activities | 26/04/2023 12:32:24 | 26/04/2023 12:33:24 | 13/04/2023 08:00:00 | 13/04/2023 23:00:00 | "4""-P-01-2217-B1N-1T" | INSP RECOMM | 100 | INSPECTION |  |  | 15 | 15:00 | 0:01 |  | 14:59 | 13-Apr | 13-Apr | 26-Apr | 26-Apr
CDUVDU26210 | Completed | HT preparation | 26/04/2023 12:32:24 | 26/04/2023 12:33:24 | 14/04/2023 05:00:00 | 14/04/2023 15:00:00 | "4""-P-01-2217-B1N-1T" | INSP RECOMM | 100 | MECHANICAL |  |  | 10 | 10:00 | 0:01 |  | 9:59 | 14-Apr | 14-Apr | 26-Apr | 26-Apr
CDUVDU26670 | Completed | Hydrotest Witness | 26/04/2023 12:32:24 | 26/04/2023 12:33:24 | 14/04/2023 15:00:00 | 14/04/2023 19:00:00 | "4""-P-01-2217-B1N-1T" | INSP RECOMM | 100 | INSPECTION | HYDRO TEST | HYDRO TEST | 4 | 4:00 | 0:01 |  | 3:59 | 14-Apr | 14-Apr | 26-Apr | 26-Apr
CDUVDU28720 | Completed | Draining | 26/04/2023 12:32:24 | 26/04/2023 12:33:24 | 17/04/2023 03:00:00 | 17/04/2023 09:00:00 | "4""-P-01-2217-B1N-1T" | INSP RECOMM | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:01 |  | 5:59 | 17-Apr | 17-Apr | 26-Apr | 26-Apr
CDUVDU28880 | Completed | De-blinding and hand-over | 26/04/2023 12:32:24 | 26/04/2023 12:33:24 | 17/04/2023 11:00:00 | 17/04/2023 19:00:00 | "4""-P-01-2217-B1N-1T" | INSP RECOMM | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:01 |  | 7:59 | 17-Apr | 17-Apr | 26-Apr | 26-Apr
CDUVDU11410 | Completed | Blinding | 26/04/2023 12:32:45 | 26/04/2023 12:33:45 | 06/04/2023 13:00:00 | 06/04/2023 21:00:00 | "4""-P-01-2216-B1N-1T" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:01 |  | 7:59 | 06-Apr | 06-Apr | 26-Apr | 26-Apr
CDUVDU25090 | Completed | Cutting, grinding, fit-up, welding and NDT (24 ID) | 26/04/2023 12:32:45 | 26/04/2023 12:33:45 | 13/04/2023 08:00:00 | 14/04/2023 16:00:00 | "4""-P-01-2216-B1N-1T" | INSP RECOMM | 100 | MECHANICAL |  |  | 32 | 32:00 | 0:01 |  | 31:59 | 13-Apr | 14-Apr | 26-Apr | 26-Apr
CDUVDU26700 | Completed | Inspection activities | 26/04/2023 12:32:45 | 26/04/2023 12:33:45 | 14/04/2023 16:00:00 | 15/04/2023 07:00:00 | "4""-P-01-2216-B1N-1T" | INSP RECOMM | 100 | INSPECTION |  |  | 15 | 15:00 | 0:01 |  | 14:59 | 14-Apr | 15-Apr | 26-Apr | 26-Apr
CDUVDU27280 | Completed | HT preparation | 26/04/2023 12:32:45 | 26/04/2023 12:33:45 | 15/04/2023 07:00:00 | 15/04/2023 13:00:00 | "4""-P-01-2216-B1N-1T" | INSP RECOMM | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:01 |  | 5:59 | 15-Apr | 15-Apr | 26-Apr | 26-Apr
CDUVDU27520 | Completed | Hydrotest Witness | 26/04/2023 12:32:45 | 26/04/2023 12:33:45 | 15/04/2023 13:00:00 | 15/04/2023 18:00:00 | "4""-P-01-2216-B1N-1T" | INSP RECOMM | 100 | INSPECTION | HYDRO TEST | HYDRO TEST | 5 | 5:00 | 0:01 |  | 4:59 | 15-Apr | 15-Apr | 26-Apr | 26-Apr
CDUVDU28840 | Completed | Draining | 26/04/2023 12:32:45 | 26/04/2023 12:33:45 | 17/04/2023 09:00:00 | 17/04/2023 15:00:00 | "4""-P-01-2216-B1N-1T" | INSP RECOMM | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:01 |  | 5:59 | 17-Apr | 17-Apr | 26-Apr | 26-Apr
CDUVDU29080 | Completed | De-blinding and hand-over | 26/04/2023 12:32:45 | 26/04/2023 12:33:45 | 17/04/2023 19:00:00 | 18/04/2023 03:00:00 | "4""-P-01-2216-B1N-1T" | INSP RECOMM | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:01 |  | 7:59 | 17-Apr | 18-Apr | 26-Apr | 26-Apr
CDUVDU11820 | Completed | Blinding | 08/04/2023 14:30:35 | 08/04/2023 16:01:39 | 06/04/2023 18:00:00 | 07/04/2023 02:00:00 | "4""-P-01-1805-B1N-1T" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 1:31 |  | 6:29 | 06-Apr | 07-Apr | 08-Apr | 08-Apr
CDUVDU26710 | Completed | Cutting, grinding, fit-up, welding and NDT (40 ID) | 08/04/2023 14:30:43 | 13/04/2023 17:15:05 | 14/04/2023 16:00:00 | 16/04/2023 00:00:00 | "4""-P-01-1805-B1N-1T" | INSP RECOMM | 100 | MECHANICAL |  |  | 32 | 32:00 | 122:44 | 90:44 |  | 14-Apr | 16-Apr | 08-Apr | 13-Apr
CDUVDU27850 | Not Started | Inspection activities |  |  | 16/04/2023 00:00:00 | 16/04/2023 16:00:00 | "4""-P-01-1805-B1N-1T" | INSP RECOMM | 0 | INSPECTION |  |  | 16 | 16:00 | 0:00 |  |  | 16-Apr | 16-Apr | - Date check | - Date check
CDUVDU28500 | Not Started | HT preparation |  |  | 16/04/2023 20:00:00 | 17/04/2023 02:00:00 | "4""-P-01-1805-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 16-Apr | 17-Apr | - Date check | - Date check
CDUVDU28640 | Not Started | Hydrotest Witness |  |  | 17/04/2023 02:00:00 | 17/04/2023 07:00:00 | "4""-P-01-1805-B1N-1T" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 5 | 5:00 | 0:00 |  |  | 17-Apr | 17-Apr | - Date check | - Date check
CDUVDU28810 | Not Started | Draining |  |  | 17/04/2023 07:00:00 | 17/04/2023 13:00:00 | "4""-P-01-1805-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 17-Apr | 17-Apr | - Date check | - Date check
CDUVDU29270 | Not Started | De-blinding and hand-over |  |  | 18/04/2023 03:00:00 | 18/04/2023 11:00:00 | "4""-P-01-1805-B1N-1T" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:00 |  |  | 18-Apr | 18-Apr | - Date check | - Date check
CDUVDU11830 | Completed | Blinding | 13/04/2023 17:08:22 | 13/04/2023 17:08:39 | 06/04/2023 18:00:00 | 07/04/2023 03:00:00 | "4""-P-01-2213-B1N-1T" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 9 | 9:00 | 0:00 |  | 9:00 | 06-Apr | 07-Apr | 13-Apr | 13-Apr
CDUVDU27860 | Not Started | Cutting, grinding, fit-up, welding and NDT (8 ID) |  |  | 16/04/2023 00:00:00 | 17/04/2023 11:00:00 | "4""-P-01-2213-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 35 | 35:00 | 0:00 |  |  | 16-Apr | 17-Apr | - Date check | - Date check
CDUVDU28890 | Not Started | Inspection activities |  |  | 17/04/2023 11:00:00 | 18/04/2023 02:00:00 | "4""-P-01-2213-B1N-1T" | INSP RECOMM | 0 | INSPECTION |  |  | 15 | 15:00 | 0:00 |  |  | 17-Apr | 18-Apr | - Date check | - Date check
CDUVDU29200 | Not Started | HT preparation |  |  | 18/04/2023 02:00:00 | 18/04/2023 08:00:00 | "4""-P-01-2213-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 18-Apr | 18-Apr | - Date check | - Date check
CDUVDU29360 | Not Started | Hydrotest Witness |  |  | 18/04/2023 08:00:00 | 18/04/2023 14:00:00 | "4""-P-01-2213-B1N-1T" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 6 | 6:00 | 0:00 |  |  | 18-Apr | 18-Apr | - Date check | - Date check
CDUVDU29390 | Not Started | Draining |  |  | 18/04/2023 14:00:00 | 18/04/2023 19:00:00 | "4""-P-01-2213-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 5 | 5:00 | 0:00 |  |  | 18-Apr | 18-Apr | - Date check | - Date check
CDUVDU29540 | Not Started | De-blinding and hand-over |  |  | 18/04/2023 19:00:00 | 19/04/2023 04:00:00 | "4""-P-01-2213-B1N-1T" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 9 | 9:00 | 0:00 |  |  | 18-Apr | 19-Apr | - Date check | - Date check
CDUVDU11840 | Completed | Blinding | 23/04/2023 11:55:26 | 23/04/2023 11:55:26 | 06/04/2023 18:00:00 | 07/04/2023 02:00:00 | "4""-P-01-2212-B1N-1T" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  |  | 06-Apr | 07-Apr | 23-Apr | 23-Apr
CDUVDU28900 | In Progress | Cutting, grinding, fit-up, welding and NDT(6 ID) | 23/04/2023 11:55:53 |  | 17/04/2023 11:00:00 | 19/04/2023 03:00:00 | "4""-P-01-2212-B1N-1T" | INSP RECOMM | 75 | MECHANICAL |  |  | 40 | 40:00 | 0:00 |  |  | 17-Apr | 19-Apr | 23-Apr | - Date check
CDUVDU29670 | In Progress | Inspection activities | 23/04/2023 11:57:52 |  | 19/04/2023 03:00:00 | 19/04/2023 15:00:00 | "4""-P-01-2212-B1N-1T" | INSP RECOMM | 75 | INSPECTION |  |  | 12 | 12:00 | 0:00 |  |  | 19-Apr | 19-Apr | 23-Apr | - Date check
CDUVDU29810 | Not Started | HT preparation |  |  | 19/04/2023 15:00:00 | 19/04/2023 21:00:00 | "4""-P-01-2212-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 19-Apr | 19-Apr | - Date check | - Date check
CDUVDU29920 | Not Started | Hydrotest Witness |  |  | 19/04/2023 21:00:00 | 20/04/2023 01:00:00 | "4""-P-01-2212-B1N-1T" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 4 | 4:00 | 0:00 |  |  | 19-Apr | 20-Apr | - Date check | - Date check
CDUVDU29980 | Not Started | Draining |  |  | 20/04/2023 01:00:00 | 20/04/2023 05:00:00 | "4""-P-01-2212-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  |  | 20-Apr | 20-Apr | - Date check | - Date check
CDUVDU30020 | Not Started | De-blinding and hand-over |  |  | 20/04/2023 05:00:00 | 20/04/2023 13:00:00 | "4""-P-01-2212-B1N-1T" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:00 |  |  | 20-Apr | 20-Apr | - Date check | - Date check
CDUVDU11810 | Completed | Cutting, grinding, fit-up, welding and NDT(24 ID) | 18/04/2023 15:52:38 | 18/04/2023 16:09:40 | 06/04/2023 18:00:00 | 08/04/2023 10:00:00 | "4""- P-01-2104-B1N" | INSP RECOMM | 100 | MECHANICAL |  |  | 40 | 40:00 | 0:17 |  | 39:43 | 06-Apr | 08-Apr | 18-Apr | 18-Apr
CDUVDU18270 | Completed | Inspection activities | 20/04/2023 13:09:43 | 20/04/2023 13:09:47 | 10/04/2023 06:00:00 | 11/04/2023 22:00:00 | "4""- P-01-2104-B1N" | INSP RECOMM | 100 | INSPECTION |  |  | 40 | 40:00 | 0:00 |  | 40:00 | 10-Apr | 11-Apr | 20-Apr | 20-Apr
CDUVDU22170 | Completed | HT preparation | 20/04/2023 13:09:57 | 20/04/2023 13:10:01 | 11/04/2023 22:00:00 | 12/04/2023 18:00:00 | "4""- P-01-2104-B1N" | INSP RECOMM | 100 | MECHANICAL |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 11-Apr | 12-Apr | 20-Apr | 20-Apr
CDUVDU24040 | Completed | Hydrotest Witness | 20/04/2023 13:10:09 | 20/04/2023 13:10:31 | 12/04/2023 18:00:00 | 13/04/2023 06:00:00 | "4""- P-01-2104-B1N" | INSP RECOMM | 100 | INSPECTION | HYDRO TEST | HYDRO TEST | 12 | 12:00 | 0:00 |  | 12:00 | 12-Apr | 13-Apr | 20-Apr | 20-Apr
CDUVDU24940 | Completed | Draining | 20/04/2023 13:10:47 | 20/04/2023 13:10:51 | 13/04/2023 06:00:00 | 14/04/2023 02:00:00 | "4""- P-01-2104-B1N" | INSP RECOMM | 100 | MECHANICAL |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 13-Apr | 14-Apr | 20-Apr | 20-Apr
CDUVDU26000 | Completed | De-blinding and hand-over | 20/04/2023 13:10:59 | 20/04/2023 13:11:05 | 14/04/2023 02:00:00 | 14/04/2023 22:00:00 | "4""- P-01-2104-B1N" | INSP RECOMM | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 20 | 20:00 | 0:00 |  | 20:00 | 14-Apr | 14-Apr | 20-Apr | 20-Apr
CDUVDU8750 | Completed | Blinding | 18/04/2023 15:51:30 | 18/04/2023 15:52:22 | 04/04/2023 14:00:00 | 05/04/2023 06:00:00 | "4""- P-01-2104-B1N" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 16 | 16:00 | 0:01 |  | 15:59 | 04-Apr | 05-Apr | 18-Apr | 18-Apr
CDUVDU11850 | Completed | Blinding | 15/04/2023 15:25:23 | 15/04/2023 15:25:35 | 06/04/2023 18:00:00 | 07/04/2023 02:00:00 | "4""-P-01-2161-B1N-1T" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 06-Apr | 07-Apr | 15-Apr | 15-Apr
CDUVDU12370 | In Progress | Cutting, grinding, fit-up, welding and NDT(16 ID) | 15/04/2023 15:25:43 |  | 07/04/2023 02:00:00 | 08/04/2023 13:00:00 | "4""-P-01-2161-B1N-1T" | INSP RECOMM | 75 | MECHANICAL |  |  | 35 | 35:00 | 0:00 |  |  | 07-Apr | 08-Apr | 15-Apr | - Date check
CDUVDU14560 | In Progress | Inspection activities | 15/04/2023 15:26:13 |  | 08/04/2023 13:00:00 | 09/04/2023 04:00:00 | "4""-P-01-2161-B1N-1T" | INSP RECOMM | 75 | INSPECTION |  |  | 15 | 15:00 | 0:00 |  |  | 08-Apr | 09-Apr | 15-Apr | - Date check
CDUVDU15830 | Not Started | HT preparation |  |  | 09/04/2023 04:00:00 | 09/04/2023 10:00:00 | "4""-P-01-2161-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 09-Apr | 09-Apr | - Date check | - Date check
CDUVDU16260 | Not Started | Hydrotest Witness |  |  | 09/04/2023 10:00:00 | 09/04/2023 13:00:00 | "4""-P-01-2161-B1N-1T" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 3 | 3:00 | 0:00 |  |  | 09-Apr | 09-Apr | - Date check | - Date check
CDUVDU16530 | Not Started | Draining |  |  | 09/04/2023 13:00:00 | 09/04/2023 17:00:00 | "4""-P-01-2161-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  |  | 09-Apr | 09-Apr | - Date check | - Date check
CDUVDU16840 | Not Started | De-blinding and hand-over |  |  | 09/04/2023 17:00:00 | 10/04/2023 01:00:00 | "4""-P-01-2161-B1N-1T" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:00 |  |  | 09-Apr | 10-Apr | - Date check | - Date check
CDUVDU11860 | Completed | Blinding | 15/04/2023 15:26:39 | 15/04/2023 15:26:43 | 06/04/2023 18:00:00 | 07/04/2023 12:00:00 | "4""-P-01-2211-B1N-1T" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 18 | 18:00 | 0:00 |  | 18:00 | 06-Apr | 07-Apr | 15-Apr | 15-Apr
CDUVDU13210 | Completed | Cutting, grinding, fit-up, welding and NDT (24 ID) | 15/04/2023 15:26:55 | 15/04/2023 15:27:12 | 07/04/2023 15:00:00 | 08/04/2023 12:00:00 | "4""-P-01-2211-B1N-1T" | INSP RECOMM | 100 | MECHANICAL |  |  | 21 | 21:00 | 0:00 |  | 21:00 | 07-Apr | 08-Apr | 15-Apr | 15-Apr
CDUVDU14530 | Completed | Inspection activities | 15/04/2023 15:27:33 | 15/04/2023 15:27:43 | 08/04/2023 12:00:00 | 09/04/2023 08:00:00 | "4""-P-01-2211-B1N-1T" | INSP RECOMM | 100 | INSPECTION |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 08-Apr | 09-Apr | 15-Apr | 15-Apr
CDUVDU16030 | Not Started | HT preparation |  |  | 09/04/2023 08:00:00 | 09/04/2023 20:00:00 | "4""-P-01-2211-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 12 | 12:00 | 0:00 |  |  | 09-Apr | 09-Apr | - Date check | - Date check
CDUVDU17180 | Not Started | Hydrotest Witness |  |  | 09/04/2023 20:00:00 | 10/04/2023 02:00:00 | "4""-P-01-2211-B1N-1T" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 6 | 6:00 | 0:00 |  |  | 09-Apr | 10-Apr | - Date check | - Date check
CDUVDU18110 | Not Started | Draining |  |  | 10/04/2023 05:00:00 | 10/04/2023 15:00:00 | "4""-P-01-2211-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 10 | 10:00 | 0:00 |  |  | 10-Apr | 10-Apr | - Date check | - Date check
CDUVDU19080 | Not Started | De-blinding and hand-over |  |  | 10/04/2023 15:00:00 | 11/04/2023 09:00:00 | "4""-P-01-2211-B1N-1T" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 18 | 18:00 | 0:00 |  |  | 10-Apr | 11-Apr | - Date check | - Date check
CDUVDU12010 | Completed | Blinding | 08/04/2023 09:52:38 | 08/04/2023 09:52:43 | 06/04/2023 21:00:00 | 07/04/2023 05:00:00 | "4""-P-01-1722-B1N-1T" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 06-Apr | 07-Apr | 08-Apr | 08-Apr
CDUVDU14540 | Completed | Cutting, grinding, fit-up, welding and NDT | 08/04/2023 09:52:59 | 15/04/2023 15:28:10 | 08/04/2023 12:00:00 | 09/04/2023 08:00:00 | "4""-P-01-1722-B1N-1T" | INSP RECOMM | 100 | MECHANICAL |  |  | 20 | 20:00 | 173:35 | 153:35 |  | 08-Apr | 09-Apr | 08-Apr | 15-Apr
CDUVDU16040 | Completed | Inspection activities | 15/04/2023 15:28:25 | 15/04/2023 15:28:37 | 09/04/2023 08:00:00 | 10/04/2023 04:00:00 | "4""-P-01-1722-B1N-1T" | INSP RECOMM | 100 | INSPECTION |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 09-Apr | 10-Apr | 15-Apr | 15-Apr
CDUVDU18280 | Not Started | HT preparation |  |  | 10/04/2023 06:00:00 | 10/04/2023 12:00:00 | "4""-P-01-1722-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 10-Apr | 10-Apr | - Date check | - Date check
CDUVDU18730 | Not Started | Hydrotest Witness |  |  | 10/04/2023 12:00:00 | 10/04/2023 17:00:00 | "4""-P-01-1722-B1N-1T" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 5 | 5:00 | 0:00 |  |  | 10-Apr | 10-Apr | - Date check | - Date check
CDUVDU19200 | Not Started | Draining |  |  | 10/04/2023 17:00:00 | 10/04/2023 21:00:00 | "4""-P-01-1722-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  |  | 10-Apr | 10-Apr | - Date check | - Date check
CDUVDU20820 | Not Started | De-blinding and hand-over |  |  | 11/04/2023 09:00:00 | 11/04/2023 17:00:00 | "4""-P-01-1722-B1N-1T" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:00 |  |  | 11-Apr | 11-Apr | - Date check | - Date check
CDUVDU12020 | Completed | Blinding | 13/04/2023 17:04:00 | 13/04/2023 17:04:16 | 06/04/2023 21:00:00 | 07/04/2023 03:00:00 | "2""-CBD-01-3225-A1A-N" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 6 | 6:00 | 0:00 |  | 6:00 | 06-Apr | 07-Apr | 13-Apr | 13-Apr
CDUVDU16050 | Completed | Cutting, grinding, fit-up, welding and NDT | 13/04/2023 17:04:53 | 13/04/2023 17:10:04 | 09/04/2023 08:00:00 | 10/04/2023 04:00:00 | "2""-CBD-01-3225-A1A-N" | INSP RECOMM | 100 | MECHANICAL |  |  | 20 | 20:00 | 0:05 |  | 19:55 | 09-Apr | 10-Apr | 13-Apr | 13-Apr
CDUVDU18290 | Not Started | Inspection activities |  |  | 10/04/2023 06:00:00 | 11/04/2023 02:00:00 | "2""-CBD-01-3225-A1A-N" | INSP RECOMM | 0 | INSPECTION |  |  | 20 | 20:00 | 0:00 |  |  | 10-Apr | 11-Apr | - Date check | - Date check
CDUVDU20490 | Not Started | HT preparation |  |  | 11/04/2023 05:00:00 | 11/04/2023 11:00:00 | "2""-CBD-01-3225-A1A-N" | INSP RECOMM | 0 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 11-Apr | 11-Apr | - Date check | - Date check
CDUVDU21020 | Not Started | Hydrotest Witness |  |  | 11/04/2023 11:00:00 | 11/04/2023 14:00:00 | "2""-CBD-01-3225-A1A-N" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 3 | 3:00 | 0:00 |  |  | 11-Apr | 11-Apr | - Date check | - Date check
CDUVDU21370 | Not Started | Draining |  |  | 11/04/2023 14:00:00 | 11/04/2023 18:00:00 | "2""-CBD-01-3225-A1A-N" | INSP RECOMM | 0 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  |  | 11-Apr | 11-Apr | - Date check | - Date check
CDUVDU21920 | Not Started | De-blinding and hand-over |  |  | 11/04/2023 18:00:00 | 12/04/2023 00:00:00 | "2""-CBD-01-3225-A1A-N" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 6 | 6:00 | 0:00 |  |  | 11-Apr | 12-Apr | - Date check | - Date check
CDUVDU12030 | Completed | Blinding | 15/04/2023 15:28:58 | 15/04/2023 15:29:04 | 06/04/2023 21:00:00 | 07/04/2023 03:00:00 | "6""-P-01-P-2101-A6N-1T" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 6 | 6:00 | 0:00 |  | 6:00 | 06-Apr | 07-Apr | 15-Apr | 15-Apr
CDUVDU18020 | Completed | Cutting, grinding, fit-up, welding and NDT | 15/04/2023 15:29:14 | 15/04/2023 15:29:25 | 10/04/2023 04:00:00 | 11/04/2023 00:00:00 | "6""-P-01-P-2101-A6N-1T" | INSP RECOMM | 100 | MECHANICAL |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 10-Apr | 11-Apr | 15-Apr | 15-Apr
CDUVDU20150 | Completed | Inspection activities | 15/04/2023 15:29:41 | 15/04/2023 15:29:47 | 11/04/2023 02:00:00 | 11/04/2023 22:00:00 | "6""-P-01-P-2101-A6N-1T" | INSP RECOMM | 100 | INSPECTION |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 11-Apr | 11-Apr | 15-Apr | 15-Apr
CDUVDU22190 | Not Started | HT preparation |  |  | 11/04/2023 22:00:00 | 12/04/2023 04:00:00 | "6""-P-01-P-2101-A6N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 11-Apr | 12-Apr | - Date check | - Date check
CDUVDU22850 | Not Started | Hydrotest Witness |  |  | 12/04/2023 04:00:00 | 12/04/2023 07:00:00 | "6""-P-01-P-2101-A6N-1T" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 3 | 3:00 | 0:00 |  |  | 12-Apr | 12-Apr | - Date check | - Date check
CDUVDU23110 | Not Started | Draining |  |  | 12/04/2023 07:00:00 | 12/04/2023 11:00:00 | "6""-P-01-P-2101-A6N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  |  | 12-Apr | 12-Apr | - Date check | - Date check
CDUVDU23440 | Not Started | De-blinding and hand-over |  |  | 12/04/2023 11:00:00 | 12/04/2023 17:00:00 | "6""-P-01-P-2101-A6N-1T" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 6 | 6:00 | 0:00 |  |  | 12-Apr | 12-Apr | - Date check | - Date check
CDUVDU12210 | Completed | Blinding | 15/04/2023 15:30:15 | 15/04/2023 15:30:20 | 06/04/2023 23:00:00 | 07/04/2023 19:00:00 | "4""-P-01-P-2104-B1N-1T" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 20 | 20:00 | 0:00 |  | 20:00 | 06-Apr | 07-Apr | 15-Apr | 15-Apr
CDUVDU20430 | Completed | Cutting, grinding, fit-up, welding and NDT | 15/04/2023 15:30:31 | 15/04/2023 15:30:44 | 11/04/2023 04:00:00 | 13/04/2023 08:00:00 | "4""-P-01-P-2104-B1N-1T" | INSP RECOMM | 100 | MECHANICAL |  |  | 52 | 52:00 | 0:00 |  | 52:00 | 11-Apr | 13-Apr | 15-Apr | 15-Apr
CDUVDU25100 | Completed | Inspection activities | 15/04/2023 15:31:29 | 15/04/2023 15:31:40 | 13/04/2023 08:00:00 | 14/04/2023 04:00:00 | "4""-P-01-P-2104-B1N-1T" | INSP RECOMM | 100 | INSPECTION |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 13-Apr | 14-Apr | 15-Apr | 15-Apr
CDUVDU26160 | Not Started | HT preparation |  |  | 14/04/2023 04:00:00 | 14/04/2023 16:00:00 | "4""-P-01-P-2104-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 12 | 12:00 | 0:00 |  |  | 14-Apr | 14-Apr | - Date check | - Date check
CDUVDU26720 | Not Started | Hydrotest Witness |  |  | 14/04/2023 16:00:00 | 14/04/2023 22:00:00 | "4""-P-01-P-2104-B1N-1T" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 6 | 6:00 | 0:00 |  |  | 14-Apr | 14-Apr | - Date check | - Date check
CDUVDU26950 | Not Started | Draining |  |  | 14/04/2023 22:00:00 | 15/04/2023 08:00:00 | "4""-P-01-P-2104-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 10 | 10:00 | 0:00 |  |  | 14-Apr | 15-Apr | - Date check | - Date check
CDUVDU27480 | Not Started | De-blinding and hand-over |  |  | 15/04/2023 12:00:00 | 16/04/2023 08:00:00 | "4""-P-01-P-2104-B1N-1T" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 20 | 20:00 | 0:00 |  |  | 15-Apr | 16-Apr | - Date check | - Date check
CDUVDU12220 | In Progress | Blinding | 17/04/2023 15:23:04 |  | 06/04/2023 23:00:00 | 07/04/2023 19:00:00 | "8""-P-01-P-2152-B1N-1T" | INSP RECOMM | 70 | MECHANICAL | BLINDING | BLINDING | 20 | 20:00 | 0:00 |  |  | 06-Apr | 07-Apr | 17-Apr | - Date check
CDUVDU25110 | Not Started | Cutting, grinding, fit-up, welding and NDT |  |  | 13/04/2023 08:00:00 | 14/04/2023 16:00:00 | "8""-P-01-P-2152-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 32 | 32:00 | 0:00 |  |  | 13-Apr | 14-Apr | - Date check | - Date check
CDUVDU26730 | Not Started | Inspection activities |  |  | 14/04/2023 16:00:00 | 15/04/2023 12:00:00 | "8""-P-01-P-2152-B1N-1T" | INSP RECOMM | 0 | INSPECTION |  |  | 20 | 20:00 | 0:00 |  |  | 14-Apr | 15-Apr | - Date check | - Date check
CDUVDU27490 | Not Started | HT preparation |  |  | 15/04/2023 12:00:00 | 16/04/2023 08:00:00 | "8""-P-01-P-2152-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 20 | 20:00 | 0:00 |  |  | 15-Apr | 16-Apr | - Date check | - Date check
CDUVDU28100 | Not Started | Hydrotest Witness |  |  | 16/04/2023 08:00:00 | 16/04/2023 14:00:00 | "8""-P-01-P-2152-B1N-1T" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 6 | 6:00 | 0:00 |  |  | 16-Apr | 16-Apr | - Date check | - Date check
CDUVDU28330 | Not Started | Draining |  |  | 16/04/2023 14:00:00 | 16/04/2023 22:00:00 | "8""-P-01-P-2152-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  |  | 16-Apr | 16-Apr | - Date check | - Date check
CDUVDU28520 | Not Started | De-blinding and hand-over |  |  | 16/04/2023 22:00:00 | 17/04/2023 18:00:00 | "8""-P-01-P-2152-B1N-1T" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 20 | 20:00 | 0:00 |  |  | 16-Apr | 17-Apr | - Date check | - Date check
CDUVDU12290 | In Progress | Blinding | 19/04/2023 10:29:08 |  | 07/04/2023 01:00:00 | 07/04/2023 13:00:00 | "8""-P-01-P-2153-B1N-1T" | INSP RECOMM | 78 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 0:00 |  |  | 07-Apr | 07-Apr | 19-Apr | - Date check
CDUVDU26740 | Not Started | Cutting, grinding, fit-up, welding and NDT |  |  | 14/04/2023 16:00:00 | 15/04/2023 12:00:00 | "8""-P-01-P-2153-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 20 | 20:00 | 0:00 |  |  | 14-Apr | 15-Apr | - Date check | - Date check
CDUVDU27500 | Not Started | Inspection activities |  |  | 15/04/2023 12:00:00 | 16/04/2023 08:00:00 | "8""-P-01-P-2153-B1N-1T" | INSP RECOMM | 0 | INSPECTION |  |  | 20 | 20:00 | 0:00 |  |  | 15-Apr | 16-Apr | - Date check | - Date check
CDUVDU28180 | Not Started | HT preparation |  |  | 16/04/2023 10:00:00 | 16/04/2023 16:00:00 | "8""-P-01-P-2153-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 16-Apr | 16-Apr | - Date check | - Date check
CDUVDU28400 | Not Started | Hydrotest Witness |  |  | 16/04/2023 16:00:00 | 16/04/2023 20:00:00 | "8""-P-01-P-2153-B1N-1T" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 4 | 4:00 | 0:00 |  |  | 16-Apr | 16-Apr | - Date check | - Date check
CDUVDU28530 | Not Started | Draining |  |  | 16/04/2023 22:00:00 | 17/04/2023 03:00:00 | "8""-P-01-P-2153-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 5 | 5:00 | 0:00 |  |  | 16-Apr | 17-Apr | - Date check | - Date check
CDUVDU29030 | Not Started | De-blinding and hand-over |  |  | 17/04/2023 18:00:00 | 18/04/2023 06:00:00 | "8""-P-01-P-2153-B1N-1T" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  |  | 17-Apr | 18-Apr | - Date check | - Date check
CDUVDU12300 | Completed | Blinding | 19/04/2023 10:30:19 | 24/04/2023 11:14:44 | 07/04/2023 01:00:00 | 07/04/2023 13:00:00 | "10""-P-01-P-2157-B1N-1T" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 120:44 | 108:44 |  | 07-Apr | 07-Apr | 19-Apr | 24-Apr
CDUVDU27510 | Completed | Cutting, grinding, fit-up, welding and NDT | 24/04/2023 11:15:00 | 24/04/2023 11:15:21 | 15/04/2023 12:00:00 | 16/04/2023 08:00:00 | "10""-P-01-P-2157-B1N-1T" | INSP RECOMM | 100 | MECHANICAL |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 15-Apr | 16-Apr | 24-Apr | 24-Apr
CDUVDU28190 | Not Started | Inspection activities |  |  | 16/04/2023 10:00:00 | 17/04/2023 06:00:00 | "10""-P-01-P-2157-B1N-1T" | INSP RECOMM | 0 | INSPECTION |  |  | 20 | 20:00 | 0:00 |  |  | 16-Apr | 17-Apr | - Date check | - Date check
CDUVDU28770 | Not Started | HT preparation |  |  | 17/04/2023 06:00:00 | 17/04/2023 14:00:00 | "10""-P-01-P-2157-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  |  | 17-Apr | 17-Apr | - Date check | - Date check
CDUVDU28960 | Not Started | Hydrotest Witness |  |  | 17/04/2023 14:00:00 | 17/04/2023 18:00:00 | "10""-P-01-P-2157-B1N-1T" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 4 | 4:00 | 0:00 |  |  | 17-Apr | 17-Apr | - Date check | - Date check
CDUVDU29040 | Not Started | Draining |  |  | 17/04/2023 18:00:00 | 17/04/2023 22:00:00 | "10""-P-01-P-2157-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  |  | 17-Apr | 17-Apr | - Date check | - Date check
CDUVDU29310 | Not Started | De-blinding and hand-over |  |  | 18/04/2023 06:00:00 | 18/04/2023 18:00:00 | "10""-P-01-P-2157-B1N-1T" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  |  | 18-Apr | 18-Apr | - Date check | - Date check
CDUVDU12310 | Completed | Blinding | 23/04/2023 12:08:37 | 23/04/2023 12:08:42 | 07/04/2023 01:00:00 | 07/04/2023 13:00:00 | "6""-P-01-P-2215-A6N-1T" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 07-Apr | 07-Apr | 23-Apr | 23-Apr
CDUVDU28110 | Completed | Cutting, grinding, fit-up, welding and NDT | 23/04/2023 12:07:54 | 23/04/2023 12:08:26 | 16/04/2023 08:00:00 | 18/04/2023 00:00:00 | "6""-P-01-P-2215-A6N-1T" | INSP RECOMM | 100 | MECHANICAL |  |  | 40 | 40:00 | 0:01 |  | 39:59 | 16-Apr | 18-Apr | 23-Apr | 23-Apr
CDUVDU29180 | Completed | Inspection activities | 23/04/2023 12:09:19 | 23/04/2023 12:09:19 | 18/04/2023 00:00:00 | 18/04/2023 20:00:00 | "6""-P-01-P-2215-A6N-1T" | INSP RECOMM | 100 | INSPECTION |  |  | 20 | 20:00 | 0:00 |  |  | 18-Apr | 18-Apr | 23-Apr | 23-Apr
CDUVDU29570 | Not Started | HT preparation |  |  | 18/04/2023 20:00:00 | 19/04/2023 04:00:00 | "6""-P-01-P-2215-A6N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 8 | 8:00 | 0:00 |  |  | 18-Apr | 19-Apr | - Date check | - Date check
CDUVDU29750 | Not Started | Hydrotest Witness |  |  | 19/04/2023 08:00:00 | 19/04/2023 12:00:00 | "6""-P-01-P-2215-A6N-1T" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 4 | 4:00 | 0:00 |  |  | 19-Apr | 19-Apr | - Date check | - Date check
CDUVDU29790 | Not Started | Draining |  |  | 19/04/2023 12:00:00 | 19/04/2023 16:00:00 | "6""-P-01-P-2215-A6N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  |  | 19-Apr | 19-Apr | - Date check | - Date check
CDUVDU29840 | Not Started | De-blinding and hand-over |  |  | 19/04/2023 16:00:00 | 20/04/2023 04:00:00 | "6""-P-01-P-2215-A6N-1T" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  |  | 19-Apr | 20-Apr | - Date check | - Date check
CDUVDU14380 | Completed | Cutting, grinding, fit-up, welding and NDT(12 ID) | 26/04/2023 18:45:27 | 26/04/2023 18:45:36 | 08/04/2023 10:00:00 | 09/04/2023 18:00:00 | "6""-P-01-2101-A6N" | INSP RECOMM | 100 | MECHANICAL |  |  | 32 | 32:00 | 0:00 |  | 32:00 | 08-Apr | 09-Apr | 26-Apr | 26-Apr
CDUVDU22180 | Not Started | Inspection activities |  |  | 11/04/2023 22:00:00 | 12/04/2023 18:00:00 | "6""-P-01-2101-A6N" | INSP RECOMM | 0 | INSPECTION |  |  | 20 | 20:00 | 0:00 |  |  | 11-Apr | 12-Apr | - Date check | - Date check
CDUVDU24050 | Not Started | HT preparation |  |  | 12/04/2023 18:00:00 | 13/04/2023 14:00:00 | "6""-P-01-2101-A6N" | INSP RECOMM | 0 | MECHANICAL |  |  | 20 | 20:00 | 0:00 |  |  | 12-Apr | 13-Apr | - Date check | - Date check
CDUVDU25360 | Not Started | Hydrotest Witness |  |  | 13/04/2023 14:00:00 | 14/04/2023 02:00:00 | "6""-P-01-2101-A6N" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 12 | 12:00 | 0:00 |  |  | 13-Apr | 14-Apr | - Date check | - Date check
CDUVDU26010 | Not Started | Draining |  |  | 14/04/2023 02:00:00 | 14/04/2023 22:00:00 | "6""-P-01-2101-A6N" | INSP RECOMM | 0 | MECHANICAL |  |  | 20 | 20:00 | 0:00 |  |  | 14-Apr | 14-Apr | - Date check | - Date check
CDUVDU26930 | Not Started | De-blinding and hand-over |  |  | 14/04/2023 22:00:00 | 15/04/2023 14:00:00 | "6""-P-01-2101-A6N" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 16 | 16:00 | 0:00 |  |  | 14-Apr | 15-Apr | - Date check | - Date check
CDUVDU8760 | Completed | Blinding | 18/04/2023 15:55:15 | 18/04/2023 15:55:21 | 04/04/2023 14:00:00 | 05/04/2023 02:00:00 | "6""-P-01-2101-A6N" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 04-Apr | 05-Apr | 18-Apr | 18-Apr
CDUVDU13030 | Completed | Blinding | 08/04/2023 09:54:09 | 08/04/2023 09:54:13 | 07/04/2023 13:00:00 | 08/04/2023 01:00:00 | "6""-P-01-P-1517-A1A-1H" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 07-Apr | 08-Apr | 08-Apr | 08-Apr
CDUVDU13760 | Completed | Cutting, grinding, fit-up, welding and NDT | 08/04/2023 09:54:25 | 15/04/2023 15:32:34 | 08/04/2023 01:00:00 | 09/04/2023 17:00:00 | "6""-P-01-P-1517-A1A-1H" | INSP RECOMM | 100 | MECHANICAL |  |  | 40 | 40:00 | 173:38 | 133:38 |  | 08-Apr | 09-Apr | 08-Apr | 15-Apr
CDUVDU29560 | Completed | Inspection activities | 15/04/2023 15:32:52 | 15/04/2023 15:33:01 | 18/04/2023 20:00:00 | 19/04/2023 16:00:00 | "6""-P-01-P-1517-A1A-1H" | INSP RECOMM | 100 | INSPECTION |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 18-Apr | 19-Apr | 15-Apr | 15-Apr
CDUVDU29930 | Not Started | HT preparation |  |  | 19/04/2023 21:00:00 | 20/04/2023 03:00:00 | "6""-P-01-P-1517-A1A-1H" | INSP RECOMM | 0 | MECHANICAL |  |  | 6 | 6:00 | 0:00 |  |  | 19-Apr | 20-Apr | - Date check | - Date check
CDUVDU30010 | Not Started | Hydrotest Witness |  |  | 20/04/2023 03:00:00 | 20/04/2023 06:00:00 | "6""-P-01-P-1517-A1A-1H" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 3 | 3:00 | 0:00 |  |  | 20-Apr | 20-Apr | - Date check | - Date check
CDUVDU30040 | Not Started | Draining |  |  | 20/04/2023 11:00:00 | 20/04/2023 15:00:00 | "6""-P-01-P-1517-A1A-1H" | INSP RECOMM | 0 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  |  | 20-Apr | 20-Apr | - Date check | - Date check
CDUVDU30050 | Not Started | De-blinding and hand-over |  |  | 20/04/2023 15:00:00 | 21/04/2023 03:00:00 | "6""-P-01-P-1517-A1A-1H" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  |  | 20-Apr | 21-Apr | - Date check | - Date check
CDUVDU13040 | Completed | Blinding | 08/04/2023 09:56:51 | 08/04/2023 09:56:57 | 07/04/2023 13:00:00 | 08/04/2023 07:00:00 | "10""-P-01-P-1515-A1A-1H" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 18 | 18:00 | 0:00 |  | 18:00 | 07-Apr | 08-Apr | 08-Apr | 08-Apr
CDUVDU14100 | Completed | Cutting, grinding, fit-up, welding and NDT(12 ID) | 15/04/2023 15:33:21 | 15/04/2023 15:33:36 | 08/04/2023 07:00:00 | 09/04/2023 23:00:00 | "10""-P-01-P-1515-A1A-1H" | INSP RECOMM | 100 | MECHANICAL |  |  | 40 | 40:00 | 0:00 |  | 40:00 | 08-Apr | 09-Apr | 15-Apr | 15-Apr
CDUVDU17480 | Completed | Inspection activities | 15/04/2023 15:33:49 | 15/04/2023 15:34:00 | 09/04/2023 23:00:00 | 10/04/2023 19:00:00 | "10""-P-01-P-1515-A1A-1H" | INSP RECOMM | 100 | INSPECTION |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 09-Apr | 10-Apr | 15-Apr | 15-Apr
CDUVDU19420 | Completed | HT preparation | 20/04/2023 09:37:13 | 20/04/2023 09:37:53 | 10/04/2023 19:00:00 | 11/04/2023 01:00:00 | "10""-P-01-P-1515-A1A-1H" | INSP RECOMM | 100 | MECHANICAL |  |  | 6 | 6:00 | 0:01 |  | 5:59 | 10-Apr | 11-Apr | 20-Apr | 20-Apr
CDUVDU20100 | Completed | Hydrotest Witness | 20/04/2023 09:37:23 | 20/04/2023 09:37:58 | 11/04/2023 01:00:00 | 11/04/2023 05:00:00 | "10""-P-01-P-1515-A1A-1H" | INSP RECOMM | 100 | INSPECTION | HYDRO TEST | HYDRO TEST | 4 | 4:00 | 0:01 |  | 3:59 | 11-Apr | 11-Apr | 20-Apr | 20-Apr
CDUVDU21030 | Completed | Draining | 20/04/2023 09:37:35 | 20/04/2023 09:38:02 | 11/04/2023 11:00:00 | 11/04/2023 15:00:00 | "10""-P-01-P-1515-A1A-1H" | INSP RECOMM | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 11-Apr | 11-Apr | 20-Apr | 20-Apr
CDUVDU21930 | Completed | De-blinding and hand-over | 20/04/2023 09:37:44 | 20/04/2023 09:38:35 | 11/04/2023 18:00:00 | 12/04/2023 12:00:00 | "10""-P-01-P-1515-A1A-1H" | INSP RECOMM | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 18 | 18:00 | 0:01 |  | 17:59 | 11-Apr | 12-Apr | 20-Apr | 20-Apr
CDUVDU14110 | Completed | Blinding | 05/04/2023 19:27:48 | 07/04/2023 15:31:49 | 08/04/2023 07:00:00 | 08/04/2023 15:00:00 | "6""-P-01-P-1615-A1A-N" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 44:04 | 36:04 |  | 08-Apr | 08-Apr | 05-Apr | 07-Apr
CDUVDU14840 | Completed | Cutting, grinding, fit-up, welding and NDT | 07/04/2023 15:32:02 | 07/04/2023 15:32:32 | 08/04/2023 15:00:00 | 09/04/2023 11:00:00 | "6""-P-01-P-1615-A1A-N" | INSP RECOMM | 100 | MECHANICAL |  |  | 20 | 20:00 | 0:01 |  | 20:00 | 08-Apr | 09-Apr | 07-Apr | 07-Apr
CDUVDU14850 | Completed | Inspection activities | 07/04/2023 15:32:50 | 07/04/2023 15:32:56 | 08/04/2023 15:00:00 | 09/04/2023 11:00:00 | "6""-P-01-P-1615-A1A-N" | INSP RECOMM | 100 | INSPECTION |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 08-Apr | 09-Apr | 07-Apr | 07-Apr
CDUVDU16390 | Completed | HT preparation | 07/04/2023 15:33:19 | 07/04/2023 15:33:51 | 09/04/2023 11:00:00 | 09/04/2023 23:00:00 | "6""-P-01-P-1615-A1A-N" | INSP RECOMM | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:01 |  | 11:59 | 09-Apr | 09-Apr | 07-Apr | 07-Apr
CDUVDU17490 | Completed | Hydrotest Witness | 07/04/2023 15:34:07 | 07/04/2023 15:34:13 | 09/04/2023 23:00:00 | 10/04/2023 04:00:00 | "6""-P-01-P-1615-A1A-N" | INSP RECOMM | 100 | INSPECTION | HYDRO TEST | HYDRO TEST | 5 | 5:00 | 0:00 |  | 5:00 | 09-Apr | 10-Apr | 07-Apr | 07-Apr
CDUVDU18030 | Completed | Draining | 07/04/2023 15:34:32 | 07/04/2023 15:34:38 | 10/04/2023 04:00:00 | 10/04/2023 08:00:00 | "6""-P-01-P-1615-A1A-N" | INSP RECOMM | 100 | MECHANICAL |  |  | 4 | 4:00 | 0:00 |  | 4:00 | 10-Apr | 10-Apr | 07-Apr | 07-Apr
CDUVDU18410 | Completed | De-blinding and hand-over | 07/04/2023 15:34:54 | 07/04/2023 15:34:59 | 10/04/2023 08:00:00 | 10/04/2023 16:00:00 | "6""-P-01-P-1615-A1A-N" | INSP RECOMM | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 10-Apr | 10-Apr | 07-Apr | 07-Apr
CDUVDU16910 | Completed | Cutting, grinding, fit-up, welding and NDT(12 ID) | 26/04/2023 18:46:59 | 26/04/2023 18:47:04 | 09/04/2023 18:00:00 | 11/04/2023 02:00:00 | "6""-P-01-2103-A6N" | INSP RECOMM | 100 | MECHANICAL |  |  | 32 | 32:00 | 0:00 |  | 32:00 | 09-Apr | 11-Apr | 26-Apr | 26-Apr
CDUVDU24060 | Not Started | Inspection activities |  |  | 12/04/2023 18:00:00 | 13/04/2023 14:00:00 | "6""-P-01-2103-A6N" | INSP RECOMM | 0 | INSPECTION |  |  | 20 | 20:00 | 0:00 |  |  | 12-Apr | 13-Apr | - Date check | - Date check
CDUVDU25370 | Not Started | HT preparation |  |  | 13/04/2023 14:00:00 | 14/04/2023 10:00:00 | "6""-P-01-2103-A6N" | INSP RECOMM | 0 | MECHANICAL |  |  | 20 | 20:00 | 0:00 |  |  | 13-Apr | 14-Apr | - Date check | - Date check
CDUVDU26410 | Not Started | Hydrotest Witness |  |  | 14/04/2023 10:00:00 | 14/04/2023 22:00:00 | "6""-P-01-2103-A6N" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 12 | 12:00 | 0:00 |  |  | 14-Apr | 14-Apr | - Date check | - Date check
CDUVDU26940 | Not Started | Draining |  |  | 14/04/2023 22:00:00 | 15/04/2023 18:00:00 | "6""-P-01-2103-A6N" | INSP RECOMM | 0 | MECHANICAL |  |  | 20 | 20:00 | 0:00 |  |  | 14-Apr | 15-Apr | - Date check | - Date check
CDUVDU27650 | Not Started | De-blinding and hand-over |  |  | 15/04/2023 18:00:00 | 16/04/2023 14:00:00 | "6""-P-01-2103-A6N" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 20 | 20:00 | 0:00 |  |  | 15-Apr | 16-Apr | - Date check | - Date check
CDUVDU8770 | Completed | Blinding | 19/04/2023 10:26:56 | 26/04/2023 18:46:44 | 04/04/2023 14:00:00 | 05/04/2023 05:00:00 | "6""-P-01-2103-A6N" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 15 | 15:00 | 176:20 | 161:20 |  | 04-Apr | 05-Apr | 19-Apr | 26-Apr
CDUVDU15520 | Not Started | Blinding |  |  | 09/04/2023 01:00:00 | 09/04/2023 19:00:00 | PT-3606 | INSP RECOMM | 0 | MECHANICAL | BLINDING | BLINDING | 18 | 18:00 | 0:00 |  |  | 09-Apr | 09-Apr | - Date check | - Date check
CDUVDU16990 | Not Started | Cutting, grinding, fit-up, welding and NDT |  |  | 09/04/2023 19:00:00 | 10/04/2023 16:00:00 | PT-3606 | INSP RECOMM | 0 | MECHANICAL |  |  | 21 | 21:00 | 0:00 |  |  | 09-Apr | 10-Apr | - Date check | - Date check
CDUVDU17880 | Not Started | Inspection activities |  |  | 10/04/2023 03:00:00 | 10/04/2023 23:00:00 | PT-3606 | INSP RECOMM | 0 | INSPECTION |  |  | 20 | 20:00 | 0:00 |  |  | 10-Apr | 10-Apr | - Date check | - Date check
CDUVDU19820 | Not Started | HT preparation |  |  | 10/04/2023 23:00:00 | 11/04/2023 11:00:00 | PT-3606 | INSP RECOMM | 0 | MECHANICAL |  |  | 12 | 12:00 | 0:00 |  |  | 10-Apr | 11-Apr | - Date check | - Date check
CDUVDU21060 | Not Started | Hydrotest Witness |  |  | 11/04/2023 11:00:00 | 11/04/2023 17:00:00 | PT-3606 | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 6 | 6:00 | 0:00 |  |  | 11-Apr | 11-Apr | - Date check | - Date check
CDUVDU21730 | Not Started | Draining |  |  | 11/04/2023 17:00:00 | 12/04/2023 03:00:00 | PT-3606 | INSP RECOMM | 0 | MECHANICAL |  |  | 10 | 10:00 | 0:00 |  |  | 11-Apr | 12-Apr | - Date check | - Date check
CDUVDU22710 | Not Started | De-blinding and hand-over |  |  | 12/04/2023 03:00:00 | 12/04/2023 21:00:00 | PT-3606 | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 18 | 18:00 | 0:00 |  |  | 12-Apr | 12-Apr | - Date check | - Date check
CDUVDU15530 | Completed | Blinding | 26/04/2023 12:37:19 | 26/04/2023 12:38:19 | 09/04/2023 01:00:00 | 09/04/2023 19:00:00 | "3""-CL-01-4204-A2A-IH" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 18 | 18:00 | 0:01 |  | 17:59 | 09-Apr | 09-Apr | 26-Apr | 26-Apr
CDUVDU17000 | Completed | Cutting, grinding, fit-up, welding and NDT | 26/04/2023 12:37:19 | 26/04/2023 12:38:19 | 09/04/2023 19:00:00 | 10/04/2023 16:00:00 | "3""-CL-01-4204-A2A-IH" | INSP RECOMM | 100 | MECHANICAL |  |  | 21 | 21:00 | 0:01 |  | 20:59 | 09-Apr | 10-Apr | 26-Apr | 26-Apr
CDUVDU17890 | Completed | Inspection activities | 26/04/2023 12:37:19 | 26/04/2023 12:38:19 | 10/04/2023 03:00:00 | 10/04/2023 23:00:00 | "3""-CL-01-4204-A2A-IH" | INSP RECOMM | 100 | INSPECTION |  |  | 20 | 20:00 | 0:01 |  | 19:59 | 10-Apr | 10-Apr | 26-Apr | 26-Apr
CDUVDU19830 | Completed | HT preparation | 26/04/2023 12:37:19 | 26/04/2023 12:38:19 | 10/04/2023 23:00:00 | 11/04/2023 11:00:00 | "3""-CL-01-4204-A2A-IH" | INSP RECOMM | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:01 |  | 11:59 | 10-Apr | 11-Apr | 26-Apr | 26-Apr
CDUVDU21070 | Completed | Hydrotest Witness | 26/04/2023 12:37:19 | 26/04/2023 12:38:19 | 11/04/2023 11:00:00 | 11/04/2023 17:00:00 | "3""-CL-01-4204-A2A-IH" | INSP RECOMM | 100 | INSPECTION | HYDRO TEST | HYDRO TEST | 6 | 6:00 | 0:01 |  | 5:59 | 11-Apr | 11-Apr | 26-Apr | 26-Apr
CDUVDU21740 | Completed | Draining | 26/04/2023 12:37:19 | 26/04/2023 12:38:19 | 11/04/2023 17:00:00 | 12/04/2023 03:00:00 | "3""-CL-01-4204-A2A-IH" | INSP RECOMM | 100 | MECHANICAL |  |  | 10 | 10:00 | 0:01 |  | 9:59 | 11-Apr | 12-Apr | 26-Apr | 26-Apr
CDUVDU22720 | Completed | De-blinding and hand-over | 26/04/2023 12:37:19 | 26/04/2023 12:38:19 | 12/04/2023 03:00:00 | 12/04/2023 21:00:00 | "3""-CL-01-4204-A2A-IH" | INSP RECOMM | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 18 | 18:00 | 0:01 |  | 17:59 | 12-Apr | 12-Apr | 26-Apr | 26-Apr
CDUVDU15540 | Completed | Blinding | 26/04/2023 12:37:41 | 26/04/2023 12:38:41 | 09/04/2023 01:00:00 | 09/04/2023 19:00:00 | "3""-CL-01-4208-A2A-IH" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 18 | 18:00 | 0:01 |  | 17:59 | 09-Apr | 09-Apr | 26-Apr | 26-Apr
CDUVDU17010 | Completed | Cutting, grinding, fit-up, welding and NDT | 26/04/2023 12:37:41 | 26/04/2023 12:38:41 | 09/04/2023 19:00:00 | 10/04/2023 16:00:00 | "3""-CL-01-4208-A2A-IH" | INSP RECOMM | 100 | MECHANICAL |  |  | 21 | 21:00 | 0:01 |  | 20:59 | 09-Apr | 10-Apr | 26-Apr | 26-Apr
CDUVDU17900 | Completed | Inspection activities | 26/04/2023 12:37:41 | 26/04/2023 12:38:41 | 10/04/2023 03:00:00 | 10/04/2023 23:00:00 | "3""-CL-01-4208-A2A-IH" | INSP RECOMM | 100 | INSPECTION |  |  | 20 | 20:00 | 0:01 |  | 19:59 | 10-Apr | 10-Apr | 26-Apr | 26-Apr
CDUVDU19840 | Completed | HT preparation | 26/04/2023 12:37:41 | 26/04/2023 12:38:41 | 10/04/2023 23:00:00 | 11/04/2023 11:00:00 | "3""-CL-01-4208-A2A-IH" | INSP RECOMM | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:01 |  | 11:59 | 10-Apr | 11-Apr | 26-Apr | 26-Apr
CDUVDU21080 | Completed | Hydrotest Witness | 26/04/2023 12:37:41 | 26/04/2023 12:38:41 | 11/04/2023 11:00:00 | 11/04/2023 17:00:00 | "3""-CL-01-4208-A2A-IH" | INSP RECOMM | 100 | INSPECTION | HYDRO TEST | HYDRO TEST | 6 | 6:00 | 0:01 |  | 5:59 | 11-Apr | 11-Apr | 26-Apr | 26-Apr
CDUVDU21750 | Completed | Draining | 26/04/2023 12:37:41 | 26/04/2023 12:38:41 | 11/04/2023 17:00:00 | 12/04/2023 03:00:00 | "3""-CL-01-4208-A2A-IH" | INSP RECOMM | 100 | MECHANICAL |  |  | 10 | 10:00 | 0:01 |  | 9:59 | 11-Apr | 12-Apr | 26-Apr | 26-Apr
CDUVDU22730 | Completed | De-blinding and hand-over | 26/04/2023 12:37:41 | 26/04/2023 12:38:41 | 12/04/2023 03:00:00 | 12/04/2023 21:00:00 | "3""-CL-01-4208-A2A-IH" | INSP RECOMM | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 18 | 18:00 | 0:01 |  | 17:59 | 12-Apr | 12-Apr | 26-Apr | 26-Apr
CDUVDU15550 | Completed | Blinding | 26/04/2023 12:38:15 | 26/04/2023 12:39:15 | 09/04/2023 01:00:00 | 09/04/2023 19:00:00 | "1""-SM-01-4501-B2A-IH" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 18 | 18:00 | 0:01 |  | 17:59 | 09-Apr | 09-Apr | 26-Apr | 26-Apr
CDUVDU17020 | Completed | Cutting, grinding, fit-up, welding and NDT | 26/04/2023 12:38:15 | 26/04/2023 12:39:15 | 09/04/2023 19:00:00 | 10/04/2023 16:00:00 | "1""-SM-01-4501-B2A-IH" | INSP RECOMM | 100 | MECHANICAL |  |  | 21 | 21:00 | 0:01 |  | 20:59 | 09-Apr | 10-Apr | 26-Apr | 26-Apr
CDUVDU17910 | Completed | Inspection activities | 26/04/2023 12:38:15 | 26/04/2023 12:39:15 | 10/04/2023 03:00:00 | 10/04/2023 23:00:00 | "1""-SM-01-4501-B2A-IH" | INSP RECOMM | 100 | INSPECTION |  |  | 20 | 20:00 | 0:01 |  | 19:59 | 10-Apr | 10-Apr | 26-Apr | 26-Apr
CDUVDU19850 | Completed | HT preparation | 26/04/2023 12:38:15 | 26/04/2023 12:39:15 | 10/04/2023 23:00:00 | 11/04/2023 11:00:00 | "1""-SM-01-4501-B2A-IH" | INSP RECOMM | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:01 |  | 11:59 | 10-Apr | 11-Apr | 26-Apr | 26-Apr
CDUVDU21090 | Completed | Hydrotest Witness | 26/04/2023 12:38:15 | 26/04/2023 12:39:15 | 11/04/2023 11:00:00 | 11/04/2023 17:00:00 | "1""-SM-01-4501-B2A-IH" | INSP RECOMM | 100 | INSPECTION | HYDRO TEST | HYDRO TEST | 6 | 6:00 | 0:01 |  | 5:59 | 11-Apr | 11-Apr | 26-Apr | 26-Apr
CDUVDU21760 | Completed | Draining | 26/04/2023 12:38:15 | 26/04/2023 12:39:15 | 11/04/2023 17:00:00 | 12/04/2023 03:00:00 | "1""-SM-01-4501-B2A-IH" | INSP RECOMM | 100 | MECHANICAL |  |  | 10 | 10:00 | 0:01 |  | 9:59 | 11-Apr | 12-Apr | 26-Apr | 26-Apr
CDUVDU22740 | Completed | De-blinding and hand-over | 26/04/2023 12:38:15 | 26/04/2023 12:39:15 | 12/04/2023 03:00:00 | 12/04/2023 21:00:00 | "1""-SM-01-4501-B2A-IH" | INSP RECOMM | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 18 | 18:00 | 0:01 |  | 17:59 | 12-Apr | 12-Apr | 26-Apr | 26-Apr
CDUVDU15560 | Completed | Blinding | 26/04/2023 12:38:30 | 26/04/2023 12:39:30 | 09/04/2023 01:00:00 | 09/04/2023 19:00:00 | "3""-SM-01-4004-B2A-IH" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 18 | 18:00 | 0:01 |  | 17:59 | 09-Apr | 09-Apr | 26-Apr | 26-Apr
CDUVDU17030 | Completed | Cutting, grinding, fit-up, welding and NDT | 26/04/2023 12:38:30 | 26/04/2023 12:39:30 | 09/04/2023 19:00:00 | 10/04/2023 16:00:00 | "3""-SM-01-4004-B2A-IH" | INSP RECOMM | 100 | MECHANICAL |  |  | 21 | 21:00 | 0:01 |  | 20:59 | 09-Apr | 10-Apr | 26-Apr | 26-Apr
CDUVDU17920 | Completed | Inspection activities | 26/04/2023 12:38:30 | 26/04/2023 12:39:30 | 10/04/2023 03:00:00 | 10/04/2023 23:00:00 | "3""-SM-01-4004-B2A-IH" | INSP RECOMM | 100 | INSPECTION |  |  | 20 | 20:00 | 0:01 |  | 19:59 | 10-Apr | 10-Apr | 26-Apr | 26-Apr
CDUVDU19860 | Completed | HT preparation | 26/04/2023 12:38:30 | 26/04/2023 12:39:30 | 10/04/2023 23:00:00 | 11/04/2023 11:00:00 | "3""-SM-01-4004-B2A-IH" | INSP RECOMM | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:01 |  | 11:59 | 10-Apr | 11-Apr | 26-Apr | 26-Apr
CDUVDU21100 | Completed | Hydrotest Witness | 26/04/2023 12:38:30 | 26/04/2023 12:39:30 | 11/04/2023 11:00:00 | 11/04/2023 17:00:00 | "3""-SM-01-4004-B2A-IH" | INSP RECOMM | 100 | INSPECTION | HYDRO TEST | HYDRO TEST | 6 | 6:00 | 0:01 |  | 5:59 | 11-Apr | 11-Apr | 26-Apr | 26-Apr
CDUVDU21770 | Completed | Draining | 26/04/2023 12:38:30 | 26/04/2023 12:39:30 | 11/04/2023 17:00:00 | 12/04/2023 03:00:00 | "3""-SM-01-4004-B2A-IH" | INSP RECOMM | 100 | MECHANICAL |  |  | 10 | 10:00 | 0:01 |  | 9:59 | 11-Apr | 12-Apr | 26-Apr | 26-Apr
CDUVDU22750 | Completed | De-blinding and hand-over | 26/04/2023 12:38:30 | 26/04/2023 12:39:30 | 12/04/2023 03:00:00 | 12/04/2023 21:00:00 | "3""-SM-01-4004-B2A-IH" | INSP RECOMM | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 18 | 18:00 | 0:01 |  | 17:59 | 12-Apr | 12-Apr | 26-Apr | 26-Apr
CDUVDU15570 | Completed | Blinding | 26/04/2023 12:38:53 | 26/04/2023 12:39:53 | 09/04/2023 01:00:00 | 09/04/2023 19:00:00 | "3""-SM-01-3804-B2A-IH" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 18 | 18:00 | 0:01 |  | 17:59 | 09-Apr | 09-Apr | 26-Apr | 26-Apr
CDUVDU17040 | Completed | Cutting, grinding, fit-up, welding and NDT | 26/04/2023 12:38:53 | 26/04/2023 12:39:53 | 09/04/2023 19:00:00 | 10/04/2023 16:00:00 | "3""-SM-01-3804-B2A-IH" | INSP RECOMM | 100 | MECHANICAL |  |  | 21 | 21:00 | 0:01 |  | 20:59 | 09-Apr | 10-Apr | 26-Apr | 26-Apr
CDUVDU17930 | Completed | Inspection activities | 26/04/2023 12:38:53 | 26/04/2023 12:39:53 | 10/04/2023 03:00:00 | 10/04/2023 23:00:00 | "3""-SM-01-3804-B2A-IH" | INSP RECOMM | 100 | INSPECTION |  |  | 20 | 20:00 | 0:01 |  | 19:59 | 10-Apr | 10-Apr | 26-Apr | 26-Apr
CDUVDU19870 | Completed | HT preparation | 26/04/2023 12:38:53 | 26/04/2023 12:39:53 | 10/04/2023 23:00:00 | 11/04/2023 11:00:00 | "3""-SM-01-3804-B2A-IH" | INSP RECOMM | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:01 |  | 11:59 | 10-Apr | 11-Apr | 26-Apr | 26-Apr
CDUVDU21110 | Completed | Hydrotest Witness | 26/04/2023 12:38:53 | 26/04/2023 12:39:53 | 11/04/2023 11:00:00 | 11/04/2023 17:00:00 | "3""-SM-01-3804-B2A-IH" | INSP RECOMM | 100 | INSPECTION | HYDRO TEST | HYDRO TEST | 6 | 6:00 | 0:01 |  | 5:59 | 11-Apr | 11-Apr | 26-Apr | 26-Apr
CDUVDU21780 | Completed | Draining | 26/04/2023 12:38:53 | 26/04/2023 12:39:53 | 11/04/2023 17:00:00 | 12/04/2023 03:00:00 | "3""-SM-01-3804-B2A-IH" | INSP RECOMM | 100 | MECHANICAL |  |  | 10 | 10:00 | 0:01 |  | 9:59 | 11-Apr | 12-Apr | 26-Apr | 26-Apr
CDUVDU22760 | Completed | De-blinding and hand-over | 26/04/2023 12:38:53 | 26/04/2023 12:39:53 | 12/04/2023 03:00:00 | 12/04/2023 21:00:00 | "3""-SM-01-3804-B2A-IH" | INSP RECOMM | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 18 | 18:00 | 0:01 |  | 17:59 | 12-Apr | 12-Apr | 26-Apr | 26-Apr
CDUVDU15580 | Completed | Blinding | 23/04/2023 12:20:18 | 23/04/2023 12:21:18 | 09/04/2023 01:00:00 | 09/04/2023 19:00:00 | "2""-FLO-01-3433-A1A" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 18 | 18:00 | 0:01 |  | 17:59 | 09-Apr | 09-Apr | 23-Apr | 23-Apr
CDUVDU17050 | Completed | Cutting, grinding, fit-up, welding and NDT | 23/04/2023 12:20:18 | 23/04/2023 12:21:18 | 09/04/2023 19:00:00 | 10/04/2023 16:00:00 | "2""-FLO-01-3433-A1A" | INSP RECOMM | 100 | MECHANICAL |  |  | 21 | 21:00 | 0:01 |  | 20:59 | 09-Apr | 10-Apr | 23-Apr | 23-Apr
CDUVDU17940 | Completed | Inspection activities | 23/04/2023 12:20:18 | 23/04/2023 12:21:18 | 10/04/2023 03:00:00 | 10/04/2023 23:00:00 | "2""-FLO-01-3433-A1A" | INSP RECOMM | 100 | INSPECTION |  |  | 20 | 20:00 | 0:01 |  | 19:59 | 10-Apr | 10-Apr | 23-Apr | 23-Apr
CDUVDU19880 | Completed | HT preparation | 23/04/2023 12:20:18 | 23/04/2023 12:21:18 | 10/04/2023 23:00:00 | 11/04/2023 11:00:00 | "2""-FLO-01-3433-A1A" | INSP RECOMM | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:01 |  | 11:59 | 10-Apr | 11-Apr | 23-Apr | 23-Apr
CDUVDU21120 | Completed | Hydrotest Witness | 23/04/2023 12:20:18 | 23/04/2023 12:21:18 | 11/04/2023 11:00:00 | 11/04/2023 17:00:00 | "2""-FLO-01-3433-A1A" | INSP RECOMM | 100 | INSPECTION | HYDRO TEST | HYDRO TEST | 6 | 6:00 | 0:01 |  | 5:59 | 11-Apr | 11-Apr | 23-Apr | 23-Apr
CDUVDU21790 | Completed | Draining | 23/04/2023 12:20:18 | 23/04/2023 12:21:18 | 11/04/2023 17:00:00 | 12/04/2023 03:00:00 | "2""-FLO-01-3433-A1A" | INSP RECOMM | 100 | MECHANICAL |  |  | 10 | 10:00 | 0:01 |  | 9:59 | 11-Apr | 12-Apr | 23-Apr | 23-Apr
CDUVDU22770 | Completed | De-blinding and hand-over | 23/04/2023 12:20:18 | 23/04/2023 12:21:18 | 12/04/2023 03:00:00 | 12/04/2023 21:00:00 | "2""-FLO-01-3433-A1A" | INSP RECOMM | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 18 | 18:00 | 0:01 |  | 17:59 | 12-Apr | 12-Apr | 23-Apr | 23-Apr
CDUVDU15590 | Completed | Blinding | 26/04/2023 11:38:14 | 26/04/2023 11:39:14 | 09/04/2023 01:00:00 | 09/04/2023 19:00:00 | "2""-C-01-2701-A1K" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 18 | 18:00 | 0:01 |  | 17:59 | 09-Apr | 09-Apr | 26-Apr | 26-Apr
CDUVDU17060 | Completed | Cutting, grinding, fit-up, welding and NDT | 26/04/2023 11:38:14 | 26/04/2023 11:39:14 | 09/04/2023 19:00:00 | 10/04/2023 16:00:00 | "2""-C-01-2701-A1K" | INSP RECOMM | 100 | MECHANICAL |  |  | 21 | 21:00 | 0:01 |  | 20:59 | 09-Apr | 10-Apr | 26-Apr | 26-Apr
CDUVDU17950 | Completed | Inspection activities | 26/04/2023 11:38:14 | 26/04/2023 11:39:14 | 10/04/2023 03:00:00 | 10/04/2023 23:00:00 | "2""-C-01-2701-A1K" | INSP RECOMM | 100 | INSPECTION |  |  | 20 | 20:00 | 0:01 |  | 19:59 | 10-Apr | 10-Apr | 26-Apr | 26-Apr
CDUVDU19890 | Completed | HT preparation | 26/04/2023 11:38:14 | 26/04/2023 11:39:14 | 10/04/2023 23:00:00 | 11/04/2023 11:00:00 | "2""-C-01-2701-A1K" | INSP RECOMM | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:01 |  | 11:59 | 10-Apr | 11-Apr | 26-Apr | 26-Apr
CDUVDU21130 | Completed | Hydrotest Witness | 26/04/2023 11:38:14 | 26/04/2023 11:39:14 | 11/04/2023 11:00:00 | 11/04/2023 17:00:00 | "2""-C-01-2701-A1K" | INSP RECOMM | 100 | INSPECTION | HYDRO TEST | HYDRO TEST | 6 | 6:00 | 0:01 |  | 5:59 | 11-Apr | 11-Apr | 26-Apr | 26-Apr
CDUVDU21800 | Completed | Draining | 26/04/2023 11:38:14 | 26/04/2023 11:39:14 | 11/04/2023 17:00:00 | 12/04/2023 03:00:00 | "2""-C-01-2701-A1K" | INSP RECOMM | 100 | MECHANICAL |  |  | 10 | 10:00 | 0:01 |  | 9:59 | 11-Apr | 12-Apr | 26-Apr | 26-Apr
CDUVDU22780 | Completed | De-blinding and hand-over | 26/04/2023 11:38:14 | 26/04/2023 11:39:14 | 12/04/2023 03:00:00 | 12/04/2023 21:00:00 | "2""-C-01-2701-A1K" | INSP RECOMM | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 18 | 18:00 | 0:01 |  | 17:59 | 12-Apr | 12-Apr | 26-Apr | 26-Apr
CDUVDU14120 | Completed | Blinding | 23/04/2023 12:13:27 | 23/04/2023 12:13:27 | 08/04/2023 07:00:00 | 09/04/2023 01:00:00 | "2""-WDM-01-1605-A3A" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 18 | 18:00 | 0:00 |  |  | 08-Apr | 09-Apr | 23-Apr | 23-Apr
CDUVDU15460 | Completed | Cutting, grinding, fit-up, welding and NDT | 23/04/2023 12:13:27 | 23/04/2023 12:13:27 | 09/04/2023 01:00:00 | 09/04/2023 22:00:00 | "2""-WDM-01-1605-A3A" | INSP RECOMM | 100 | MECHANICAL |  |  | 21 | 21:00 | 0:00 |  |  | 09-Apr | 09-Apr | 23-Apr | 23-Apr
CDUVDU16160 | Completed | Inspection activities | 23/04/2023 12:13:27 | 23/04/2023 12:13:27 | 09/04/2023 09:00:00 | 10/04/2023 05:00:00 | "2""-WDM-01-1605-A3A" | INSP RECOMM | 100 | INSPECTION |  |  | 20 | 20:00 | 0:00 |  |  | 09-Apr | 10-Apr | 23-Apr | 23-Apr
CDUVDU18120 | Completed | HT preparation | 23/04/2023 12:13:27 | 23/04/2023 12:13:27 | 10/04/2023 05:00:00 | 10/04/2023 17:00:00 | "2""-WDM-01-1605-A3A" | INSP RECOMM | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:00 |  |  | 10-Apr | 10-Apr | 23-Apr | 23-Apr
CDUVDU19210 | Completed | Hydrotest Witness | 23/04/2023 12:13:27 | 23/04/2023 12:13:27 | 10/04/2023 17:00:00 | 10/04/2023 23:00:00 | "2""-WDM-01-1605-A3A" | INSP RECOMM | 100 | INSPECTION | HYDRO TEST | HYDRO TEST | 6 | 6:00 | 0:00 |  |  | 10-Apr | 10-Apr | 23-Apr | 23-Apr
CDUVDU19760 | Completed | Draining | 23/04/2023 12:13:27 | 23/04/2023 12:13:27 | 10/04/2023 23:00:00 | 11/04/2023 09:00:00 | "2""-WDM-01-1605-A3A" | INSP RECOMM | 100 | MECHANICAL |  |  | 10 | 10:00 | 0:00 |  |  | 10-Apr | 11-Apr | 23-Apr | 23-Apr
CDUVDU20830 | Completed | De-blinding and hand-over | 23/04/2023 12:13:27 | 23/04/2023 12:13:27 | 11/04/2023 09:00:00 | 12/04/2023 03:00:00 | "2""-WDM-01-1605-A3A" | INSP RECOMM | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 18 | 18:00 | 0:00 |  |  | 11-Apr | 12-Apr | 23-Apr | 23-Apr
CDUVDU17070 | Completed | Blinding | 26/04/2023 11:38:33 | 26/04/2023 11:39:33 | 09/04/2023 19:00:00 | 10/04/2023 13:00:00 | "2""-C-01-2702-A1K" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 18 | 18:00 | 0:01 |  | 17:59 | 09-Apr | 10-Apr | 26-Apr | 26-Apr
CDUVDU18780 | Completed | Cutting, grinding, fit-up, welding and NDT | 26/04/2023 11:38:33 | 26/04/2023 11:39:33 | 10/04/2023 13:00:00 | 11/04/2023 10:00:00 | "2""-C-01-2702-A1K" | INSP RECOMM | 100 | MECHANICAL |  |  | 21 | 21:00 | 0:01 |  | 20:59 | 10-Apr | 11-Apr | 26-Apr | 26-Apr
CDUVDU19580 | Completed | Inspection activities | 26/04/2023 11:38:33 | 26/04/2023 11:39:33 | 10/04/2023 21:00:00 | 11/04/2023 17:00:00 | "2""-C-01-2702-A1K" | INSP RECOMM | 100 | INSPECTION |  |  | 20 | 20:00 | 0:01 |  | 19:59 | 10-Apr | 11-Apr | 26-Apr | 26-Apr
CDUVDU21810 | Completed | HT preparation | 26/04/2023 11:38:33 | 26/04/2023 11:39:33 | 11/04/2023 17:00:00 | 12/04/2023 05:00:00 | "2""-C-01-2702-A1K" | INSP RECOMM | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:01 |  | 11:59 | 11-Apr | 12-Apr | 26-Apr | 26-Apr
CDUVDU22900 | Completed | Hydrotest Witness | 26/04/2023 11:38:33 | 26/04/2023 11:39:33 | 12/04/2023 05:00:00 | 12/04/2023 11:00:00 | "2""-C-01-2702-A1K" | INSP RECOMM | 100 | INSPECTION | HYDRO TEST | HYDRO TEST | 6 | 6:00 | 0:01 |  | 5:59 | 12-Apr | 12-Apr | 26-Apr | 26-Apr
CDUVDU23450 | Completed | Draining | 26/04/2023 11:38:33 | 26/04/2023 11:39:33 | 12/04/2023 11:00:00 | 12/04/2023 21:00:00 | "2""-C-01-2702-A1K" | INSP RECOMM | 100 | MECHANICAL |  |  | 10 | 10:00 | 0:01 |  | 9:59 | 12-Apr | 12-Apr | 26-Apr | 26-Apr
CDUVDU24230 | Completed | De-blinding and hand-over | 26/04/2023 11:38:33 | 26/04/2023 11:39:33 | 12/04/2023 21:00:00 | 13/04/2023 15:00:00 | "2""-C-01-2702-A1K" | INSP RECOMM | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 18 | 18:00 | 0:01 |  | 17:59 | 12-Apr | 13-Apr | 26-Apr | 26-Apr
CDUVDU8810 | Not Started | Support rectification |  |  | 04/04/2023 14:00:00 | 05/04/2023 11:00:00 | "10""-P-01-2117-A1F-IT" | INSP RECOMM | 0 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 21 | 21:00 | 0:00 |  |  | 04-Apr | 05-Apr | - Date check | - Date check
CDUVDU8800 | Not Started | Support rectification |  |  | 04/04/2023 14:00:00 | 05/04/2023 11:00:00 | "12""- SL-01-2101-A2A-IH" | INSP RECOMM | 0 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 21 | 21:00 | 0:00 |  |  | 04-Apr | 05-Apr | - Date check | - Date check
CDUVDU17080 | Completed | Blinding | 26/04/2023 11:39:01 | 26/04/2023 11:40:01 | 09/04/2023 19:00:00 | 10/04/2023 13:00:00 | "2""-C-01-2705-A1K" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 18 | 18:00 | 0:01 |  | 17:59 | 09-Apr | 10-Apr | 26-Apr | 26-Apr
CDUVDU18790 | Completed | Cutting, grinding, fit-up, welding and NDT | 26/04/2023 11:39:01 | 26/04/2023 11:40:01 | 10/04/2023 13:00:00 | 11/04/2023 10:00:00 | "2""-C-01-2705-A1K" | INSP RECOMM | 100 | MECHANICAL |  |  | 21 | 21:00 | 0:01 |  | 20:59 | 10-Apr | 11-Apr | 26-Apr | 26-Apr
CDUVDU19590 | Completed | Inspection activities | 26/04/2023 11:39:01 | 26/04/2023 11:40:01 | 10/04/2023 21:00:00 | 11/04/2023 17:00:00 | "2""-C-01-2705-A1K" | INSP RECOMM | 100 | INSPECTION |  |  | 20 | 20:00 | 0:01 |  | 19:59 | 10-Apr | 11-Apr | 26-Apr | 26-Apr
CDUVDU21820 | Completed | HT preparation | 26/04/2023 11:39:01 | 26/04/2023 11:40:01 | 11/04/2023 17:00:00 | 12/04/2023 05:00:00 | "2""-C-01-2705-A1K" | INSP RECOMM | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:01 |  | 11:59 | 11-Apr | 12-Apr | 26-Apr | 26-Apr
CDUVDU22910 | Completed | Hydrotest Witness | 26/04/2023 11:39:01 | 26/04/2023 11:40:01 | 12/04/2023 05:00:00 | 12/04/2023 11:00:00 | "2""-C-01-2705-A1K" | INSP RECOMM | 100 | INSPECTION | HYDRO TEST | HYDRO TEST | 6 | 6:00 | 0:01 |  | 5:59 | 12-Apr | 12-Apr | 26-Apr | 26-Apr
CDUVDU23460 | Completed | Draining | 26/04/2023 11:39:01 | 26/04/2023 11:40:01 | 12/04/2023 11:00:00 | 12/04/2023 21:00:00 | "2""-C-01-2705-A1K" | INSP RECOMM | 100 | MECHANICAL |  |  | 10 | 10:00 | 0:01 |  | 9:59 | 12-Apr | 12-Apr | 26-Apr | 26-Apr
CDUVDU24240 | Completed | De-blinding and hand-over | 26/04/2023 11:39:01 | 26/04/2023 11:40:01 | 12/04/2023 21:00:00 | 13/04/2023 15:00:00 | "2""-C-01-2705-A1K" | INSP RECOMM | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 18 | 18:00 | 0:01 |  | 17:59 | 12-Apr | 13-Apr | 26-Apr | 26-Apr
CDUVDU17090 | Completed | Blinding | 26/04/2023 11:39:20 | 26/04/2023 11:40:20 | 09/04/2023 19:00:00 | 10/04/2023 13:00:00 | "2""-C-01-2706-A1K" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 18 | 18:00 | 0:01 |  | 17:59 | 09-Apr | 10-Apr | 26-Apr | 26-Apr
CDUVDU18800 | Completed | Cutting, grinding, fit-up, welding and NDT | 26/04/2023 11:39:20 | 26/04/2023 11:40:20 | 10/04/2023 13:00:00 | 11/04/2023 10:00:00 | "2""-C-01-2706-A1K" | INSP RECOMM | 100 | MECHANICAL |  |  | 21 | 21:00 | 0:01 |  | 20:59 | 10-Apr | 11-Apr | 26-Apr | 26-Apr
CDUVDU19600 | Completed | Inspection activities | 26/04/2023 11:39:20 | 26/04/2023 11:40:20 | 10/04/2023 21:00:00 | 11/04/2023 17:00:00 | "2""-C-01-2706-A1K" | INSP RECOMM | 100 | INSPECTION |  |  | 20 | 20:00 | 0:01 |  | 19:59 | 10-Apr | 11-Apr | 26-Apr | 26-Apr
CDUVDU21830 | Completed | HT preparation | 26/04/2023 11:39:20 | 26/04/2023 11:40:20 | 11/04/2023 17:00:00 | 12/04/2023 05:00:00 | "2""-C-01-2706-A1K" | INSP RECOMM | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:01 |  | 11:59 | 11-Apr | 12-Apr | 26-Apr | 26-Apr
CDUVDU22920 | Completed | Hydrotest Witness | 26/04/2023 11:39:20 | 26/04/2023 11:40:20 | 12/04/2023 05:00:00 | 12/04/2023 11:00:00 | "2""-C-01-2706-A1K" | INSP RECOMM | 100 | INSPECTION | HYDRO TEST | HYDRO TEST | 6 | 6:00 | 0:01 |  | 5:59 | 12-Apr | 12-Apr | 26-Apr | 26-Apr
CDUVDU23470 | Completed | Draining | 26/04/2023 11:39:20 | 26/04/2023 11:40:20 | 12/04/2023 11:00:00 | 12/04/2023 21:00:00 | "2""-C-01-2706-A1K" | INSP RECOMM | 100 | MECHANICAL |  |  | 10 | 10:00 | 0:01 |  | 9:59 | 12-Apr | 12-Apr | 26-Apr | 26-Apr
CDUVDU24250 | Completed | De-blinding and hand-over | 26/04/2023 11:39:20 | 26/04/2023 11:40:20 | 12/04/2023 21:00:00 | 13/04/2023 15:00:00 | "2""-C-01-2706-A1K" | INSP RECOMM | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 18 | 18:00 | 0:01 |  | 17:59 | 12-Apr | 13-Apr | 26-Apr | 26-Apr
CDUVDU17100 | Completed | Blinding | 23/04/2023 12:24:23 | 23/04/2023 12:24:23 | 09/04/2023 19:00:00 | 10/04/2023 13:00:00 | "3""-FG-01-2806-A1A" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 18 | 18:00 | 0:00 |  |  | 09-Apr | 10-Apr | 23-Apr | 23-Apr
CDUVDU18810 | Completed | Cutting, grinding, fit-up, welding and NDT | 23/04/2023 12:24:23 | 23/04/2023 12:24:23 | 10/04/2023 13:00:00 | 11/04/2023 10:00:00 | "3""-FG-01-2806-A1A" | INSP RECOMM | 100 | MECHANICAL |  |  | 21 | 21:00 | 0:00 |  |  | 10-Apr | 11-Apr | 23-Apr | 23-Apr
CDUVDU19610 | Completed | Inspection activities | 23/04/2023 12:24:23 | 23/04/2023 12:24:23 | 10/04/2023 21:00:00 | 11/04/2023 17:00:00 | "3""-FG-01-2806-A1A" | INSP RECOMM | 100 | INSPECTION |  |  | 20 | 20:00 | 0:00 |  |  | 10-Apr | 11-Apr | 23-Apr | 23-Apr
CDUVDU21840 | Completed | HT preparation | 23/04/2023 12:24:23 | 23/04/2023 12:24:23 | 11/04/2023 17:00:00 | 12/04/2023 05:00:00 | "3""-FG-01-2806-A1A" | INSP RECOMM | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:00 |  |  | 11-Apr | 12-Apr | 23-Apr | 23-Apr
CDUVDU22930 | Completed | Hydrotest Witness | 23/04/2023 12:24:23 | 23/04/2023 12:24:23 | 12/04/2023 05:00:00 | 12/04/2023 11:00:00 | "3""-FG-01-2806-A1A" | INSP RECOMM | 100 | INSPECTION | HYDRO TEST | HYDRO TEST | 6 | 6:00 | 0:00 |  |  | 12-Apr | 12-Apr | 23-Apr | 23-Apr
CDUVDU23480 | Completed | Draining | 23/04/2023 12:24:23 | 23/04/2023 12:24:23 | 12/04/2023 11:00:00 | 12/04/2023 21:00:00 | "3""-FG-01-2806-A1A" | INSP RECOMM | 100 | MECHANICAL |  |  | 10 | 10:00 | 0:00 |  |  | 12-Apr | 12-Apr | 23-Apr | 23-Apr
CDUVDU24260 | Completed | De-blinding and hand-over | 23/04/2023 12:24:23 | 23/04/2023 12:24:23 | 12/04/2023 21:00:00 | 13/04/2023 15:00:00 | "3""-FG-01-2806-A1A" | INSP RECOMM | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 18 | 18:00 | 0:00 |  |  | 12-Apr | 13-Apr | 23-Apr | 23-Apr
CDUVDU17110 | Not Started | Blinding |  |  | 09/04/2023 19:00:00 | 10/04/2023 13:00:00 | "2""-CBD-01-3220-B1A" | INSP RECOMM | 0 | MECHANICAL | BLINDING | BLINDING | 18 | 18:00 | 0:00 |  |  | 09-Apr | 10-Apr | - Date check | - Date check
CDUVDU18820 | Not Started | Cutting, grinding, fit-up, welding and NDT |  |  | 10/04/2023 13:00:00 | 11/04/2023 10:00:00 | "2""-CBD-01-3220-B1A" | INSP RECOMM | 0 | MECHANICAL |  |  | 21 | 21:00 | 0:00 |  |  | 10-Apr | 11-Apr | - Date check | - Date check
CDUVDU19620 | Not Started | Inspection activities |  |  | 10/04/2023 21:00:00 | 11/04/2023 17:00:00 | "2""-CBD-01-3220-B1A" | INSP RECOMM | 0 | INSPECTION |  |  | 20 | 20:00 | 0:00 |  |  | 10-Apr | 11-Apr | - Date check | - Date check
CDUVDU21850 | Not Started | HT preparation |  |  | 11/04/2023 17:00:00 | 12/04/2023 05:00:00 | "2""-CBD-01-3220-B1A" | INSP RECOMM | 0 | MECHANICAL |  |  | 12 | 12:00 | 0:00 |  |  | 11-Apr | 12-Apr | - Date check | - Date check
CDUVDU22940 | Not Started | Hydrotest Witness |  |  | 12/04/2023 05:00:00 | 12/04/2023 11:00:00 | "2""-CBD-01-3220-B1A" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 6 | 6:00 | 0:00 |  |  | 12-Apr | 12-Apr | - Date check | - Date check
CDUVDU23490 | Not Started | Draining |  |  | 12/04/2023 11:00:00 | 12/04/2023 21:00:00 | "2""-CBD-01-3220-B1A" | INSP RECOMM | 0 | MECHANICAL |  |  | 10 | 10:00 | 0:00 |  |  | 12-Apr | 12-Apr | - Date check | - Date check
CDUVDU24270 | Not Started | De-blinding and hand-over |  |  | 12/04/2023 21:00:00 | 13/04/2023 15:00:00 | "2""-CBD-01-3220-B1A" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 18 | 18:00 | 0:00 |  |  | 12-Apr | 13-Apr | - Date check | - Date check
CDUVDU17120 | Completed | Blinding | 08/04/2023 15:58:51 | 08/04/2023 15:59:11 | 09/04/2023 19:00:00 | 10/04/2023 13:00:00 | "4""-P-01-1533-A1A-IS" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 18 | 18:00 | 0:00 |  | 18:00 | 09-Apr | 10-Apr | 08-Apr | 08-Apr
CDUVDU18830 | Completed | Cutting, grinding, fit-up, welding and NDT | 08/04/2023 15:59:02 | 08/04/2023 15:59:20 | 10/04/2023 13:00:00 | 11/04/2023 10:00:00 | "4""-P-01-1533-A1A-IS" | INSP RECOMM | 100 | MECHANICAL |  |  | 21 | 21:00 | 0:00 |  | 21:00 | 10-Apr | 11-Apr | 08-Apr | 08-Apr
CDUVDU19630 | Completed | Inspection activities | 18/04/2023 10:42:52 | 18/04/2023 10:43:00 | 10/04/2023 21:00:00 | 11/04/2023 17:00:00 | "4""-P-01-1533-A1A-IS" | INSP RECOMM | 100 | INSPECTION |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 10-Apr | 11-Apr | 18-Apr | 18-Apr
CDUVDU21860 | Not Started | HT preparation |  |  | 11/04/2023 17:00:00 | 12/04/2023 05:00:00 | "4""-P-01-1533-A1A-IS" | INSP RECOMM | 0 | MECHANICAL |  |  | 12 | 12:00 | 0:00 |  |  | 11-Apr | 12-Apr | - Date check | - Date check
CDUVDU22950 | Not Started | Hydrotest Witness |  |  | 12/04/2023 05:00:00 | 12/04/2023 11:00:00 | "4""-P-01-1533-A1A-IS" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 6 | 6:00 | 0:00 |  |  | 12-Apr | 12-Apr | - Date check | - Date check
CDUVDU23500 | Not Started | Draining |  |  | 12/04/2023 11:00:00 | 12/04/2023 21:00:00 | "4""-P-01-1533-A1A-IS" | INSP RECOMM | 0 | MECHANICAL |  |  | 10 | 10:00 | 0:00 |  |  | 12-Apr | 12-Apr | - Date check | - Date check
CDUVDU24280 | Not Started | De-blinding and hand-over |  |  | 12/04/2023 21:00:00 | 13/04/2023 15:00:00 | "4""-P-01-1533-A1A-IS" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 18 | 18:00 | 0:00 |  |  | 12-Apr | 13-Apr | - Date check | - Date check
CDUVDU18840 | Completed | Blinding | 23/04/2023 12:26:50 | 23/04/2023 12:27:50 | 10/04/2023 13:00:00 | 11/04/2023 07:00:00 | "4""-P-01-2188-A1A-N" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 18 | 18:00 | 0:01 |  | 17:59 | 10-Apr | 11-Apr | 23-Apr | 23-Apr
CDUVDU20680 | Completed | Cutting, grinding, fit-up, welding and NDT | 23/04/2023 12:29:08 | 23/04/2023 12:29:08 | 11/04/2023 07:00:00 | 12/04/2023 04:00:00 | "4""-P-01-2188-A1A-N" | INSP RECOMM | 100 | MECHANICAL |  |  | 21 | 21:00 | 0:00 |  |  | 11-Apr | 12-Apr | 23-Apr | 23-Apr
CDUVDU21570 | Completed | Inspection activities | 23/04/2023 12:29:08 | 23/04/2023 12:29:08 | 11/04/2023 15:00:00 | 12/04/2023 11:00:00 | "4""-P-01-2188-A1A-N" | INSP RECOMM | 100 | INSPECTION |  |  | 20 | 20:00 | 0:00 |  |  | 11-Apr | 12-Apr | 23-Apr | 23-Apr
CDUVDU23510 | Completed | HT preparation | 23/04/2023 12:26:10 | 23/04/2023 12:27:10 | 12/04/2023 11:00:00 | 12/04/2023 23:00:00 | "4""-P-01-2188-A1A-N" | INSP RECOMM | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:01 |  | 11:59 | 12-Apr | 12-Apr | 23-Apr | 23-Apr
CDUVDU24450 | Completed | Hydrotest Witness | 23/04/2023 12:26:19 | 23/04/2023 12:27:19 | 12/04/2023 23:00:00 | 13/04/2023 05:00:00 | "4""-P-01-2188-A1A-N" | INSP RECOMM | 100 | INSPECTION | HYDRO TEST | HYDRO TEST | 6 | 6:00 | 0:01 |  | 5:59 | 12-Apr | 13-Apr | 23-Apr | 23-Apr
CDUVDU24860 | Completed | Draining | 23/04/2023 12:26:28 | 23/04/2023 12:27:28 | 13/04/2023 05:00:00 | 13/04/2023 15:00:00 | "4""-P-01-2188-A1A-N" | INSP RECOMM | 100 | MECHANICAL |  |  | 10 | 10:00 | 0:01 |  | 9:59 | 13-Apr | 13-Apr | 23-Apr | 23-Apr
CDUVDU25480 | Completed | De-blinding and hand-over | 23/04/2023 12:26:42 | 23/04/2023 12:27:42 | 13/04/2023 15:00:00 | 14/04/2023 09:00:00 | "4""-P-01-2188-A1A-N" | INSP RECOMM | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 18 | 18:00 | 0:01 |  | 17:59 | 13-Apr | 14-Apr | 23-Apr | 23-Apr
CDUVDU18850 | Completed | Blinding | 23/04/2023 12:28:50 | 23/04/2023 12:29:50 | 10/04/2023 13:00:00 | 11/04/2023 07:00:00 | "4""-WB-01-2704-A2A-IH" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 18 | 18:00 | 0:01 |  | 17:59 | 10-Apr | 11-Apr | 23-Apr | 23-Apr
CDUVDU20690 | Completed | Cutting, grinding, fit-up, welding and NDT | 23/04/2023 12:31:24 | 23/04/2023 12:31:24 | 11/04/2023 07:00:00 | 12/04/2023 04:00:00 | "4""-WB-01-2704-A2A-IH" | INSP RECOMM | 100 | MECHANICAL |  |  | 21 | 21:00 | 0:00 |  |  | 11-Apr | 12-Apr | 23-Apr | 23-Apr
CDUVDU21580 | Completed | Inspection activities | 23/04/2023 12:31:24 | 23/04/2023 12:31:24 | 11/04/2023 15:00:00 | 12/04/2023 11:00:00 | "4""-WB-01-2704-A2A-IH" | INSP RECOMM | 100 | INSPECTION |  |  | 20 | 20:00 | 0:00 |  |  | 11-Apr | 12-Apr | 23-Apr | 23-Apr
CDUVDU23520 | Completed | HT preparation | 23/04/2023 12:29:29 | 23/04/2023 12:30:29 | 12/04/2023 11:00:00 | 12/04/2023 23:00:00 | "4""-WB-01-2704-A2A-IH" | INSP RECOMM | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:01 |  | 11:59 | 12-Apr | 12-Apr | 23-Apr | 23-Apr
CDUVDU24460 | Completed | Hydrotest Witness | 23/04/2023 12:29:16 | 23/04/2023 12:30:16 | 12/04/2023 23:00:00 | 13/04/2023 05:00:00 | "4""-WB-01-2704-A2A-IH" | INSP RECOMM | 100 | INSPECTION | HYDRO TEST | HYDRO TEST | 6 | 6:00 | 0:01 |  | 5:59 | 12-Apr | 13-Apr | 23-Apr | 23-Apr
CDUVDU24870 | Completed | Draining | 23/04/2023 12:29:08 | 23/04/2023 12:30:08 | 13/04/2023 05:00:00 | 13/04/2023 15:00:00 | "4""-WB-01-2704-A2A-IH" | INSP RECOMM | 100 | MECHANICAL |  |  | 10 | 10:00 | 0:01 |  | 9:59 | 13-Apr | 13-Apr | 23-Apr | 23-Apr
CDUVDU25490 | Completed | De-blinding and hand-over | 23/04/2023 12:28:59 | 23/04/2023 12:29:59 | 13/04/2023 15:00:00 | 14/04/2023 09:00:00 | "4""-WB-01-2704-A2A-IH" | INSP RECOMM | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 18 | 18:00 | 0:01 |  | 17:59 | 13-Apr | 14-Apr | 23-Apr | 23-Apr
CDUVDU14130 | Completed | Blinding | 23/04/2023 12:13:49 | 23/04/2023 12:13:49 | 08/04/2023 07:00:00 | 09/04/2023 01:00:00 | "2""-WDM-01-1604-A3A" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 18 | 18:00 | 0:00 |  |  | 08-Apr | 09-Apr | 23-Apr | 23-Apr
CDUVDU15470 | Completed | Cutting, grinding, fit-up, welding and NDT | 23/04/2023 12:13:49 | 23/04/2023 12:13:49 | 09/04/2023 01:00:00 | 09/04/2023 22:00:00 | "2""-WDM-01-1604-A3A" | INSP RECOMM | 100 | MECHANICAL |  |  | 21 | 21:00 | 0:00 |  |  | 09-Apr | 09-Apr | 23-Apr | 23-Apr
CDUVDU16170 | Completed | Inspection activities | 23/04/2023 12:13:49 | 23/04/2023 12:13:49 | 09/04/2023 09:00:00 | 10/04/2023 05:00:00 | "2""-WDM-01-1604-A3A" | INSP RECOMM | 100 | INSPECTION |  |  | 20 | 20:00 | 0:00 |  |  | 09-Apr | 10-Apr | 23-Apr | 23-Apr
CDUVDU18130 | Completed | HT preparation | 23/04/2023 12:13:49 | 23/04/2023 12:13:49 | 10/04/2023 05:00:00 | 10/04/2023 17:00:00 | "2""-WDM-01-1604-A3A" | INSP RECOMM | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:00 |  |  | 10-Apr | 10-Apr | 23-Apr | 23-Apr
CDUVDU19220 | Completed | Hydrotest Witness | 23/04/2023 12:13:49 | 23/04/2023 12:13:49 | 10/04/2023 17:00:00 | 10/04/2023 23:00:00 | "2""-WDM-01-1604-A3A" | INSP RECOMM | 100 | INSPECTION | HYDRO TEST | HYDRO TEST | 6 | 6:00 | 0:00 |  |  | 10-Apr | 10-Apr | 23-Apr | 23-Apr
CDUVDU19770 | Completed | Draining | 23/04/2023 12:13:49 | 23/04/2023 12:13:49 | 10/04/2023 23:00:00 | 11/04/2023 09:00:00 | "2""-WDM-01-1604-A3A" | INSP RECOMM | 100 | MECHANICAL |  |  | 10 | 10:00 | 0:00 |  |  | 10-Apr | 11-Apr | 23-Apr | 23-Apr
CDUVDU20840 | Completed | De-blinding and hand-over | 23/04/2023 12:13:49 | 23/04/2023 12:13:49 | 11/04/2023 09:00:00 | 12/04/2023 03:00:00 | "2""-WDM-01-1604-A3A" | INSP RECOMM | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 18 | 18:00 | 0:00 |  |  | 11-Apr | 12-Apr | 23-Apr | 23-Apr
CDUVDU18860 | Completed | Blinding | 23/04/2023 12:32:58 | 23/04/2023 12:32:58 | 10/04/2023 13:00:00 | 11/04/2023 07:00:00 | "3"" FG VV-005 TO VV-021" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 18 | 18:00 | 0:00 |  |  | 10-Apr | 11-Apr | 23-Apr | 23-Apr
CDUVDU20700 | Completed | Cutting, grinding, fit-up, welding and NDT | 23/04/2023 12:32:58 | 23/04/2023 12:32:58 | 11/04/2023 07:00:00 | 12/04/2023 04:00:00 | "3"" FG VV-005 TO VV-021" | INSP RECOMM | 100 | MECHANICAL |  |  | 21 | 21:00 | 0:00 |  |  | 11-Apr | 12-Apr | 23-Apr | 23-Apr
CDUVDU21590 | Not Started | Inspection activities |  |  | 11/04/2023 15:00:00 | 12/04/2023 11:00:00 | "3"" FG VV-005 TO VV-021" | INSP RECOMM | 0 | INSPECTION |  |  | 20 | 20:00 | 0:00 |  |  | 11-Apr | 12-Apr | - Date check | - Date check
CDUVDU23530 | Not Started | HT preparation |  |  | 12/04/2023 11:00:00 | 12/04/2023 23:00:00 | "3"" FG VV-005 TO VV-021" | INSP RECOMM | 0 | MECHANICAL |  |  | 12 | 12:00 | 0:00 |  |  | 12-Apr | 12-Apr | - Date check | - Date check
CDUVDU24470 | Not Started | Hydrotest Witness |  |  | 12/04/2023 23:00:00 | 13/04/2023 05:00:00 | "3"" FG VV-005 TO VV-021" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 6 | 6:00 | 0:00 |  |  | 12-Apr | 13-Apr | - Date check | - Date check
CDUVDU24880 | Not Started | Draining |  |  | 13/04/2023 05:00:00 | 13/04/2023 15:00:00 | "3"" FG VV-005 TO VV-021" | INSP RECOMM | 0 | MECHANICAL |  |  | 10 | 10:00 | 0:00 |  |  | 13-Apr | 13-Apr | - Date check | - Date check
CDUVDU25500 | Not Started | De-blinding and hand-over |  |  | 13/04/2023 15:00:00 | 14/04/2023 09:00:00 | "3"" FG VV-005 TO VV-021" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 18 | 18:00 | 0:00 |  |  | 13-Apr | 14-Apr | - Date check | - Date check
CDUVDU11440 | Completed | Cutting and remove existing pipe | 02/04/2023 18:25:15 | 11/04/2023 12:42:36 | 06/04/2023 14:00:00 | 09/04/2023 02:00:00 | "REPLACE 28"" LINE" | INSP RECOMM | 100 | MECHANICAL |  |  | 60 | 60:00 | 210:17 | 150:17 |  | 06-Apr | 09-Apr | 02-Apr | 11-Apr
CDUVDU15630 | Completed | Site erection and fitup | 04/04/2023 10:16:09 | 15/04/2023 18:55:42 | 09/04/2023 02:00:00 | 17/04/2023 06:00:00 | "REPLACE 28"" LINE" | INSP RECOMM | 100 | MECHANICAL |  |  | 196 | 196:00 | 272:40 | 76:40 |  | 09-Apr | 17-Apr | 04-Apr | 15-Apr
CDUVDU17720 | Completed | Wedling and Inspection | 04/04/2023 18:59:10 | 20/04/2023 16:56:09 | 10/04/2023 02:00:00 | 19/04/2023 06:00:00 | "REPLACE 28"" LINE" | INSP RECOMM | 100 | INSPECTION |  |  | 220 | 220:00 | 381:57 | 161:57 |  | 10-Apr | 19-Apr | 04-Apr | 20-Apr
CDUVDU29690 | Completed | Hydro test | 22/04/2023 08:52:20 | 22/04/2023 08:53:20 | 19/04/2023 06:00:00 | 20/04/2023 18:00:00 | "REPLACE 28"" LINE" | INSP RECOMM | 100 | INSPECTION |  |  | 36 | 36:00 | 0:01 |  | 35:59 | 19-Apr | 20-Apr | 22-Apr | 22-Apr
CDUVDU30060 | Not Started | Dismantle scaffold |  |  | 20/04/2023 18:00:00 | 22/04/2023 18:00:00 | "REPLACE 28"" LINE" | INSP RECOMM | 0 | MECHANICAL |  |  | 48 | 48:00 | 0:00 |  |  | 20-Apr | 22-Apr | - Date check | - Date check
CDUVDU30180 | Completed | Carry out DeBlinding | 23/04/2023 11:28:02 | 23/04/2023 11:28:02 | 22/04/2023 18:00:00 | 23/04/2023 14:00:00 | "REPLACE 28"" LINE" | INSP RECOMM | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 20 | 20:00 | 0:00 |  |  | 22-Apr | 23-Apr | 23-Apr | 23-Apr
CDUVDU8780 | Completed | Carry out blinding | 04/04/2023 09:26:53 | 07/04/2023 10:00:26 | 04/04/2023 14:00:00 | 05/04/2023 14:00:00 | "REPLACE 28"" LINE" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 24 | 24:00 | 72:34 | 48:34 |  | 04-Apr | 05-Apr | 04-Apr | 07-Apr
CDUVDU8790 | Completed | Site mobilization of fabricated spools | 03/04/2023 17:52:00 | 15/04/2023 09:46:58 | 04/04/2023 14:00:00 | 06/04/2023 14:00:00 | "REPLACE 28"" LINE" | INSP RECOMM | 100 | MECHANICAL |  |  | 48 | 48:00 | 279:55 | 231:55 |  | 04-Apr | 06-Apr | 03-Apr | 15-Apr
CDUVDU8980 | Completed | Carry out Scaffolding wherever req | 30/03/2023 15:44:10 | 30/03/2023 15:44:23 | 04/04/2023 14:00:00 | 05/04/2023 14:00:00 | "REPLACE 28"" LINE" | INSP RECOMM | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 04-Apr | 05-Apr | 30-Mar | 30-Mar
CDUVDU10750 | Not Started | 4"-WS-01-2901-A3A-N Service water header above old booster pump |  |  | 04/04/2023 14:00:00 | 04/04/2023 14:00:00 | ONLINE SEALING | ONLINE SEALING | 0 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 0 | 0:00 | 0:00 |  |  | 04-Apr | 04-Apr | - Date check | - Date check
CDUVDU13070 | Not Started | 1.5"-WS-01-2903-A3A-N Service water line above FF-01 pass-2 I/V |  |  | 04/04/2023 14:00:00 | 04/04/2023 14:00:00 | ONLINE SEALING | ONLINE SEALING | 0 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 0 | 0:00 | 0:00 |  |  | 04-Apr | 04-Apr | - Date check | - Date check
CDUVDU17730 | Completed | 3" -A2A Tracing steam header above 01-PA-03A/B( CCR side) | 25/04/2023 19:49:29 | 25/04/2023 19:49:29 | 04/04/2023 14:00:00 | 04/04/2023 14:00:00 | ONLINE SEALING | ONLINE SEALING | 100 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 0 | 0:00 | 0:00 |  |  | 04-Apr | 04-Apr | 25-Apr | 25-Apr
CDUVDU20170 | Completed | 0.75"-B2A MP steam drip leg i/v near 01-PA-05A/B | 25/04/2023 19:49:29 | 25/04/2023 19:49:29 | 04/04/2023 14:00:00 | 04/04/2023 14:00:00 | ONLINE SEALING | ONLINE SEALING | 100 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 0 | 0:00 | 0:00 |  |  | 04-Apr | 04-Apr | 25-Apr | 25-Apr
CDUVDU23670 | Completed | 26"-P-01-1409-B1F-IH Fillet joint(1.5") of 01-PT-1411 ( transfer line) | 25/04/2023 19:49:29 | 25/04/2023 19:49:29 | 04/04/2023 14:00:00 | 04/04/2023 14:00:00 | ONLINE SEALING | ONLINE SEALING | 100 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 0 | 0:00 | 0:00 |  |  | 04-Apr | 04-Apr | 25-Apr | 25-Apr
CDUVDU25380 | Completed | 0.75"-B1N LV-2107 (slop distillate to VR) u/s LPD i/v welding leakage | 25/04/2023 19:49:29 | 25/04/2023 19:49:29 | 04/04/2023 14:00:00 | 04/04/2023 14:00:00 | ONLINE SEALING | ONLINE SEALING | 100 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 0 | 0:00 | 0:00 |  |  | 04-Apr | 04-Apr | 25-Apr | 25-Apr
CDUVDU26020 | Completed | 0.5"-D1A Welding crack at fillet joint of 01- FE-1403 low side root valve ( pass flow) | 25/04/2023 19:49:29 | 25/04/2023 19:49:29 | 04/04/2023 14:00:00 | 04/04/2023 14:00:00 | ONLINE SEALING | ONLINE SEALING | 100 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 0 | 0:00 | 0:00 |  |  | 04-Apr | 04-Apr | 25-Apr | 25-Apr
CDUVDU26130 | Not Started | 0.75"-C-01-2566-A1A-N Neutralising amine of 01-CC-006 at column bottom |  |  | 04/04/2023 14:00:00 | 04/04/2023 14:00:00 | ONLINE SEALING | ONLINE SEALING | 0 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 0 | 0:00 | 0:00 |  |  | 04-Apr | 04-Apr | - Date check | - Date check
CDUVDU26260 | Not Started | 0.75"-C-01-2564-A1A-N Neutralising amine of 01-CC-001 at column bottom |  |  | 04/04/2023 14:00:00 | 04/04/2023 14:00:00 | ONLINE SEALING | ONLINE SEALING | 0 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 0 | 0:00 | 0:00 |  |  | 04-Apr | 04-Apr | - Date check | - Date check
CDUVDU8990 | Not Started | 2"-WS-01-2601-A3A-N Service water line to desalter |  |  | 04/04/2023 14:00:00 | 04/04/2023 14:00:00 | ONLINE SEALING | ONLINE SEALING | 0 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 0 | 0:00 | 0:00 |  |  | 04-Apr | 04-Apr | - Date check | - Date check
CDUVDU14140 | Completed | Blinding | 23/04/2023 12:14:05 | 23/04/2023 12:14:05 | 08/04/2023 07:00:00 | 09/04/2023 01:00:00 | "2""-WDM-01-1618-A3A" | INSP RECOMM | 100 | MECHANICAL | BLINDING | BLINDING | 18 | 18:00 | 0:00 |  |  | 08-Apr | 09-Apr | 23-Apr | 23-Apr
CDUVDU15480 | Completed | Cutting, grinding, fit-up, welding and NDT | 23/04/2023 12:14:05 | 23/04/2023 12:14:05 | 09/04/2023 01:00:00 | 09/04/2023 22:00:00 | "2""-WDM-01-1618-A3A" | INSP RECOMM | 100 | MECHANICAL |  |  | 21 | 21:00 | 0:00 |  |  | 09-Apr | 09-Apr | 23-Apr | 23-Apr
CDUVDU16180 | Completed | Inspection activities | 23/04/2023 12:14:05 | 23/04/2023 12:14:05 | 09/04/2023 09:00:00 | 10/04/2023 05:00:00 | "2""-WDM-01-1618-A3A" | INSP RECOMM | 100 | INSPECTION |  |  | 20 | 20:00 | 0:00 |  |  | 09-Apr | 10-Apr | 23-Apr | 23-Apr
CDUVDU18140 | Completed | HT preparation | 23/04/2023 12:14:05 | 23/04/2023 12:14:05 | 10/04/2023 05:00:00 | 10/04/2023 17:00:00 | "2""-WDM-01-1618-A3A" | INSP RECOMM | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:00 |  |  | 10-Apr | 10-Apr | 23-Apr | 23-Apr
CDUVDU19230 | Completed | Hydrotest Witness | 23/04/2023 12:14:05 | 23/04/2023 12:14:05 | 10/04/2023 17:00:00 | 10/04/2023 23:00:00 | "2""-WDM-01-1618-A3A" | INSP RECOMM | 100 | INSPECTION | HYDRO TEST | HYDRO TEST | 6 | 6:00 | 0:00 |  |  | 10-Apr | 10-Apr | 23-Apr | 23-Apr
CDUVDU19780 | Completed | Draining | 23/04/2023 12:14:05 | 23/04/2023 12:14:05 | 10/04/2023 23:00:00 | 11/04/2023 09:00:00 | "2""-WDM-01-1618-A3A" | INSP RECOMM | 100 | MECHANICAL |  |  | 10 | 10:00 | 0:00 |  |  | 10-Apr | 11-Apr | 23-Apr | 23-Apr
CDUVDU20850 | Completed | De-blinding and hand-over | 23/04/2023 12:14:05 | 23/04/2023 12:14:05 | 11/04/2023 09:00:00 | 12/04/2023 03:00:00 | "2""-WDM-01-1618-A3A" | INSP RECOMM | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 18 | 18:00 | 0:00 |  |  | 11-Apr | 12-Apr | 23-Apr | 23-Apr
CDUVDU10590 | Not Started | Cutting, grinding, fit-up, welding and NDT (24 ID) |  |  | 05/04/2023 21:00:00 | 07/04/2023 15:00:00 | "3""-P-01-3704-A1A" | INSP RECOMM | 0 | MECHANICAL |  |  | 42 | 42:00 | 0:00 |  |  | 05-Apr | 07-Apr | - Date check | - Date check
CDUVDU13200 | Not Started | Inspection activities |  |  | 07/04/2023 15:00:00 | 09/04/2023 07:00:00 | "3""-P-01-3704-A1A" | INSP RECOMM | 0 | INSPECTION |  |  | 40 | 40:00 | 0:00 |  |  | 07-Apr | 09-Apr | - Date check | - Date check
CDUVDU15980 | Not Started | HT preparation |  |  | 09/04/2023 07:00:00 | 10/04/2023 03:00:00 | "3""-P-01-3704-A1A" | INSP RECOMM | 0 | MECHANICAL |  |  | 20 | 20:00 | 0:00 |  |  | 09-Apr | 10-Apr | - Date check | - Date check
CDUVDU17850 | Not Started | Hydrotest Witness |  |  | 10/04/2023 03:00:00 | 10/04/2023 15:00:00 | "3""-P-01-3704-A1A" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 12 | 12:00 | 0:00 |  |  | 10-Apr | 10-Apr | - Date check | - Date check
CDUVDU19070 | Not Started | Draining |  |  | 10/04/2023 15:00:00 | 11/04/2023 11:00:00 | "3""-P-01-3704-A1A" | INSP RECOMM | 0 | MECHANICAL |  |  | 20 | 20:00 | 0:00 |  |  | 10-Apr | 11-Apr | - Date check | - Date check
CDUVDU21010 | Not Started | De-blinding and hand-over |  |  | 11/04/2023 11:00:00 | 12/04/2023 07:00:00 | "3""-P-01-3704-A1A" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 20 | 20:00 | 0:00 |  |  | 11-Apr | 12-Apr | - Date check | - Date check
CDUVDU9710 | Not Started | Blinding |  |  | 05/04/2023 05:00:00 | 05/04/2023 21:00:00 | "3""-P-01-3704-A1A" | INSP RECOMM | 0 | MECHANICAL | BLINDING | BLINDING | 16 | 16:00 | 0:00 |  |  | 05-Apr | 05-Apr | - Date check | - Date check
CDUVDU1070 | Completed | Blinding As Per List | 31/03/2023 16:00:20 | 31/03/2023 16:00:26 | 30/03/2023 08:00:00 | 30/03/2023 16:00:00 | 01-EA-002 | FIN FAN COOLER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 30-Mar | 30-Mar | 31-Mar | 31-Mar
CDUVDU1150 | Completed | Plug Opening | 31/03/2023 18:17:06 | 31/03/2023 18:17:11 | 30/03/2023 16:00:00 | 31/03/2023 16:00:00 | 01-EA-002 | FIN FAN COOLER | 100 | MECHANICAL | OPENING | OPENING | 24 | 24:00 | 0:00 |  | 24:00 | 30-Mar | 31-Mar | 31-Mar | 31-Mar
CDUVDU1260 | Completed | Pre-Cleaning Inspection | 01/04/2023 11:46:06 | 01/04/2023 11:47:23 | 31/03/2023 16:00:00 | 31/03/2023 19:00:00 | 01-EA-002 | FIN FAN COOLER | 100 | INSPECTION |  |  | 3 | 3:00 | 0:01 |  | 2:59 | 31-Mar | 31-Mar | 01-Apr | 01-Apr
CDUVDU1340 | Completed | Hydrojetting | 01/04/2023 16:35:32 | 02/04/2023 06:39:41 | 31/03/2023 19:00:00 | 01/04/2023 23:00:00 | 01-EA-002 | FIN FAN COOLER | 100 | MECHANICAL | HYDROJETTING |  | 28 | 28:00 | 14:04 |  | 13:56 | 31-Mar | 01-Apr | 01-Apr | 02-Apr
CDUVDU1370 | Completed | Post Cleaning Inspection | 05/04/2023 22:17:58 | 05/04/2023 22:17:58 | 01/04/2023 23:00:00 | 02/04/2023 07:00:00 | 01-EA-002 | FIN FAN COOLER | 100 | INSPECTION | INSPECTION | INSPECTION | 8 | 8:00 | 0:00 |  |  | 01-Apr | 02-Apr | 05-Apr | 05-Apr
CDUVDU1400 | Completed | Plug Box-up | 06/04/2023 07:53:04 | 06/04/2023 07:54:00 | 02/04/2023 07:00:00 | 03/04/2023 19:00:00 | 01-EA-002 | FIN FAN COOLER | 100 | MECHANICAL | BOX UP | BOX UP | 36 | 36:00 | 0:01 |  | 35:59 | 02-Apr | 03-Apr | 06-Apr | 06-Apr
CDUVDU1770 | Completed | Hydrotest | 08/04/2023 07:38:52 | 08/04/2023 07:40:01 | 03/04/2023 19:00:00 | 04/04/2023 07:00:00 | 01-EA-002 | FIN FAN COOLER | 100 | INSPECTION | FINAL TEST |  | 12 | 12:00 | 0:01 |  | 11:59 | 03-Apr | 04-Apr | 08-Apr | 08-Apr
CDUVDU1790 | Completed | Deblinding | 17/04/2023 02:01:32 | 17/04/2023 02:01:37 | 04/04/2023 07:00:00 | 04/04/2023 15:00:00 | 01-EA-002 | FIN FAN COOLER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 04-Apr | 04-Apr | 17-Apr | 17-Apr
CDUVDU19500 | Completed | Install new tube bundle | 03/04/2023 14:50:19 | 03/04/2023 15:36:37 | 10/04/2023 20:30:00 | 11/04/2023 08:30:00 | 01-EA-001B | FIN FAN COOLER | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:46 |  | 11:14 | 10-Apr | 11-Apr | 03-Apr | 03-Apr
CDUVDU1980 | Completed | Blinding | 04/04/2023 12:02:31 | 04/04/2023 12:02:31 | 31/03/2023 14:30:00 | 31/03/2023 22:30:00 | 01-EA-001B | FIN FAN COOLER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  |  | 31-Mar | 31-Mar | 04-Apr | 04-Apr
CDUVDU24200 | Completed | IRIS inspection | 09/04/2023 18:45:08 | 09/04/2023 18:45:12 | 12/04/2023 20:30:00 | 13/04/2023 16:30:00 | 01-EA-001B | FIN FAN COOLER | 100 | INSPECTION |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 12-Apr | 13-Apr | 09-Apr | 09-Apr
CDUVDU2490 | Completed | Opening of covers | 04/04/2023 12:02:31 | 04/04/2023 12:02:31 | 31/03/2023 22:30:00 | 01/04/2023 12:30:00 | 01-EA-001B | FIN FAN COOLER | 100 | MECHANICAL | OPENING | OPENING | 14 | 14:00 | 0:00 |  |  | 31-Mar | 01-Apr | 04-Apr | 04-Apr
CDUVDU25550 | Completed | Post cleaning inspection | 09/04/2023 18:45:25 | 09/04/2023 18:45:31 | 13/04/2023 16:30:00 | 14/04/2023 00:30:00 | 01-EA-001B | FIN FAN COOLER | 100 | INSPECTION | INSPECTION | INSPECTION | 8 | 8:00 | 0:00 |  | 8:00 | 13-Apr | 14-Apr | 09-Apr | 09-Apr
CDUVDU25960 | Completed | Box up of covers | 09/04/2023 18:45:40 | 09/04/2023 18:45:45 | 14/04/2023 00:30:00 | 14/04/2023 20:30:00 | 01-EA-001B | FIN FAN COOLER | 100 | MECHANICAL | BOX UP | BOX UP | 20 | 20:00 | 0:00 |  | 20:00 | 14-Apr | 14-Apr | 09-Apr | 09-Apr
CDUVDU26880 | Completed | Hydrotest | 09/04/2023 18:46:05 | 10/04/2023 12:32:32 | 14/04/2023 20:30:00 | 15/04/2023 08:30:00 | 01-EA-001B | FIN FAN COOLER | 100 | INSPECTION | FINAL TEST |  | 12 | 12:00 | 17:46 | 5:46 |  | 14-Apr | 15-Apr | 09-Apr | 10-Apr
CDUVDU27330 | Completed | Deblinding | 17/04/2023 01:56:04 | 17/04/2023 01:56:41 | 15/04/2023 08:30:00 | 15/04/2023 20:30:00 | 01-EA-001B | FIN FAN COOLER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:01 |  | 11:59 | 15-Apr | 15-Apr | 17-Apr | 17-Apr
CDUVDU6220 | Completed | Removal of tubes bundle for replacement | 02/04/2023 19:02:45 | 02/04/2023 19:02:50 | 02/04/2023 17:30:00 | 03/04/2023 14:30:00 | 01-EA-001B | FIN FAN COOLER | 100 | MECHANICAL |  |  | 21 | 21:00 | 0:00 |  | 21:00 | 02-Apr | 03-Apr | 02-Apr | 02-Apr
CDUVDU18430 | Completed | Install new tube bundle | 03/04/2023 17:09:13 | 03/04/2023 17:09:19 | 10/04/2023 08:30:00 | 10/04/2023 20:30:00 | 01-EA-001C | FIN FAN COOLER | 100 | MECHANICAL |  |  | 12 | 12:00 | 0:00 |  | 12:00 | 10-Apr | 10-Apr | 03-Apr | 03-Apr
CDUVDU2500 | Completed | Blinding | 04/04/2023 12:02:52 | 04/04/2023 12:02:52 | 31/03/2023 22:30:00 | 01/04/2023 06:30:00 | 01-EA-001C | FIN FAN COOLER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  |  | 31-Mar | 01-Apr | 04-Apr | 04-Apr
CDUVDU25560 | Completed | IRIS inspection | 09/04/2023 18:49:01 | 09/04/2023 18:49:05 | 13/04/2023 16:30:00 | 14/04/2023 12:30:00 | 01-EA-001C | FIN FAN COOLER | 100 | INSPECTION |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 13-Apr | 14-Apr | 09-Apr | 09-Apr
CDUVDU26790 | Completed | Post cleaning inspection | 09/04/2023 18:49:29 | 09/04/2023 18:49:34 | 14/04/2023 17:30:00 | 15/04/2023 01:30:00 | 01-EA-001C | FIN FAN COOLER | 100 | INSPECTION | INSPECTION | INSPECTION | 8 | 8:00 | 0:00 |  | 8:00 | 14-Apr | 15-Apr | 09-Apr | 09-Apr
CDUVDU27050 | Completed | Box up of covers | 09/04/2023 18:50:03 | 09/04/2023 18:50:16 | 15/04/2023 01:30:00 | 15/04/2023 21:30:00 | 01-EA-001C | FIN FAN COOLER | 100 | MECHANICAL | BOX UP | BOX UP | 20 | 20:00 | 0:00 |  | 20:00 | 15-Apr | 15-Apr | 09-Apr | 09-Apr
CDUVDU27750 | Completed | Hydrotesting | 12/04/2023 09:43:22 | 12/04/2023 09:43:26 | 15/04/2023 21:30:00 | 16/04/2023 09:30:00 | 01-EA-001C | FIN FAN COOLER | 100 | INSPECTION | FINAL TEST |  | 12 | 12:00 | 0:00 |  | 12:00 | 15-Apr | 16-Apr | 12-Apr | 12-Apr
CDUVDU28160 | Completed | De blinding | 17/04/2023 01:59:56 | 17/04/2023 02:00:01 | 16/04/2023 09:30:00 | 16/04/2023 21:30:00 | 01-EA-001C | FIN FAN COOLER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 16-Apr | 16-Apr | 17-Apr | 17-Apr
CDUVDU2960 | Completed | Opening of covers | 04/04/2023 12:02:52 | 04/04/2023 12:02:52 | 01/04/2023 12:30:00 | 02/04/2023 02:30:00 | 01-EA-001C | FIN FAN COOLER | 100 | MECHANICAL | OPENING | OPENING | 14 | 14:00 | 0:00 |  |  | 01-Apr | 02-Apr | 04-Apr | 04-Apr
CDUVDU8030 | Completed | Removal of tubes bundle for replacement | 02/04/2023 19:03:07 | 02/04/2023 19:03:14 | 03/04/2023 20:30:00 | 04/04/2023 17:30:00 | 01-EA-001C | FIN FAN COOLER | 100 | MECHANICAL |  |  | 21 | 21:00 | 0:00 |  | 21:00 | 03-Apr | 04-Apr | 02-Apr | 02-Apr
CDUVDU16090 | Completed | Install new tube bundle | 03/04/2023 17:26:46 | 04/04/2023 12:04:45 | 09/04/2023 08:30:00 | 10/04/2023 08:30:00 | 01-EA-001D | FIN FAN COOLER | 100 | MECHANICAL |  |  | 24 | 24:00 | 18:38 |  | 5:22 | 09-Apr | 10-Apr | 03-Apr | 04-Apr
CDUVDU26540 | Completed | IRIS inspection | 09/04/2023 18:52:01 | 09/04/2023 18:52:05 | 14/04/2023 12:30:00 | 15/04/2023 08:30:00 | 01-EA-001D | FIN FAN COOLER | 100 | INSPECTION |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 14-Apr | 15-Apr | 09-Apr | 09-Apr
CDUVDU2670 | Completed | Blinding | 04/04/2023 12:03:18 | 04/04/2023 12:03:18 | 01/04/2023 06:30:00 | 01/04/2023 14:30:00 | 01-EA-001D | FIN FAN COOLER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  |  | 01-Apr | 01-Apr | 04-Apr | 04-Apr
CDUVDU27340 | Completed | Post cleaning inspection | 09/04/2023 18:52:25 | 09/04/2023 18:52:29 | 15/04/2023 08:30:00 | 15/04/2023 16:30:00 | 01-EA-001D | FIN FAN COOLER | 100 | INSPECTION | INSPECTION | INSPECTION | 8 | 8:00 | 0:00 |  | 8:00 | 15-Apr | 15-Apr | 09-Apr | 09-Apr
CDUVDU27760 | Completed | Box up of covers | 09/04/2023 18:52:38 | 09/04/2023 18:52:42 | 15/04/2023 21:30:00 | 16/04/2023 22:30:00 | 01-EA-001D | FIN FAN COOLER | 100 | MECHANICAL | BOX UP | BOX UP | 25 | 25:00 | 0:00 |  | 25:00 | 15-Apr | 16-Apr | 09-Apr | 09-Apr
CDUVDU28560 | Completed | Hydrotest | 11/04/2023 20:11:36 | 11/04/2023 20:11:41 | 16/04/2023 22:30:00 | 17/04/2023 13:30:00 | 01-EA-001D | FIN FAN COOLER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 0:00 |  | 15:00 | 16-Apr | 17-Apr | 11-Apr | 11-Apr
CDUVDU29090 | Completed | De blinding | 17/04/2023 02:00:21 | 17/04/2023 02:00:24 | 17/04/2023 19:30:00 | 18/04/2023 07:30:00 | 01-EA-001D | FIN FAN COOLER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 17-Apr | 18-Apr | 17-Apr | 17-Apr
CDUVDU4490 | Completed | Opening of covers | 04/04/2023 12:03:18 | 04/04/2023 12:03:18 | 02/04/2023 02:30:00 | 02/04/2023 16:30:00 | 01-EA-001D | FIN FAN COOLER | 100 | MECHANICAL | OPENING | OPENING | 14 | 14:00 | 0:00 |  |  | 02-Apr | 02-Apr | 04-Apr | 04-Apr
CDUVDU9200 | Completed | Removal of tubes bundle for replacement | 02/04/2023 19:03:51 | 02/04/2023 19:03:56 | 04/04/2023 17:30:00 | 05/04/2023 14:30:00 | 01-EA-001D | FIN FAN COOLER | 100 | MECHANICAL |  |  | 21 | 21:00 | 0:00 |  | 21:00 | 04-Apr | 05-Apr | 02-Apr | 02-Apr
CDUVDU10240 | Completed | Removal of tubes bundle for replacement | 02/04/2023 19:04:11 | 02/04/2023 19:04:17 | 05/04/2023 14:30:00 | 06/04/2023 11:30:00 | 01-EA-001E | FIN FAN COOLER | 100 | MECHANICAL |  |  | 21 | 21:00 | 0:00 |  | 21:00 | 05-Apr | 06-Apr | 02-Apr | 02-Apr
CDUVDU14220 | Completed | Install new tube bundle | 04/04/2023 09:32:32 | 04/04/2023 09:32:42 | 08/04/2023 08:30:00 | 09/04/2023 08:30:00 | 01-EA-001E | FIN FAN COOLER | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 08-Apr | 09-Apr | 04-Apr | 04-Apr
CDUVDU27350 | Completed | IRIS inspection | 09/04/2023 18:53:03 | 09/04/2023 18:53:07 | 15/04/2023 08:30:00 | 16/04/2023 04:30:00 | 01-EA-001E | FIN FAN COOLER | 100 | INSPECTION |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 15-Apr | 16-Apr | 09-Apr | 09-Apr
CDUVDU27990 | Completed | Post cleaning inspection | 09/04/2023 18:53:28 | 09/04/2023 18:53:34 | 16/04/2023 04:30:00 | 16/04/2023 12:30:00 | 01-EA-001E | FIN FAN COOLER | 100 | INSPECTION | INSPECTION | INSPECTION | 8 | 8:00 | 0:00 |  | 8:00 | 16-Apr | 16-Apr | 09-Apr | 09-Apr
CDUVDU28570 | Completed | Box up of covers | 09/04/2023 18:53:43 | 09/04/2023 18:53:48 | 16/04/2023 22:30:00 | 17/04/2023 23:30:00 | 01-EA-001E | FIN FAN COOLER | 100 | MECHANICAL | BOX UP | BOX UP | 25 | 25:00 | 0:00 |  | 25:00 | 16-Apr | 17-Apr | 09-Apr | 09-Apr
CDUVDU29280 | Completed | Hydrotest | 10/04/2023 12:32:50 | 10/04/2023 12:33:01 | 18/04/2023 04:30:00 | 18/04/2023 19:30:00 | 01-EA-001E | FIN FAN COOLER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 0:00 |  | 15:00 | 18-Apr | 18-Apr | 10-Apr | 10-Apr
CDUVDU29550 | Completed | De blinding | 17/04/2023 02:00:42 | 17/04/2023 02:00:45 | 18/04/2023 19:30:00 | 19/04/2023 07:30:00 | 01-EA-001E | FIN FAN COOLER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 18-Apr | 19-Apr | 17-Apr | 17-Apr
CDUVDU3020 | Completed | Blinding | 04/04/2023 12:03:40 | 04/04/2023 12:03:40 | 01/04/2023 14:30:00 | 01/04/2023 22:30:00 | 01-EA-001E | FIN FAN COOLER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  |  | 01-Apr | 01-Apr | 04-Apr | 04-Apr
CDUVDU6360 | Completed | Opening of covers | 04/04/2023 12:03:40 | 04/04/2023 12:03:40 | 02/04/2023 21:30:00 | 03/04/2023 11:30:00 | 01-EA-001E | FIN FAN COOLER | 100 | MECHANICAL | OPENING | OPENING | 14 | 14:00 | 0:00 |  |  | 02-Apr | 03-Apr | 04-Apr | 04-Apr
CDUVDU11340 | Completed | Removal of tubes bundle for replacement | 02/04/2023 19:04:32 | 02/04/2023 19:04:39 | 06/04/2023 11:30:00 | 07/04/2023 08:30:00 | 01-EA-001F | FIN FAN COOLER | 100 | MECHANICAL |  |  | 21 | 21:00 | 0:00 |  | 21:00 | 06-Apr | 07-Apr | 02-Apr | 02-Apr
CDUVDU12800 | Completed | Install new tube bundle | 04/04/2023 09:33:16 | 04/04/2023 09:33:26 | 07/04/2023 08:30:00 | 08/04/2023 08:30:00 | 01-EA-001F | FIN FAN COOLER | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 07-Apr | 08-Apr | 04-Apr | 04-Apr
CDUVDU28000 | Completed | IRIS inspection | 09/04/2023 18:54:10 | 09/04/2023 18:54:15 | 16/04/2023 04:30:00 | 17/04/2023 00:30:00 | 01-EA-001F | FIN FAN COOLER | 100 | INSPECTION |  |  | 20 | 20:00 | 0:00 |  | 20:00 | 16-Apr | 17-Apr | 09-Apr | 09-Apr
CDUVDU28620 | Completed | Post cleaning inspection | 09/04/2023 18:54:29 | 09/04/2023 18:54:34 | 17/04/2023 00:30:00 | 17/04/2023 08:30:00 | 01-EA-001F | FIN FAN COOLER | 100 | INSPECTION | INSPECTION | INSPECTION | 8 | 8:00 | 0:00 |  | 8:00 | 17-Apr | 17-Apr | 09-Apr | 09-Apr
CDUVDU29160 | Completed | Box up of covers | 09/04/2023 18:54:41 | 09/04/2023 18:54:47 | 17/04/2023 23:30:00 | 19/04/2023 00:30:00 | 01-EA-001F | FIN FAN COOLER | 100 | MECHANICAL | BOX UP | BOX UP | 25 | 25:00 | 0:00 |  | 25:00 | 17-Apr | 19-Apr | 09-Apr | 09-Apr
CDUVDU29620 | Completed | Hydrotest | 10/04/2023 12:33:22 | 10/04/2023 12:33:30 | 19/04/2023 00:30:00 | 19/04/2023 15:30:00 | 01-EA-001F | FIN FAN COOLER | 100 | INSPECTION | FINAL TEST |  | 15 | 15:00 | 0:00 |  | 15:00 | 19-Apr | 19-Apr | 10-Apr | 10-Apr
CDUVDU29820 | Completed | De blinding | 17/04/2023 02:01:10 | 17/04/2023 02:01:14 | 19/04/2023 15:30:00 | 20/04/2023 03:30:00 | 01-EA-001F | FIN FAN COOLER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 12:00 | 0:00 |  | 12:00 | 19-Apr | 20-Apr | 17-Apr | 17-Apr
CDUVDU4070 | Completed | Blinding | 04/04/2023 12:04:05 | 04/04/2023 12:04:05 | 01/04/2023 22:30:00 | 02/04/2023 06:30:00 | 01-EA-001F | FIN FAN COOLER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  |  | 01-Apr | 02-Apr | 04-Apr | 04-Apr
CDUVDU7440 | Completed | Opening of covers | 04/04/2023 12:04:05 | 04/04/2023 12:04:05 | 03/04/2023 11:30:00 | 04/04/2023 01:30:00 | 01-EA-001F | FIN FAN COOLER | 100 | MECHANICAL | OPENING | OPENING | 14 | 14:00 | 0:00 |  |  | 03-Apr | 04-Apr | 04-Apr | 04-Apr
CDUVDU1080 | Completed | Blinding As Per List | 31/03/2023 10:31:42 | 31/03/2023 17:30:48 | 30/03/2023 08:00:00 | 30/03/2023 16:00:00 | 01-EA-004 | FIN FAN COOLER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 6:59 |  | 1:01 | 30-Mar | 30-Mar | 31-Mar | 31-Mar
CDUVDU1160 | Completed | Plug Opening | 31/03/2023 18:17:28 | 31/03/2023 18:17:37 | 30/03/2023 16:00:00 | 31/03/2023 16:00:00 | 01-EA-004 | FIN FAN COOLER | 100 | MECHANICAL | OPENING | OPENING | 24 | 24:00 | 0:00 |  | 24:00 | 30-Mar | 31-Mar | 31-Mar | 31-Mar
CDUVDU1270 | Completed | Pre-Cleaning Inspection | 01/04/2023 11:47:53 | 01/04/2023 11:48:03 | 31/03/2023 16:00:00 | 31/03/2023 19:00:00 | 01-EA-004 | FIN FAN COOLER | 100 | INSPECTION |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 31-Mar | 31-Mar | 01-Apr | 01-Apr
CDUVDU1380 | Completed | Hydrojetting | 01/04/2023 11:49:52 | 05/04/2023 11:19:18 | 01/04/2023 23:00:00 | 03/04/2023 03:00:00 | 01-EA-004 | FIN FAN COOLER | 100 | MECHANICAL | HYDROJETTING |  | 28 | 28:00 | 95:29 | 67:29 |  | 01-Apr | 03-Apr | 01-Apr | 05-Apr
CDUVDU1410 | Completed | Post Cleaning Inspection | 05/04/2023 22:18:22 | 05/04/2023 22:18:22 | 03/04/2023 03:00:00 | 03/04/2023 11:00:00 | 01-EA-004 | FIN FAN COOLER | 100 | INSPECTION | INSPECTION | INSPECTION | 8 | 8:00 | 0:00 |  |  | 03-Apr | 03-Apr | 05-Apr | 05-Apr
CDUVDU1560 | Completed | Plug Box-up | 06/04/2023 07:54:18 | 08/04/2023 07:49:07 | 03/04/2023 11:00:00 | 04/04/2023 23:00:00 | 01-EA-004 | FIN FAN COOLER | 100 | MECHANICAL | BOX UP | BOX UP | 36 | 36:00 | 47:55 | 11:55 |  | 03-Apr | 04-Apr | 06-Apr | 08-Apr
CDUVDU2440 | Completed | Hydrotest | 08/04/2023 17:38:40 | 10/04/2023 04:20:00 | 04/04/2023 23:00:00 | 05/04/2023 11:00:00 | 01-EA-004 | FIN FAN COOLER | 100 | INSPECTION | FINAL TEST |  | 12 | 12:00 | 34:41 | 22:41 |  | 04-Apr | 05-Apr | 08-Apr | 10-Apr
CDUVDU2860 | Completed | Deblinding | 17/04/2023 02:02:25 | 17/04/2023 02:02:28 | 05/04/2023 11:00:00 | 05/04/2023 19:00:00 | 01-EA-004 | FIN FAN COOLER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 05-Apr | 05-Apr | 17-Apr | 17-Apr
CDUVDU1090 | Completed | Blinding As Per List | 30/03/2023 11:34:32 | 30/03/2023 14:50:21 | 30/03/2023 08:00:00 | 30/03/2023 16:00:00 | 01-EA-005A | FIN FAN COOLER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 3:16 |  | 4:44 | 30-Mar | 30-Mar | 30-Mar | 30-Mar
CDUVDU1170 | Completed | Plug Opening | 31/03/2023 10:21:23 | 31/03/2023 10:21:32 | 30/03/2023 16:00:00 | 31/03/2023 16:00:00 | 01-EA-005A | FIN FAN COOLER | 100 | MECHANICAL | OPENING | OPENING | 24 | 24:00 | 0:00 |  | 24:00 | 30-Mar | 31-Mar | 31-Mar | 31-Mar
CDUVDU1280 | Completed | Pre-Cleaning Inspection | 31/03/2023 11:00:15 | 31/03/2023 11:00:23 | 31/03/2023 16:00:00 | 31/03/2023 19:00:00 | 01-EA-005A | FIN FAN COOLER | 100 | INSPECTION |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 31-Mar | 31-Mar | 31-Mar | 31-Mar
CDUVDU1420 | Completed | Hydrojetting | 31/03/2023 11:00:56 | 02/04/2023 05:40:02 | 03/04/2023 03:00:00 | 04/04/2023 07:00:00 | 01-EA-005A | FIN FAN COOLER | 100 | MECHANICAL | HYDROJETTING |  | 28 | 28:00 | 42:39 | 14:39 |  | 03-Apr | 04-Apr | 31-Mar | 02-Apr
CDUVDU1800 | Completed | Post Cleaning Inspection | 05/04/2023 11:53:28 | 05/04/2023 11:53:49 | 04/04/2023 07:00:00 | 04/04/2023 15:00:00 | 01-EA-005A | FIN FAN COOLER | 100 | INSPECTION | INSPECTION | INSPECTION | 8 | 8:00 | 0:00 |  | 8:00 | 04-Apr | 04-Apr | 05-Apr | 05-Apr
CDUVDU1930 | Completed | Plug Box-up | 05/04/2023 11:54:02 | 05/04/2023 16:36:11 | 04/04/2023 15:00:00 | 06/04/2023 03:00:00 | 01-EA-005A | FIN FAN COOLER | 100 | MECHANICAL | BOX UP | BOX UP | 36 | 36:00 | 4:42 |  | 31:18 | 04-Apr | 06-Apr | 05-Apr | 05-Apr
CDUVDU4480 | Completed | Hydrotest | 06/04/2023 07:49:09 | 07/04/2023 07:31:15 | 06/04/2023 03:00:00 | 06/04/2023 15:00:00 | 01-EA-005A | FIN FAN COOLER | 100 | INSPECTION | FINAL TEST |  | 12 | 12:00 | 23:42 | 11:42 |  | 06-Apr | 06-Apr | 06-Apr | 07-Apr
CDUVDU5290 | Completed | Deblinding | 17/04/2023 02:02:54 | 17/04/2023 02:02:57 | 06/04/2023 15:00:00 | 06/04/2023 23:00:00 | 01-EA-005A | FIN FAN COOLER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 06-Apr | 06-Apr | 17-Apr | 17-Apr
CDUVDU1100 | Completed | Blinding As Per List | 30/03/2023 11:36:55 | 30/03/2023 14:50:57 | 30/03/2023 08:00:00 | 30/03/2023 16:00:00 | 01-EA-005B | FIN FAN COOLER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 3:14 |  | 4:46 | 30-Mar | 30-Mar | 30-Mar | 30-Mar
CDUVDU1180 | Completed | Plug Opening | 31/03/2023 10:22:52 | 31/03/2023 10:22:59 | 30/03/2023 16:00:00 | 31/03/2023 16:00:00 | 01-EA-005B | FIN FAN COOLER | 100 | MECHANICAL | OPENING | OPENING | 24 | 24:00 | 0:00 |  | 24:00 | 30-Mar | 31-Mar | 31-Mar | 31-Mar
CDUVDU1290 | Completed | Pre-Cleaning Inspection | 02/04/2023 06:40:40 | 02/04/2023 06:40:46 | 31/03/2023 16:00:00 | 31/03/2023 19:00:00 | 01-EA-005B | FIN FAN COOLER | 100 | INSPECTION |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 31-Mar | 31-Mar | 02-Apr | 02-Apr
CDUVDU1810 | Completed | Hydrojetting | 31/03/2023 11:00:42 | 01/04/2023 10:34:20 | 04/04/2023 07:00:00 | 05/04/2023 11:00:00 | 01-EA-005B | FIN FAN COOLER | 100 | MECHANICAL | HYDROJETTING |  | 28 | 28:00 | 23:34 |  | 4:26 | 04-Apr | 05-Apr | 31-Mar | 01-Apr
CDUVDU2870 | Completed | Post Cleaning Inspection | 05/04/2023 11:54:48 | 05/04/2023 11:54:52 | 05/04/2023 11:00:00 | 05/04/2023 19:00:00 | 01-EA-005B | FIN FAN COOLER | 100 | INSPECTION | INSPECTION | INSPECTION | 8 | 8:00 | 0:00 |  | 8:00 | 05-Apr | 05-Apr | 05-Apr | 05-Apr
CDUVDU3910 | Completed | Plug Box-up | 05/04/2023 11:54:59 | 05/04/2023 16:36:32 | 05/04/2023 19:00:00 | 07/04/2023 07:00:00 | 01-EA-005B | FIN FAN COOLER | 100 | MECHANICAL | BOX UP | BOX UP | 36 | 36:00 | 4:42 |  | 31:18 | 05-Apr | 07-Apr | 05-Apr | 05-Apr
CDUVDU6870 | Completed | Hydrotest | 07/04/2023 07:31:32 | 07/04/2023 07:31:42 | 07/04/2023 07:00:00 | 07/04/2023 19:00:00 | 01-EA-005B | FIN FAN COOLER | 100 | INSPECTION | FINAL TEST |  | 12 | 12:00 | 0:00 |  | 12:00 | 07-Apr | 07-Apr | 07-Apr | 07-Apr
CDUVDU7950 | Completed | Deblinding | 17/04/2023 02:03:15 | 17/04/2023 02:03:19 | 07/04/2023 19:00:00 | 08/04/2023 03:00:00 | 01-EA-005B | FIN FAN COOLER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 07-Apr | 08-Apr | 17-Apr | 17-Apr
CDUVDU1110 | Completed | Blinding As Per List | 30/03/2023 14:51:22 | 30/03/2023 16:52:16 | 30/03/2023 08:00:00 | 30/03/2023 16:00:00 | 01-EA-005C | FIN FAN COOLER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 2:01 |  | 5:59 | 30-Mar | 30-Mar | 30-Mar | 30-Mar
CDUVDU1190 | Completed | Plug Opening | 31/03/2023 10:23:14 | 31/03/2023 10:23:29 | 30/03/2023 16:00:00 | 31/03/2023 16:00:00 | 01-EA-005C | FIN FAN COOLER | 100 | MECHANICAL | OPENING | OPENING | 24 | 24:00 | 0:00 |  | 24:00 | 30-Mar | 31-Mar | 31-Mar | 31-Mar
CDUVDU1300 | Completed | Pre-Cleaning Inspection | 31/03/2023 10:47:31 | 31/03/2023 10:47:45 | 31/03/2023 16:00:00 | 31/03/2023 19:00:00 | 01-EA-005C | FIN FAN COOLER | 100 | INSPECTION |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 31-Mar | 31-Mar | 31-Mar | 31-Mar
CDUVDU2880 | Completed | Hydrojetting | 31/03/2023 16:53:36 | 01/04/2023 10:34:46 | 05/04/2023 11:00:00 | 06/04/2023 15:00:00 | 01-EA-005C | FIN FAN COOLER | 100 | MECHANICAL | HYDROJETTING |  | 28 | 28:00 | 17:41 |  | 10:19 | 05-Apr | 06-Apr | 31-Mar | 01-Apr
CDUVDU5300 | Completed | Post Cleaning Inspection | 02/04/2023 18:55:37 | 02/04/2023 18:55:48 | 06/04/2023 15:00:00 | 06/04/2023 23:00:00 | 01-EA-005C | FIN FAN COOLER | 100 | INSPECTION | INSPECTION | INSPECTION | 8 | 8:00 | 0:00 |  | 8:00 | 06-Apr | 06-Apr | 02-Apr | 02-Apr
CDUVDU6350 | Completed | Plug Box-up | 05/04/2023 11:56:56 | 06/04/2023 07:55:20 | 06/04/2023 23:00:00 | 08/04/2023 11:00:00 | 01-EA-005C | FIN FAN COOLER | 100 | MECHANICAL | BOX UP | BOX UP | 36 | 36:00 | 19:58 |  | 16:02 | 06-Apr | 08-Apr | 05-Apr | 06-Apr
CDUVDU8590 | Completed | Hydrotest | 07/04/2023 07:32:16 | 07/04/2023 07:42:12 | 08/04/2023 11:00:00 | 08/04/2023 23:00:00 | 01-EA-005C | FIN FAN COOLER | 100 | INSPECTION | FINAL TEST |  | 12 | 12:00 | 0:10 |  | 11:50 | 08-Apr | 08-Apr | 07-Apr | 07-Apr
CDUVDU9260 | Completed | Deblinding | 17/04/2023 02:03:34 | 17/04/2023 02:03:37 | 08/04/2023 23:00:00 | 09/04/2023 07:00:00 | 01-EA-005C | FIN FAN COOLER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 08-Apr | 09-Apr | 17-Apr | 17-Apr
CDUVDU10080 | Completed | Hydrotest | 06/04/2023 12:48:02 | 07/04/2023 22:16:53 | 09/04/2023 15:00:00 | 10/04/2023 03:00:00 | 01-EA-005D | FIN FAN COOLER | 100 | INSPECTION | FINAL TEST |  | 12 | 12:00 | 33:29 | 21:29 |  | 09-Apr | 10-Apr | 06-Apr | 07-Apr
CDUVDU10690 | Completed | Deblinding | 17/04/2023 02:03:55 | 17/04/2023 02:04:02 | 10/04/2023 03:00:00 | 10/04/2023 11:00:00 | 01-EA-005D | FIN FAN COOLER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 10-Apr | 10-Apr | 17-Apr | 17-Apr
CDUVDU1120 | Completed | Blinding As Per List | 30/03/2023 14:53:55 | 30/03/2023 16:52:59 | 30/03/2023 08:00:00 | 30/03/2023 16:00:00 | 01-EA-005D | FIN FAN COOLER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 1:59 |  | 6:01 | 30-Mar | 30-Mar | 30-Mar | 30-Mar
CDUVDU1200 | Completed | Plug Opening | 31/03/2023 10:23:44 | 31/03/2023 10:24:03 | 30/03/2023 16:00:00 | 31/03/2023 16:00:00 | 01-EA-005D | FIN FAN COOLER | 100 | MECHANICAL | OPENING | OPENING | 24 | 24:00 | 0:00 |  | 24:00 | 30-Mar | 31-Mar | 31-Mar | 31-Mar
CDUVDU1310 | Completed | Pre-Cleaning Inspection | 31/03/2023 10:48:06 | 31/03/2023 10:48:22 | 31/03/2023 16:00:00 | 31/03/2023 19:00:00 | 01-EA-005D | FIN FAN COOLER | 100 | INSPECTION |  |  | 3 | 3:00 | 0:00 |  | 3:00 | 31-Mar | 31-Mar | 31-Mar | 31-Mar
CDUVDU5310 | Completed | Hydrojetting | 31/03/2023 10:51:10 | 01/04/2023 10:35:17 | 06/04/2023 15:00:00 | 07/04/2023 19:00:00 | 01-EA-005D | FIN FAN COOLER | 100 | MECHANICAL | HYDROJETTING |  | 28 | 28:00 | 23:44 |  | 4:16 | 06-Apr | 07-Apr | 31-Mar | 01-Apr
CDUVDU7960 | Completed | Post Cleaning Inspection | 02/04/2023 18:56:04 | 02/04/2023 18:56:08 | 07/04/2023 19:00:00 | 08/04/2023 03:00:00 | 01-EA-005D | FIN FAN COOLER | 100 | INSPECTION | INSPECTION | INSPECTION | 8 | 8:00 | 0:00 |  | 8:00 | 07-Apr | 08-Apr | 02-Apr | 02-Apr
CDUVDU8320 | Completed | Plug Box-up | 05/04/2023 11:59:01 | 06/04/2023 07:55:38 | 08/04/2023 03:00:00 | 09/04/2023 15:00:00 | 01-EA-005D | FIN FAN COOLER | 100 | MECHANICAL | BOX UP | BOX UP | 36 | 36:00 | 19:57 |  | 16:03 | 08-Apr | 09-Apr | 05-Apr | 06-Apr
CDUVDU1130 | Completed | Blinding As Per List | 01/04/2023 03:48:58 | 01/04/2023 03:49:05 | 30/03/2023 14:30:00 | 30/03/2023 22:30:00 | 01-EA-006A | FIN FAN COOLER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 30-Mar | 30-Mar | 01-Apr | 01-Apr
CDUVDU11760 | Completed | Hydrotest | 16/04/2023 01:00:30 | 16/04/2023 12:40:21 | 10/04/2023 19:00:00 | 11/04/2023 07:00:00 | 01-EA-006A | FIN FAN COOLER | 100 | INSPECTION | FINAL TEST |  | 12 | 12:00 | 11:40 |  | 0:20 | 10-Apr | 11-Apr | 16-Apr | 16-Apr
CDUVDU1210 | Completed | Plug Opening | 01/04/2023 10:01:54 | 02/04/2023 05:35:47 | 30/03/2023 22:30:00 | 31/03/2023 22:30:00 | 01-EA-006A | FIN FAN COOLER | 100 | MECHANICAL | OPENING | OPENING | 24 | 24:00 | 19:34 |  | 4:26 | 30-Mar | 31-Mar | 01-Apr | 02-Apr
CDUVDU12610 | Completed | Deblinding | 17/04/2023 02:05:50 | 17/04/2023 02:05:53 | 11/04/2023 07:00:00 | 11/04/2023 15:00:00 | 01-EA-006A | FIN FAN COOLER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 11-Apr | 11-Apr | 17-Apr | 17-Apr
CDUVDU1320 | Completed | Pre-Cleaning Inspection | 02/04/2023 13:53:27 | 03/04/2023 18:29:27 | 31/03/2023 22:30:00 | 01/04/2023 01:30:00 | 01-EA-006A | FIN FAN COOLER | 100 | INSPECTION |  |  | 3 | 3:00 | 28:36 | 25:36 |  | 31-Mar | 01-Apr | 02-Apr | 03-Apr
CDUVDU7970 | Completed | Hydrojetting | 02/04/2023 13:53:27 | 05/04/2023 12:20:43 | 07/04/2023 19:00:00 | 08/04/2023 23:00:00 | 01-EA-006A | FIN FAN COOLER | 100 | MECHANICAL | HYDROJETTING |  | 28 | 28:00 | 70:27 | 42:27 |  | 07-Apr | 08-Apr | 02-Apr | 05-Apr
CDUVDU9270 | Completed | Post Cleaning Inspection | 03/04/2023 16:42:02 | 05/04/2023 12:21:34 | 08/04/2023 23:00:00 | 09/04/2023 07:00:00 | 01-EA-006A | FIN FAN COOLER | 100 | INSPECTION | INSPECTION | INSPECTION | 8 | 8:00 | 43:40 | 35:40 |  | 08-Apr | 09-Apr | 03-Apr | 05-Apr
CDUVDU9770 | Completed | Plug Box-up | 15/04/2023 03:37:33 | 15/04/2023 06:01:25 | 09/04/2023 07:00:00 | 10/04/2023 19:00:00 | 01-EA-006A | FIN FAN COOLER | 100 | MECHANICAL | BOX UP | BOX UP | 36 | 36:00 | 2:24 |  | 33:36 | 09-Apr | 10-Apr | 15-Apr | 15-Apr
CDUVDU10700 | Completed | Post Cleaning Inspection | 03/04/2023 16:45:35 | 05/04/2023 12:21:56 | 10/04/2023 03:00:00 | 10/04/2023 11:00:00 | 01-EA-006B | FIN FAN COOLER | 100 | INSPECTION | INSPECTION | INSPECTION | 8 | 8:00 | 43:36 | 35:36 |  | 10-Apr | 10-Apr | 03-Apr | 05-Apr
CDUVDU11210 | Completed | Plug Box-up | 15/04/2023 03:38:02 | 15/04/2023 06:01:43 | 10/04/2023 11:00:00 | 11/04/2023 23:00:00 | 01-EA-006B | FIN FAN COOLER | 100 | MECHANICAL | BOX UP | BOX UP | 36 | 36:00 | 2:24 |  | 33:36 | 10-Apr | 11-Apr | 15-Apr | 15-Apr
CDUVDU1140 | Completed | Blinding As Per List | 01/04/2023 03:50:34 | 01/04/2023 03:50:41 | 30/03/2023 14:30:00 | 30/03/2023 22:30:00 | 01-EA-006B | FIN FAN COOLER | 100 | MECHANICAL | BLINDING | BLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 30-Mar | 30-Mar | 01-Apr | 01-Apr
CDUVDU1220 | Completed | Plug Opening | 01/04/2023 10:02:15 | 02/04/2023 05:36:34 | 30/03/2023 22:30:00 | 31/03/2023 22:30:00 | 01-EA-006B | FIN FAN COOLER | 100 | MECHANICAL | OPENING | OPENING | 24 | 24:00 | 19:34 |  | 4:26 | 30-Mar | 31-Mar | 01-Apr | 02-Apr
CDUVDU1330 | Completed | Pre-Cleaning Inspection | 02/04/2023 13:52:51 | 03/04/2023 18:30:39 | 31/03/2023 22:30:00 | 01/04/2023 01:30:00 | 01-EA-006B | FIN FAN COOLER | 100 | INSPECTION |  |  | 3 | 3:00 | 28:38 | 25:38 |  | 31-Mar | 01-Apr | 02-Apr | 03-Apr
CDUVDU13590 | Completed | Hydrotest | 16/04/2023 01:00:49 | 16/04/2023 12:39:29 | 11/04/2023 23:00:00 | 12/04/2023 11:00:00 | 01-EA-006B | FIN FAN COOLER | 100 | INSPECTION | FINAL TEST |  | 12 | 12:00 | 11:39 |  | 0:21 | 11-Apr | 12-Apr | 16-Apr | 16-Apr
CDUVDU14300 | Completed | Deblinding | 17/04/2023 02:06:21 | 17/04/2023 02:06:31 | 12/04/2023 11:00:00 | 12/04/2023 19:00:00 | 01-EA-006B | FIN FAN COOLER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 8:00 | 0:00 |  | 8:00 | 12-Apr | 12-Apr | 17-Apr | 17-Apr
CDUVDU9280 | Completed | Hydrojetting | 02/04/2023 13:52:37 | 05/04/2023 12:21:47 | 08/04/2023 23:00:00 | 10/04/2023 03:00:00 | 01-EA-006B | FIN FAN COOLER | 100 | MECHANICAL | HYDROJETTING |  | 28 | 28:00 | 70:29 | 42:29 |  | 08-Apr | 10-Apr | 02-Apr | 05-Apr
CDUVDU1600 | Completed | Carry Out Blinding | 04/04/2023 12:01:30 | 04/04/2023 12:01:35 | 30/03/2023 14:30:00 | 31/03/2023 14:30:00 | 01-EA-001A | FIN FAN COOLER | 100 | MECHANICAL | BLINDING | BLINDING | 24 | 24:00 | 0:00 |  | 24:00 | 30-Mar | 31-Mar | 04-Apr | 04-Apr
CDUVDU1970 | Completed | Opening of covers/ Plug | 04/04/2023 12:01:58 | 04/04/2023 12:02:05 | 31/03/2023 14:30:00 | 01/04/2023 06:30:00 | 01-EA-001A | FIN FAN COOLER | 100 | MECHANICAL | OPENING | OPENING | 16 | 16:00 | 0:00 |  | 16:00 | 31-Mar | 01-Apr | 04-Apr | 04-Apr
CDUVDU20760 | Completed | Install new tube bundle | 03/04/2023 11:41:32 | 04/04/2023 12:07:06 | 11/04/2023 08:30:00 | 11/04/2023 20:30:00 | 01-EA-001A | FIN FAN COOLER | 100 | MECHANICAL |  |  | 12 | 12:00 | 24:26 | 12:26 |  | 11-Apr | 11-Apr | 03-Apr | 04-Apr
CDUVDU22070 | Completed | IRIS inspection | 09/04/2023 18:43:54 | 09/04/2023 18:43:59 | 11/04/2023 20:30:00 | 12/04/2023 20:30:00 | 01-EA-001A | FIN FAN COOLER | 100 | INSPECTION |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 11-Apr | 12-Apr | 09-Apr | 09-Apr
CDUVDU24190 | Completed | Post cleaning inspection | 09/04/2023 18:44:15 | 09/04/2023 18:44:20 | 12/04/2023 20:30:00 | 13/04/2023 04:30:00 | 01-EA-001A | FIN FAN COOLER | 100 | INSPECTION | INSPECTION | INSPECTION | 8 | 8:00 | 0:00 |  | 8:00 | 12-Apr | 13-Apr | 09-Apr | 09-Apr
CDUVDU24830 | Completed | Box up of covers/ Plug | 09/04/2023 18:44:34 | 09/04/2023 18:44:38 | 13/04/2023 04:30:00 | 13/04/2023 16:30:00 | 01-EA-001A | FIN FAN COOLER | 100 | MECHANICAL | BOX UP | BOX UP | 12 | 12:00 | 0:00 |  | 12:00 | 13-Apr | 13-Apr | 09-Apr | 09-Apr
CDUVDU25540 | Completed | Hydrotest | 09/04/2023 18:44:52 | 10/04/2023 12:32:23 | 13/04/2023 16:30:00 | 14/04/2023 16:30:00 | 01-EA-001A | FIN FAN COOLER | 100 | INSPECTION | FINAL TEST |  | 24 | 24:00 | 17:48 |  | 6:12 | 13-Apr | 14-Apr | 09-Apr | 10-Apr
CDUVDU26760 | Completed | Deblinding | 17/04/2023 01:54:31 | 17/04/2023 01:54:35 | 14/04/2023 16:30:00 | 15/04/2023 16:30:00 | 01-EA-001A | FIN FAN COOLER | 100 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 24:00 | 0:00 |  | 24:00 | 14-Apr | 15-Apr | 17-Apr | 17-Apr
CDUVDU2950 | Completed | Removal of tubes bundle for replacement | 02/04/2023 19:02:21 | 02/04/2023 19:02:27 | 01/04/2023 11:30:00 | 02/04/2023 11:30:00 | 01-EA-001A | FIN FAN COOLER | 100 | MECHANICAL |  |  | 24 | 24:00 | 0:00 |  | 24:00 | 01-Apr | 02-Apr | 02-Apr | 02-Apr
CDUVDU30190 | Not Started | Handover to Operation |  |  | 23/04/2023 14:00:00 | 23/04/2023 14:00:00 | HANDOVER | PLANT | 0 | MECHANICAL |  |  | 0 | 0:00 | 0:00 |  |  | 23-Apr | 23-Apr | - Date check | - Date check
CDUVDU30200 | Not Started | Start Up and Feed Cut in |  |  | 23/04/2023 14:00:00 | 26/04/2023 02:00:00 | UNIT START UP | PLANT | 0 | OPERATION |  |  | 60 | 60:00 | 0:00 |  |  | 23-Apr | 26-Apr | - Date check | - Date check

## Table
(BL)Project Start Date | (BL)Project Finish Date | Actual Start Date | Actual Finish Date | Plan to Start | Plan to Finish | Actually Start | Actually Finish
2023-03-26 | 2023-03-26 | 2023-03-26 | 2023-03-26 | 9 | 2 | 5 | 1
2023-03-27 | 2023-03-27 | 2023-04-22 | 2023-04-19 | 2 | 3 | 73 | 28
2023-03-28 | 2023-04-21 | 2023-04-16 | 2023-04-16 | 43 | 51 | 57 | 64
2023-03-30 | 2023-04-04 | 2023-03-28 | 2023-04-06 | 5 | 4 | 30 | 70
2023-03-31 | 2023-03-30 | 2023-03-27 | 2023-03-31 | 2 | 18 | 92 | 96
2023-04-01 | 2023-03-31 | 2023-03-31 | 2023-03-30 | 50 | 104 | 31 | 185
2023-04-02 | 2023-04-01 | 2023-04-17 | 2023-04-01 | 83 | 34 | 47 | 74
2023-04-03 | 2023-04-05 | 2023-03-30 | 2023-04-03 | 231 | 142 | 111 | 188
2023-04-04 | 2023-04-06 | 2023-04-06 | 2023-04-18 | 137 | 141 | 178 | 91
2023-04-05 | 2023-04-02 | 2023-04-01 | 2023-04-17 | 178 | 61 | 98 | 44
2023-04-06 | 2023-04-03 | 2023-04-03 | 2023-04-02 | 162 | 130 | 48 | 91
2023-04-07 | 2023-04-07 | 2023-04-02 | 2023-04-04 | 135 | 229 | 178 | 92
2023-04-08 | 2023-04-08 | 2023-04-05 | 2023-04-05 | 162 | 175 | 98 | 140
2023-04-09 | 2023-04-09 | 2023-04-18 | 2023-04-07 | 152 | 155 | 152 | 187
2023-04-10 | 2023-04-10 | 2023-04-04 | 2023-04-08 | 173 | 160 | 117 | 103
2023-04-11 | 2023-04-11 | 2023-04-07 | 2023-04-09 | 223 | 206 | 86 | 103
2023-04-12 | 2023-04-12 | 2023-04-08 | 2023-04-10 | 250 | 243 | 175 | 130
2023-04-13 | 2023-04-13 | 2023-04-09 | 2023-04-20 | 238 | 237 | 105 | 104
2023-04-14 | 2023-04-14 | 2023-04-10 | 2023-04-22 | 218 | 252 | 132 | 112
2023-04-15 | 2023-04-15 | 2023-04-11 | 2023-04-11 | 137 | 156 | 120 | 106
2023-04-16 | 2023-04-16 | 2023-04-12 | 2023-04-12 | 112 | 126 | 113 | 34
2023-04-17 | 2023-04-17 | 2023-04-13 | 2023-04-13 | 83 | 101 | 79 | 82
2023-04-18 | 2023-04-18 | 2023-04-14 | 2023-04-14 | 83 | 88 | 71 | 71
2023-04-19 | 2023-04-19 | 2023-04-15 | 2023-04-15 | 54 | 70 | 74 | 63
2023-04-20 | 2023-04-22 | 2023-03-29 | 2023-03-29 | 35 | 44 | 74 | 83
2023-04-21 | 2023-04-20 | 2023-04-20 | 2023-03-27 | 13 | 12 | 42 | 45
2023-04-22 | 2023-04-23 | 2023-04-19 | 2023-03-28 | 5 | 30 | 89 | 6
2023-04-23 | 2023-03-28 | 2023-04-21 | 2023-04-23 | 2 | 2 | 27 | 113
| 2023-04-26 | 2023-04-24 | 2023-04-21 | 0 | 1 | 11 | 30
|  | 2023-04-25 | 2023-04-24 | 0 | 0 | 23 | 16
|  | 2023-04-23 | 2023-04-25 | 0 | 0 | 101 | 26
|  | - Date check | 2023-04-26 | 0 | 0 | 215 | 132
|  | 2023-04-26 | - Date check | 0 | 0 | 125 | 264
|  |  | 2023-04-27 | 0 | 0 | 0 | 3
Dates | Plan to Start | Plan to Finish | Actually Start | Actually Finish | Plan Deviation | Completion Deviation | Daily Starting compliance | Daily Finishing compliance
2023-03-26 | 9 | 2 | 5 | 2 | -4 | 0 | 55.56%
2023-03-27 | 2 | 3 | 92 | 12 | 86 | 9 | 4600%
2023-03-28 | 43 | 2 | 30 | 30 | 73 | 37 | 69.77%
2023-03-29 | 0 | 0 | 74 | 44 | 147 | 81 | 0%
2023-03-30 | 5 | 18 | 111 | 104 | 253 | 167 | 2220%
2023-03-31 | 2 | 104 | 31 | 18 | 282 | 81 | 1550%
2023-04-01 | 50 | 34 | 98 | 34 | 330 | 81 | 196%
2023-04-02 | 83 | 61 | 178 | 130 | 425 | 150 | 214.5%
2023-04-03 | 231 | 130 | 48 | 142 | 242 | 162 | 20.78%
2023-04-04 | 137 | 4 | 117 | 229 | 222 | 387 | 85.4%
2023-04-05 | 178 | 142 | 98 | 175 | 142 | 420 | 55.06%
2023-04-06 | 162 | 141 | 178 | 4 | 158 | 283 | 109.9%
2023-04-07 | 135 | 229 | 86 | 155 | 109 | 209 | 63.7%
2023-04-08 | 162 | 175 | 175 | 160 | 122 | 194 | 108%
2023-04-09 | 152 | 155 | 105 | 206 | 75 | 245 | 69.08%
2023-04-10 | 173 | 160 | 132 | 243 | 34 | 328 | 76.3%
2023-04-11 | 223 | 206 | 120 | 156 | -69 | 278 | 53.81%
2023-04-12 | 250 | 243 | 113 | 126 | -206 | 161 | 45.2%
2023-04-13 | 238 | 237 | 79 | 101 | -365 | 25 | 33.19%
2023-04-14 | 218 | 252 | 71 | 88 | -512 | -139 | 32.57%
2023-04-15 | 137 | 156 | 74 | 70 | -575 | -225 | 54.01%
2023-04-16 | 112 | 126 | 57 | 51 | -630 | -300 | 50.89%
2023-04-17 | 83 | 101 | 47 | 61 | -666 | -340 | 56.63%
2023-04-18 | 83 | 88 | 152 | 141 | -597 | -287 | 183.1%
2023-04-19 | 54 | 70 | 89 | 3 | -562 | -354 | 164.8%
2023-04-20 | 35 | 12 | 42 | 237 | -555 | -129 | 120%
2023-04-21 | 13 | 51 | 27 | 1 | -541 | -179 | 207.7%
2023-04-22 | 5 | 44 | 73 | 252 | -473 | 29 | 1460%
2023-04-23 | 2 | 30 | 101 | 2 | -374 | 1 | 5050%
2023-04-24 | 0 | 0 | 11 | 0 | -363 | 1 | 0%
2023-04-25 | 0 | 0 | 23 | 0 | -340 | 1 | 0%
2023-04-26 | 0 | 1 | 125 | 0 | -215 | 0 | 0%
2023-04-27 | 0 | 0 | 0 | 0 | -215 | 0 | 0%
Planned Hour | 2134.25
Completed Hour | 1893.2648
Extra spending | 1238.6645
Saving hours | 23666:36
Total Planed hour completed | 1640.7083 | 76.88%
Remaing Planed hour | 11845:00 | 23.12%
Number of Activity not started | 215
In Progress | 49

## Pending Task
Activity ID | Activity Status | Activity Name | Machine | Machine Type | Progress | Department | Machine Label | Machine Label Group | Planned Duration (Hrs) | Planned Duration(hh:mm:ss) | Actual time(hh:mm:sec) | Extra Spending (hh:mm:sec) | Saving(hh:mm:ss) | (BL)Project Start Date | (BL)Project Finish Date
CDUVDU20930 | Not Started | All header and box emergency steam nozzle checking of FF-1& 2 in both convection and radiation section. | 01-FF-001 AND 002 | MECHANICAL JOBS | 0 | MECHANICAL |  |  | 120 | 5 | 0 |  |  | 11-Apr | 16-Apr
CDUVDU8110 | In Progress | Heat efficiency painting in 01-FF-01/02 wall | 01-FF-01/02 wall | CIVIL JOBS | 90 | CIVIL |  |  | 180 | 7.5 | 0 |  |  | 03-Apr | 11-Apr
CDUVDU9020 | In Progress | underground leakage arrest | CIVIL JOBS | CIVIL JOBS | 90 | CIVIL |  |  | 240 | 10 | 0 |  |  | 04-Apr | 14-Apr
CDUVDU8910 | In Progress | Providing auto sprinkler for LPG Reflux pump PA-12 A/B | SAFETY JOB | SAFETY JOBS | 53 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 240 | 10 | 0 |  |  | 04-Apr | 14-Apr
CDUVDU8920 | In Progress | Providing closed loop sampling for all sampling points | SAFETY JOB | SAFETY JOBS | 16 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 420 | 17.5 | 0 |  |  | 04-Apr | 22-Apr
A1230 | In Progress | TSV outlet routing from OWS to Closed system (CBD) | SAFETY JOB | SAFETY JOBS | 50 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 120 | 5 | 0 |  |  | 10-Apr | 15-Apr
A1000 | In Progress | Seal Plan Change of CDU VDU Pumps | SEAL PLAN PUMPS | HOT JOB | 79.6 | MECHANICAL |  |  | 96 | 4 | 0 |  |  | 07-Apr | 11-Apr
CDUVDU29110 | In Progress | Provide double mechanical seal | MOC/V2/31 | MOC JOBS AFTER CUT OFF | 0 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 96 | 4 | 0 |  |  | 17-Apr | 21-Apr
CDUVDU20590 | In Progress | Commissioning | MOC/423 | MOC JOBS AFTER CUT OFF | 85 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 240 | 10 | 0 |  |  | 11-Apr | 21-Apr
CDUVDU8950 | In Progress | Additional facillity for corrosion inhibitor dosing to VDU Overhead | MOC/V2/69 | MOC JOBS AFTER CUT OFF | 0 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 120 | 5 | 0 |  |  | 04-Apr | 09-Apr
A1200 | In Progress | Installation of 4 numbers of ultrasonic mass flow meters in Vacuum furnace Pass flow. | MOC/V2/52 | MOC JOBS AFTER CUT OFF | 44 | INSTRUMENTATION | WORK COMPLETED | WORK COMPLETED | 120 | 5 | 0 |  |  | 16-Apr | 21-Apr
A1210 | In Progress | ROV1501 to be closed on actuation of CDU bottom Level Low Low interlock | MOC/V2/85 | MOC JOBS AFTER CUT OFF | 90 | INSTRUMENTATION | WORK COMPLETED | WORK COMPLETED | 120 | 5 | 0 |  |  | 16-Apr | 21-Apr
A1160 | In Progress | Seal Plan change of CDU/VDU pumps to API plan 54 | MOC/700 | MOC JOBS BEFORE CUT OFF | 93.05 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 120 | 5 | 0 |  |  | 16-Apr | 21-Apr
CDUVDU14630 | In Progress | Installation of remote operated HVLRM(2 Nos) | MOC/611 | MOC JOBS BEFORE CUT OFF | 93.61 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 240 | 10 | 0 |  |  | 08-Apr | 18-Apr
A1180 | In Progress | Provision of minimum circulation flow in 01-PA-18A/B. | MOC/V2/9 | MOC JOBS BEFORE CUT OFF | 63 | INSTRUMENTATION | WORK COMPLETED | WORK COMPLETED | 120 | 5 | 0 |  |  | 16-Apr | 21-Apr
A1020 | In Progress | ICMS OVERHAULING | ICMS O/H | ICMS O/H | 95 | PPM |  |  | 444 | 18.5 | 0 |  |  | 02-Apr | 20-Apr
CDUVDU21640 | In Progress | Carry out Process inspection of burners | 01-FF-001 | FURNACE | 70 | TS |  |  | 4 | 0.16667 | 0 |  |  | 11-Apr | 11-Apr
CDUVDU3790 | In Progress | Carry out servicing of burners | 01-FF-001 | FURNACE | 92 | MECHANICAL |  |  | 240 | 10 | 0 |  |  | 01-Apr | 11-Apr
CDUVDU13790 | In Progress | Carry out servicing of dampers and lovers | 01-FF-001 | FURNACE | 81 | MECHANICAL |  |  | 120 | 5 | 0 |  |  | 07-Apr | 12-Apr
CDUVDU24620 | In Progress | Carry out Inspection by ops | 01-FF-001 | FURNACE | 63 | OPERATION |  |  | 3 | 0.125 | 0 |  |  | 12-Apr | 12-Apr
CDUVDU20900 | Not Started | Carry out final inspection | 01-FF-001 | FURNACE | 0 | INSPECTION |  |  | 24 | 1 | 0 |  |  | 11-Apr | 12-Apr
CDUVDU23310 | Not Started | Carry out box up of manway | 01-FF-001 | FURNACE | 0 | MECHANICAL |  |  | 12 | 0.5 | 0 |  |  | 12-Apr | 12-Apr
CDUVDU29210 | Not Started | Carry out removal of internal scaffolding | 01-FF-001 | FURNACE | 0 | MECHANICAL |  |  | 12 | 0.5 | 0 |  |  | 17-Apr | 18-Apr
CDUVDU29400 | Not Started | Carry out fixing of burners | 01-FF-001 | FURNACE | 0 | MECHANICAL |  |  | 18 | 0.75 | 0 |  |  | 18-Apr | 19-Apr
CDUVDU29760 | In Progress | Carry out repair of damaged floor refractory | 01-FF-001 | FURNACE | 0 | CIVIL |  |  | 18 | 0.75 | 0 |  |  | 19-Apr | 19-Apr
CDUVDU29990 | Not Started | Carry out allignment check of burners | 01-FF-001 | FURNACE | 0 | TS |  |  | 12 | 0.5 | 0 |  |  | 19-Apr | 20-Apr
CDUVDU30000 | Not Started | Carry out box of header panels of convection section | 01-FF-001 | FURNACE | 0 | MECHANICAL |  |  | 18 | 0.75 | 0 |  |  | 19-Apr | 20-Apr
CDUVDU30090 | Not Started | Carry out manway box up | 01-FF-001 | FURNACE | 0 | MECHANICAL | BOX UP | BOX UP | 12 | 0.5 | 0 |  |  | 20-Apr | 21-Apr
CDUVDU30140 | Not Started | Carry out deblinding | 01-FF-001 | FURNACE | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 1 | 0 |  |  | 21-Apr | 22-Apr
CDUVDU24330 | In Progress | Carry out Process inspection of burners | 01-FF-002 | FURNACE | 60 | TS |  |  | 4 | 0.16667 | 0 |  |  | 12-Apr | 12-Apr
CDUVDU6390 | In Progress | Carry out servicing of burners | 01-FF-002 | FURNACE | 60 | MECHANICAL |  |  | 240 | 10 | 0 |  |  | 02-Apr | 12-Apr
CDUVDU24630 | In Progress | Carry out Inspection by ops | 01-FF-002 | FURNACE | 60 | OPERATION |  |  | 3 | 0.125 | 0 |  |  | 12-Apr | 12-Apr
CDUVDU14400 | In Progress | Carry out inspection | 01-FF-002 | FURNACE | 57 | INSPECTION |  |  | 24 | 1 | 0 |  |  | 08-Apr | 09-Apr
CDUVDU27910 | Not Started | Carry out final inspection | 01-FF-002 | FURNACE | 0 | INSPECTION |  |  | 24 | 1 | 0 |  |  | 15-Apr | 16-Apr
CDUVDU28660 | Not Started | Carry out box up of manway | 01-FF-002 | FURNACE | 0 | MECHANICAL |  |  | 12 | 0.5 | 0 |  |  | 16-Apr | 17-Apr
CDUVDU7400 | In Progress | Carry out servicing of damper and power cylinder | 01-FF-002 | FURNACE | 50 | MECHANICAL |  |  | 96 | 4 | 0 |  |  | 03-Apr | 07-Apr
CDUVDU29500 | Not Started | Carry out removal of internal scaffolding | 01-FF-002 | FURNACE | 0 | MECHANICAL |  |  | 12 | 0.5 | 0 |  |  | 18-Apr | 18-Apr
CDUVDU29700 | Not Started | Carry out fixing of burners | 01-FF-002 | FURNACE | 0 | MECHANICAL |  |  | 24 | 1 | 0 |  |  | 18-Apr | 19-Apr
CDUVDU30070 | Not Started | Carry out allignment check of burners | 01-FF-002 | FURNACE | 0 | TS |  |  | 24 | 1 | 0 |  |  | 20-Apr | 21-Apr
CDUVDU30080 | Not Started | Carry out box of header panels of convection section | 01-FF-002 | FURNACE | 0 | MECHANICAL |  |  | 18 | 0.75 | 0 |  |  | 20-Apr | 21-Apr
CDUVDU30150 | Not Started | Carry out manway box up | 01-FF-002 | FURNACE | 0 | MECHANICAL | BOX UP | BOX UP | 12 | 0.5 | 0 |  |  | 21-Apr | 22-Apr
CDUVDU30170 | Not Started | Carry out deblinding | 01-FF-002 | FURNACE | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 1 | 0 |  |  | 22-Apr | 23-Apr
CDUVDU29420 | In Progress | Alignment of fan and Deblinding | ID/FD FAN | ID/FD FAN | 60 | MECHANICAL |  |  | 24 | 1 | 0 |  |  | 18-Apr | 19-Apr
CDUVDU30110 | In Progress | Box up | APH | APH | 90 | MECHANICAL |  |  | 21 | 0.875 | 0 |  |  | 20-Apr | 21-Apr
CDUVDU29290 | In Progress | Carry out deblinding | 01-CC-002 | COLUMN | 90 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 1 | 0 |  |  | 18-Apr | 19-Apr
CDUVDU29870 | In Progress | Carry out deblinding | 01-CC-003 | COLUMN | 90 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 1 | 0 |  |  | 19-Apr | 20-Apr
CDUVDU29880 | In Progress | Carry out deblinding | 01-CC-004 | COLUMN | 90 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 1 | 0 |  |  | 19-Apr | 20-Apr
CDUVDU29860 | In Progress | Carry out deblinding | 01-CC-001 | COLUMN | 90 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 1 | 0 |  |  | 19-Apr | 20-Apr
CDUVDU16470 | In Progress | Deblinding | 01-VV-001 | VESSEL | 90 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 1 | 0 |  |  | 09-Apr | 10-Apr
CDUVDU29710 | In Progress | Deblinding | 01-VV-025 | VESSEL | 95 | MECHANICAL | DEBLINDING | DEBLINDING | 24 | 1 | 0 |  |  | 19-Apr | 20-Apr
CDUVDU13100 | Not Started | Hydrotest | L-113(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | HYDRO TEST | HYDRO TEST | 20 | 0.83333 | 0 |  |  | 07-Apr | 08-Apr
CDUVDU14430 | Not Started | Hydrotest Witness | L-113(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | INSPECTION |  |  | 3 | 0.125 | 0 |  |  | 08-Apr | 08-Apr
CDUVDU14580 | Not Started | Drainning of water | L-113(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 6 | 0.25 | 0 |  |  | 08-Apr | 08-Apr
CDUVDU15070 | Not Started | Deblinding & handover to Operation. | L-113(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 0.5 | 0 |  |  | 08-Apr | 09-Apr
CDUVDU9560 | Not Started | Water filling | L-113(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 24 | 1 | 0 |  |  | 05-Apr | 06-Apr
CDUVDU30280 | Not Started | Blinding | L-4B(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | BLINDING | BLINDING | 12 | 0.5 | 0 |  |  | 09-Apr | 10-Apr
CDUVDU30290 | Not Started | Water filling | L-4B(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 48 | 2 | 0 |  |  | 10-Apr | 12-Apr
CDUVDU30310 | Not Started | Hydrotest | L-4B(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | HYDRO TEST | HYDRO TEST | 24 | 1 | 0 |  |  | 12-Apr | 13-Apr
CDUVDU30320 | Not Started | Drainning of water | L-4B(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 8 | 0.33333 | 0 |  |  | 13-Apr | 13-Apr
CDUVDU30330 | Not Started | Deblinding & handover to Operation. | L-4B(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 0.5 | 0 |  |  | 13-Apr | 14-Apr
CDUVDU30340 | Not Started | Hydrotest Witness | L-4B(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | INSPECTION |  |  | 3 | 0.125 | 0 |  |  | 13-Apr | 13-Apr
CDUVDU30350 | Not Started | Blinding | VV-004-PSV1602(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | BLINDING | BLINDING | 12 | 0.5 | 0 |  |  | 10-Apr | 10-Apr
CDUVDU30360 | Not Started | Water filling | VV-004-PSV1602(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 20 | 0.83333 | 0 |  |  | 10-Apr | 11-Apr
CDUVDU30380 | Not Started | Hydrotest | VV-004-PSV1602(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | HYDRO TEST | HYDRO TEST | 20 | 0.83333 | 0 |  |  | 11-Apr | 12-Apr
CDUVDU30390 | Not Started | Drainning of water | VV-004-PSV1602(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 6 | 0.25 | 0 |  |  | 12-Apr | 12-Apr
CDUVDU30400 | Not Started | Deblinding & handover to Operation. | VV-004-PSV1602(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 0.5 | 0 |  |  | 12-Apr | 13-Apr
CDUVDU30410 | Not Started | Hydrotest Witness | VV-004-PSV1602(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | INSPECTION |  |  | 3 | 0.125 | 0 |  |  | 12-Apr | 12-Apr
CDUVDU30530 | Not Started | Drainning of water | L-72(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 8 | 0.33333 | 0 |  |  | 14-Apr | 14-Apr
CDUVDU30540 | Not Started | Deblinding & handover to Operation. | L-72(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 0.5 | 0 |  |  | 14-Apr | 15-Apr
CDUVDU30550 | Not Started | Hydrotest Witness | L-72(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | INSPECTION |  |  | 3 | 0.125 | 0 |  |  | 14-Apr | 14-Apr
CDUVDU30560 | Not Started | Blinding | L-129PA(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | BLINDING | BLINDING | 12 | 0.5 | 0 |  |  | 11-Apr | 12-Apr
CDUVDU30570 | Not Started | Water filling | L-129PA(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 20 | 0.83333 | 0 |  |  | 12-Apr | 12-Apr
CDUVDU30590 | Not Started | Hydrotest | L-129PA(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | HYDRO TEST | HYDRO TEST | 20 | 0.83333 | 0 |  |  | 12-Apr | 13-Apr
CDUVDU30600 | Not Started | Drainning of water | L-129PA(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 6 | 0.25 | 0 |  |  | 13-Apr | 14-Apr
CDUVDU30610 | Not Started | Deblinding & handover to Operation. | L-129PA(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 0.5 | 0 |  |  | 14-Apr | 14-Apr
CDUVDU30620 | Not Started | Hydrotest Witness | L-129PA(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | INSPECTION |  |  | 3 | 0.125 | 0 |  |  | 13-Apr | 13-Apr
CDUVDU30630 | Not Started | Blinding | L-116(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | BLINDING | BLINDING | 12 | 0.5 | 0 |  |  | 12-Apr | 12-Apr
CDUVDU30640 | Not Started | Water filling | L-116(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 20 | 0.83333 | 0 |  |  | 12-Apr | 13-Apr
CDUVDU30660 | Not Started | Hydrotest | L-116(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | HYDRO TEST | HYDRO TEST | 20 | 0.83333 | 0 |  |  | 13-Apr | 14-Apr
CDUVDU30670 | Not Started | Drainning of water | L-116(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 6 | 0.25 | 0 |  |  | 14-Apr | 14-Apr
CDUVDU30680 | Not Started | Deblinding & handover to Operation. | L-116(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 0.5 | 0 |  |  | 14-Apr | 15-Apr
CDUVDU30690 | Not Started | Hydrotest Witness | L-116(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | INSPECTION |  |  | 3 | 0.125 | 0 |  |  | 14-Apr | 14-Apr
CDUVDU15710 | Not Started | Blinding | L-91(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | BLINDING | BLINDING | 12 | 0.5 | 0 |  |  | 09-Apr | 09-Apr
CDUVDU16650 | Not Started | Water filling | L-91(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 24 | 1 | 0 |  |  | 09-Apr | 10-Apr
CDUVDU20250 | Not Started | Hydrotest | L-91(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | HYDRO TEST | HYDRO TEST | 20 | 0.83333 | 0 |  |  | 11-Apr | 12-Apr
CDUVDU22220 | Not Started | Hydrotest Witness | L-91(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | INSPECTION |  |  | 3 | 0.125 | 0 |  |  | 12-Apr | 12-Apr
CDUVDU22430 | Not Started | Drainning of water | L-91(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 6 | 0.25 | 0 |  |  | 12-Apr | 12-Apr
CDUVDU23120 | Not Started | Deblinding & handover to Operation. | L-91(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 0.5 | 0 |  |  | 12-Apr | 13-Apr
CDUVDU10200 | Not Started | Water filling | L-114(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 36 | 1.5 | 0 |  |  | 05-Apr | 07-Apr
CDUVDU14670 | Not Started | Hydrotest | L-114(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | HYDRO TEST | HYDRO TEST | 24 | 1 | 0 |  |  | 08-Apr | 09-Apr
CDUVDU16630 | Not Started | Hydrotest Witness | L-114(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | INSPECTION |  |  | 3 | 0.125 | 0 |  |  | 09-Apr | 09-Apr
CDUVDU16860 | Not Started | Drainning of water | L-114(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 8 | 0.33333 | 0 |  |  | 09-Apr | 10-Apr
CDUVDU17660 | Not Started | Deblinding & handover to Operation. | L-114(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 0.5 | 0 |  |  | 10-Apr | 10-Apr
CDUVDU10210 | Not Started | Blinding | VV-008 OVHD(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | BLINDING | BLINDING | 12 | 0.5 | 0 |  |  | 05-Apr | 06-Apr
CDUVDU10790 | Not Started | Water filling | VV-008 OVHD(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 20 | 0.83333 | 0 |  |  | 06-Apr | 06-Apr
CDUVDU13420 | Not Started | Hydrotest | VV-008 OVHD(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | HYDRO TEST | HYDRO TEST | 20 | 0.83333 | 0 |  |  | 07-Apr | 08-Apr
CDUVDU14680 | Not Started | Hydrotest Witness | VV-008 OVHD(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | INSPECTION |  |  | 3 | 0.125 | 0 |  |  | 08-Apr | 08-Apr
CDUVDU14950 | Not Started | Drainning of water | VV-008 OVHD(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 6 | 0.25 | 0 |  |  | 08-Apr | 08-Apr
CDUVDU15350 | Not Started | Deblinding & handover to Operation. | VV-008 OVHD(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 0.5 | 0 |  |  | 08-Apr | 09-Apr
CDUVDU13110 | In Progress | Water filling | L-152(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 24 | 1 | 0 |  |  | 07-Apr | 08-Apr
CDUVDU15670 | Not Started | Hydrotest | L-152(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | HYDRO TEST | HYDRO TEST | 20 | 0.83333 | 0 |  |  | 09-Apr | 09-Apr
CDUVDU17320 | Not Started | Hydrotest Witness | L-152(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | INSPECTION |  |  | 3 | 0.125 | 0 |  |  | 09-Apr | 10-Apr
CDUVDU17670 | Not Started | Drainning of water | L-152(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 6 | 0.25 | 0 |  |  | 10-Apr | 10-Apr
CDUVDU18370 | Not Started | Deblinding & handover to Operation. | L-152(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 0.5 | 0 |  |  | 10-Apr | 10-Apr
CDUVDU13130 | Not Started | Blinding | L-125(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | BLINDING | BLINDING | 12 | 0.5 | 0 |  |  | 07-Apr | 08-Apr
CDUVDU13850 | Not Started | Water filling | L-125(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 24 | 1 | 0 |  |  | 08-Apr | 09-Apr
CDUVDU15680 | Not Started | Hydrotest | L-125(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | HYDRO TEST | HYDRO TEST | 20 | 0.83333 | 0 |  |  | 09-Apr | 09-Apr
CDUVDU17330 | Not Started | Hydrotest Witness | L-125(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | INSPECTION |  |  | 3 | 0.125 | 0 |  |  | 09-Apr | 10-Apr
CDUVDU17680 | Not Started | Drainning of water | L-125(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 8 | 0.33333 | 0 |  |  | 10-Apr | 10-Apr
CDUVDU18480 | Not Started | Deblinding & handover to Operation. | L-125(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 0.5 | 0 |  |  | 10-Apr | 10-Apr
CDUVDU14700 | Not Started | Blinding | L-165(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | BLINDING | BLINDING | 12 | 0.5 | 0 |  |  | 08-Apr | 09-Apr
CDUVDU15690 | Not Started | Water filling | L-165(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 20 | 0.83333 | 0 |  |  | 09-Apr | 09-Apr
CDUVDU17340 | Not Started | Hydrotest | L-165(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | HYDRO TEST | HYDRO TEST | 20 | 0.83333 | 0 |  |  | 09-Apr | 10-Apr
CDUVDU19360 | Not Started | Hydrotest Witness | L-165(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | INSPECTION |  |  | 3 | 0.125 | 0 |  |  | 10-Apr | 10-Apr
CDUVDU19640 | Not Started | Drainning of water | L-165(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 6 | 0.25 | 0 |  |  | 10-Apr | 11-Apr
CDUVDU20370 | Not Started | Deblinding & handover to Operation. | L-165(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 0.5 | 0 |  |  | 11-Apr | 11-Apr
CDUVDU30210 | In Progress | Blinding | L-107(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | BLINDING | BLINDING | 12 | 0.5 | 0 |  |  | 08-Apr | 08-Apr
CDUVDU30220 | In Progress | Water filling | L-107(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 48 | 2 | 0 |  |  | 08-Apr | 10-Apr
CDUVDU30240 | In Progress | Hydrotest | L-107(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | HYDRO TEST | HYDRO TEST | 24 | 1 | 0 |  |  | 10-Apr | 11-Apr
CDUVDU30250 | In Progress | Drainning of water | L-107(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL |  |  | 10 | 0.41667 | 0 |  |  | 11-Apr | 12-Apr
CDUVDU30260 | In Progress | Deblinding & handover to Operation. | L-107(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 0.5 | 0 |  |  | 12-Apr | 12-Apr
CDUVDU30270 | In Progress | Hydrotest Witness | L-107(HT-INSP/MOC) | HYDRO TEST LOOPS | 0 | INSPECTION |  |  | 3 | 0.125 | 0 |  |  | 11-Apr | 11-Apr
CDUVDU11950 | In Progress | Inspection activities | "2""-P-01-2015-A6N" | INSP RECOMM | 0 | INSPECTION |  |  | 84 | 3.5 | 0 |  |  | 06-Apr | 10-Apr
CDUVDU18400 | Not Started | HT preparation | "2""-P-01-2015-A6N" | INSP RECOMM | 0 | MECHANICAL |  |  | 20 | 0.83333 | 0 |  |  | 10-Apr | 11-Apr
CDUVDU20420 | Not Started | Hydrotest Witness | "2""-P-01-2015-A6N" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 20 | 0.83333 | 0 |  |  | 11-Apr | 12-Apr
CDUVDU22350 | Not Started | Draining | "2""-P-01-2015-A6N" | INSP RECOMM | 0 | MECHANICAL |  |  | 12 | 0.5 | 0 |  |  | 12-Apr | 12-Apr
CDUVDU23560 | Not Started | De-blinding and hand-over | "2""-P-01-2015-A6N" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 20 | 0.83333 | 0 |  |  | 12-Apr | 13-Apr
CDUVDU9500 | In Progress | Cutting, grinding, fit-up, welding and NDT (133 ID) | "2""-P-01-2015-A6N" | INSP RECOMM | 60.1504 | MECHANICAL |  |  | 42 | 1.75 | 0 |  |  | 05-Apr | 06-Apr
CDUVDU18000 | Not Started | Inspection activities | "4""-P-01-2149-A6N" | INSP RECOMM | 0 | INSPECTION |  |  | 40 | 1.6667 | 0 |  |  | 10-Apr | 11-Apr
CDUVDU22060 | Not Started | HT preparation | "4""-P-01-2149-A6N" | INSP RECOMM | 0 | MECHANICAL |  |  | 20 | 0.83333 | 0 |  |  | 11-Apr | 12-Apr
CDUVDU23910 | Not Started | Hydrotest Witness | "4""-P-01-2149-A6N" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 12 | 0.5 | 0 |  |  | 12-Apr | 13-Apr
CDUVDU24800 | Not Started | Draining | "4""-P-01-2149-A6N" | INSP RECOMM | 0 | MECHANICAL |  |  | 12 | 0.5 | 0 |  |  | 13-Apr | 13-Apr
CDUVDU25530 | Not Started | De-blinding and hand-over | "4""-P-01-2149-A6N" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 20 | 0.83333 | 0 |  |  | 13-Apr | 14-Apr
CDUVDU30900 | Not Started | HT preparation | "3""-P-01-4021-A1A" | INSP RECOMM | 0 | MECHANICAL |  |  | 12 | 0.5 | 0 |  |  | 08-Apr | 09-Apr
CDUVDU30910 | Not Started | Hydrotest Witness | "3""-P-01-4021-A1A" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 3 | 0.125 | 0 |  |  | 09-Apr | 09-Apr
CDUVDU30920 | Not Started | Draining | "3""-P-01-4021-A1A" | INSP RECOMM | 0 | MECHANICAL |  |  | 6 | 0.25 | 0 |  |  | 09-Apr | 10-Apr
CDUVDU30930 | Not Started | De-blinding and hand-over | "3""-P-01-4021-A1A" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 0.33333 | 0 |  |  | 10-Apr | 10-Apr
CDUVDU11800 | Not Started | Inspection activities | "4""-P-01-2132-B1N" | INSP RECOMM | 0 | INSPECTION |  |  | 84 | 3.5 | 0 |  |  | 06-Apr | 10-Apr
CDUVDU18260 | Not Started | HT preparation | "4""-P-01-2132-B1N" | INSP RECOMM | 0 | MECHANICAL |  |  | 20 | 0.83333 | 0 |  |  | 10-Apr | 11-Apr
CDUVDU20140 | Not Started | Hydrotest Witness | "4""-P-01-2132-B1N" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 12 | 0.5 | 0 |  |  | 11-Apr | 11-Apr
CDUVDU21330 | Not Started | Draining | "4""-P-01-2132-B1N" | INSP RECOMM | 0 | MECHANICAL |  |  | 20 | 0.83333 | 0 |  |  | 11-Apr | 12-Apr
CDUVDU23290 | Not Started | De-blinding and hand-over | "4""-P-01-2132-B1N" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 15 | 0.625 | 0 |  |  | 12-Apr | 13-Apr
CDUVDU9510 | In Progress | Cutting, grinding, fit-up, welding and NDT(32 ID) | "4""-P-01-2132-B1N" | INSP RECOMM | 50 | MECHANICAL |  |  | 40 | 1.6667 | 0 |  |  | 05-Apr | 06-Apr
CDUVDU27850 | Not Started | Inspection activities | "4""-P-01-1805-B1N-1T" | INSP RECOMM | 0 | INSPECTION |  |  | 16 | 0.66667 | 0 |  |  | 16-Apr | 16-Apr
CDUVDU28500 | Not Started | HT preparation | "4""-P-01-1805-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 6 | 0.25 | 0 |  |  | 16-Apr | 17-Apr
CDUVDU28640 | Not Started | Hydrotest Witness | "4""-P-01-1805-B1N-1T" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 5 | 0.20833 | 0 |  |  | 17-Apr | 17-Apr
CDUVDU28810 | Not Started | Draining | "4""-P-01-1805-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 6 | 0.25 | 0 |  |  | 17-Apr | 17-Apr
CDUVDU29270 | Not Started | De-blinding and hand-over | "4""-P-01-1805-B1N-1T" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 0.33333 | 0 |  |  | 18-Apr | 18-Apr
CDUVDU27860 | Not Started | Cutting, grinding, fit-up, welding and NDT (8 ID) | "4""-P-01-2213-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 35 | 1.4583 | 0 |  |  | 16-Apr | 17-Apr
CDUVDU28890 | Not Started | Inspection activities | "4""-P-01-2213-B1N-1T" | INSP RECOMM | 0 | INSPECTION |  |  | 15 | 0.625 | 0 |  |  | 17-Apr | 18-Apr
CDUVDU29200 | Not Started | HT preparation | "4""-P-01-2213-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 6 | 0.25 | 0 |  |  | 18-Apr | 18-Apr
CDUVDU29360 | Not Started | Hydrotest Witness | "4""-P-01-2213-B1N-1T" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 6 | 0.25 | 0 |  |  | 18-Apr | 18-Apr
CDUVDU29390 | Not Started | Draining | "4""-P-01-2213-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 5 | 0.20833 | 0 |  |  | 18-Apr | 18-Apr
CDUVDU29540 | Not Started | De-blinding and hand-over | "4""-P-01-2213-B1N-1T" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 9 | 0.375 | 0 |  |  | 18-Apr | 19-Apr
CDUVDU28900 | In Progress | Cutting, grinding, fit-up, welding and NDT(6 ID) | "4""-P-01-2212-B1N-1T" | INSP RECOMM | 75 | MECHANICAL |  |  | 40 | 1.6667 | 0 |  |  | 17-Apr | 19-Apr
CDUVDU29670 | In Progress | Inspection activities | "4""-P-01-2212-B1N-1T" | INSP RECOMM | 75 | INSPECTION |  |  | 12 | 0.5 | 0 |  |  | 19-Apr | 19-Apr
CDUVDU29810 | Not Started | HT preparation | "4""-P-01-2212-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 6 | 0.25 | 0 |  |  | 19-Apr | 19-Apr
CDUVDU29920 | Not Started | Hydrotest Witness | "4""-P-01-2212-B1N-1T" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 4 | 0.16667 | 0 |  |  | 19-Apr | 20-Apr
CDUVDU29980 | Not Started | Draining | "4""-P-01-2212-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 4 | 0.16667 | 0 |  |  | 20-Apr | 20-Apr
CDUVDU30020 | Not Started | De-blinding and hand-over | "4""-P-01-2212-B1N-1T" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 0.33333 | 0 |  |  | 20-Apr | 20-Apr
CDUVDU12370 | In Progress | Cutting, grinding, fit-up, welding and NDT(16 ID) | "4""-P-01-2161-B1N-1T" | INSP RECOMM | 75 | MECHANICAL |  |  | 35 | 1.4583 | 0 |  |  | 07-Apr | 08-Apr
CDUVDU14560 | In Progress | Inspection activities | "4""-P-01-2161-B1N-1T" | INSP RECOMM | 75 | INSPECTION |  |  | 15 | 0.625 | 0 |  |  | 08-Apr | 09-Apr
CDUVDU15830 | Not Started | HT preparation | "4""-P-01-2161-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 6 | 0.25 | 0 |  |  | 09-Apr | 09-Apr
CDUVDU16260 | Not Started | Hydrotest Witness | "4""-P-01-2161-B1N-1T" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 3 | 0.125 | 0 |  |  | 09-Apr | 09-Apr
CDUVDU16530 | Not Started | Draining | "4""-P-01-2161-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 4 | 0.16667 | 0 |  |  | 09-Apr | 09-Apr
CDUVDU16840 | Not Started | De-blinding and hand-over | "4""-P-01-2161-B1N-1T" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 0.33333 | 0 |  |  | 09-Apr | 10-Apr
CDUVDU16030 | Not Started | HT preparation | "4""-P-01-2211-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 12 | 0.5 | 0 |  |  | 09-Apr | 09-Apr
CDUVDU17180 | Not Started | Hydrotest Witness | "4""-P-01-2211-B1N-1T" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 6 | 0.25 | 0 |  |  | 09-Apr | 10-Apr
CDUVDU18110 | Not Started | Draining | "4""-P-01-2211-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 10 | 0.41667 | 0 |  |  | 10-Apr | 10-Apr
CDUVDU19080 | Not Started | De-blinding and hand-over | "4""-P-01-2211-B1N-1T" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 18 | 0.75 | 0 |  |  | 10-Apr | 11-Apr
CDUVDU18280 | Not Started | HT preparation | "4""-P-01-1722-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 6 | 0.25 | 0 |  |  | 10-Apr | 10-Apr
CDUVDU18730 | Not Started | Hydrotest Witness | "4""-P-01-1722-B1N-1T" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 5 | 0.20833 | 0 |  |  | 10-Apr | 10-Apr
CDUVDU19200 | Not Started | Draining | "4""-P-01-1722-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 4 | 0.16667 | 0 |  |  | 10-Apr | 10-Apr
CDUVDU20820 | Not Started | De-blinding and hand-over | "4""-P-01-1722-B1N-1T" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 8 | 0.33333 | 0 |  |  | 11-Apr | 11-Apr
CDUVDU18290 | Not Started | Inspection activities | "2""-CBD-01-3225-A1A-N" | INSP RECOMM | 0 | INSPECTION |  |  | 20 | 0.83333 | 0 |  |  | 10-Apr | 11-Apr
CDUVDU20490 | Not Started | HT preparation | "2""-CBD-01-3225-A1A-N" | INSP RECOMM | 0 | MECHANICAL |  |  | 6 | 0.25 | 0 |  |  | 11-Apr | 11-Apr
CDUVDU21020 | Not Started | Hydrotest Witness | "2""-CBD-01-3225-A1A-N" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 3 | 0.125 | 0 |  |  | 11-Apr | 11-Apr
CDUVDU21370 | Not Started | Draining | "2""-CBD-01-3225-A1A-N" | INSP RECOMM | 0 | MECHANICAL |  |  | 4 | 0.16667 | 0 |  |  | 11-Apr | 11-Apr
CDUVDU21920 | Not Started | De-blinding and hand-over | "2""-CBD-01-3225-A1A-N" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 6 | 0.25 | 0 |  |  | 11-Apr | 12-Apr
CDUVDU22190 | Not Started | HT preparation | "6""-P-01-P-2101-A6N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 6 | 0.25 | 0 |  |  | 11-Apr | 12-Apr
CDUVDU22850 | Not Started | Hydrotest Witness | "6""-P-01-P-2101-A6N-1T" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 3 | 0.125 | 0 |  |  | 12-Apr | 12-Apr
CDUVDU23110 | Not Started | Draining | "6""-P-01-P-2101-A6N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 4 | 0.16667 | 0 |  |  | 12-Apr | 12-Apr
CDUVDU23440 | Not Started | De-blinding and hand-over | "6""-P-01-P-2101-A6N-1T" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 6 | 0.25 | 0 |  |  | 12-Apr | 12-Apr
CDUVDU26160 | Not Started | HT preparation | "4""-P-01-P-2104-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 12 | 0.5 | 0 |  |  | 14-Apr | 14-Apr
CDUVDU26720 | Not Started | Hydrotest Witness | "4""-P-01-P-2104-B1N-1T" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 6 | 0.25 | 0 |  |  | 14-Apr | 14-Apr
CDUVDU26950 | Not Started | Draining | "4""-P-01-P-2104-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 10 | 0.41667 | 0 |  |  | 14-Apr | 15-Apr
CDUVDU27480 | Not Started | De-blinding and hand-over | "4""-P-01-P-2104-B1N-1T" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 20 | 0.83333 | 0 |  |  | 15-Apr | 16-Apr
CDUVDU12220 | In Progress | Blinding | "8""-P-01-P-2152-B1N-1T" | INSP RECOMM | 70 | MECHANICAL | BLINDING | BLINDING | 20 | 0.83333 | 0 |  |  | 06-Apr | 07-Apr
CDUVDU25110 | Not Started | Cutting, grinding, fit-up, welding and NDT | "8""-P-01-P-2152-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 32 | 1.3333 | 0 |  |  | 13-Apr | 14-Apr
CDUVDU26730 | Not Started | Inspection activities | "8""-P-01-P-2152-B1N-1T" | INSP RECOMM | 0 | INSPECTION |  |  | 20 | 0.83333 | 0 |  |  | 14-Apr | 15-Apr
CDUVDU27490 | Not Started | HT preparation | "8""-P-01-P-2152-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 20 | 0.83333 | 0 |  |  | 15-Apr | 16-Apr
CDUVDU28100 | Not Started | Hydrotest Witness | "8""-P-01-P-2152-B1N-1T" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 6 | 0.25 | 0 |  |  | 16-Apr | 16-Apr
CDUVDU28330 | Not Started | Draining | "8""-P-01-P-2152-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 8 | 0.33333 | 0 |  |  | 16-Apr | 16-Apr
CDUVDU28520 | Not Started | De-blinding and hand-over | "8""-P-01-P-2152-B1N-1T" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 20 | 0.83333 | 0 |  |  | 16-Apr | 17-Apr
CDUVDU12290 | In Progress | Blinding | "8""-P-01-P-2153-B1N-1T" | INSP RECOMM | 78 | MECHANICAL | BLINDING | BLINDING | 12 | 0.5 | 0 |  |  | 07-Apr | 07-Apr
CDUVDU26740 | Not Started | Cutting, grinding, fit-up, welding and NDT | "8""-P-01-P-2153-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 20 | 0.83333 | 0 |  |  | 14-Apr | 15-Apr
CDUVDU27500 | Not Started | Inspection activities | "8""-P-01-P-2153-B1N-1T" | INSP RECOMM | 0 | INSPECTION |  |  | 20 | 0.83333 | 0 |  |  | 15-Apr | 16-Apr
CDUVDU28180 | Not Started | HT preparation | "8""-P-01-P-2153-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 6 | 0.25 | 0 |  |  | 16-Apr | 16-Apr
CDUVDU28400 | Not Started | Hydrotest Witness | "8""-P-01-P-2153-B1N-1T" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 4 | 0.16667 | 0 |  |  | 16-Apr | 16-Apr
CDUVDU28530 | Not Started | Draining | "8""-P-01-P-2153-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 5 | 0.20833 | 0 |  |  | 16-Apr | 17-Apr
CDUVDU29030 | Not Started | De-blinding and hand-over | "8""-P-01-P-2153-B1N-1T" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 0.5 | 0 |  |  | 17-Apr | 18-Apr
CDUVDU28190 | Not Started | Inspection activities | "10""-P-01-P-2157-B1N-1T" | INSP RECOMM | 0 | INSPECTION |  |  | 20 | 0.83333 | 0 |  |  | 16-Apr | 17-Apr
CDUVDU28770 | Not Started | HT preparation | "10""-P-01-P-2157-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 8 | 0.33333 | 0 |  |  | 17-Apr | 17-Apr
CDUVDU28960 | Not Started | Hydrotest Witness | "10""-P-01-P-2157-B1N-1T" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 4 | 0.16667 | 0 |  |  | 17-Apr | 17-Apr
CDUVDU29040 | Not Started | Draining | "10""-P-01-P-2157-B1N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 4 | 0.16667 | 0 |  |  | 17-Apr | 17-Apr
CDUVDU29310 | Not Started | De-blinding and hand-over | "10""-P-01-P-2157-B1N-1T" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 0.5 | 0 |  |  | 18-Apr | 18-Apr
CDUVDU29570 | Not Started | HT preparation | "6""-P-01-P-2215-A6N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 8 | 0.33333 | 0 |  |  | 18-Apr | 19-Apr
CDUVDU29750 | Not Started | Hydrotest Witness | "6""-P-01-P-2215-A6N-1T" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 4 | 0.16667 | 0 |  |  | 19-Apr | 19-Apr
CDUVDU29790 | Not Started | Draining | "6""-P-01-P-2215-A6N-1T" | INSP RECOMM | 0 | MECHANICAL |  |  | 4 | 0.16667 | 0 |  |  | 19-Apr | 19-Apr
CDUVDU29840 | Not Started | De-blinding and hand-over | "6""-P-01-P-2215-A6N-1T" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 0.5 | 0 |  |  | 19-Apr | 20-Apr
CDUVDU22180 | Not Started | Inspection activities | "6""-P-01-2101-A6N" | INSP RECOMM | 0 | INSPECTION |  |  | 20 | 0.83333 | 0 |  |  | 11-Apr | 12-Apr
CDUVDU24050 | Not Started | HT preparation | "6""-P-01-2101-A6N" | INSP RECOMM | 0 | MECHANICAL |  |  | 20 | 0.83333 | 0 |  |  | 12-Apr | 13-Apr
CDUVDU25360 | Not Started | Hydrotest Witness | "6""-P-01-2101-A6N" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 12 | 0.5 | 0 |  |  | 13-Apr | 14-Apr
CDUVDU26010 | Not Started | Draining | "6""-P-01-2101-A6N" | INSP RECOMM | 0 | MECHANICAL |  |  | 20 | 0.83333 | 0 |  |  | 14-Apr | 14-Apr
CDUVDU26930 | Not Started | De-blinding and hand-over | "6""-P-01-2101-A6N" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 16 | 0.66667 | 0 |  |  | 14-Apr | 15-Apr
CDUVDU29930 | Not Started | HT preparation | "6""-P-01-P-1517-A1A-1H" | INSP RECOMM | 0 | MECHANICAL |  |  | 6 | 0.25 | 0 |  |  | 19-Apr | 20-Apr
CDUVDU30010 | Not Started | Hydrotest Witness | "6""-P-01-P-1517-A1A-1H" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 3 | 0.125 | 0 |  |  | 20-Apr | 20-Apr
CDUVDU30040 | Not Started | Draining | "6""-P-01-P-1517-A1A-1H" | INSP RECOMM | 0 | MECHANICAL |  |  | 4 | 0.16667 | 0 |  |  | 20-Apr | 20-Apr
CDUVDU30050 | Not Started | De-blinding and hand-over | "6""-P-01-P-1517-A1A-1H" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 12 | 0.5 | 0 |  |  | 20-Apr | 21-Apr
CDUVDU24060 | Not Started | Inspection activities | "6""-P-01-2103-A6N" | INSP RECOMM | 0 | INSPECTION |  |  | 20 | 0.83333 | 0 |  |  | 12-Apr | 13-Apr
CDUVDU25370 | Not Started | HT preparation | "6""-P-01-2103-A6N" | INSP RECOMM | 0 | MECHANICAL |  |  | 20 | 0.83333 | 0 |  |  | 13-Apr | 14-Apr
CDUVDU26410 | Not Started | Hydrotest Witness | "6""-P-01-2103-A6N" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 12 | 0.5 | 0 |  |  | 14-Apr | 14-Apr
CDUVDU26940 | Not Started | Draining | "6""-P-01-2103-A6N" | INSP RECOMM | 0 | MECHANICAL |  |  | 20 | 0.83333 | 0 |  |  | 14-Apr | 15-Apr
CDUVDU27650 | Not Started | De-blinding and hand-over | "6""-P-01-2103-A6N" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 20 | 0.83333 | 0 |  |  | 15-Apr | 16-Apr
CDUVDU15520 | Not Started | Blinding | PT-3606 | INSP RECOMM | 0 | MECHANICAL | BLINDING | BLINDING | 18 | 0.75 | 0 |  |  | 09-Apr | 09-Apr
CDUVDU16990 | Not Started | Cutting, grinding, fit-up, welding and NDT | PT-3606 | INSP RECOMM | 0 | MECHANICAL |  |  | 21 | 0.875 | 0 |  |  | 09-Apr | 10-Apr
CDUVDU17880 | Not Started | Inspection activities | PT-3606 | INSP RECOMM | 0 | INSPECTION |  |  | 20 | 0.83333 | 0 |  |  | 10-Apr | 10-Apr
CDUVDU19820 | Not Started | HT preparation | PT-3606 | INSP RECOMM | 0 | MECHANICAL |  |  | 12 | 0.5 | 0 |  |  | 10-Apr | 11-Apr
CDUVDU21060 | Not Started | Hydrotest Witness | PT-3606 | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 6 | 0.25 | 0 |  |  | 11-Apr | 11-Apr
CDUVDU21730 | Not Started | Draining | PT-3606 | INSP RECOMM | 0 | MECHANICAL |  |  | 10 | 0.41667 | 0 |  |  | 11-Apr | 12-Apr
CDUVDU22710 | Not Started | De-blinding and hand-over | PT-3606 | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 18 | 0.75 | 0 |  |  | 12-Apr | 12-Apr
CDUVDU8810 | Not Started | Support rectification | "10""-P-01-2117-A1F-IT" | INSP RECOMM | 0 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 21 | 0.875 | 0 |  |  | 04-Apr | 05-Apr
CDUVDU8800 | Not Started | Support rectification | "12""- SL-01-2101-A2A-IH" | INSP RECOMM | 0 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 21 | 0.875 | 0 |  |  | 04-Apr | 05-Apr
CDUVDU17110 | Not Started | Blinding | "2""-CBD-01-3220-B1A" | INSP RECOMM | 0 | MECHANICAL | BLINDING | BLINDING | 18 | 0.75 | 0 |  |  | 09-Apr | 10-Apr
CDUVDU18820 | Not Started | Cutting, grinding, fit-up, welding and NDT | "2""-CBD-01-3220-B1A" | INSP RECOMM | 0 | MECHANICAL |  |  | 21 | 0.875 | 0 |  |  | 10-Apr | 11-Apr
CDUVDU19620 | Not Started | Inspection activities | "2""-CBD-01-3220-B1A" | INSP RECOMM | 0 | INSPECTION |  |  | 20 | 0.83333 | 0 |  |  | 10-Apr | 11-Apr
CDUVDU21850 | Not Started | HT preparation | "2""-CBD-01-3220-B1A" | INSP RECOMM | 0 | MECHANICAL |  |  | 12 | 0.5 | 0 |  |  | 11-Apr | 12-Apr
CDUVDU22940 | Not Started | Hydrotest Witness | "2""-CBD-01-3220-B1A" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 6 | 0.25 | 0 |  |  | 12-Apr | 12-Apr
CDUVDU23490 | Not Started | Draining | "2""-CBD-01-3220-B1A" | INSP RECOMM | 0 | MECHANICAL |  |  | 10 | 0.41667 | 0 |  |  | 12-Apr | 12-Apr
CDUVDU24270 | Not Started | De-blinding and hand-over | "2""-CBD-01-3220-B1A" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 18 | 0.75 | 0 |  |  | 12-Apr | 13-Apr
CDUVDU21860 | Not Started | HT preparation | "4""-P-01-1533-A1A-IS" | INSP RECOMM | 0 | MECHANICAL |  |  | 12 | 0.5 | 0 |  |  | 11-Apr | 12-Apr
CDUVDU22950 | Not Started | Hydrotest Witness | "4""-P-01-1533-A1A-IS" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 6 | 0.25 | 0 |  |  | 12-Apr | 12-Apr
CDUVDU23500 | Not Started | Draining | "4""-P-01-1533-A1A-IS" | INSP RECOMM | 0 | MECHANICAL |  |  | 10 | 0.41667 | 0 |  |  | 12-Apr | 12-Apr
CDUVDU24280 | Not Started | De-blinding and hand-over | "4""-P-01-1533-A1A-IS" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 18 | 0.75 | 0 |  |  | 12-Apr | 13-Apr
CDUVDU21590 | Not Started | Inspection activities | "3"" FG VV-005 TO VV-021" | INSP RECOMM | 0 | INSPECTION |  |  | 20 | 0.83333 | 0 |  |  | 11-Apr | 12-Apr
CDUVDU23530 | Not Started | HT preparation | "3"" FG VV-005 TO VV-021" | INSP RECOMM | 0 | MECHANICAL |  |  | 12 | 0.5 | 0 |  |  | 12-Apr | 12-Apr
CDUVDU24470 | Not Started | Hydrotest Witness | "3"" FG VV-005 TO VV-021" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 6 | 0.25 | 0 |  |  | 12-Apr | 13-Apr
CDUVDU24880 | Not Started | Draining | "3"" FG VV-005 TO VV-021" | INSP RECOMM | 0 | MECHANICAL |  |  | 10 | 0.41667 | 0 |  |  | 13-Apr | 13-Apr
CDUVDU25500 | Not Started | De-blinding and hand-over | "3"" FG VV-005 TO VV-021" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 18 | 0.75 | 0 |  |  | 13-Apr | 14-Apr
CDUVDU30060 | Not Started | Dismantle scaffold | "REPLACE 28"" LINE" | INSP RECOMM | 0 | MECHANICAL |  |  | 48 | 2 | 0 |  |  | 20-Apr | 22-Apr
CDUVDU10750 | Not Started | 4"-WS-01-2901-A3A-N Service water header above old booster pump | ONLINE SEALING | ONLINE SEALING | 0 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 0 | 0 | 0 |  |  | 04-Apr | 04-Apr
CDUVDU13070 | Not Started | 1.5"-WS-01-2903-A3A-N Service water line above FF-01 pass-2 I/V | ONLINE SEALING | ONLINE SEALING | 0 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 0 | 0 | 0 |  |  | 04-Apr | 04-Apr
CDUVDU26130 | Not Started | 0.75"-C-01-2566-A1A-N Neutralising amine of 01-CC-006 at column bottom | ONLINE SEALING | ONLINE SEALING | 0 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 0 | 0 | 0 |  |  | 04-Apr | 04-Apr
CDUVDU26260 | Not Started | 0.75"-C-01-2564-A1A-N Neutralising amine of 01-CC-001 at column bottom | ONLINE SEALING | ONLINE SEALING | 0 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 0 | 0 | 0 |  |  | 04-Apr | 04-Apr
CDUVDU8990 | Not Started | 2"-WS-01-2601-A3A-N Service water line to desalter | ONLINE SEALING | ONLINE SEALING | 0 | MECHANICAL | WORK COMPLETED | WORK COMPLETED | 0 | 0 | 0 |  |  | 04-Apr | 04-Apr
CDUVDU10590 | Not Started | Cutting, grinding, fit-up, welding and NDT (24 ID) | "3""-P-01-3704-A1A" | INSP RECOMM | 0 | MECHANICAL |  |  | 42 | 1.75 | 0 |  |  | 05-Apr | 07-Apr
CDUVDU13200 | Not Started | Inspection activities | "3""-P-01-3704-A1A" | INSP RECOMM | 0 | INSPECTION |  |  | 40 | 1.6667 | 0 |  |  | 07-Apr | 09-Apr
CDUVDU15980 | Not Started | HT preparation | "3""-P-01-3704-A1A" | INSP RECOMM | 0 | MECHANICAL |  |  | 20 | 0.83333 | 0 |  |  | 09-Apr | 10-Apr
CDUVDU17850 | Not Started | Hydrotest Witness | "3""-P-01-3704-A1A" | INSP RECOMM | 0 | INSPECTION | HYDRO TEST | HYDRO TEST | 12 | 0.5 | 0 |  |  | 10-Apr | 10-Apr
CDUVDU19070 | Not Started | Draining | "3""-P-01-3704-A1A" | INSP RECOMM | 0 | MECHANICAL |  |  | 20 | 0.83333 | 0 |  |  | 10-Apr | 11-Apr
CDUVDU21010 | Not Started | De-blinding and hand-over | "3""-P-01-3704-A1A" | INSP RECOMM | 0 | MECHANICAL | DEBLINDING | DEBLINDING | 20 | 0.83333 | 0 |  |  | 11-Apr | 12-Apr
CDUVDU9710 | Not Started | Blinding | "3""-P-01-3704-A1A" | INSP RECOMM | 0 | MECHANICAL | BLINDING | BLINDING | 16 | 0.66667 | 0 |  |  | 05-Apr | 05-Apr
CDUVDU30190 | Not Started | Handover to Operation | HANDOVER | PLANT | 0 | MECHANICAL |  |  | 0 | 0 | 0 |  |  | 23-Apr | 23-Apr
CDUVDU30200 | Not Started | Start Up and Feed Cut in | UNIT START UP | PLANT | 0 | OPERATION |  |  | 60 | 2.5 | 0 |  |  | 23-Apr | 26-Apr